## Sheet1
PayPoint: Project plan
Item | Day | Milestones | Reporting requirements | Compliance Statements | Description | Comments | Dependencies
1 | Day 0 - Implementation Date | Milestone 1: PayPoint is notified of Ofgem’s decision to accept the Commitments |  |  | PayPoint is notified of Ofgem’s decision to accept the Commitments |  | n/a
2 | On or before Day 30 | Milestone 2: Commitment 1 (paragraph 10(a)) - First OTC Letter |  |  | The Relevant PayPoint Company shall write to all Energy Suppliers that are party to contracts in force at the Implementation Date for the provision of OTC energy prepayment services which include an Exclusive Purchase Obligation or Exclusivity Rebate to seek that Energy Supplier’s written agreement to amend such contract to remove such terms for the remainder of the contract term, and to confirm that – pending the agreement of the Energy Supplier to the proposed amendment by return – the Relevant PayPoint Company does not intend to enforce the relevant contractual provision(s) (the First OTC Letter). |  | n/a
3 | On or before Day 30 | Milestone 3: Commitment 2 (paragraph 12(a)) - First Non-OTC Letter |  |  | The Relevant PayPoint Company shall write to each Energy Supplier that is party to a contract in force at the Implementation Date for the provision of non-OTC energy prepayment services which includes an Exclusive Purchase Obligation or Exclusivity Rebate to: (i) seek that Energy Supplier’s written agreement to amend such contract to remove any Exclusive Purchase Obligation or Exclusivity Rebate for the remainder of the contract term; (ii) where the relevant Energy Supplier contracts for the provision of both OTC and non-OTC energy prepayment services in one and the same contract, seek that Energy Supplier’s written agreement to amend the contract to include an early right of termination in relation to the non-OTC energy prepayment services provided under the relevant contract; and/or (iii) where currently restricted in the relevant contract, seek that Energy Supplier’s written agreement to amend such contract to clarify that Energy Suppliers are not prevented from developing and/or deploying their own non-OTC energy prepayment services during the contract term (the First Non-OTC Letter). |  | n/a
4 | On or before Day 30 | Milestone 4: Commitment 3 (Multiple Retailers) (paragraph 14(a)) - First Multiple Retailer Letter |  |  | The Relevant PayPoint Company shall – as applicable under the terms of the relevant contract – write to all Multiple Retailers to: (i) unilaterally remove the Energy Payment Equipment Provision. Such amendment shall take effect on the day that is 58 days from the Implementation Date ; (ii) seek that Multiple Retailer’s written agreement to the amendment to remove the Energy Payment Equipment Prohibition; or (iii) submit a change request to seek that Multiple Retailer’s consent to remove the Energy Payment Equipment Prohibition, (the First Multiple Retailer Letter). The Relevant PayPoint Company shall also confirm in the First Multiple Retailer Letter that – pending the agreement of the Retailer to the proposed amendment by return – PayPoint will not enforce the relevant contractual provision(s). |  | n/a
5 | On or before Day 30 | Milestone 5: Commitment 3 (Independent Retailers) (paragraph 14(c)) |  |  | The Relevant PayPoint Company shall notify all Independent Retailers that it will unilaterally remove the term(s) in the General Retailer Agreement that prohibit(s) the hosting of equipment of other payment service providers for the processing of OTC payments for prepayment energy customers. |  | n/a
6 | On or before Day 30 | Milestone 6: Commitment 4 (paragraph 16) |  |  | PayPoint will make a donation of £12.5 million to Ofgem's Energy Industry Voluntary Redress Scheme to support vulnerable energy consumers. |  | n/a
7 | On or before Day 30 | Milestone 7: Commitments Compliance Officer Appointment (paragraph 17) |  |  | PayPoint shall appoint a Commitments Compliance Officer whose function will be to: (a) monitor compliance with the Commitments for as long as they remain in force; and (b) provide monthly reports to Ofgem against the Milestones described in Column C of this Appendix 2 for a period of six months following Day 30 (subject to paragraph 20 of the Commitments). The Commitments Compliance Officer shall report to Ofgem within 3 working days any delays or changes in milestones and provide sufficient information for Ofgem to assess the reasonableness of such changes. |  | n/a
8 | First Monday following Day 30 (Month 1) |  | Month 1 Reporting Date |  | PayPoint to provide Ofgem with a written report covering the Milestones described in Column C of this Appendix 2, an update on progress, and one (1) electronic copy of any contractual amendments to implement the Commitments that have been issued to or agreed with Energy Suppliers and/or Retailers in the previous month |  | n/a
9 | Day 30+15 Working Days |  |  | Compliance Statement | PayPoint to provide Ofgem with a signed Compliance Statement within 15 Working Days of Day 30, i.e. the date on which Milestones 1-7, as listed in Column C of this Appendix 2 are substantially complete |  | Completion of Milestones 1-7, as described in Column C
10 | Day 58 | Milestone 8: Date on which amendment pursuant to Commitment 3 (Independent Retailers) (paragraph 14(c )) takes effect |  |  | Clause F.2 of the General Retailer Agreement requires that any variations are made on 28 days’ prior written notice to Retailers - this timing assumes that the relevant notice is provided to all Independent Retailers by Day 30 |  | Completion of Milestone 5, above
11 | First Monday of following Calendar month (Month 2) |  | Month 2 Reporting Date |  | PayPoint to provide Ofgem with a written report covering the Milestones described in Column C of this Appendix 2, an update on progress, and one (1) electronic copy of any contractual amendments to implement the Commitments that have been issued to or agreed with Energy Suppliers and/or Retailers in the previous month |  | n/a
12 | Day 30+3 months | Milestone 9: Second OTC Letter, Second Non-OTC Letter, and Second Multiple Retailer Letter |  |  | To the extent that any of the Energy Suppliers or Multiple Retailers which have been contacted pursuant to Commitments 1-3 have not confirmed their agreement to the amendments described therein by this date, the Relevant PayPoint Company shall write again to those parties to remind them of the request set out in the First OTC Letter, First Non-OTC Letter and First Multiple Retailer Letter for agreement to the proposed amendments by return. |  | Third party Energy Suppliers and Multiple Retailers to confirm updated terms are acceptable
13 | First Monday of following Calendar month (Month 3) |  | Month 3 Reporting Date |  | PayPoint to provide Ofgem with a written report covering the Milestones described in Column C of this Appendix 2, an update on progress, and one (1) electronic copy of any contractual amendments to implement the Commitments that have been issued to or agreed with Energy Suppliers and/or Retailers in the previous month |  | n/a
14 | First Monday of following Calendar month (Month 4) |  | Month 4 Reporting Date |  | PayPoint to provide Ofgem with a written report covering the Milestones described in Column C of this Appendix 2, an update on progress, and one (1) electronic copy of any contractual amendments to implement the Commitments that have been issued to or agreed with Energy Suppliers and/or Retailers in the previous month |  | n/a
15 | First Monday of following Calendar month (Month 5) |  | Month 5 Reporting Date |  | PayPoint to provide Ofgem with a written report covering the Milestones described in Column C of this Appendix 2, an update on progress, and one (1) electronic copy of any contractual amendments to implement the Commitments that have been issued to or agreed with Energy Suppliers and/or Retailers in the previous month |  | n/a
16 | First Monday of following Calendar month (Month 6) |  | Month 6 Reporting Date |  | PayPoint to provide Ofgem with a written report covering the Milestones described in Column C of this Appendix 2, an update on progress, and one (1) electronic copy of any contractual amendments to implement the Commitments that have been issued to or agreed with Energy Suppliers and/or Retailers in the previous month. To the extent that any of the Energy Suppliers or Multiple Retailers which have been contacted pursuant to Commitments 1-3 have not confirmed their agreement to the amendments described therein by the date that is six months following Day 30, PayPoint shall continue to provide monthly reports to Ofgem for a further three month period, or until such date on which all milestones have been met, whichever is the soonest (subject to Ofgem’s approval that all such milestones have in fact been met) |  | n/a
17 | First Monday of following Calendar month (Month 7) |  | Month 7 Reporting Date (if applicable) |  | PayPoint to provide Ofgem with a written report covering the Milestones described in Column C of this Appendix 2, an update on progress, and one (1) electronic copy of any contractual amendments to implement the Commitments that have been issued to or agreed with Energy Suppliers and/or Retailers in the previous month |  | n/a
18 | First Monday of following Calendar month (Month 8) |  | Month 8 Reporting Date (if applicable) |  | PayPoint to provide Ofgem with a written report covering the Milestones described in Column C of this Appendix 2, an update on progress, and one (1) electronic copy of any contractual amendments to implement the Commitments that have been issued to or agreed with Energy Suppliers and/or Retailers in the previous month |  | n/a
19 | First Monday of following Calendar month (Month 9) |  | Month 9 Reporting Date (if applicable) |  | PayPoint to provide Ofgem with a written report covering the Milestones described in Column C of this Appendix 2, an update on progress, and one (1) electronic copy of any contractual amendments to implement the Commitments that have been issued to or agreed with Energy Suppliers and/or Retailers in the previous month |  | n/a
20 | Day 30+9 months | Milestone 10: Long-stop completion date for seeking consent of Energy Suppliers and Multiple Retailers pursuant to rows 2, 3 and 4 above |  |  | All Energy Suppliers and Multiple Retailers who have been contacted pursuant to Commitments 1-3 (and whose written consent is required to implement the relevant changes) to confirm that amendments to relevant contracts are acceptable, finalise and sign revised terms. To the extent that any of the Energy Suppliers or Multiple Retailers described above have not confirmed their agreement to the amendments described therein by the date that is nine months from Day 30, PayPoint's reporting obligations pursuant to paragraph 19 of the Commitments shall nonetheless cease, subject to Ofgem’s approval that every reasonable step to reach an agreement has been taken. |  | Written agreement received from all third party Energy Suppliers and Multiple Retailers to revised terms
21 | Day 0 + 1 Year (and 15 Working Days) |  |  | Year 1 Compliance Statement | PayPoint to provide Ofgem with a signed Compliance Statement to confirm that the future-looking obligations set out in respect of Commitments 1-3 at paragraphs 11, 13 and 15 of the Commitments have been complied with in the relevant year |  | Continued compliance with Commitments in Year 1
22 | Day 0 + 2 Years (and 15 Working Days) |  |  | Year 2 Compliance Statement | PayPoint to provide Ofgem with a signed Compliance Statement to confirm that the future-looking obligations set out in respect of Commitments 1-3 at paragraphs 11, 13 and 15 of the Commitments have been complied with in the relevant year |  | Continued compliance with Commitments in Year 2
23 | Day 0 + 3 Years (and 15 Working Days) |  |  | Year 3 Compliance Statement | PayPoint to provide Ofgem with a signed Compliance Statement to confirm that the future-looking obligations set out in respect of Commitments 1-3 at paragraphs 11, 13 and 15 of the Commitments have been complied with in the relevant year |  | Continued compliance with Commitments in Year 3
24 | Day 0 + 4 Years (and 15 Working Days) |  |  | Year 4 Compliance Statement | PayPoint to provide Ofgem with a signed Compliance Statement to confirm that the future-looking obligations set out in respect of Commitments 1-3 at paragraphs 11, 13 and 15 of the Commitments have been complied with in the relevant year |  | Continued compliance with Commitments in Year 4
25 | Day 0 + 5 Years (and 15 Working Days) |  |  | Year 5 Compliance Statement | PayPoint to provide Ofgem with a signed Compliance Statement to confirm that the future-looking obligations set out in respect of Commitments 1-3 at paragraphs 11, 13 and 15 of the Commitments have been complied with in the relevant year |  | Continued compliance with Commitments in Year 5