## Log
Ref | Subgroup | Product | Product section/item ref | Item | Description of issue | Original text (where applicable) | What change is required
C003 | Correction | URS | 4.7.8 | Synchronise REL Address to ECOES, DES, MPAS, UK Link, and Smart Metering [1.4.8, 2.24] | This section in the URS incorrectly states that the REL is being sent to the DSP, when it should be the MPL that should be sent | When the REL Address is updated, the update, which includes the officially-recognised regional language equivalent (if relevant), is synchronised to ECOES, DES, MPAS, and UK Link over the RetailEnergyLocation interface and to Smart Metering over the RMPRegApptSync interface. | Remove reference to Smart Metering, and add new subsection to 4.5 to articulate updates to MPL location and the sync to smart metering thereafter
C179 | Correction | URS | 4.9.2 | Various | Heading currently states "Operator Access to CSS" This heading appears to conflict with how the CR was implemented into the products | Operator Access to CSS | Revise heading and paragraph to reference "Switching Operator" rather than "CSS Operations"
C195 | Cosmetic | Solution Architecture |  |  | Appendix 2 – Service Impacts by Business Process from Solution Architecture is outdated as this is referencing interfaces (which have been replaced by messaging model), and this level of information is captured in ABACUS |  | Remove Appendix 2 – Service Impacts by Business Process from Solution Architecture
C197 | Cosmetic | URS | 3.2 CSS, Address Service and Switching Network |  | Reference to customer instead of energy consumer |  | Replace "customer" with "energy consumer"
C314 | Correction | Solution Architecture | References | Outdated references | The E2E Solution Architecture includes a reference to D2.1.7 Technology and Comms Standards. This product was never formally published and should not be referenced. |  | Remove the reference to D2.1.7 Technology and Comms Standards in the E2E Solution Architecture.
C317 | Correction | URS |  |  | Documentation needs to indicate that logical model does not split out gas and electricity variants of messages and that physical model shall need to split out gas and electricity messages along with attributes for fuel type |  | Add a comment in URS to state that the physical model should split these out. Also, attributes for fuel type should be implemented in the physical message model appropriately.
C321 | Correction | URS | 4.6.18 Registration Request State Transitions | Table 3 and Table 4 | Registration status notifications are supposed to go via the RegNotification interface. However, the table has a copy and paste error where it references this information as going over the RegMgmtRequestNotification interface | Registration status notifications (via RegMgmtRequest Notification) | Replace "Registration status notifications (via RegMgmtRequest Notification)" with "Registration status notifications (via RegNotification)"
C326 | Correction | Solution Architecture | 3.59 | Table | Table is missing RegNotification interface to Suppliers |  | Add RegNotification to table
C327 | Correction | Solution Architecture | 3.6 | Figure 8 – New/Changed Interface between Supplier and CSS | Diagram is missing RegNotification interface to Suppliers |  | Add RegNotification to diagram
C328 | Correction | Solution Architecture | 3.64 | Table | Table refers to RegMgmtRequestNotification instead of RegNotification interface to Shippers |  | Replace RegMgmtRequestNofitication with RegNotification in table
C329 | Correction | Solution Architecture | 3.65 | Figure 9 – New/Changed Interface between Shippers and CSS | Diagram refers to RegMgmtRequestNotification instead of RegNotification interface to Shippers |  | Replace RegMgmtRequestNofitication with RegNotification in diagram
C330 | Correction | Solution Architecture | 3.69 | Table | Table refers to RegMgmtRequestNotification instead of RegNotification interface to DC |  | Replace RegMgmtRequestNofitication with RegNotification in table
C331 | Correction | Solution Architecture | 3.7 | Figure 10 – New/Changed Interface for the Data Collection Service | Diagram refers RegMgmtRequestNotification instead of RegNotification interface to DC |  | Replace RegMgmtRequestNofitication with RegNotification in diagram
C332 | Correction | Solution Architecture | 3.74 | Table | Table refers to RegMgmtRequestNotification instead of RegNotification interface to DA |  | Replace RegMgmtRequestNofitication with RegNotification in table
C333 | Correction | Solution Architecture | 3.75 | Figure 11 – New/ Interfaces for the Data Aggregation Service | Diagram refers RegMgmtRequestNotification instead of RegNotification interface to DA |  | Replace RegMgmtRequestNofitication with RegNotification in diagram
C334 | Correction | Solution Architecture | 3.81 | Table | Table refers to RegMgmtRequestNotification instead of RegNotification interface to MEM |  | Replace RegMgmtRequestNofitication with RegNotification in table
C335 | Correction | Solution Architecture | 3.82 | Figure 12 – New/Changed Interface with the MEM Data Services | Diagram refers RegMgmtRequestNotification instead of RegNotification interface to MEM |  | Replace RegMgmtRequestNofitication with RegNotification in diagram
C336 | Correction | Solution Architecture | 3.97 | Table | RegMgmtRequestNotification instead of Table refers to RegNotification interface to MAP |  | Replace RegMgmtRequestNofitication with RegNotification in table
C337 | Correction | Solution Architecture | 3.98 | Figure 15 – New/Changed Interfaces with the MAP Data Service | Diagram refers RegMgmtRequestNotification instead of RegNotification interface to MAP |  | Replace RegMgmtRequestNofitication with RegNotification in diagram
C338 | Correction | Solution Architecture | 4.32 | Notifications | Table does not include scenario for forced registration |  | Include forced registration scenario in table to be in line with URS. E.g.: Submitting supplier (Gas): notification that the request has been confirmed Gaining shipper: notification of a request being confirmed Gainint supplier: notification that a pending registration has been created in the system
C340 | Correction | Solution Architecture | 4.36 | Table | Table does not include RegNotification interface |  | Add RegNotification to table
C341 | Correction | Solution Architecture | 5.3 | Figure 20 - CSS Outbound Interfaces | Diagram is missing RegNotification interface to Suppliers |  | Add RegNotification to diagram
C342 | Correction | Solution Architecture | 5.3 | Table | Table is missing RegNotification interface to Suppliers |  | Add RegNotification to table