## External Change Log
Switching Programme External Change Control Log
|  |  |  | Any questions relating to product changes/the change process should be submitted to the SwitchingPMO@ofgem.gov.uk email address | [6 empty] | Last updated: | 2019-06-03
Change Request Reference | Change Request Title | Date CR raised | Raised by | Change Window CR included in | Change Request Status | Description of the change | Product(s) affected (incl. PBS references) | Link to Change Request Form | Decision | CR Decision Date | Decision notes | Product(s) affected by CR updated and published?
CR001-006 | These Change Requests were either incorporated into products published at DB3 (12 February 2018) or were incorporated into products as part of their development prior to their first publication at DB4 (22 June 2018).
CR007 | CSS Communications Networks Requirements | 2018-05-01 | DCC | N/A | Decision made | This Change Request places a requirement on DCC to develop a new product “D-4.2.8 CSS Comms Network Requirements”. This pulls together the comms network requirements in one place. The Change Request also proposes consequential changes to update the constituent products from which the requirements have been drawn. N.B. that it is not intended that D-4.2.8 will be maintained through the Switching Programme change control arrangements. Changes to these requirements will be managed through amendments to the constituent master products from which they have been drawn. | • D-4.1.5 E2E Solution Architecture • D-4.2.1 CSS User Requirements Specification • D-4.2.2 CSS Non-Functional Requirements • D-4.2.5 CSS Security Approach and Requirements* | N/A | Approved | 2018-06-06 | N/A | Yes *N.B. as per the DB4 letter, the Security products are currently not publically available
CR008 | Welsh Addresses | 2018-05-15 | DCC | N/A | Decision made | This Change Request covers the addition of Welsh Addresses to the existing baseline. In practice it requires CSS to support a second Retail Energy Location (REL) Address stored in an officially-recognised regional language. | • D-4.2.1 CSS User Requirements Specification • D-4.1.2 E2E Detailed Design Model • D-4.1.3 E2E Data Architecture and Data Governance • D-4.1.5 E2E Solution Architecture • D-4.2.2 CSS Non-Functional Requirements | N/A | Approved | 2018-06-06 | N/A | Yes
CR009 | Misc. Consistency Corrections | 2018-05-15 | DCC | N/A | Decision made | This Change Request proposes a series of minor amendments to products. These include correction of typos, adding clarifications and improving alignment between products. | • D-4.1.2 E2E Detailed Design Model • D-4.1.4 E2E Non-Functional Requirements • D-4.1.5 E2E Solution Architecture • D-4.1.9 E2E Switching Arrangements Service Management Strategy • D-4.2.1 CSS User Requirements Specification | N/A | Approved | 2018-06-06 | N/A | Yes
CR010 | Billing | 2018-05-15 | DCC | N/A | Decision made | This Change Request confirms that CSS will provide all necessary data to RECCo to facilitate the construction of invoices to switching participants. It does not at this stage confirm what data is required or how it will be transferred. | • D-4.2.1 CSS User Requirements Specification | N/A | Approved | 2018-06-06 | N/A | Yes
CR011 | This Change Request is currently going through internal programme development and is not ready for publication
CR012 | Logical Text for Design Products | 2018-06-07 | Ofgem | N/A | Decision made | This Change Request proposed to add a paragraph to several products to clarify that, as they contain illustrative information on how central systems will operate, the requirements may be updated as the design progresses from the logical to the physical level. In particular, updates may be required as a result of procurement of the CSS as well as development of the changes needed to other central data services, such as UK Link and MPAS, which are being progressed under the UNC and MRA. | • D-4.1.2 E2E Detailed Design Model • D-4.1.3 Data Architecture and Data Governance • D-4.1.4 E2E Non-Functional Requirements • D-4.1.5 E2E Solution Architecture • D-4.1.6 E2E Operational Choreography • D-4.2.1 CSS User Requirements Specification • D-4.2.2 CSS Detailed Non-Functional Requirements | N/A | Approved | 2018-06-13 | N/A | Yes
CR-E01 | Gate Closure for Change of Shipper Registration Event | 2018-07-06 | Xoserve | Window 1 | Decision made | This Change Request proposes an amendment to the process in the CSS data models that allows the registered Supplier to submit a change of Shipper registration event; where it is unrelated to a Supplier registration request, to incorporate a 5pm cut-off / gate closure time in line with the process for Supplier registrations. In addition all Shipper and Supplier portfolio updates must be included as part of the gate closure Gas Registration synchronisation messages received by UK Link on D-1 of the effective date. | • D-4.1.2 E2E Detailed Design Models V2 • D-4.2.1 CSS User Requirement Specification V2 •D-4.1.6 E2E Operational Choreography v2 | Gate Closure for Change of Shipper Registration Event | Approved | 2018-07-31 | N/A | Yes
CR-E02 | RegistrationSync Interface Definition | 2018-07-06 | Xoserve | Window 1 | Decision made | This Change Request is seeking to have the following two data elements added into the RegistrationSync interface definition: • Registration Request Domestic Indicator • Registration Request Effective From Date | • D-4.1.2 E2E Detailed Design Models (Abacus) V2 | RegistrationSync Interface Definition | Approved | 2018-07-31 | N/A | Yes
CR-E03 | Synchronisation latency of secured switches to UK Link / Gemini | 2018-07-06 | Xoserve | Window 1 | Decision made | This Change Request proposes an additional NFR to ensure that the secured Gas Registration synchronisation message that are received into UK Link from the CSS and updated to Gemini are prioritised in order to fulfil the downstream gas balancing processes; including Gas Nominations, Gas Allocations, UIG and gas energy balancing. Note that consideration is also being given to including an equivalent NFR for electricity as part of this change request | • D-4.1.4 E2E Non-Functional Requirements V2 • D-4.2.2 CSS Detailed Non-Functional Requirements V2 | Synchronisation latency of secured switches to UK Link / Gemini | Approved | 2018-07-31 | N/A | Yes
CR-E04 | Within day switching | 2018-07-06 | DCC | Window 1 | Decision made | This Change Request proposes to widen the Central Switching Service functionality to accommodate within-day switching | • D-4.1.2 E2E Detailed Design Models V2 • D-4.1.3 E2E Data Architecture and Data Governance V2 • D-4.1.6 E2E Operational Choreography V2 | Within day switching | Approved | 2018-07-31 | N/A | Yes
CR-E05 | Future-proofing CSS data model and messaging | 2018-07-19 | DCC | Window 1 | Decision made | This Change Request is proposes that the CSS data model should be expanded to cover: • smart devices: o their relationship with meter points and suppliers o device Registration Requests (an initial registration or a switch) • multiple concurrent suppliers: o ability for a meter point or smart device to be registered to more than one supplier at a given time o a new kind of Registration Event that may be submitted by a supplier to allow other additional suppliers to register the same RMP (in a secondary context) o identification in a Registration Request of whether an existing supplier is being switched or a new supplier added (to be registered concurrently). | • D-4.2.1 CSS User Requirements Specification (data model section) – V2 • D-4.1.3 E2E Data Architecture and Data Governance V2: CSS data model (Messaging) held in ABACUS (which will be made available to appropriate users for information purposes) | Future-proofing CSS data model and messaging | Deferred | 2018-07-31 | The Design Authority made the decision to defer this CR: more work is required on this CR (and more widely on related policy positions and impacts), the intent of the CR is being included in the quality aspects of the CSS procurement so the CR is not needed at this stage. It will be picked up again once all ITT's have been received from bidders to assess need for this CR at that stage of the procurement. | N/A
CR-E06 | Aligment of Switching Speed text between the OBC and Operational Choreography products | 2018-09-04 | Jenny Boothe | Window 6 | Decision made | This CR seeks to align the text between the OBC and the Operational Choreography document in relation to the switching speed for pre-payment metered customers. | D-4.1.6 E2E Operational Choreography V2 | Pre-payment customer policy text alignment | Approved | 2018-10-26 |  | Yes
CR-E07 | DSP Fault Tolerance Omission from the E2E NFRs | 2018-09-04 | Jenny Boothe | Window 6 | Decision made | This CR seesk to rectify an apparent omission in the E2E NFRs in relation to the DSP and detection/rectification of faults in messaging and synchronisation. | D-4.1.4 E2E Non-Functional Requirements Spreadsheet | DSP Fault tolerance omission from the E2E NFRs | Approved | 2018-10-26 |  | Yes
CR-E08 | Automated interface for forced registrations | 2018-09-14 | Jenny Boothe/Kate Goodman | Window 6 | Decision made | This CR is related to CR E09. The CR seeks to create an automated facility to assist with the high number of forced registration. Also notification of failure to be sent to submitter of the registration as well as relevant suppliers and only available for initial registrations. | D-4.1.2 E2E Detailed Design Models V2.0 22nd June 2018 D-4.1.3 E2E Data Architecture and Data Governance V2.0 22nd June 2018 D-4.1.5 E2E Solution Architecture V2.0 22nd June 2018 D-4.2.1 CSS User Requirements Specification V2.0 22nd June 2018 D-4.2.2 CSS Non-Functional Requirements V2.0 22nd June 2018 D-4.2.3 CSS Service Management and Operational Approach V1.0 28th March 2018 D-10.2 CSS Service Management Requirements V1.0 22nd June 2018 D-10.3 CSS Operational Requirements V1.0 22nd June 2018 D-10.4 CSS Service Management Tools Requirements V1.0 22nd June 2018 | Automated interface for forced registrations | Approved | 2018-10-26 |  | Yes
CR-E09 | Forced registrations cannot be withdrawn | 2018-09-14 | Jenny Boothe/Kate Goodman | Window 6 | Decision made | This CR is related to CR E08. The CR seeks for CSS to record a registration, either a forced registration or a normal registration submitted by a supplier. Also carries out additional piece of validation upon receipt of a withdrawal request – that the withdrawal fails if the registration is a forced registration. | D-4.1.2 E2E Detailed Design Models V2.0 22nd June 2018 D-4.1.3 E2E Data Architecture and Data Governance V2.0 22nd June 2018 D-4.1.5 E2E Solution Architecture V2.0 22nd June 2018 D-4.2.1 CSS User Requirements Specification V2.0 22nd June 2018 | Forced registrations cannot be withdrawn | Approved | 2018-10-26 |  | Yes
CR-E10 | Data Model elaboration | 2018-09-14 | Jenny Boothe/Kate Goodman | Window 6 | Decision made | The CR proposes that the repository needs to be updated so that it incorporates the detailed CSS design into the E2E baseline. It also needs to be updated further to define the messages passed to/from CSS. The logical data content and structure of messages that are passed between CSS and other data services under the new switching arrangements will be added. | D-4.1.2 E2E Detailed Design Models V2.0 22nd June 2018 D-4.1.3 E2E Data Architecture and Data Governance V2.0 22nd June 2018 D-4.2.1 CSS User Requirements Specification V2.0 22nd June 2018 | Data model elaboration, message definition | Approved | 2018-10-26 |  | Yes
CR-E11 | Network requirements additions | 2018-09-14 | Jenny Boothe/Kate Goodman | Window 6 | Decision made | This CR seeks to augment the policy requirements (exchange of data between a number of interconnected systems). This will be done by ensuring the communication network, across which data is transferred, ensures the zero loss of data should it become unavailable for a period of time. | D-4.1.2 E2E Detailed Design Models V2.0 22nd June 2018 D-4.1.3 E2E Data Architecture and Data Governance V2.0 22nd June 2018 D-4.2.1 CSS User Requirements Specification V2.0 22nd June 2018 | Network requirments additions | Approved | 2018-10-26 |  | Yes
CR-E12 | Provision of REL address updates to market participants | 2018-09-27 | Jenny Boothe | Window 7 | Decision made | This change request seeks to add new functional requirement(s) to enable an automated interface to transfer updated REL details to Gas Transporters Distribution Network Operators and energy suppliers. | D-4.2.1 CSS User Requirements Specification D-4.2.2 CSS Non Functional Requirements D-4.1.2 E2E Detailed Design Model | Provision of REL updates to market participants | Approved | 2018-11-09 |  | Yes
CR-E13 | CSS Data Archival Interval Text Clarification | 2018-09-28 | Phil Bryan | Window 7 | Decision made | This change request applies to NFR0560 text, to make it clearer than the interval over which CSS data may be retained is 7 years in total. The archived data interval is 7 years less the interval over which online data is held. | 4.2.2 CSS Detailed Non-Functional Requirements v2.0 22 June 2018 | CSS Data archival | Approved | 2018-10-26 |  | Yes
CR-E14 | CSS Address Format | 2018-09-28 | FSEG | Window 7 | Decision made | This Change Request proposes that this same standard is adopted for the Meter Point Address in the CSS MeteringPointSync Interface (and therefore within the CSS). This would require an additional line to be added to the address format specified. | D-4.2.6 CSS Data Migration Plan (v2.0; published on 22 June 2018) D-4.1.5 E2E Solution Architecture (v2.0; published on 22 June 2018) | CSS Address format | Rejected | 2019-02-20 | This CR is on hold. CAT are currently considering whether to proceed with this CR. An update will be provided in due course. | N/A
CR-E15 | Retrospective update of MPAN Import/Export indicator | 2018-09-28 | FSEG | Window 7 | Withdrawn | The change requested is to allow the Distribution Network Operators (DNOs) to update CSS with the import and export status of a supply via the Meter Point Administration Service (MPAS) in any data refresh as changes to the import / export Statuses are made. This will ensure that the enduring processes can continue outside of the CSS and ensure that the CSS continues to remain synchronised with MPAS. | D-4.1.5 E2E Solution architecture Detailed Switching Design Repository (ABACUS) (https://dcc2-pub.avolutionsoftware.com/Switchingbaseline) | Retrospective update of MPAN import export indicator | Rejected | N/A | This CR has been withdrawn. A future CR to be raised by the programme team to remove this indicator from the design. | N/A
CR-E16 | Primary Meter Asset – Electricity | 2018-09-28 | FSEG | Window 7 | Decision made | The change request advocates the removal of the Primary Meter Asset Indicator field from the interface between MPAS and the Central Switching Service (CSS). | ABACUS E2E Logical Data Model, Source Reference 2.13 D-4.2.1 CSS User Requirements Specification v2.0 D-4.2.1 CSS User Requirement Specification – Functional Requirements Spreadsheet v2.0 D-4.2.1 CSS User Requirements Specification - CSS Logical Data Model v2.0 D-4.1.2 Detailed Design Model (ABACUS) D-4.1.3 Data Architecture & Data Governance D-4.2.1 CSS User Requirement Specification – Functional Requirements Spreadsheet v2.1 | Primary Meter Asset | Approved | TBC | 24/05: v2.0 of this CR has been approved at Design Authority held 25/05/2019. 13/05: This was approved on 29/01/2019. This was brought back through the change control pipeline as the CR Form needed to be updated to reflect additional Products. This was brought to DF on 13/05 and obtained a recommendation for approval. An updated version of this CR was discussed at Design Forum (13 Dec), further updates are to be made in advance of re-circulation | N/A
CR-E17 | Registration Event elaboration | 2018-10-05 | Andrew Wallace/ Phil Bryan | Window 8 | Decision made | This change request seeks to retain a fully auditable record that is consistent, coherent and complete within secondary data services as well as CSS, the mastering data service, a Transaction Date will be captured from the Registration Event Request in addition to the Registration Event Effective From Date | D-4.1.2 E2E Detailed Design Models V2.0 22nd June 2018 D-4.1.3 E2E Data Architecture and Data Governance V2.0 22nd June 2018 D-4.2.1 CSS User Requirements Specification V2.0 22nd June 2018 | Registration Event elaboration | Approved | 2018-11-09 |  | Yes
CR-E18 | Registration Deactivation elaboration | 2018-10-05 | Andrew Wallace/ Phil Bryan | Window 8 | Decision made | This change request seeks to retain a fully auditable record that is consistent, coherent and complete within secondary data services as well as CSS (the mastering data service), a Transaction Date will be captured from the Registration Deactivation Request in addition to the Registration Lifecycle Status From Date. | D-4.1.2 E2E Detailed Design Models V2.0 22nd June 2018 D-4.1.3 E2E Data Architecture and Data Governance V2.0 22nd June 2018 D-4.2.1 CSS User Requirements Specification V2.0 22nd June 2018 | Registration Deactivation elaboration | Approved | 2018-11-09 |  | Yes
CR-E19 | Non-qualified supplier loss notification | 2018-10-15 | Jenny Boothe | Window 9 | Decision made | This change request proposes to clarify that suppliers that are currently operating in the market will, if they have a valid network connection, be sent loss notification messages by the CSS. They will be sent this information if they have a network connection, regardless of whether they have passed UEPT. | D-10.2 CSS Service Management Requirements D-10.3 CSS Service Management Operational Requirements | Non-qualified supplier loss notification | Approved | 2018-11-09 |  | Yes
CR-E20 | Service Management Tools Requirements | 2018-10-15 | Paul Harding & Christine Pearson | Window 8 | Decision made | This change request proposes that the existing requirement for a hosted solution is amended to make it clear it is an either/or choice rather than a must. Also to add the option for a cloud-based solution as a new requirement. | D-10.4 CSS Service Management Tools Requirements | Service Management Tools Requirements | Approved | 2018-11-09 |  | Yes
CR-E21 | Service Management Requirements | 2018-10-16 | Paul Harding & Christine Pearson | Window 8 | Decision made | This change request seeks to amend/change the wording/text on SM009 & SM015 -SM017 to remove an inconsistency between the requirements | D-10.2 CSS Service Management Requirements | Service Management Requirements |  |  |  | N/A
CR-E22 | Removal of the synchronisation message to the DSP of a validated switch request | 2018-10-24 | Jenny Boothe | Window 9 | Withdrawn | This change request seeks to remove the synchronisation message that is sent to the DSP when a registration request has successfully completed validation. | ABACUS Processes ABACUS data architecture model Solution Architecture URS URS requirements spreadsheet | Removal of the synchronisation message to the DSP of a validated switch request | Rejected | N/A | This CR has been withdrawn and been replaced by CR-E23 | N/A
CR-E23 | Removal of the Registration ‘confirmed’ synch message to the Central Data Services Provider | 2018-11-01 | Jenny Boothe | Window 10 | Decision made | This change request seeks to clarify what information is actually being synchronised to the Central Data Services (CDSs) and seeks to remove the ‘confirmed’ synch as it is no longer necessary for the effective execution of a registration request. | D-4.1.2 E2E Detailed Design Model D-4.1.5 E2E Solution Architecture D-4.1.6 Operational Choreography D-4.2.1 CSS User Requirements Specification | Removal of the Registration ‘confirmed’ synch message to the Central Data Services Provider | Approved | 2018-11-30 |  | No
CR-E24 | Decommissioning of Existing (SEC) Registation Data Provider Communication Links | 2018-11-08 | Mark Deacon | Window 10 | Submitted to DA | This change request (CR) proposes that the new CSS will provide capability to transfer DSP data to the current RDP or their successors on a daily basis rather than use existing connections. | D-4.1.2 E2E Detailed Design Model D-4.1.5 E2E Solution Architecture D-4.2.1 CSS User Requirements Specification | Decommissioning of Existing (SEC) Registation Data Provider Communication Links | Deferred | 2018-11-30 | DA was in favour of taking forward this CR but required further information on cost benefit and consequential CSS impacts. This is CR will be re-considered once further IA work has been completed, a further draft of this CR is in development and will be shared when ready. | N/A
CR-E25 | CSS Change Project 4 contract award date | 2018-12-07 | Arno Vanden Eynde | Window 12 | On Hold | Purpose of this change request is to shift the contract signature date of Service Management System Proivders (SMSP) from 16 Aprl 2019 to 30 April 2019; and the contract award date of Procurement Project 4 (service management tools) from 16 March 2019 to 29 March 2019 | N/A | N/A
CR-E26 | Change to the date of Incentivised Milestone 3 | 2018-12-07 | Arno Vanden Eynde | Window 12 | Decision made | DCC considers that it is appropriate for IM3 to account for the delivery of both Procurement Projects given the initial incentive scope for IM3 focussed on the delivery of Contract Award of Procurement Project 1 as well as the importance of this project to the programme. DCC therefore proposes that IM3 covers both Project 1 and Project 4 (reflecting the original scope of IM3) and that the incentivised date is split to align with project 1 and project 4. | Two recommendation reports will still be needed. | N/A | Approved | 2019-01-29 |  | Yes
CR-E27 | Service Management System non-functional requirements | 2018-12-10 | Christine Pearson | Window 13 | Decision made | During review of the Service Management System (SMS) requirement document (D-10.4) ahead of the tender pack issuance for Project 4 (Service Management System) a lack on non- functional requirements was identified. For the SMS providers to understand the volumes by which the system will need to operate several non-functional requirements have been produced based on assumptions. These are to be included in the tender pack for Project 4 | D-10.4 - Service Management Tools Requirements (requirements spreadsheet) | Service Management System non-functional requirements | Approved | 2019-01-29 |  | Yes
CR-E28 | Service Management tools requirements update | 2018-12-10 | Christine Pearson | Window 13 | Decision made | For the SMS and Portal Service providers to fully understand the requirements and to add further clarity on the needs of Switching updates are necessary. These are to be included in the tender pack for Project 4 and the full list of changes can be found in the accompanying document. See ‘Requirements Comparison v0.2” for full details of changes. A total of 30 SMS and Service Portal requirements are recommended for change | D-10.4 - Service Management Tools Requirements (requirements spreadsheet) | Service Management tools requirements update | Approved | 2019-01-29 |  | Yes
CR-E29 | Amendment to the geographic location of SP provided services in D-10.2 Service Management Requirements spreadsheet V1.0 | 2018-12-13 | Paul Harding | Window 13 | Decision made | During the tender for Project 1 (Service Management requirements for Address and Registration Service) we spotted an inconsistency between the document sets D-10.2 Service Management Requirements (SM009) and CSS Security Approach Requirements (DCC_PS04). A clarification response has already been issued to correct this and this CR is to ensure that the D-10.2 Service Management Requirement spreadsheet is update and aligned to ensure its clear to the CSS Providers. | D-10.4 - Service Management Tools Requirements (requirements spreadsheet) | Amendment to the geographic location of SP provided services in D-10.2 Service Management Requirements spreadsheet V1.0 | Approved | 2019-01-29 |  | Yes
CR-E30 | Removal of requirement for a Licence Exempt Network Indicator | 2018-12-31 | Sarah Mower | Window 13 | Withdrawn | In the current design, there is a Licence Exempt Network Indicator which would alert the CSS by MPAS that a site being switched is Licence Exempt. It was established during discussions with the DCC, that there is no requirement for the CSS to hold this information for switching purposes. It was agreed though that it would be useful for industry to know if a site is on a LEN, however, this could be displayed via ECOES from a feed from MPAS. In addition, the Line Loss Factor would indicate the status of the MPAN currently.This would therefore remove this requirement from the critical path for CSS and could be evolved under ‘BAU’ industry change processes. The impact will be less development, and therefore cost, required for existing system providers with in timescales for the Switching Programmes Stage Zero. | D-4.1.5 E2E Solution Architecture v2.0 1 section 3.15 D-4.2.1 CSS User Requirements Specification v2.1, 4.5.3 RMP-Related Updates D-4.2.6 CSS Data Migration Plan v2.0, Appendix E D-4.3.4 E2E Transition Plan - Implementation Approach v1.0 | Removal of requirement for a Licence Exempt Network Indicator | Withdrawn | 2019-01-28 | This Change Request was withdrawn following Design Forum on 28 January 2019. On review of the CR, it was agreed that CR-E30 should be withdrawn. The switching design was baselined on the 2nd June 2018 along with the Outline Business Case (OBC). Within the OBC was an elaboration of the RP2a design that stated the implications of the new design on the existing service providers. The extract below is from the Reform Package Summary Spreadsheet annexed with the OBC. This clearly sets out the requirements for the indicator. Therefore, by withdrawing the CR we have reverted back to the original design. | N/A
CR-E31 | Additional Network Requirements | 2019-01-09 | Ian Marshall | Window 14 | Decision made | The Switching Programme is reliant on the effective exchange of data between a number of interconnected systems. In the event of any of these systems becoming offline, it is necessary for the success of a switch that no data is lost. This is a necessary requirement if the data is in transit or within the mastering system. The purpose of this change request is to augment this policy requirement by ensuring the communication network, across which data is transferred, ensures the zero loss of data should it become unavailable for a period of time. This change request is in addition to changes previously defined in CR-E11 | D-4.2.8 Communications Network Requirements V0.3 D-4.1.4 E2E Switching Arrangements Non-Functional Requirements v2.1 D-4.2.2 CSS Detailed Non-Functional Requirements Specification v2.1 | Additional Network Requirements | Approved | 2019-02-08 |  | Yes
CR-E32 | Clarification of where Defect Response Times in D4.3.3 E2E Testing Plan will be defined. | 2019-02-14 | Steven Poole | Window 17 | Decision made | Section 15.2.2 of D4.3.3 E2E Testing Plan sets out Defect Types, Classifications and Definitions. This section provides a representative example of how defects may be classified. Clarification is required in relation to Response Time. This Change Request is to clarify and update the E2E Testing Plan to clarify the intent and explain that the detailed Response times will be articulated in the Defect Management Plan produced by the Systems Integrator. | Section 15.2.2 of D4.3.3 E2E Test Plan. | Defect Response Times | Approved | 2019-02-22 |  | Yes
CR-E33 | Updates to E2E and CSS Design Products | 2019-02-27 | Andy Boojers | Window 18 | Decision made | The Design Product sets – E2E and CSS – represent the detailed design for the End-to-End and Central Switching Service (CSS). They provide the specifications that will be used to support the forthcoming procurement of the CSS that should also be used to assist the update of existing actors’ systems and processes. A number of minor changes have been identified to the CSS User Requirements Specification and the E2E Solution Architecture. These have been classified as follows: • Cosmetic – immaterial changes to address spelling errors, minor corrections of terminology, improvements to the structure and presentation of the model • Corrections – clarifications, omissions, inaccuracies or inconsistencies that could result in miscommunication or misinterpretation of the design | CSS D4.2.1 CSS User Requirements Specification V2.1 E2E D4.1.5 E2E Solution Architecture V2.1 | Updates to E2E and CSS Design Products | Approved | 2019-03-29 |  | Yes
CR-E34 | Updates to functional and non-functional requirements | 2019-02-27 | Andy Boojers | Window 18 | Decision made | The Design Product sets – E2E and CSS – include several requirements specifications. These requirements include functional, non-functional and security requirements sets. Following a ‘deep dive’ review of the full design product sets, a number of proposed changes have been identified. These have been classified by the following categories. • Cosmetic – immaterial changes to address spelling errors, minor corrections of terminology, improvements to the structure and presentation of the model • Corrections – clarifications, omissions, inaccuracies or inconsistencies that could result in miscommunication or misinterpretation of the design • Enhancements – changes that may impact the solution design | CSS D4.2.1 CSS Functional Requirements Spreadsheet V2.1 CSS D4.2.2 CSS Non-Functional Requirements Spreadsheet V2.1 | Updates to functional and non-functional requirements | Approved | 2019-03-29 |  | Yes
CR-E35 | Incremental Updates to the Data Compinents of the ABACUS Switching Model | 2019-02-27 | Andy Boojers | Window 18 | Decision made | The Switching Design Repository defines the future state of the E2E arrangements across a number of inter-connected components – Motivations, People, Services, Process and Data. The Data Domain comprises a number of components including an E2E logical data model, class and element catalogues, a data mastership catalogue, and an interface catalogue, The previous release, v4, introduced message definitions. Following the release of V4, several initiatives (DWG/FSEG Data Model review, ESP engagement and OFGEM detailed review) identified a number of candidate changes to the data components. These have been classified into the following categories: • Cosmetic – immaterial changes to address spelling errors, minor corrections of terminology, improvements to the structure and presentation of the model • Corrections – clarifications, omissions, inaccuracies or inconsistencies that could result in miscommunication or misinterpretation of the design • Enhancements – changes that may impact the solution design | Detailed Switching Design Repository - Switching Baseline Final V4 | Incremental Updates to the Data Compinents of the ABACUS Switching Model | Approved | 2019-03-29 |  | Yes
CR-E36 | Incremental changes to the Switching Design Repository | 2019-02-27 | Andy Boojers | Window 18 | Decision made | The Switching Design Repository is a constituent of a product suite that defines the future state of the E2E arrangements across a number of inter-connected components – Motivations, People, Services, Process and Data. Several increments of the model have been released, the most recent being published during November 2018. During the management of the changes introduced during November 2018, and through subsequent reviews (both formal and informal), across the programme, a number of additional candidate changes have been identified. These changes have been classified as follows: • Cosmetic – immaterial changes to address spelling errors, minor corrections of terminology, improvements to the structure and presentation of the model • Corrections – clarifications, omissions, inaccuracies or inconsistencies that could result in miscommunication or misinterpretation of the design • Enhancements – changes that may impact the solution design Note that changes to the data components of the Design Repository are being addressed by a separate CR – CR-E35. The scope of this change request is to address other dimensions of the Design Repository. | Detailed Switching Design Repository - Switching Baseline Final V4 | Incremental changes to the Switching Design Repository | Approved | 2019-03-29 |  | Yes
CR-E37 | Retrospectively updating MPAN’s Import/Export Indicator | 2019-03-15 | Elisabeth Rekker | Window 19 | Decision made | It has been identified that the Central Switching Service (CSS) design assumes that the electricity supply (either import or export) to a premise will not change in the lifetime of the Meter Point Administration Number (MPAN). This is not reflective of the demands made by customers nor does it reflect the functionality currently in operation. The current CSS design assumption is essentially a retrograde step, which will impact customers and the ability of the Industry to serve and meet their needs, if the design requirement is carried through to other central systems. The change requested is to allow the Distribution Network Operators (DNOs) to update CSS with the import and export status of a supply via the Meter Point Administration Service (MPAS) in any data refresh as changes to the import / export Statuses are made. This will ensure that the enduring processes can continue outside of the CSS and ensure that the CSS continues to remain synchronised with MPAS. Additionally, as the import / export status will be derived by an enduring DNO attribute, the Line Loss Factor Class (LLFC) ID for pricing, billing and settlement and not related to switching, a change is requested to continue refreshing the Electricity Central Online Enquiry Service (ECOES) with this information directly from MPAS rather than from the CSS. | D-4.1.5 E2E Solution Architecture Ofgem Switching Programme v2.1 (3.15) | Retrospectively updating MPAN’s Import/Export Indicator | Approved | 2019-05-10 |  | Yes
CR-E38 | Switching Domain Data Management | 2019-04-15 | John Wiggins | Window 20 | Decision made | The drafting of the REC Data Management Schedule (DMS) and the Abacus baseline design related to the processes and management of Switching Domain Data (SDD) is at present incomplete and requires further detailed design. A review within the Switching Programme has taken place to further elaborate the design of the data and end to end processes which support SDD, this included a review of the required CSS Messages and interactions between Elexon, Xoserve, REC Code Manager, CSS and other Market Participants. Summary of Current High-Level Design: SDD can be categorised as being composed of 4 types of data, which require different processes, governance arrangements and privacy controls: 1. Management of Market Participant Role identifiers and Energy Companies 2. Management of Market Participant Role Events 3. Management of Market Participant Role Alliances 4. Management of CSS Parameters and switching reference data. | Detailed Design Repository (Abacus) • CSS Message Model • E2E Process Maps • Logical Data Model REC Data Management Schedule | Switching Domain Data Management | Approved | 2019-06-11 | 26/04: Decision was deferred. Scheduled for DA on 24th May. | Yes
CR-E39 | Clarification of Registration Lifecycle statuses and removal of DSP confirmed synchronisation | 2019-04-29 | Asif Nawab | Window 21 | Decision made | This change request will be clarifying Registration Lifecycle statuses within the existing logical design with regards to status changes of the following: • Registration (during a Registration Request) • Registration (during the life of a Registration). Additionally, this change request seeks to clarify what data is synchronised to the Smart Metering Data Service Provider and Central Data Services (CDSs) and seeks to remove the ‘confirmed’ synch to the Smart Metering Data Service Provider (DSP) only as it is not necessary for the effective management of Smart Metering activities. Without this change, the current design and associated terminology will lead to confusion about the data that is being synchronised, increase the risk of an incorrect solution and retain a process step that could make next-day switching more cumbersome. | D-4.1.2 E2E Detailed Design Model: D-4.1.6 E2E Operational Choreography: | Clarification of Registration Lifecycle statuses and removal of DSP confirmed synchronisation | Rejected | 2019-06-07 | 07/06: Withdrawn 13/05: This CR will be discussed in a separate meeting scheduled for 14/05/2019 in which it will be brough back to Design Forum on 20th May. 29/04: Was discussed at Design Forum. No recommendation for approval was sought. Will be brought back to DF. | Yes
CR-E40 | REC Annex Incorporation into E2E Integration Plan | 2019-04-29 | Laura Kanabe | Window 21 | Decision made | Switching Programme will require collaboration between different existing service providers for the DBT phase of the programme. The existing service providers and DCC are signing a multiparty cooperation agreement (Memorandum Of Understanding), that sets out the way of working during the DBT phase. The Annex is mirroring the cooperation obligations from the cooperation agreement into REC v1.0. This will ensure the cooperation obligations are set out in the regulation for switching. The current change request is submitting a first iteration of the REC Annex, based on the information that is currently available. As more detail becomes available in DBT (due to work done by the System Integrator together with the Programme participants), a new iteration of REC annex will follow (most likely in summer 2019). | ‘End To End Integration Plan’ (REC v1.0) | REC Annex Incorporation into E2E Integration Plan | Approved | 2019-05-24 | 24/05: Approved at Design Authority held on 24/05/2019. 13/05: Discussed at DF on 13/05 and obtained a recommendation for approval. 03/05: Scheduled for Design Forum on Monday 13th May. | Yes
CR-E41 | Update to Registration Request Status, Registration Status and Supporting Business Rules. | 2019-05-21 | John Wiggins | Window 24 | Decision made | This change request will reduce the complexity of the current design and address several changes requested via previous CR’s or change requirements identified by Ofgem, the DCC, the MRA Faster Switching Expert Group and Xoserve. The high-level changes are: 1) Create an optimal solution (requirement previously referenced within CR-E23 and CR-E39) to support the removal of additional synchronisations to the DSP so that they only receive two synchronisations; the validation of an Initial Registration Request or Switch Request and a subsequent synchronisation when the associated Registration becomes ‘secured’ or ‘cancelled’. 2) Amend the synchronisations and notifications specified in the design following the implementation of CR-E08 so that Xoserve only receive notifications when a GT Initiated Registration is ‘validated’ or ‘rejected’, with additional notifications and synchronisations following the same pattern as an Initial Registration. 3) Provide greater detail and precision within the end to end design detailing the process, data and business rules associated to Registration Deactivation Requests. 4) Provide greater detail and precision within the end to end design detailing the process, data and business rules associated to Change of Shipper Registration Requests. | The following changes have been determined from an initial impact assessment. Further changes may be identified during implementation of this CR. Any deviation from this list will be clearly articulated, so long as they are within the spirit of this CR. D-4.1.2 E2E Detailed Design Model: Decision Rules: • Annulment window end date rule • Annulment window open rule • Check for Active Switch Request Rule • Domestic objection window end date rule • Elec active registration notify rule • Elec confirmed notify Rule • Elec secured notify rule • Elec validated confirmed, and secured sync rule • Elec validated notify rule • Elec validated sync rule • Gas active registration notify rule • Gas confirmed notify rule • Gas secured notify rule • Gas validated notify rule • Gas validated sync rule • Gas validated, confirmed, and secured sync rule • Non-domestic objection window end date rule • Objection consistency rule • Parent related RMP check rule • Parent RMP Switch Rule • Registration RMP rule • Single pending registration rule • Switch annulled rule • Switch request status rule Processes: • 1.4.8 Send Initial Registration confirmed notifications and synchronise • 2.3 Switch Request: o 2.3.8 Issue Switch Validated notifications and synchronise – change from ‘Switch validated’ to ‘Registration pending’ o 2.3.23 Issue Switch Confirmed notifications and synchronise – change from ‘Switch confirmed’ to ‘Registration confirmed’ • 2.3.8 Issue switch validated notifications and synchronise: o Change from ‘Switch validated’ to ‘Registration pending’ • 2.5 Execute switch: o Change ‘Switch secured’/’Secured Switch’ to ‘Registration Secured Active’ o Change notification interface to be used in description from RegMgmtRequestNotification to RegNotification • 2.7.11 Issue switch rejected notification for previously confirmed switch: o Replace references to ‘Switch validation’ and ‘Switch confirmed’ with ‘Pending registration’ and ‘Registration confirmed’ • 3.3 Deactivate registration: o 3.3.5 Issue registration inactive notifications and synchronise change ‘Registration inactive’ to ‘Registration secured inactive’ Interaction Sequence Diagrams: • Changes to titles required. Also need to check that state changes and when messages sent are correct – as above we believe the messages to DCC will need looking at for initial reg and annulment / withdrawal • The following ISDs may just need to be replicated for the additional syncs rather than changing. o Initial Registration Request - Rejected Validation o Initial Registration Request (gas) – Confirmed o Initial Registration Request (elec) – Confirmed o Execute Initial Registration (gas) o Execute Initial Registration (elec) o Post Initial Registration Execution (gas trad) o Post Initial Registration Execution (elec trad) o Post Initial Registration Execution (gas SMETS2) o Post Initial Registration Execution (elec SMETS2) o Post Execute Switch (gas SMETS2) Post Execute Switch (elec SMETS2) o Post Execute Switch (gas trad) o Post Execute Switch (elec trad) o Execute Switch (gas) o Execute Switch (elec) o Switch Request (gas) - Switch Confirmed o Switch Request (elec) - Switch Confirmed o Switch Request - (gas) Switch Rejected Objection o Switch Request - (elec) Switch Rejected Objection o Switch Request - Switch Rejected Validation o Switch Request - Switch Validation o Switch Withdrawal (gas - preconfirmed) o Switch Withdrawal (elec - preconfirmed) o Switch Withdrawal (gas - post confirmed) o Switch Withdrawal (elec - post confirmed) o Switch Annulment - (gas - preconfirmed) o Switch Annulment - (elec - preconfirmed) o Switch Annulment - (gas – post confirmed) o Switch Annulment - (elec – post confirmed) o Registration Deactivation (gas) o Registration Deactivation (elec) o RMP Termination - (gas - pre confirmed) o RMP Termination - (elec - pre confirmed) o RMP Termination - (gas - post confirmed) o RMP Termination - (elec – post confirmed) D-4.1.6 E2E Operational Choreography: • Table 2 Electricity Switch dependencies - Remove reference to Smart Metering sync at Switch Confirmed • Figure 12 Switch - Electricity Future Arrangements, Traditional Credit Meter - Remove reference to Smart Metering • 3.44 Remove reference to Smart Metering sync at Switch Confirmed • 3.45 Remove reference to Smart Metering sync at Switch Confirmed • Table 4 Gas Switch dependencies - Remove reference to Smart Metering sync at Switch Confirmed • Figure 13 Switch - Gas Future Arrangements, Traditional Credit Meter - Remove reference to Smart Metering • 3.56 Remove reference to Smart Metering sync at Switch Confirmed • 3.57 Remove reference to Smart Metering sync at Switch Confirmed • Supplier challenge of a GB standardised address link - Change to ME address • 3.87 - Change to ME address • 3.88 - Change to ME address D-4.2.1 CSS User Requirement Specifications • 4.3 Registration Lifecycle State • 4.4 Registration Request State 1.1.1. RMP Creation and State Update [1.2, 2.14, 3.1] • • 4.6.2 Initial Registration Request [1.4] • Table 3 –Registration Request state transitions | To follow | Approved | 2019-06-14 |  | Yes
CR-E42 | Removal of Changes Proposed under CR-E33 (plus one additional minor change) | 2019-05-28 | Andy Boojers | Window 24 | Decision made | CR-E33 included a set of 23 changes to be introduced to the CSS URS and the E2E SA. 17 of these referred to updating references to an interface called ‘RegMgmtRequestNotification’ to an interface ‘called ‘RegNotification’. This interface was originally proposed as an option during the analysis and design to support CRs CR-E08 and CR-E09, but not taken forward into the design. The proposed changes to update references are therefore obsolete and the existing references are correct. URS P56 Figure 10 Outbound Interfaces also includes a reference to this obsolete interface in the diagram. This CR proposes to remove this. In addition, this CR proposes to reject a change set out in CR E-33 to amend references from ‘CSS operations’ to ‘Switching Operator’. Finally, to support a proposed change to the E2E SA included in CR-E33 to remove Appendix 2, references to this, and realignment of appendix references is proposed. The ‘Programme Products Impacted’ section further elaborates on all of these changes. | URS and E2E SA | To follow | Approved | 2019-06-14 |  | Yes
CR-E43 | Reduction of Scope of CR-E34 | 2019-05-28 | Andy Boojers | Window 24 | Decision made | CR-E34 included a set of 31 changes to be introduced to CSS functional and non-functional requirements. A number of these were changes to amend references to ‘CSS Operation user’, as a result of queries raised during the CSS procurement process by one particular bidder who was subsequently unsuccessful. The changes were originally proposed to mitigate any false interpretation by CSS bidders of expectations regarding the responsibility of undertaking certain activities and processes, but are now considered obsolete and unnecessary. In addition, this CR is proposing to remove a requirement proposed in CR-E34, to explicitly cover real-time processing of registration requests, due to being identified as obsolete. | D-4.2.2 CSS Non-Functional Requirements spreadsheet | To follow | Approved | 2019-06-14 |  | Yes
CR-E44 | Rejection of Cosmetic Change Proposed Under CR E-35 (to include unique identifiers for data elements included in messages) | 2019-05-28 | Andy Boojers | Window 24 | Decision made | Change item C207, included in CR-E35, defined a cosmetic change to include a unique identifier for each data element for each instance of that element in any message. The effort required to complete this has been fully assessed and is considered high relative to the value the change would add. It is therefore proposed to reject this change in order to expedite publication of the design products containing other changes defined in CRs E33-E36. | No Programme Products are affected by this change. If approved, the result will be that the ABACUS data model does not introduce the new data element instance-level identifier as proposed in CR E-35. | To follow | Approved | 2019-06-14 |  | Yes
CR-E45 | Rejection of Cosmetic Change Proposed under CR E-36 (to include unique identifiers for data elements included in messages) | 2019-05-28 | Andy Boojers | Window 24 | Decision made | CR-E36 described 26 changes for the Detailed Switching Repository (ABACUS) for artefacts other than those related to data and messages. 4 of these proposed changes related to updating elements of the model with the notion of a RegNotification interface. This notion was originally proposed as a design option for CR-E08/09 but discounted. Therefore these changes are obsolete. In accordance with CRs E-x, E-x this CR will ensure that all obsolete changes are backed out in a consistent manner. Also included within CR was a proposed change to update the description of interactions contained in several sequence diagrams. It is proposed to reject this change on the basis that these sequence diagrams are likely to be impacted by CR-E4x ‘Update to Registration Request Status, Registration Status and supporting business rules’. | No Programme Products are affected by this change. If approved, the result will be that changes proposed under CR-E36 will not be applied to the Detailed Switching Repository (ABACUS). | To follow | Approved | 2019-06-14 |  | Yes
CR-E46 | Integration of the Smart Metering Enduring Change of Supplier (ECoS) solution with the Switching Architecture. | 2019-06-28 | Andy Boojers | Window 27 | In triage | A Government consultation on a proposal to direct DCC to provide Enduring Change of Supplier (ECoS) arrangements for smart meters commenced on 30th May 2019 . The proposed solution (See Appendix) will impact on the Switching design through the introduction of a new ‘CoS Party’ to the Switching ecosystem, which will require registration data from the Central Registrations Service (CRS) in order to undertake its responsibilities.
CR-E47 | Corrections to ABACUS Sequence Diagrams (ISD) | 2019-08-30 | Gary Morris | Window 31 | Decision made | There are a number of discrepancies within the Sequence Diagrams in ABACUS that either refer to an incorrect dataflow reference or that refer to dataflows exchanged between incorrectly identified market participants. Plus, some diagrams on the ABACUS homepage link through to diagrams that are different to what the title implies. | "ABACUS Sequence Diagrams: • ISD - Post Initial Registration Confirmation (elec) (https://dcc2-pub.avolutionsoftware.com/Switchingbaseline/#Content/Diagrams/4695046.svg) o ‘Confirm Settlement’ from MPAS to Supplier following a D0205 (Supplier to MPAS) should reference a D0172 and not a D0217. o ‘New Connection Request’ (D0142) is documented as being sent from Supplier to Data Collection but should instead be from Supplier to MEM. • ISD – Post Switch Confirmation (elec) (https://dcc2-pub.avolutionsoftware.com/Switchingbaseline/#Content/Diagrams/4696377.svg) o ‘Confirm Settlement’ from MPAS to Supplier following a D0205 (Supplier to MPAS) should reference a D0172 and not a D0217. • ISD – Post Initial Registration Execution (elec SMETS2) (https://dcc2-pub.avolutionsoftware.com/Switchingbaseline/#Content/Diagrams/4619930.svg) o ‘Notify Asset/RMP/Supplier’ (D0303) is documented as being sent from Data Collection to MAP but should instead be from MEM to MAP. • ISD – Change of Asset Ownership (elec) (https://dcc2-pub.avolutionsoftware.com/Switchingbaseline/#Content/Diagrams/4697799.svg) o ‘Notify Change’ from Supplier to MPAS should instead originate from the MEM to MPAS and should reference a D0304 and not a D0205. o ‘Notify Change’ from MEM to Supplier should reference a D0304 and not a D0150. • ISD – Replace meter (elec) (https://dcc2-pub.avolutionsoftware.com/Switchingbaseline/#Content/Diagrams/4697681.svg) o Add instance of ‘Notify change of asset/MAP’ from MEM to MPAS of a D0312. o Amend instance of ‘Notify change of asset/MAP’ from MEM to Supplier from D0150 to D0149/D0150. • ISD - Create New related RMPs (https://dcc2-pub.avolutionsoftware.com/Switchingbaseline/#Content/Diagrams/4620150.svg) o Supplier to CSS should be sending a RegMgmtRequestSubmission request and not RegMgmtRequestNotification The following ISDs on the ABACUS Home page https://dcc2-pub.avolutionsoftware.com/Switchingbaseline/#Content/Diagrams/4631096.svg link to different diagrams than described: • When you click on the “Determine objection window” it takes the user to the “Create RMP (gas)” ISD. • When clicking on the “Post Initial Registration Execution (elec trad)” box it takes the user to the “Post Switch Execution (elec trad)” ISD. • When clicking on the “Process GB standardised address update” box in the gas column it takes the user to the “Process GB standardised address update (elec)” instead of “Process GB standardised address update (gas)”. Add new participant message from CSS to DSP for RMP status changes (post-creation/operational): • RECM_SN_02950 Smart Metering RMP Lifecycle Synchronisation " | http://my.hdle.it/72929500 | Approved | 2019-09-20 | 20/09/19: Approved at Design Authority on 20th Sept 2019. | Yes
CR-E48 | Market Participant Role Identifier use in physical messaging model | 2019-08-30 | Andy Boojers | Window 31 | Decision made | "1. Remove Market Participant Role Identifier from all messages Use of Market Participant Role and Market Participant MPID in CSS Messages will be used instead of the concatenated Market Participant Role Identifier. " | D-4.1.3 E2E Data Architecture and Data Governance | http://my.hdle.it/72929745 | Approved | 2019-09-20 | 20/09/19: Approved at Design Authority on 20th Sept 2019. | Yes
CR-E49 | Additional data elements provided in Registration Event Notifications provided to Shippers | 2019-09-12 | Andy Boojers | Window 32 | Decision made | Additional information has been highlighted as being required by shippers when a registration event occurs. The following changes to Registration Event Notification going out to Shipper(s) [RECM_SN_CSS02350 – Registration Event Notification] are proposed. 1. Supply Meter Point Reference Number -- [Mandatory] 2. Registration Identifier -- [Mandatory] 3. Registration Event Type -- [Mandatory] 4. Registration Event Effective From Date -- [Mandatory, if Event Type is Change in Shipper] 5. Domestic Premises Indicator -- [Mandatory] 6. Shipper Role/MPID -- Losing Shippers ID [Mandatory, if Event Type is Change in Shipper] 7. Shipper Role/MPID -- Gaining Shippers ID [Mandatory, if Event Type is Change in Shipper] 8. Supplier Role/MPID -- [Mandatory, if Event Type is Change in Shipper] | D-4.1.3 E2E Data Architecture and Data Governance | http://my.hdle.it/73288872 | Approved | 2019-09-20 | 20/09/19: Approved at Design Authority on 20th Sept 2019. | Yes
CR-E50 | From' and 'Through' Dates Message Removal | 2019-09-19 | Andy Boojers | Window 32 | Submitted to DA | The following ‘from’ and ‘through’ dates will be generated by CSS upon being informed that a business event has taken place, rather than require the source of the event to provide the information. Therefore they are being removed from the inbound messages within which they are currently provided, as follows: Retail Energy Group Membership (RECM_SN_CSS04100) • Retail Energy Company Group Membership Effective From Date • Retail Energy Company Group Membership Effective Through Date Market Participant Role Ownership (RECM_SN_CSS05200) • Market Participant Role Ownership Effective From Date • Market Participant Role Ownership Effective Through Date RMP Comms Hub Link (RECM_SN_CSS00100) • RMP CommsHub Link From Date • RMP CommsHub Link Through Date RMP Association (RECM_SN_CSS00500) • RMP Association From Date • RMP Association Through Date RMP DCC Service Event (RECM_SN_CSS00400, RECM_SN_CSS01200) • RMP Event Effective From Date • RMP Event Effective Through Date RMP Asset Ownership Event (RECM_SN_CSS00400, RECM_SN_CSS01200) • RMP Event Effective From Date • RMP Event Effective Through Date Premises Supply Condition Registration Event (RECM_SN_CSS02000) • Registration Event Effective From Date • Registration Event Effective Through Date | D-4.1.3 E2E Data Architecture and Data Governance | http://my.hdle.it/73288668