## Jan 2021 consultation responses
No. | Date raised | Comment from | Reference | Section | Comment | Suggested alternative text (if necessary) | Response
8 | 2021-01-29 | Centrica | Process | Annex 1, indicative process | Rejection of non-compliant applications: It is proposed that an application not in accordance with any of the relevant requirements may be rejected. We expect this is intended to deter companies from submitting applications that do not comply with all requirements. We agree companies should be discouraged from submitting non-compliant applications but are concerned this may result in consumer dis-benefit. Investment which could deliver consumer value may be delayed or cancelled. Instead, we recommend companies are financially penalised if applications are non-compliant; this may be a more effective deterrent. |  | We maintain our policy decision to reject applications if they do not comply with the requirements of relevant licence conditions, or the Re-opener Guidance and Application Requirements document.
14 | 2021-01-19 | Citizens Advice | Annex 1 - 1.1 | Annex 1, indicative process | Application process timeline - We note that the aim is to complete the review process within 9 months or less, although that there may be some circumstances that this may not be possible. We welcome the formal timeline for the decision and recognise that some time is needed to be able to evaluate complex submissions and to allow for appropriate stakeholder consultation and its consideration.​ Ofgem needs to consider the risk that with a demanding workload they may be stretched to ensure that decisions are made in a timely manner and with full scrutiny given the potential volume of re-opener applications.​ ​We would also ask that the process timeline remains under review to support network companies and stakeholders to respond to net zero targets or other requirements. |  | Comment noted. We have decided on an approach using assessment tiers to allow for agile and timely decision making, and added the pre-application engagement stage to aid this agility.
15 | 2021-01-19 | Citizens Advice | Annex 1 - 1.9 | Annex 1, indicative process | Tiered assessment - We support the use of the tiered approach, where additional scrutiny is applied to more complex projects and a fast-track tier is applied to high quality applications and less complex projects. |  | Comment noted
16 | 2021-01-19 | Citizens Advice | Annex 1 | Annex 1, indicative process | Authority triggered re-opener process - We support the explanations relating to the triggering of the re-opener process and also support the transparency for the reasons for triggering a re-opener. |  | Comment noted
18 | 2021-01-19 | ENWL | 1.8 | Annex 1, indicative process | All and any changes to the guidance documents, associated documents and annexes/appendices should be subject to the same consultation process. | Annex 1 provides information on how we intend to manage the flow of applications during RIIO-2 and the process we will follow when assessing re-opener applications. This does not form any part of the Guidance and may be modified and updated at any time without prior consultation. | We believe this refers to 1.8 of the draft Re-opener Guidance and Application Requirements document issued on 17 December 2020. The process has been moved into a separate working document but we have worked closely with licensees to develop this through consultations and workshops.
27 | 2021-01-19 | ENWL | 1.1 (annex 1) | Annex 1, indicative process | The cited period of nine months or less should be shortened to allow for agile timely decision making |  | A proportionate approach with assessment tiers will be used to allow for agile and timely decision making.
28 | 2021-01-19 | ENWL | Table 1, 1., bullet 2 (annex 1) | Annex 1, indicative process | We welcome that earlier discussion is encouraged, but this should also be ongoing if merited in the run up to submission. It shouldn't be a requirement to have at least 6 months before discussed any issues, as it may not be known a full 6 months before an application is being submitted. | Discussions between Ofgem and the licensee take place to understand forthcoming applications, any difficult areas, and for the Authority to provide guidance where appropriate. These discussions should take place at least six months before the application window opens. | The level of pre-engagement should be determined on a case-by-case basis, but engagement at least 3 months before an application is submitted is requested where possible (reduced from the previously requested 6 months).
29 | 2021-01-19 | ENWL | Table 1, 3., final para (annex 1) | Annex 1, indicative process | The justification for rejection should be provided to companies on notification and sufficient detail so that this can be learned from for future applications | Applications will only be accepted and proceed to the next stage if they pass this initial assessment. We will notify licensees if an application is rejected inlcuding the reasons and evidence for any rejection, and publish details on our website. | Drafting has been amended to reflect this comment.
30 | 2021-01-19 | ENWL | Table 1, 4. (annex 1) | Annex 1, indicative process | The SQ process should be timed and defined from a process point of view in advance and set out in this document |  | The timings of the SQ process may vary on a case-by-case basis as part of our proportionate approach and assessment tier process.
31 | 2021-01-19 | ENWL | 1.3 (annex 1) | Annex 1, indicative process | Some reopeners will be reactive to new information and/or will be driven by recent change. This may give relatively short time for the companies to react to consider if say the materiality threshold is crossed. Therefore it cannot be a requirement that a reopener must have been on this log process. | The aim of the re-opener pipeline process is to ensure an efficient and timely approach is taken when a re-opener is to be triggered. As such, a re-opener application pipeline log will be used to: • monitor the flow of expected re-opener applications. For the avoidance of doubt non-inclusion in the log of a submission subsequently made will not impact the company making and achieving a reopener adjustment it submits. | Information in the Re-opener pipeline log should be forecasted as far as is reasonably practicable.
32 | 2021-01-19 | ENWL | 1.4 (annex 1) | Annex 1, indicative process | Clarity should be provided that this a reasonable view only - not a binding view, including undue influence on the full reopener application if submitted | Licensees are required to provide potential applications they anticipate submitting with reasonable up to date information in their annual RRP on potential applications they anticipate submitting during RIIO-2. The information required may include: | Information in the Re-opener pipeline log should be forecasted as far as is reasonably practicable.
33 | 2021-01-19 | ENWL | 1.4 (bullets 2 and 3) (annex 1) | Annex 1, indicative process | Bullet 2 and 3 are extremely speculative and it is unclear what benefit to the Ofgem or the company they provide. | Remove bullets 2 and 3 | Information in the Re-opener pipeline log should be forecasted as far as is reasonably practicable.
34 | 2021-01-19 | ENWL | 1.7 (annex 1) | Annex 1, indicative process | 1.7 is inconsistent with the narrative in table 1 (annex1) |  | Drafting has been amended to reflect this comment.
35 | 2021-01-19 | ENWL | 1.11 (annex1) | Annex 1, indicative process | Ofgem should predefine the time period to identify any extra info it needs if any, or the application should be treated as complete by a given duration if no further data is requested. This kind of provision applies in ED1 and is good practice |  | The timings of the process may vary on a case-by-case basis as part of our proportionate approach and assessment tier process.
36 | 2021-01-19 | ENWL | 1.18 (annex 1) | Annex 1, indicative process | A fair and reasonable minimum timeframe for company response should be provided and defined and should be based upon the timescales over which Ofgem has prepared it's reopener to allow the company to undertake a similar depth of work if desired and/or required. The timescales for a company to respond should be adequate for the company to fully assess the information from Ofgem and provide further insight, which may take time to provide if substantial evidence needs to be collated. This is particularly a concern where the Authority may trigger a reopener itself. |  | Comment noted. The timeframe for the information requested as part of an Authority Triggered Re-opener will be decided on a case-by-case basis and is intended to be proportionate in nature.
48 | 2021-01-29 | National Grid | 1.8 | Annex 1, indicative process | 1.8 - This states that Annex 1: Application process does not form part of the guidance document. The rationale for this is unclear and we believe that this should be included, and changes to Annex 1 consulted on as with other parts of the document. It would be contrary to best regulatory practice for Ofgem to consult on Annex 1 now but to then seek to make any material changes to the policy in it without further consultation. It is also clearly unhelpful for the regulatory framework to have an Associated Document which contains material which is stated to not be part of that Associated Document. |  | We believe this refers to 1.8 of the draft Re-opener Guidance and Application Requirements document issued on 17 December 2020. The process has been moved into a separate working document but we have worked closely with licensees to develop this through consultation and workshops.
69 | 2021-01-29 | National Grid | Annex 1 | Annex 1, indicative process | Table 1, Step 3 – This step involves Ofgem reviewing whether it has all information. Under the current draft, Ofgem stating that certain information has not been provided would be a determination of licence breach and so would (to be consistent) need to follow Ofgem’s enforcement process, with the work and delay that this would involve. This is an important reason why Ofgem should accept the changes we propose in the “General” section of this response. Should Ofgem retain the current approach, our understanding is that before Ofgem makes any determination of breach as part of an application process, it will follow its published enforcement process. |  | The Re-opener Guidance and Application document was updated following review of consultation responses. An option was added for the licensee to provide justification of why information was not submitted.
70 | 2021-01-29 | National Grid | Annex 1 | Annex 1, indicative process | Table 1 – We propose that timescales are included for clarity and request that the licensee is provided with the Ofgem draft documents for comment prior to Ofgem publishing on their website. |  | The timings of the process may vary on a case-by-case basis. Should it be felt appropriate to share particular decision documents with the licensee prior to publication this will be for the limited purpose of fact / redaction checking only.
71 | 2021-01-29 | National Grid | Annex 1 | Annex 1, indicative process | 1.4 - Re-opener pipeline log – The requirements here are quite detailed and we note might not be proportionate to be provided in all cases. |  | Information in the Re-opener pipeline log should be forecasted as far as is reasonably practicable.
72 | 2021-01-29 | National Grid | Annex 1 | Annex 1, indicative process | 1.10 – states “We will work with stakeholders to develop this tiered assessment process, including the criteria for the three tiers”. We would be grateful if Ofgem would confirm timescales for this further work. |  | Workshop with licensees held in May 2021.
73 | 2021-01-29 | National Grid | Annex 1 | Annex 1, indicative process | Authority triggered reopener process – We propose that timescales are included for each step to aid clarity |  | The timings of the process may vary on a case-by-case basis.
76 | 2021-01-29 | NGN | 1.8 | Annex 1, indicative process | If annex 1 is not part of the guidance it should not form part of the guidance | Remove annex 1 and paragraph 1.8 | We believe this refers to 1.8 of the draft Re-opener Guidance and Application Requirements document issued on 17 December 2020. The process has been moved into a separate working document but we have worked closely with licensees to develop this through consultation and workshops.
80 | 2021-01-27 | NPG |  | Annex 1, indicative process | Paragraph 1.8 states that Annex 1 sets out how Ofgem intends to manage the re-opener process but also states that it “does not form any part of the Guidance and may be modified and updated at any time without prior consultation”. In that respect: As drafted, Annex 1 imposes obligations on the licensee. If that is Ofgem’s intent, it is not appropriate either for Ofgem to be able to change those obligations without consulting with the licensee or for them not to be subject to the usual change control process. Either Annex 1 should be made subject to consultation in its entirety or any obligations on the licensee contained therein should be carved out such that they are made subject to consultation; or If it is Ofgem’s intent for Annex 1 not to be within the scope of the Guidance and, therefore, the licence condition, such that it does not impose obligations on the licensee, Ofgem should make that position unambiguously clear within paragraph 1.8 of the Guidance. |  | We believe this refers to 1.8 of the draft Re-opener Guidance and Application Requirements document issued on 17 December 2020. The process has been moved into a separate working document but we have worked closely with licensees to develop this through consultation and workshops.
97 | 2021-01-29 | SGN | Annex 1, para 1.12 | Annex 1, indicative process | Rejection of an application. It is important that an applicant should have an opportunity to rectify any shortfall if an application does not pass the pre-acceptance screening on a technicality or due to a lack of clarity or confusion in the guidance | Proposed wording. "If an application does not pass the initial assessment for a technical reason the applicant will be given the opportunity to rectify that specific shortfall." | We intend to reject applications if they do not evidently comply with the requirements of the relevant licence conditions or do not evidently comply with the Re-opener Guidance and Application Requirements document.
98 | 2021-01-29 | SGN | Annex 1 Para 1.15 | Annex 1, indicative process | Definition of the window in which SQs will be asked is required, these will normally involve subject matter experts who are entitled to take annual leave. Alternatively, we need to recognise that response times of greater than 5 days may be required where the subject matter expert is on leave. |  | Drafting has been amended to reflect this comment.
99 | 2021-01-29 | SGN | Annex 1 Para 1.17 | Annex 1, indicative process | For an authority triggered reopener it is important to have a further step, a consultation on the appropriateness and the proposed scope of the re-opener. This is particularly important for reopeners such as the net-zero reopener. |  | The process is flexible. A policy consultation stage may be used where an issue has not previously been considered, and is likely to have a material impact on our Direction.
102 | 2021-01-29 | SPT |  | Annex 1, indicative process | The draft Re-opener Guidance purports that Annex 1 does not form part of the guidance and may be modified at any time without prior consultation. If Annex 1 is not part of the Reopener Guidance, it should not be issued as part of the Associated Document. It is inappropriate for a provision of any guidance to seek to circumvent the mechanisms set out in the licence around how an Associated Document should be amended |  | The process has been moved into a separate working document but we have worked closely with licensees to develop this through consultation and workshops.
104 | 2021-01-29 | SPT |  | Annex 1, indicative process | As part of Ofgem’s decision-making process for a re-opener application, Ofgem should provide timelines for the screening stage, assessment and SQ process, the minded to decision and the draft decision. Decisions and pre-acceptance screening should be consulted on with a minimum 28-day period. A long or undefined review process timeline for reopeners will directly compromise the service that SPT can provide customers and the timing of connections for new generators. As Ofgem have introduced a new Quality of Connections incentive, SPT should not be exposed to penalty risk due to uncertainty in Ofgem decision timings that will directly affect the service we are able to offer our customers for new connections that are not eligible for the volume driver. |  | The timings of the process may vary on a case-by-case basis as part of our proportionate approach and tiered assessment process. We have decided on an approach using assessment tiers to allow for agile and timely decision making.
109 | 2021-01-29 | SPT | 1.8 | Annex 1, indicative process | This paragraph purports that Annex 1 does not form part of the guidance and may be modified at any time, without prior consultation. If Annex 1 is not part of the guidance, it should not be issued with the guidance. It is wholly inappropriate for a provision of the guidance to seek to circumvent the mechanisms set out in the licence around how an Associated Document should be amended. Annex 1 must be removed from the guidance or this paragraph should be removed from the guidance and the process around modifying the guidance in SpC 9.4 not sought to be circumvented. We provide comments on Annex 1 below only on the basis that this paragraph 1.8 is deleted. | Delete paragraph 1.8. | We believe this refers to 1.8 of the draft Re-opener Guidance and Application Requirements document issued on 17 December 2020. The process has been moved into a separate working document but we have worked closely with licensees to develop this through consultation and workshops.
119 | 2021-01-29 | SPT | Annex 1 - General | Annex 1, indicative process | As per our comment above, it is not appropriate for this annex to be included in the guidance and be said not to form part of the guidance. The text "We provide below an indication of the application process. This does not form part of the guidance document and is provided on an indicative basis only." should be deleted if Annex 1 is to be retained within the guidance document. Also as stated above, we comment on this Annex on the basis that it does form part of the guidance and the Authority does have to consult on any changes to it (which is the most appropriate approach). |  | The process has been moved into a separate working document but we have worked closely with licensees to develop this through consultations and workshops.
120 | 2021-01-29 | SPT | Table 1 - Pre acceptance screening | Annex 1, indicative process | Ofgem should also provide confirmation to licensees that applications will proceed to the next stage. Timescales for the screening stage should also be provided. In terms of the consultation/ intention to reject, this should be provided for in the licence condition (as per the other mechanisms in the licence conditions which set out the process for the Authority to make a direction) and should make it clear that representations can be made with a period of at least 28 days. We would also expect Ofgem to engage with the network operator in the event that an application is considered to be lacking information before making a judgement to reject, in the event that information has been missed in error. |  | Drafting has been modified to reflect the first comment. The timings of the process may vary on a case-by-case basis as part of our proportionate approach and tiered assessment process. We intend to reject applications if they do not evidently comply with the requirements of the relevant licence conditions or do not evidently comply with the Re-opener Guidance and Application Requirements document.
121 | 2021-01-29 | SPT | Table 1 - Assessment including SQ process | Annex 1, indicative process | A timescale for this assessment and SQ process should be provided - it is essential that licensees have transparency around the timescales Ofgem ought to be working to. It is also not clear what "as approporiate for the tier" is referring to - this needs to be clarified. |  | The timings of the assessment and SQ process may vary on a case-by-case basis as part of our proportionate approach and assessment tier process. Drafting has been modified to reflect the second point and provide indicative timings for the three assessment tiers.
122 | 2021-01-29 | SPT | Table 1 - Minded to decision | Annex 1, indicative process | A minded to decision should be consulted on, with a minimum 28 day period, with the same licence mechanism described above to ensure this step and this process is captured. Also a timescale for developing and issuing the minded to decision should be provided - it is essential that licensees have transparency around the timescales Ofgem ought to be working to. |  | The document has been redrafted to explain when a policy consultation may be used. The proposed Direction will be consulted on for not less than 28 days. The timings of the process may vary on a case-by-case basis as part of our proportionate approach and assessment tier process.
123 | 2021-01-29 | SPT | Table 1 - Draft Decision and Decision | Annex 1, indicative process | A timescale for when the draft decision is likely to be issued after a minded to decision (if relevant) or assessment stage and for when the decision is likely to be issued after the draft decision should be provided - it is essential that licensees have transparency around the timescales Ofgem ought to be working to. |  | The timings of the process may vary on a case-by-case basis as part of our proportionate approach and assessment tier process.
124 | 2021-01-29 | SPT | Annex 1, 1.4 | Annex 1, indicative process | Reference to needs case should only be "(where applicable") |  | A needs case is required in all instances and this has been reflected in the main Re-opener Guidance and Application Requirements document published 26 February 2021. | Is it? What about 3.17 in NGGT's licence? What about CAM?
125 | 2021-01-29 | SPT | Annex 1, 1.6 | Annex 1, indicative process | As per SPT's Licence Consultation Response, it is not appropriate that the licence nor the guidance cross refers to the Final Determination. It is not clear why this is relevant here - and if it is, the relevant comments/ drafting from the FD should be reflected in the Annex rather than cross referring to the FD. |  | Drafting has been modified to reflect this comment.
126 | 2021-01-29 | SPT | Annex 1, 1.9 - Standard | Annex 1, indicative process | It is not clear what is meant by "similar standard level of regulatory scrutiny" - this is to be similar to what? More detail is needed regarding what is meant by "standard" |  | Drafting has been modified to reflect this comment.
127 | 2021-01-29 | SPT | Annex 1, 1.16 | Annex 1, indicative process | The details of the NGGT Annex is not relevant to SPT - why is this being referred to generically here? Is the gateway style approach relevant to SPT? More clarity is needed here. Furthermore, as per our comment above, cross reference to the Final Determination is not appropriate and any relevant detail should be reflected in the Annex. |  | Drafting has been modified to reflect this comment but the reference remains as an example of where a gateway style approach may be used.
131 | 2021-01-29 | SSEN | Annex 1 | Annex 1, indicative process | We have concerns with the pre-acceptance screening stage set out in 1.11 of Annex 1. Infrastructure projects is complex and the re-opener process should recognise this. If Ofgem reject an application at the pre-screening stage, it should commit to setting out (i) its reasons for doing so and (ii) why this is in the interests of consumers. A significant amount of the funding available to aid delivery of Net Zero during RIIO-2 will be made available through reopeners. The process for Ofgem’s review and rejection of any reopener applications should be as open and transparent as possible, particularly in light of the role of enhanced stakeholder engagement in the RIIO-2 framework and the role of stakeholders in developing re-opener applications. We note the importance of ensuring that applications are processed in a timely fashion, avoiding any unnecessary delays. We have concerns around Ofgem’s move to introduce latitude for its assessment of an application to extend beyond nine months. In paragraph 1.9 of Annex 1 Ofgem state “an application may attract additional scrutiny, potentially lengthening the process timescales from the indicative nine months, if the decision is complex, proposed costs are large, or if the submission is of a poor quality.” Fundamentally, we do not think it is appropriate for significant changes to processes (such as this) to be introduced by way of Associated Documents. The implementation risks engendered by Ofgem’s approach to RIIO-2 are significant and have been repeatedly highlighted by network companies throughout the development of the price control. We would welcome Ofgem’s confirmation that they are sufficiently resourced to ensure the timely review and approval of the many reopener applications network companies anticipate making during the period. We are concerned that Ofgem is introducing latitude to extend the review period in order to guard against insufficient resource availability to meet its timelines. |  | We intend to reject applications if they do not evidently comply with the requirements of the relevant licence conditions or do not evidently comply with the Re-opener Guidance and Application Requirements document. If an application is rejected, licensees will be informed of the reason for this. The assessment tiers have been added to the process to allow decisions to be made in a proportionate and timely manner.
148 | 2021-01-29 | UKPN | Annex 1 | Annex 1, indicative process | We are concerned that this annex is only “indicative” of the process Ofgem will follow as it introduces a number of concepts (e.g. tiered approach) which may materially affect a licensee’s application. Ofgem should reconsider this annex and introduce it formally into the guidance document following rewriting and consultation with licensees. |  | The process has been moved into a separate working document but we have worked closely with licensees to develop this through consultation and workshops.
149 | 2021-01-29 | UKPN | Annex 1 | Annex 1, indicative process | In table 1 it is not clear who owns and updates the pipeline log although para 1.2 infers it is Ofgem and not each licensee. |  | The Re-opener pipeline log must be provided by licensees as part of their RRP, as a minimum.
150 | 2021-01-29 | UKPN | Annex 1 | Annex 1, indicative process | Table 1 and para 1.11 introduce the concept of pre-application screening – such a key activity (mindful it means an application could be rejected) should be included on the face of the relevant licence condition and not in an Annex to a guidance document. We note it is not included on the face of the ED1 CAM condition which is undergoing a parallel statutory consultation. |  | This document explains our indicative process for managing Re-opener applications. We intend to reject applications if they do not evidently comply with the requirements of the relevant licence conditions or do not evidently comply with the Re-opener Guidance and Application Requirements document.
151 | 2021-01-29 | UKPN | Annex 1 | Annex 1, indicative process | Para 1.4 introduces double jeopardy on licensees as it repeats an obligation included in the RIGs. It should be reworded to avoid this. |  | This paragraph was removed from the Re-opener Guidance and Application Requirements document. The working process document notes that information on the Re-opener application pipeline log will be provided as part of the Regulatory Instructions and Guidance document for RIIO-2 which is still to be consulted on and published.
152 | 2021-01-29 | UKPN | Annex 1 | Annex 1, indicative process | Para 1.15 introduces an obligation on licensees to respond to SQs in five working days – we are unclear if this statement actually has effect on licensees mindful that Ofgem have explicitly excluded this annex from being part of the guidance document. Furthermore the turnaround time should be mindful of the materiality and scope of the SQ i.e. five working days may not be appropriate for more significant questions. |  | Drafting has been modified to reflect this comment.
153 | 2021-01-29 | UKPN | Annex 1 | Annex 1, indicative process | Para 1.7 should cross reference the process for Authority triggered reopeners set out in the relevant licence conditions. |  | The process set out in the relevant licence condition for Authority triggered Re-openers has been referenced in the Chapter on 'Authority triggered Re-opener process'. | Needs updating with new chapter name
156 | 2021-01-29 | WPD | 1.8 | Annex 1, indicative process | The last sentence suggests that Annex 1 (the process to be followed) can be changed at any time without consultation. This is unreasonable regulatory practice. All parties should be clear on the process that wil be followed. | Suggest revision to last sentence: This does not form any part of the Guidance and may be modified and updated at any time without prior consultation, ; but the Authority will seek to provide notice to licensees that changes to the process are to be implemented. | We believe this refers to 1.8 of the draft Re-opener Guidance and Application Requirements document issued on 17 December 2020. The process has been moved into a separate working document but we have worked closely with licensees to develop this through consultation and workshops.
162 | 2021-01-29 | WPD | Annex 1 1.1 | Annex 1, indicative process | What happens if the 9 month deadline cannot be met? The last sentence suggests that the timescales could be open ended. This should have a time limit included. | Suggest the addition of the following senetence at the end "If the 9 month deadline is not met the assessment will be completed in time for the Annual Iteration Process in the following year" | Drafting has been amended to reflect this comment.
163 | 2021-01-29 | WPD | Annex 1 Table 1 Item 3 | Annex 1, indicative process | This suggest a rejection of the application where any of the requirements are omitted. There should be an opportunity for licensees to submit additional details should Ofgem identify an omission. | Additional sentence to be included. "Where the Authority Identifies an omission, it will provide licensees the opportunity to submit the omitted details, before making a decision to reject the application."Applications will only be accepted and proceed to the next stage if they pass this initial assessment. We will notify licensees if an application is rejected and publish details on our website. | We reserve the right to reject an application that does not evidently comply with the requirements of the relevant licence conditions or does not evidently comply with the Re-opener Guidance and Application Requirements document.
164 | 2021-01-29 | WPD | Annex 1 Table 1 Item 4 | Annex 1, indicative process | It should be clear what the SQ are seeking to achieve. | Amended drafting suggestion: Ofgem will carry out a detailed assessment of the application (as appropriate for the tier), including asking any SQs it considers appropriate (to assist in understanding the re-opener and carry out the reopener assessement) and prepare a decision for consultation. | Drafting has been amended to reflect this comment.
165 | 2021-01-29 | WPD | Annex 1 Table 1 Item 5 | Annex 1, indicative process | Ofgem should be clear on the criteria that would lead to a minded to position being published. At present there is no indication of what would lead Ofgem to adopt the publication of a minded to position. |  | Drafting has been modified to reflect this comment.
166 | 2021-01-29 | WPD | Annex 1 Table 1 Item 7 | Annex 1, indicative process | No timescales are provided for Ofgem's consideration of consultation responses. Is such consideration open ended? |  | The timings of the process may vary on a case-by-case basis as part of our proportionate approach and tiered assessment process.
167 | 2021-01-29 | WPD | Annex 1 1.3 bullet 5 | Annex 1, indicative process | The pipeline log has a requirement for licensees to give six months notification of potential re-opener claims. Bullet 5 suggests that Authority triggered re-openers will be part of the pipeline process. The authority should operate to the same notification expectations placed upon licensees. | Suggested edit to bullet 5: make companies aware of our intention to trigger an Authority triggered re-opener, giving six months notice on a similar basis as expectations on licensees. | Pre-application engagement will likely take place for these Re-openers, where appropriate, also but flexibility has been built in to allow for proportionate treatment.
168 | 2021-01-29 | WPD | Annex 1 1.4 bullet 4 sub-bullets 2 and 3 | Annex 1, indicative process | This list of requirements for the RRP is almost the same as the details to be provided within a submission. There is no need at the pipeline stage to be detailing the options considered and evidence of costs | Suggested deletion • outline description of the application to be submitted, which should include: ○ the needs case ○ the nature of costs incurred and the evidence presented in support of these ○ the options for the proposed work and the methodology used for their assessment. | Information should be brief and provide more detail for those applications expected in the next 12 months/regulatory year.
169 | 2021-01-29 | WPD | Annex 1, para 1.9 | Annex 1, indicative process | This para covers the different tiers of assessment which seems a sensible approach in principle. Please can Ofgem confirm whether it can be DNO specific, e.g. one DNO can be fast-tracked on a reopener mechanism, whilst others submitting under the same mechanism may be go through the standard process, due to the quality of their submission |  | The assessment tier can be specific to each individual Re-opener application submitted.
170 | 2021-01-29 | WPD | Annex 1, para 1.9 | Annex 1, indicative process | This para states that "an application may attract additional scrutiny, potentially lengthening the process timescales from the indicative nine months, if the decision is complex, proposed costs are large, or if the submission is of a poor quality." All efforts should be made to avoid this as far as possible, to avoid delaying necessary investment. The factors of a complex decision and large proposed costs can be partly considered ahead and anticipated ahead of submission, such as through the pipeline log? |  | The assessment tiers and pre-application engagement are designed to allow decisions to be made in a proportionate and timely manner. There may be occasions where an application is subject to additional scrutiny, which may lengthen the process.
171 | 2021-01-29 | WPD | Annex 1 1.14 | Annex 1, indicative process | The second sentence potentially inhibits Ofgem asking for the additional data which is missing. | Suggested redraft: The SQ process is intended for clarification purposes only. Licensees should not expect to use it as a means of submitting additional information that the original re-opener application should have included and is missing, but such information should be provided if the Authority requests it as part ofthe SQ process.. | It is not our intention to use the SQ process as a means of working up weak or poor quality applications. However, we do not believe the current drafting inhibits Ofgem from requesting additional data that may be required to assess a Re-opener application.
172 | 2021-01-29 | WPD | Annex 1 1.15 | Annex 1, indicative process | There may be situations beyond a licensees control which may require the agreement of a longer time period for the provision of responses to SQs. A longer timescale could therefore be initiated by the licensee and agreed by the Authority. Such a circumstance needs to be made clear. | Suggested additional text: Licensees will be required to respond to an SQ within five working days unless otherwise specified by us or requested by the licensee and agreed by us. | Drafting has been amended to reflect this comment.
173 | 2021-01-29 | WPD | Annex 1, para 1.17-.19 | Annex 1, indicative process | As stated in WPD's ED2 SSMC consultation response, we have concerns regarding Authority triggered re-openers and so welcome more detail on this proposal. There is a concern about this being at any time during the price control. This could be incredibly complicated, and could lead to chaos. Ofgem should have defined windows so that DNOs are clear when a window is passed that no re-opener will take place that year. No windows are specified in this document |  | Pre-application engagement will likely take place for these Re-openers, where appropriate, also but flexibility has been built in to allow for an agile process.
174 | 2021-01-29 | WPD | Annex 1 1.17-1.19 | Annex 1, indicative process | The authority triggered re-opener process should be subject to a similar pipeline process of six months notice so that licensees have time to prepare resources and information for the reopener process. |  | Pre-application engagement will likely take place for these Re-openers, where appropriate, also but flexibility has been built in to allow for proportionate treatment.
175 | 2021-01-29 | WWU | 1.8 | Annex 1, indicative process | delete 1.8 | delete 1.8 | We believe this refers to 1.8 of the draft Re-opener Guidance and Application Requirements document issued on 17 December 2020. The process has been moved into a separate working document but we have worked closely with licensees to develop this through consultation and workshops.
176 | 2021-01-29 | WWU | Annex | Annex 1, indicative process | A clearly defined process is by which Ofgem will access re-opener applications is vital for licensees and this should be in the main document as an appendix. | Make the annex an appendix and delete 1.8 | The process is a separate working document but we have worked closely with licensees to develop this through consultation and workshops.
177 | 2021-01-29 | WWU | Annex | Annex 1, indicative process | Re-opener log. Given that the annex is not part of the document how is the requirement to update the log through RRP reporting to be implemented? Will this be done through Standard Special Condition A40? | this would be solved if the annex was made part of the document as proposed above | The Re-opener pipeline application log will be consulted on further through the RRP/RIGs consultation process. An information request will be issued to capture Re-opener pipeline information for 2021/22.
178 | 2021-01-29 | WWU | Annex | Annex 1, indicative process | Tiered process. We support the concept of a tiered process but the document does not contain any guidance on which re-openers are likely to be applicable for it. We suggest that one candidate will be the Net Zero pre-construction and small projects re-opener. |  | The assessment tier process will be applied to all Re-openers, where possible.
179 | 2021-01-29 | WWU | Annex | Annex 1, indicative process | In re-openers the licence refers to costs "costs incurred or expected to be incurred on or after 1 April 2021". It is not clear how expected costs will be assessed and how much certainty is required. Will informal discussions be held when the pipeline of expected submissions are notified, if so this needs to be clear in the document. |  | Within the Re-opener pipeline log, licensees should provide, so far as reasonably practicable, forecast information about applications they anticipate submitting during RIIO-2. We expect pre-application engagement from the licensee at least 3 months prior to a Re-opener application being submitted (reduced from the previously requested 6 months).
7 | 2021-01-29 | Centrica | Tiers | Annex 1, indicative process | A clear disincentive to making speculative applications is required. Re-opener mechanisms should not be seen as a ‘free bet’ to increase expenditure allowances. Companies should demonstrate the efficiency of their proposals from the consumer perspective, taking account of the expenditure allowances consumers will be required to fund via the Totex Incentive Mechanism. Also, applications should be thoroughly scrutinised. Therefore, we believe the proposed fast-track framework should be tightened. We acknowledge the intent to design the re-opener process to be agile since, relative to RIIO-1, a greater number of re-opener mechanisms is included and a greater number of applications is expected. In principle, we support the intent and we recognise this is a reason why ‘lighter touch’ assessments are proposed. However, the efficiency of all applications from the consumer perspective should be thoroughly tested - at least the standard level of regulatory scrutiny should apply. This is necessary given that up to £10bn of expenditure allowances could be provided to the transmission and gas distribution companies via uncertainty mechanisms (including re-openers). This means the proposed fast-track framework should therefore be tightened. ‘Lighter touch’ assessments may not always deliver long-term consumer value. A recent example of ‘lighter touch’ assessments is ‘fast-tracking’ at the RIIO-1 price control reviews. In its review of the RIIO arrangements, CEPA state the cost of Western Power Distribution being ‘fast-tracked’ during the RIIO-ED1 price control review is £510m of increased revenue. The benefits are less clear-cut. Further, CEPA was unable to establish whether ‘fast-tracking’ in the transmission price controls delivered consumer value. The broad approach that underpinned ‘fast-tracking’ in RIIO-1 is not dissimilar to that proposed in the guidance. Similarly, it is unclear whether the four ‘High Value Projects’ applications submitted during 2019 window for electricity distribution would have been assessed as inefficient had ‘lighter touch ’arrangements existed. If they were approved, consumers would have been required to fund £177m of expenditure allowances. It is unclear whether the ‘lighter touch’ assessments proposed can robustly identify inefficiency. As such, we recommend:•The efficiency of all applications from the consumer perspective should be thoroughly tested regardless of the initial perceptions of the quality of the evidence provided by the companies. •The efficiency of all applications from the consumer perspective should be thoroughly tested even if there is a substantial benefit or if the decision is not complex.•It may be appropriate to take a ‘lighter touch’ approach to the Needs Case stage if one was previously established and circumstances have not materially changed since. These improvements are necessary to avoid consumer value being lost due to insufficient level of scrutiny. |  | We maintain our position that assessment tiers are appropriate to allow for agile and timely decision making.

## May 2021 responses - process
URN | Comment from | Document reference | Topic/area | Comments/questions | Response
38 | NGGT & NGET | ` | 1.13 | Should just refer to the AD here and not special condition 9.4. It is the AD (not the licence condition) which requires publication of the application on the website | Drafting has been modified to reflect this change
40 | NGGT & NGET | Reopener process document | 1.25 | Says that if an application clearly does not contain the information to answer the questions in 1.19 then it would not go to standard assessment. But presumably if an application clearly does not contain this information then would it not fail at the stage 3 screening stage? | The screening stage is designed to exclude invalid applications, not exclude poor quality applications.
41 | NGGT & NGET | Reopener process document | 1.26 | Would a “weak or poor quality application” not fail at stage 3 screening? The stage 3 text needs to be clearer on what must happen for an application to fail at this stage. As written it suggests not complying with a relevant licence condition or the AD would mean failure whereas stage 4a suggests an application could be weak/ poor (which one could read as non-compliant with the AD) yet still pass at stage 3. Stage 3 failure criteria should be clear and transparent and not give Ofgem broad discretion to fail an application. | The screening stage is designed to exclude invalid applications, not exclude poor quality applications.
42 | NGGT & NGET | Reopener process document | 1.31 | Suggest “the direction” instead of “this” | Drafting has been modified to reflect this change
43 | NGGT & NGET | Reopener process document | 1.32 | This should refer to Stage 7 Direction (not decision) in line 2 | Drafting has been modified to reflect this change
44 | NGGT & NGET | Reopener process document | 1.33 | This seems to be covering scenarios both where there is no decision (but where an application has been made) and also where no application has been made. Is this the intention and licensees would therefore use forecast values even prior to submitting an application? If so, opening words could perhaps be changed to clarify “Where a Stage 7 Direction has not yet been made (including where an application has not yet been made by the licensee), the licensee should…” When considering the enduring forecasting process for re-openers, consideration should be given to the distinction between officially determined positions, and future forecasts to ensure there is full process clarity and no risk of double count. | We will continue to review this process over time and make adjustments where necessary.
45 | NGGT & NGET | Reopener process document | 1.35 | Where Ofgem is choosing to trigger a reopener, Ofgem should aim as good practice to give the network as much advance notice of this reopener being triggered as possible. | Comment noted
46 | NGGT & NGET | Reopener process document | 1.35 | The licence conditions provide for Ofgem directing alternative application windows (in addition to those specified in the particular condition). • Suggest first bullet refers to “directing an additional Re-opener window…” in order to reflect the licence drafting. • We presume that the direction referred to in the second bullet is then the direction to permit an alternative application window. It is not clear what the second sentence “in this latter case the process set out in the relevant licence condition will be followed”. Please can Ofgem clarify. | Drafting has been modified to reflect this change
34 | NGGT & NGET | Reopener process document | 1.5 | Ofgem indicate within the table that they would expect pre-application engagement to take place 6 months in advance of the reopener. This may not be practical for all reopeners. It may be that this is high level further out and more detailed as the reopener progresses, it would helpful for Ofgem to acknowledge this within the document. | Drafting has been modified to reflect this change
35 | NGGT & NGET | Reopener process document | Stage 1a Pipeline Log | Suggest another bullet point to include in the list describing the uses of the pipeline log information is: ‘to enable the Authority to plan workload and resources proportionate to the level of complexity & regulatory scrutiny envisaged’. | Drafting has been modified to reflect this change
36 | NGGT & NGET | Reopener process document | Stage 1a Pipeline Log | Pipeline reopener log: We are supportive in principle of a pipeline reopener log with a purpose of enabling Ofgem to understand the upcoming pipeline of potential reopeners. However, we have specific concerns around any perceived linkage between the pipeline log and the revenue workbook. No such linkage is called out in the list of uses for the reopener pipeline log as set out in para 1.7. Whilst there is some overlap in the information required to populate these two documents, the purpose of the pipeline log is very different to that of the revenue workbook which is used to inform the forecasting of Allowed Revenue. We therefore request that Ofgem clarify this difference between the purposes of the pipeline reopener log and the revenue workbook. In our view the pipeline reopener log should be a forward workplan and not explicitly linked to forecasting at this stage. The original inception of this document appeared to be a workload tracking tool to allow Ofgem to schedule resources. However, as drafts have evolved, it has transitioned from a pipeline tracking tool to something that feeds forecasts with a commensurate amount of financial granularity. Whilst in some circumstances, projects in the pipeline log would be known at sufficient cost certainty to provide a phased forecast, there are a number of reopeners for which a reasonable level of cost certainty is not known at this point. It may only be desirable for the values to flow through to charge setting where there is a high degree of confidence that the new values are likely to provide a more representative view of future transmission charges. For example, there ought to be a high degree of confidence that substituting a positive value for cyber costs in years 4 & 5 will be more representative than the current situation where the PCFM indicates zero cyber costs for this period. Conversely, it could be premature to flow through indicative reopener values for some future investments if there is a high degree of uncertainty around triggers. We propose that this is remedied by explicitly de-linking the pipeline log and revenue forecasting (at least for the first year of RIIO-T2). For workload planning purposes, capturing gross totex cost ranges within the pipeline log is an appropriate level of detail to help plan Ofgem’s assessment resource e.g. <£10m, £10-50m, £50-100m, £100-500m, >£500m. We would expect a degree of overlap between the information used to populate the reopener pipeline log and the revenue workbook, for example for those reopeners with a high degree of certainty in terms of cost and submission timeframe. | The RRP will collect both the cost and volume data and the PCFM requirements (i.e. the current Reg Fin revenue workbook and revenue pipeline log will be integrated into the RRP). Our aspiration remains that, where possible, the revenue workbook inputs will be auto-populated from the detail collected in the cost & volumes section of the RRP. The approach suggested in this comment would require very similar data to be collected twice. As well as creating extra regulatory burden, this may also result in inconsistent data capture. Drafting of 1.7-1.8 has been amended to reflect this comment.
22 | SSEN | Re-opener assessment process version 1 | Assessment Tiers | Ofgem should explicitly state within the document how it will communicate justification for any determination of the appropriate assessment tier. It is not clear whether this will be published (e.g. on the Ofgem website) or simply confirmed verbally via bilateral engagement. Transparent communication will assist and benefit other network companies for future reopener submission. | Drafting has been modified to reflect this change
23 | SSEN | Re-opener assessment process version 1 | Assessment Tiers | It would also be useful to understand the scope network companies be afforded to influence and challenge any determination on the assessment tie. We would appreciate confirmation from Ofgem that there is scope for network companies to recommend the applicable assessment tier in the first instance, given the background knowledge and scheme understanding. | The appropriate assessment tier may be discussed at the pre-application engagement stage. It is not proposed that the decision on the appropriate assessment tier will be subject to challenge. | Recommend changing to: "Licensees will be able to put forward their view on the assessment tier at pre-application engagement stage and as part of their application. If they disagree with the tier allocated they can communicate this to Ofgem." This is because licensees are going to do this anyway so we might as well say they can do it. Plus we don't get to say there is no method of challenge. There is, its JR.
12 | Cadent | Slide pack – slide 7 & Re-opener assessment process working document (para 1.25, p10) | Assessment Tiers | Interpretation: Applications with costs “below 1x the relevant materiality threshold may be considered suitable for the Fast-Track Assessment Tier.” Comment: As drafted it would not be possible to be considered for fast track from a materiality perspective. If below 1x the materiality threshold for the relevant re-opener then the application would not meet licence requirements and would be rejected at screening. We believe that this is intended to mean that applications less than 1x the standard materiality threshold for the relevant licensee as set out in SpC 1.1 Interpretations and Definitions of their licence may be considered for fast track. | Drafting has been modified to reflect this change
54 | SPT | Working document: RIIO-2 Re-opener assessment process version 4 | Assessment Tiers | Stage 4b Assessment Tiers. Given the scale of coverage related to the Materiality Threshold (MT), it would be appropriate to have some further guidance in relation to the Fast-Track process. There was mention made – in the workshop - of Net Zero and Cyber Security not having any MT generating this option. The rationale, however, needs further work. It could mean that a scheme (of this nature) - where the costs exceed MT – is Fast-Tracked when if it were of a different type (with an MT) it would be processed through Standard or Additional Scrutiny. | Drafting has been modified to reflect this comment.
24 | SSEN | Re-opener assessment process version 1 | Current usage | We note that Ofgem stated during the workshop discussion that this assessment process is being deployed for the current reopener applications. However, for our Cyber OT and IT applications, at the time of writing we have neither received (i) confirmation that the screening checks were passed; nor, (ii) confirmation of which assessment tier has been applied. We note that the guidance states applicants will be notified upon both rejection and/or acceptance of their application. The Guidance should also state that, in the event of rejection, Ofgem will provide detail on the justification supporting any such rejection. | This has been relayed to the Cyber Re-opener policy leads. Confirmation will be provided as and when appropriate for each individual Re-opener application. | Suggest changing to "This has been relayed to the Cyber Re-opener policy leads and we not that this early re-opener has commenced before publication of this document."
33 | NGGT & NGET | Reopener process document | Footnote 6 | This gives the example of the GT PAP process. But the reference hyperlink is to the draft determination and doesn’t work. Presumably the correct reference should be to the Final Determination document NGGT Annex paragraphs 3.27-3.38. | Drafting has been modified to reflect this change
16 | SSEN | General | General | The path to Net Zero remains uncertain and a flexible reopener assessment process is paramount in assisting both network companies and Ofgem to facilitate delivery of Net Zero at lowest cost to the consumer, while maintaining world-class levels of system reliability. | Comment noted
17 | SSEN | General | General | It is with this approach in mind that, whilst helpful, we would question the overall benefit this document will provide in delivering an agile reopener process. We would prefer to see tangible commitments based around the existing RIIO-2 framework presented in a sector specific process document. Doing so would allow Ofgem to be more specific in delivering an efficient, agile, and proportionate approach to decision making. | We do not believe that it would be appropriate to create sector specific documents, the process we have created is sufficiently flexible to accommodate the nature of all network company triggered mechanisms. We have published a specific governance document for the Net Zero Pre-Construction and Small Projects Re-opener (https://www.ofgem.gov.uk/publications-and-updates/net-zero-pre-construction-work-and-small-net-zero-projects-re-opener-governance-document), Large Onshore Transmission Investments (LOTI) Re-opener (https://www.ofgem.gov.uk/publications-and-updates/large-onshore-transmission-investments-loti-re-opener-guidance), and RIIO-2 Funded Incremental Obligated Capacity (FIOC) Re-opener (https://www.ofgem.gov.uk/publications-and-updates/riio-2-fioc-guidance-and-submissions-requirements-document-0), which should be read in conjunction with the RIIO-2 Re-opener assessment process document.
18 | SSEN | General | General | For example, in relation to Generation Connections volume driver, schemes can be determined as ‘atypical’ in cost resulting in a requirement to submit a Medium Sized Investment Project reopener (MSIP) request. We would expect Ofgem’s assessment of the cost to focus on the ‘atypical’ component of that submission only (i.e. if the undergrounding of cables results in the scheme becoming atypical, confirmation that Ofgem’s assessment of cost would focus those costs only). In this example, the remaining costs remain within tolerance of the unit cost allowances set for RIIO-2 and should not require reassessment through the MSIP reopener. This approach would deliver a tangible benefit to both Ofgem and Electricity Transmission Owners (ETOs) in the form of resource and timely approval (i.e. potentially fast tracked). | These matters are outside the scope of this document. The parameters of this particular mechanism were fully consulted on during the development of RIIO-2 licence conditions
19 | SSEN | General | General | In addition to the above, sector specific guidance would allow Ofgem to formally clarify that work requested of ETOs by the Electricity System Operator (ESO) will be deemed to have an approved needs case for the purpose of MSIP reopener submissions by ETOs. In such instances, Ofgem’s MSIP process will consist of a review of the cost efficiency of the submission and any Ofgem concerns in respect of the robustness of needs case will be addressed directly with the ESO. This will deliver tangible benefits through reduced resource requirements and timely approvals. | This is outside of the scope of this Re-opener assessment process document and is a matter for the relevant ET Policy lead
20 | SSEN | General | General | These are just two examples of where we consider Ofgem can deliver tangible benefit to consumers, network companies and the regulator itself. We would welcome further discussion with Ofgem should it determine that sector specific process guidance is required. | Comment noted
29 | NGGT & NGET | General | General | Whilst we welcome Ofgem setting out further detail regarding reopeners, we feel that there is further work to be done in creating linkages between all the different elements that contribute to the reopener reporting picture. | Comment noted
30 | NGGT & NGET | General | General | Primarily, we are struggling to understand the purpose, use and process flows around the reopener pipeline log. We are particularly keen to understand the difference and links between the pipeline log and the forecasting elements of the revenue workbook. Additionally, it is our understanding from the December 2020 draft of the reopener guidance and application requirements and noted in this draft (footnote 7) that RIGs relating to the pipeline log are to be issued and consulted on. It would be helpful to see these RIGs so that we can fully comment on this document. | The RRP will collect both the cost and volume data and the PCFM requirements (i.e. the current Reg Fin revenue workbook and revenue pipeline log will be integrated into the RRP). Our aspiration remains that, where possible, the revenue workbook inputs will be auto-populated from the detail collected in the cost & volumes section of the RRP. The RIIO-2 RIGs are yet to be consulted on. The Re-opener pipeline log guidance will be provided as part of the RIGs and the 2021 Re-opener pipeline log information request.
31 | NGGT & NGET | General | General | Given this lack of clarity, we are struggling to provide a fully comprehensive response in relation to the log and welcome a further opportunity to engage with Ofgem once all the relevant documentation is in place. | Comment noted
32 | NGGT & NGET | General | General | At this stage we believe that the pipeline log and the revenue forecasting process should be delinked for this year’s reporting requirements. We recognise there could be future process efficiency with the pipeline log when considered fully as part of future RRPs but, given time considerations and the extent to which processes need to be worked through, keeping the documents separate is prudent at this stage. | The RRP will collect both the cost and volume data and the PCFM requirements (i.e. the current Reg Fin revenue workbook and revenue pipeline log will be integrated into the RRP). Our aspiration remains that, where possible, the revenue workbook inputs will be auto-populated from the detail collected in the cost & volumes section of the RRP. We have amended the Re-opener pipeline log so that the licensee can select if each Re-opener submission should be included in the PCFM.
21 | SSEN | Re-opener assessment process version 1 | General | We note that Ofgem do not intend for the process to be binding on themselves or network companies. It is our understanding is that this is an informal working document which outlines the indicative process which will be followed. The intention is that this will be updated on an ongoing basis as Ofgem iterates its approach to the reopener assessment process throughout the price control. Without wanting to prejudice the flexibility which Ofgem is aiming for, we suggest that more rigour and formality should be put around this process and the associated working document. It would be our preference for this to be binding upon both Ofgem and network companies. This does not mean that the intended proportionality and flexibility would have to be sacrificed. We think Ofgem should consult formally upon this document and publish it as official guidance following the conclusion of that consultation. Expectations on both parties will then be clearer. | A balance must be struck between certainty and flexibility. At this point following discussions with stakeholders we believe that we have struck an appropriate balance. We will continue to review our approach in light of experience.
55 | SPT | Working document: RIIO-2 Re-opener assessment process version 5 | MSIP | • In the workshop we highlighted LSpc3.14 MSIP as a key electricity industry re-opener where it is very likely that there will be projects – which taken individually – would be below MT. We believe Ofgem understands this arrangement, however, it needs to be clear through this process how they will be dealt with: - Individual schemes (eg Cl 3.14.6 (i) iii (ESO driven Op I/t @ c£0.5m) – below MT - are brought forward when the need arises & approved through re-opener where there are no future schemes in the pipeline in this category that will take the cumulative total >MT. Does it progress and what is the ‘efficient, agile and proportionate approach’ to a decision? - Individual schemes (as above) where there are future schemes in the pipeline in this category that will take the cumulative total >MT. Is the scheme eligible for assessment on the basis of future forecast schemes creating a future total > MT are companies expected to ‘proceed at risk’ to recover such costs in a future re-opener application? - Further formal clarity would be welcome on the ‘cross-qualification’ criteria within MSIP to ensure that it can operate successfully to avoid confusion and the rejection of applications in future because they do not meet qualifying criteria. | These matters are outside the scope of this document. The parameters of this particular mechanism were fully consulted on during the development of RIIO-2 licence conditions
56 | SPT | Working document: RIIO-2 Re-opener assessment process version 6 | MSIP | As we highlighted at the workshop, we consider that Ofgem’s “RIIO-2 Re-opener Guidance and Application Requirements Document: Version 1” 26th Feb 2021 could be improved with a separate appendix on MSIP. The Guidance does not really inform the reader in terms of what might be considered ‘proportionate’ given the range of investments that may be processed through this route (eg c£0.1m to >£100m). There is still (too) wide a gap from MT to £100m and the anticipated value of scheme/project expenditure should be a feature of the process flow, which could be licensee specific (to reflect ‘size’ differences etc). | This is outside of the scope of this Re-opener assessment process document and is a matter for the relevant ET Policy lead
10 | Cadent | Re-opener assessment process working document (para 1.33, p12) | Populating re-opener PCFM variable values | Interpretation: Where Ofgem has not yet made a decision on any re-opener application, companies should populate the relevant PCFM variable values using (in order) either: 1. Any published Authority minded-to position 2. The values contained within the company’s application 3. Forecast values from its re-opener pipeline log. Comment: It would be helpful in the re-opener assessment process document could include some worked examples of how this could work. | This is outside of the scope of the Re-opener assessment process document - please refer to the ET2, GD2 and GT2 PCFM Guidance documents for further information on this process: https://www.ofgem.gov.uk/publications-and-updates/decision-riio-2-pcfm-guidance
8 | Cadent | Re-opener assessment process working document (para 1.8, p6) | Re-opener pipeline – re-opener allowance true up | Interpretation: Once a reopener application decision has been made, the decision will supersede the forecast information taken from the pipeline log and any difference will be trued up within the PCFM. Comment: It would be helpful if you could provide worked up examples of how this will work, including if a reopener application is subsequently rejected. | This is outside of the scope of the Re-opener assessment process document - please refer to the ET2, GD2 and GT2 PCFM Guidance documents for further information on this process: https://www.ofgem.gov.uk/publications-and-updates/decision-riio-2-pcfm-guidance.
7 | Cadent | Re-opener assessment process working document (para 1.8, p6) | Re-opener pipeline log – forecast of baseline allowance adjustments | Interpretation: By forecasting adjustments to baseline allowances through pipeline log and them feeding in to PCFM and the AIP – licensees’ revenues can be adjusted ahead of re-opener applications and decisions. Question: Is our interpretation that by forecasting expenditure relating to relevant re-openers that our revenues will be adjusted ahead of the relevant re-opener decision or even potentially before application submission? | This interpretation is correct. We have amended the Re-opener pipeline log so that the licensee can select if each Re-opener submission should be included in the PCFM.
5 | Cadent | Re-opener assessment process working document (para 1.6, p6) | Re-opener pipeline log – inclusion within RRP/RIGs | Interpretation: Re-opener application pipeline log would be submitted as part of our annual RRP and would be subject to RIGs. Comment: It would be helpful for Ofgem to confirm what level of assurance will be required for the information submitted as part of the pipeline log. Some wording confirming that the information is provided on a reasonable endeavour’s basis would be helpful. | The Re-opener pipeline log guidance will be part of RIGs. The guidance will also be provided alongside the Information Request for the 2021 submission.
6 | Cadent | Re-opener assessment process working document (para 1.7, p6) | Re-opener pipeline log – Ofgem use for Authority triggered re-openers | Interpretation: Ofgem will use the pipeline log to consider triggering an Authority triggered re-opener Question: Please could you provide further details of how and where this could be used? | Drafting has been modified to reflect this change
9 | Cadent | Re-opener assessment process working document (para 1.9, p6) | Re-opener pipeline log – updating outside of RIIO-2 RRP process | Interpretation: Networks can update pipeline log at other times of year (in addition to RRP) but these updates won’t be reflected in PCFM until following AIP. Comment: It would be helpful to have further details on how a company should submit a pipeline log alongside their last RIIO-1 RRP in July 2021. Including how these updates should be reflected in the PCFM and subsequently the AIP in Autumn 2021? | Ofgem intends to send an Information Request to collect the Re-opener pipeline log information in June 2021.
37 | NGGT & NGET | Reopener process document | Stage 1: Engagement | We propose there ought to be clear outputs from Stage 1 (pipeline log and preapplication engagement) in order to make for a constructive process and to manage expectations. We propose the outputs of this stage should include that the Authority will provide a written response to the licensee in respect of the pipeline log confirming for each reopener item: • The Authority view of indicative assessment tier (and reasons if the Authority view of tier differs from the licensee), • The nominated point of contact in Ofgem responsible for pre-application discussion | It would not be appropriate to make any decision as to the appropriate assessment tier until after the actual application has been received. We agree it would be useful to identify a point of contact for individual applications both in Ofgem and in the network company.
2 | Cadent | Re-opener assessment process working document (para 1.5 – 1b, p5) | Stage 1: Engagement | Interpretation: We are expected to engage Ofgem in advance of submitting our pipeline log through RRP (Discussions expected at least 6 months before an application window opens) Question: Is our interpretation that Ofgem would expect engagement in advance of submitting the pipeline log through RRP correct? (i.e. late-Jan window, means engagement in late-July the previous year at the latest) | There is no expectation that engagement should commence prior to an application having been flagged in the pipeline log, but engagement can be commenced prior to this if a licensee feels it would be helpful. It should be noted that the pipeline log is intended to collect information for the entire price control period and not just the next set of application windows.
1 | Cadent | Slide pack - Slide 3 | Stage 1: Engagement | Will pre-application engagement be with relevant Ofgem policy team (i.e. Gas Distribution team). Or will Ofgem leads for the different reopeners be communicated? | The appropriate Ofgem staff as deemed necessary by the nature of the application will participate in engagement.
51 | SPT | Working document: RIIO-2 Re-opener assessment process version 1 | Stage 1a Pipeline Log | Stage 1a discussed below (point 2). The working document, however, should include the necessary guidance to facilitate the correct and complete population of the relevant worksheets. | The Re-opener pipeline log guidance will be part of RIGs. The guidance will also be provided alongside the Information Request for the 2021 submission.
52 | SPT | Working document: RIIO-2 Re-opener assessment process version 2 | Stage 1b Pre-Application Engagement | Stage 1b Pre-Application Engagement. This is welcome and it will be helpful in reducing risk. | Comment noted
53 | SPT | Working document: RIIO-2 Re-opener assessment process version 3 | Stage 3 Screening Checks | Stage 3 Screening Checks. It is not clear what might constitute an omission and whether it would be considered ‘minor’ or ‘major’. Further guidance is requested on how long this process will take and when licensees can expect be notified of a ‘pass’ or ‘fail’ for this stage. In a circumstance where Ofgem believe that the application is not suitable and sufficient it is not clear (clause 1.15) what recourse a licensee may have to rectify – for example, if it is a ‘fail’ does the licensee need to await the next application window? Clarity is required whether screening will take place at a scheme/project or re-opener level (e.g. where a single re-opener has multiple projects associated with the submission). | Any application that has been rejected may be submitted at the next available application window. As noted in paragraphs 1.16 and 1.35 of the working document the Authority may exercise its powers at a later date to open an additional application window should that be determined to be in the interest of consumers | Suggest changing to "An application that has been rejected may be submitted during another application assuming it fulfils the relevant criteria."
11 | Cadent | Slide pack – slide 6 & Re-opener assessment process working document (para 1.14, p8) | Stage 3 Screening Checks | Interpretation: Ofgem will conduct screening checks and reject any applications that do not comply with both the relevant licence condition and the re-opener guidance and application requirements document. Comment: Important to note that the licence and re-opener guidance document are not aligned. GDN licence sets out that a Needs Case is required for Tier 1 Stubs re-opener only. Re-opener guidance says that regardless of what is set out in the licence a Needs Case is required for all re-openers. This was added without consultation in the final published re-opener guidance and was a significant change in position from previous engagement between Ofgem and networks. Our interpretation is that as the licence takes precedence, a Needs Case cannot be required unless the licence is modified through a statutory consultation. Also, there are a number of reopeners in Gas Dx where it wouldn’t be proportionate, practical or relevant to provide Needs Cases (for example – Smart Metering & Streetworks which are both high volume, low(er) cost activities rather than large projects). As outlined above we would appreciate Ofgem’s confirmation that Needs Cases will not be required. | The relevant licence conditions contain specific triggers that must have been activated prior to an application being considered valid. Any needs case will therefore need to demonstrate that the trigger points set out in the licence have indeed been activated. We understand that the detail provided will be proportionate and will vary by Re-opener mechanism. Paragraph 3.4 of the Re-opener Guidance and Application Requirements document provides for the licensee to provide a justification for not providing all of the required information, where this cannot be provided.
39 | NGGT & NGET | Reopener process document | Stage 3 Screening Checks | If an application does not pass this stage is it rejected for all time? It is not clear from this document of the AD as to whether additional information could then be provided to enable it to pass. Presumably not though as the application window would then be closed? | Any application that has been rejected may be submitted at the next available application window. As noted in paragraphs 1.16 and 1.35 of the working document the Authority may exercise its powers at a later date to open an additional application window should that be determined to be in the interest of consumers | Suggest changing to "An application that has been rejected may be submitted during another application assuming it fulfils the relevant criteria."
13 | Cadent | Re-opener assessment process working document (para 1.20, p8) | Stage 4 Assessment Questions | Interpretation: States that Ofgem must be persuaded that an intervention is justified. Comment: We would propose that the phrase “persuade us” is not used in the two bullet points at the bottom of page 8. This phrase could be replaced with “demonstrate”. | Drafting has been modified to reflect this change
14 | Cadent | Re-opener assessment process working document (para 1.20, p9) | Stage 4 Assessment Questions | Interpretation: Application should set out how each proposed intervention has been subject to a rigorous option assessment process. Comment: We can see why this is important for some, predominantly project based, re-openers. However, this wouldn’t be proportionate or relevant to all re-openers. For example, we don’t believe that it would be Ofgem’s intention for GDNs to provide this for every Smart metering intervention or where other obligations (legal, safety etc.) dictate the proposed approach. As such, it would be useful for the working document to recognise this and also for Ofgem to confirm through pipeline engagement that this will not be required ahead of application submission. | As stated on page 1 of the RIIO-2 Re-opener assessment process document, "we recognise that given the diversity of Re-opener mechanisms, we may need to adjust or diverge from this indicative process in particular circumstances". In the Re-opener Guidance and Applications Requirements document, paragraph 3.4 provides for a justification to be given by the licensee if all required information is not provided.

## May 2021 responses pipeline log
URN | Comment from | Document reference | Topic/area | Comments/questions | Response
47 | NGGT & NGET | Pipeline reopener log | Inclusion of opex escalator | Including the opex escalator in this log is an unnecessary additional complication. We don’t believe project level detail is required, and that an enduring solution could be largely automated depending on configuration of the T2 reporting data template, and the manner in which UM forecasts are established (for ET, the opex escalator runs off re-openers and volume drivers). On this basis, we don’t see the opex escalator sheet as directly relevant for establishing the initial pipeline log process. (For future reference, the key aspects required to support the opex escalator are: o An opex / capex distinction given that the mechanism is designed to provide uplifts relating to capex o A direct / indirect cost distinction given that some re-openers mechanisms are outside the scope of the opex escalator Specifically for ET, we suggest that the NOC element of the opex escalator can be simplified so that it operates in a similar way to the CAI element. Taking project level energisation dates, the NOC element is overly complex for a very small adjustment. Instead, this could operate in a similar way to the CAI component, and run off the annual profile of UM forecasts / determinations.) | The opex escalator licence algebra in its current form accurately reflects the policy intent. The RRP will collect both the cost and volume data and the PCFM requirements (i.e. the current Reg Fin revenue workbook and revenue pipeline log will be integrated into the RRP). Our aspiration remains that, where possible, the revenue workbook inputs will be auto-populated from the detail collected in the cost & volumes section of the RRP. The GT opex escalator has been removed as it is no longer necessary.
48 | NGGT & NGET | Pipeline reopener log | General | To provide clarity and consistency of how the template is intended to be used we suggest Ofgem ought to include separate tabs in the spreadsheet containing 1) explanatory notes / guidance on the nature of information to be put in each field, 2) worked examples. For example, it is not clear whether the £m should be gross or direct costs only, or totex or capex. | The Re-opener pipeline log guidance will be part of RIGs. The guidance will also be provided alongside the Information Request for the 2021 submission.
49 | NGGT & NGET | Pipeline reopener log | Adjustment terms | If Ofgem retain link to forecasting the following points would need to be considered • On GT_Reopener_Pipeline_log tab: it would aid clarity to add a field for each reopener to identify the associated PCFM term that is proposed for adjustment. | Re-opener pipeline log has been modified to reflect this comment
50 | NGGT & NGET | Pipeline reopener log | Structure of spreadsheet | Please see NGET proposal submitted alongside this response. 1) In order to make the sheet usable (e.g. to facilitate the application of filters), the whole sheet should be transposed so that projects are added as rows. 2) In order to make this worksheet interact with the rest of the T2 RRP pack, the Ofgem Scheme Reference should be included. 3) A separate tab is not needed for the opex escalator; tracking info can all be held on one sheet. 4) Is the ‘probability of submission’ column intended to be a %, or H/M/L? 5) The gross totex value of the reopener has been changed to a range to help resource planning but reduce the risk of this data being used inappropriately. Ofgem’s table only had £m for the 5 years of T2 – some reopeners have spend prior to T2 (e.g. visual amenity projects) and other will have significant spend post-T2 so having a single range better reflects the full value to be considered in the re-opener. 6) A ‘mobilisation year’ would be helpful to indicate the urgency of decision-making, and hence help Ofgem prioritise their resources. 7) The last 5 rows (e.g. ‘Outline of needs case’) are not suitable for capture on a spreadsheet. They could be used as a checklist of what will accompany re-openers, or they could be deleted. | 1) Re-opener pipeline log has been modified to reflect this comment 2) Re-opener pipeline log has been modified to reflect this comment 3) The opex escalator captures data at a project, rather than Re-opener, level so will believe a separate tab remains the easiest solution 4) The Re-opener pipeline log guidance will be part of RIGs and will also be provided alongside the Information Request for the 2021 submission. 5) We remain of the opinion that the values should be captured by regulatory year. 6) Re-opener pipeline log has been modified to reflect this comment 7) These rows will remain but Information should be brief and provide more detail for those applications expected in the next 12 months/regulatory year.
57 | SPT | Pipeline Log (Comments relate solely to ET) | ET Reopener Pipeline_log (ETRPL) worksheet | There are subtle differences between the nomenclature in this worksheet and that for the ‘ET Opex_escalator’ (ETOE) tab. The basic information omits to include the Ofgem Scheme Reference (OSR) code (although this is referenced under the Opex Escalator). It was our implicit understanding that TO’s would be expected to maintain a register of such codes as an extrapolation of the RIIO-T2 BP submission. | OSR comment: re-opener pipeline log has been modified to reflect this comment. The Opex Escalator and Pipeline Log tabs are collecting different data. The Re-opener pipeline log guidance will be part of RIGs and will also be provided alongside the Information Request for the 2021 submission, explaining the different data to be captured.
58 | SPT | Pipeline Log (Comments relate solely to ET) | ET Reopener Pipeline_log (ETRPL) worksheet | It is not clear why ‘Re-opener name’ is required given that there is a requirement to stipulate relevant licence condition and clause. What is its purpose? | The Re-opener pipeline log guidance will be part of RIGs. The guidance will also be provided alongside the Information Request for the 2021 submission.
59 | SPT | Pipeline Log (Comments relate solely to ET) | ET Reopener Pipeline_log (ETRPL) worksheet | A single re-opener (eg re-opener 1) could have multiple projects under the same licence condition and clause. Further guidance is sought on the meaning of terms like ‘re-opener 1’ and ‘project ‘ etc. There is different terminology used between ETRPL and ETOE – there should be some formal linkage between the two, where this is relevant. | The Re-opener pipeline log guidance will be part of RIGs. The guidance will also be provided alongside the Information Request for the 2021 submission.
60 | SPT | Pipeline Log (Comments relate solely to ET) | ET Reopener Pipeline_log (ETRPL) worksheet | The ‘Energisation date’ appears to be an omission as it is important to recognise, as part of an assessment process, when the output is required to be delivered. This would assist Ofgem in their planning process to better ensure prioritisation of assessment resources. This could be included under the ‘Details of Application’ section. | Re-opener pipeline log has been modified to reflect this comment
61 | SPT | Pipeline Log (Comments relate solely to ET) | ET Reopener Pipeline_log (ETRPL) worksheet | An ‘Anticipated Decision date’ would be a welcome addition to the log to better inform licensees of likely decisions for stakeholder engagement purposes. | Decision dates will be planned following submission of the Re-opener application and therefore is not considered a suitable addition to the Re-opener application pipeline log.
62 | SPT | Pipeline Log (Comments relate solely to ET) | ET Reopener Pipeline_log (ETRPL) worksheet | Guidance is required for the ‘Probability of submission’ cells eg is this H/M/L or expressed as a % etc | The Re-opener pipeline log guidance will be part of RIGs. The guidance will also be provided alongside the Information Request for the 2021 submission.
63 | SPT | Pipeline Log (Comments relate solely to ET) | ET Reopener Pipeline_log (ETRPL) worksheet | The worksheet contains a ‘Potential value of adjustment to baseline allowances’ section*. This is a different definition from the ETOE and is likely to cause confusion between them. It may be better to take a consistent approach. Furthermore, under expenditure, the cells that reference ‘totex’ should be expressed as a formula (Capex + Opex) to minimise scope for error. | Totex cells have been removed. The differences between the Re-opener pipeline log and Opex escalator tab are necessary to capture the required information in each tab.
64 | SPT | Pipeline Log (Comments relate solely to ET) | ET Reopener Pipeline_log (ETRPL) worksheet | The RIIO-T2 – in limited circumstances – stipulates an allowance for the first two years of RIIO-T3. The ‘Potential value of adjustment to baseline allowances’ section needs to take account of this. | Re-opener pipeline log has been modified to reflect this comment
65 | SPT | Pipeline Log (Comments relate solely to ET) | ET Reopener Pipeline_log (ETRPL) worksheet | It is not really clear why the requirements under ‘Details of Application (DoA)’ are necessary in a monitoring log for potential future submissions. It would seem to be more appropriate to include a brief Project Description, anticipated Cost and Outputs and expected Delivery date. | Information in the Re-opener pipeline log should be forecasted as far as is reasonably practicable. Information should be brief and provide more detail for those applications expected in the next 12 months/regulatory year.
66 | SPT | Pipeline Log (Comments relate solely to ET) | ET Reopener Pipeline_log (ETRPL) worksheet | Under DoA, ‘Any broader regulatory/policy issues’ may be relevant. This could be dealt with as a drop-down (eg Yes/No or categories etc). | We believe a free text box is more appropriate for this field.
67 | SPT | Pipeline Log (Comments relate solely to ET) | ET Reopener Pipeline_log (ETRPL) worksheet | As there are expected to be multiple applications (both re-opener windows and multiple projects under such windows) it may be better to transpose the rows and columns. It can be reasonably expected that the rows will be stable and (relatively) small in number. | Re-opener pipeline log has been modified to reflect this comment
68 | SPT | Pipeline Log (Comments relate solely to ET) | ET Opex_escalator (ETOE) worksheet | As there are expected to be multiple applications (both re-opener windows and multiple projects under such windows) it may be better to transpose the rows and columns. It can be reasonably expected that the rows will be stable and (relatively) small in number. | Re-opener pipeline log has been modified to reflect this comment
69 | SPT | Pipeline Log (Comments relate solely to ET) | ET Opex_escalator (ETOE) worksheet | Noting the point* made under ETRPL section, the Opex Escalator can generate both capex and opex allowances, therefore, it would seem appropriate that the relevant area mirrors that of the ETRPL. | The opex escalator licence algebra in its current form accurately reflects the policy intent and the Opex escalator tab has been built to reflect that.
70 | SPT | Pipeline Log (Comments relate solely to ET) | ET Opex_escalator (ETOE) worksheet | It is noted that the ETOE spreadsheet does not calculate the adjustments, further thought is required in regard to Ofgem’s intent for including costs and allowances in the ETRPL. | The opex escalator licence algebra in its current form accurately reflects the policy intent and the Opex escalator tab has been built to reflect that.
25 | SSEN | Reopener pipeline log | Guidance | We would welcome further discussion with Ofgem on the proposed guidance that will accompany the Reopener pipeline log data sheets. For example, the required detail for rows 31-35 is unclear at this stage. We assume that Ofgem intend this this will require inclusion of a brief description (whilst noting that not all information may be known at the point of submission i.e. preferred option). | The Re-opener pipeline log guidance will be part of RIGs. The guidance will also be provided alongside the Information Request for the 2021 submission. Information in the Re-opener pipeline log should be forecasted as far as is reasonably practicable. Information should be brief and provide more detail for those applications expected in the next 12 months/regulatory year.
26 | SSEN | Reopener pipeline log |  | Ofgem must recognise that information submitted as part of the Reopener pipeline log is caveated insofar as information is provided on our best view of future schemes using information available at that time and will be subject to change. We do therefore appreciate Ofgem’s encouragement for licensees to review and update their Re-opener application pipeline logs on a quarterly basis, and to share these with Ofgem. We would therefore not expect to provide detailed explanation on each occasion a scheme is entered into or removed from this submission. | Information in the Re-opener pipeline log should be forecasted as far as is reasonably practicable. Information should be brief and provide more detail for those applications expected in the next 12 months/regulatory year.
27 | SSEN | Reopener pipeline log |  | The Reopener pipeline log would benefit from a programme timeline (e.g. energisation date) which would help Ofgem and the licensee plan/prioritise projects ahead of time. | Re-opener pipeline log has been modified to reflect this comment
28 | SSEN | Reopener pipeline log |  | ETOs and Ofgem need to understand the overlap and interplay between the reopener pipeline log and the wider T2 RRP tables (especially requirements for providing lookahead forecasts/best view.) Ofgem should clarify where there are overlaps. | The RRP will collect both the cost and volume data and the PCFM requirements (i.e. the current Reg Fin revenue workbook and revenue pipeline log will be integrated into the RRP). Our aspiration remains that, where possible, the revenue workbook inputs will be auto-populated from the detail collected in the cost & volumes section of the RRP.
4 | Cadent | Re-opener pipeline log rows 15-29 | Re-opener pipeline log – baseline allowance adjustment | Is there a potential need for non-Totex rows? For example, even though Net Zero mechanisms are Authority triggered may Ofgem want networks to include forecasts for these in through the pipeline process? These costs are likely to be non-Totex, like the HyNet FEED study PCD. | We remain of the opinion that non-Totex rows are not currently needed in the Re-opener pipeline log.
15 | Cadent | Re-opener pipeline log rows 15-29 | Re-opener pipeline log – Price base | Interpretation: Confirmation of price base Comment: For the avoidance of doubt, the pipeline log should state that all costs are to be submitted in 18/19 price base. | This has been incorporated into the Re-opener pipeline log guidance which will be provided as part of RIGs and the 2021 information request.
3 | Cadent | Re-opener pipeline log rows 6 & 8 | Re-opener pipeline log – basic information | Includes rows with titles “re-opener name” and “relevant re-opener mechanism”. It would be good to understand what is the difference between these rows? | The Re-opener pipeline log guidance will be part of RIGs. The guidance will also be provided alongside the Information Request for the 2021 submission.
71 | SPT | 1. Other | General | The expenditure/ allowances section in both ETRPL and ETOE would benefit from further though on its function/ purpose. | Comment noted
72 | SPT | 1. Other | General | Ofgem’s cost assessment – if it follows the principle of RIIO-T2 BP – will determine the total efficient cost of the scheme/project and allocate allowances accordingly to T2 (noting that some schemes may have expenditure extending into T3). To do so, inherently, requires that a TO submits an indicative profile of expenditure as part of their submission eg capex. | Comment noted
73 | SPT | 1. Other | General | The ETOE worksheet could be configured to use the above information to calculate the relevant adjustments providing in-built assurance on the veracity of this allowance area and avoid multiple sources for manual input of data. This would mean that an allowance adjustment comprises: - Submitted capex of scheme/ project (for simplicity here project assumed to be efficient and expenditure = allowance), - Opex Escalator calculates CAI (capex) allowances based on profile of scheme/ project, - Opex Escalator calculates NOCs (opex) allowance based on scheme/ project delivery date. | The opex escalator licence algebra in its current form accurately reflects the policy intent and the Opex escalator tab has been built to reflect that.
74 | SPT | 1. Other | General | Alternatively, the role/need for the ETOE worksheet is reviewed by Ofgem to determine whether it is actually required for the pipeline log. The details on the ETRPL worksheet – if configured correctly – would permit Ofgem to evaluate the ETOE impact without TO intervention. | The opex escalator licence algebra in its current form accurately reflects the policy intent and the Opex escalator tab has been built to reflect that.