## Key
Question by:
Initials | Name
CO | Consultants
EP | Expert Panel
OF | Ofgem
| Letter | Criterion
| a) | Low carbon/environmental and net financial benefits
| b) | Value for money
| c) | Generates new knowledge
| d) | Is innovative
| e) | Involvement of other partners and external funding
| f) | Relevance and timing
| g) | Robust methodology and readiness to implement

## BiTraDER
Question No. | From | Proforma section | Criteria | Question | Date question asked | Date response required | Date received | Follow up to Question # | Confidential (y/n) | Attachments | Links to Answers | Ofgem comments
1 | EP | 3 | b | How long will the live network trial last please? – is it all of the period 01/05/25 until 30/06/26? | 2021-08-24 | 2021-08-26 | 2021-08-26
2 | EP | 4 | d | Is the focus on curtailment or constraining off to relieve network constraints rather than overall saturation (which is a system-wide phenomenon)? Presumably at grid-level, connection agreements specify how constraining off generators will be paid (lost profit). Is that not the case on DNs? | 2021-08-26 | 2021-08-31 | 2021-08-31
3 | EP | 4 | d | Can you clarify what needs to be added to the existing ElectronConnect market platform to deliver the required services? How different are the proposed platform and ElectronConnect? Are there no other commercial providers of such platforms with the required capability if ElectronConnect is incomplete in this regard? If not, is there a potential market for developing and proving one and if so who collects the subsequent profits from the IP? | 2021-08-26 | 2021-08-31 | 2021-08-31
4 | EP | 2 | a,b | What impact, if any, does Ofgem’s proposed reforms through the Access and Forward-Looking Charging Review have on this project? | 2021-09-07 | 2021-09-09 | 2021-09-09
5 | EP | 2 | a | How have the day rates shown on p25 for Afry and Delta been tested for value for money? (They seem high compared to other projects) | 2021-09-07 | 2021-09-09 | 2021-09-09
6 | EP | 8 | a,b | P42 On the customer engagement is this envisaged as being primarily generation assets or demand? | 2021-09-07 | 2021-09-09 | 2021-09-09
7 | EP | 10 | a | For the cost per participant quoted on p57, is that charged to participants or born by the network? If the former what assessments have been done as to whether this remains an attractive proposition for customers? | 2021-09-07 | 2021-09-09 | 2021-09-09
8 | EP | 2 | e | Please provide more detail on how you will test with Open Networks the assumption that the high-level architecture will be transferrable to other DNOs. (pages 8, 31 and 68). | 2021-09-07 | 2021-09-09 | 2021-09-09
9 | EP | 4 | c | In the simulation phase and in choosing the Harker substation for the live trial, will you be including a sufficient number of customers providing flexible demand-side services? (For instance, how many of the expected 50 potential market participants and 10-15 connected resources will be demand-side?) If this is not possible, how will you ensure that your findings will be sufficiently applicable to the use of demand-side services in future? | 2021-09-07 | 2021-09-09 | 2021-09-09
10 | EP | 10 | c | Please reconcile the description of the scaling factor mentioned on page 18 with that appearing on page 50 (point 3). | 2021-09-07 | 2021-09-09 | 2021-09-10
11 | EP | 2 | b | Will the simulation trials include trials in which stack optimisation takes account of carbon intensity? | 2021-09-07 | 2021-09-09 | 2021-09-09
12 | EP | 2 | b | Will the expected reduction in generation investment and load related expenditure arising from BiTrader generate carbon benefits (deferring or obviating use of embodied carbon)? If so, why have you chosen not to estimate this benefit? | 2021-09-07 | 2021-09-09 | 2021-09-10
13 | CO | 2 | c,d | What learning regarding the DNO/DSO/ESO interaction will be gained from this project beyond that from the NIC funded Power Potential project? | 2021-09-14 | 2021-09-16 | 2021-09-17
14 | CO | 2 | b | What is your estimate the value of the annual flexibility market (for ENWL) and by how much do you think you could increase this through this secondary market? | 2021-09-14 | 2021-09-16 | 2021-09-17
15 | CO | 2,3 | b | Can you please provide additional details on the costs of the trials. It appears that there is circa £200k allocated for trial and analysis to Electron. Does this take account of the stakeholder engagement with multiple stakeholders and how many iterations of the trials have been allowed for. Has the cost for customer engagement and project management been considered for the trail phase? | 2021-09-14 | 2021-09-16 | 2021-09-17
16 | CO | 2,3 | b | Can you please provide the day rates and a cost breakdown for each phase of the project for each stakeholder? In particular, the project management cost breakdown, i.e., ~ £2 Million | 2021-09-14 | 2021-09-16 | 2021-09-17
17 | CO | 3 | f | Has the requirements for communication infrastructure been determined? Can the BiTraDER market platform effectively operate without any communication infrastructure upgrades, particularly for legacy systems? What communication protocol will be used. e.g., utilisation of IEEE2030.5 might require significant infrastructure upgrade? | 2021-09-14 | 2021-09-16 | 2021-09-17
18 | EP | 10 | g | Page 64 states you envisage three types of constraint being traded (constraints that arise from having a flexible connection, flexibility service obligations to the DNO, service obligations to the ESO). For the latter two, please can you confirm if contract rules allow for these service obligations to be transferred to another party? If not, please can you describe the impact of this on the project. | 2021-09-16 | 2021-09-20 | 2021-09-20
19 | EP | 10 | g | Page 64 states you envisage three types of constraint being traded (constraints that arise from having a flexible connection, flexibility service obligations to the DNO, service obligations to the ESO). For the first two types, any trade still has to solve the original distribution network constraint – how do you ensure this? For the last type, any trade still has to meet ESO requirements – how do you ensure this? | 2021-09-16 | 2021-09-20 | 2021-09-20
20 | EP | 8 | e | Pg 42 states that the design and simulation phases of the project will target two groups of customers. Why are these two phases of the project limited to this subset of customers (especially when benefits may arise from three groups of customers (G1-3, pg 17) across three types of tradable constraint (pg 64))? | 2021-09-16 | 2021-09-20 | 2021-09-20
21 | EP | 4 | f | If successful, the project will result in customers operating at a different demand/generation levels compared to if they had not traded their obligation. Given these trades may happen very close to real-time, there may be an impact on suppliers (placed in imbalance) and/or other wholesale market participants. Has this impact already been considered? Please can you explain how you will explore any such impact during the project. | 2021-09-16 | 2021-09-20 | 2021-09-20
22 | EP | 10 | f | The success of the project depends on customers participating in this market. Given the absence of any customer engagement on this project/concept to-date, please can you provide more detail why you are confident that customers will participate (non-participation is given a probability score of 1 in Appendix F)? Please explain the assumptions around customer participation, e.g. what proportion of eligible customers will participate and how often? | 2021-09-16 | 2021-09-20 | 2021-09-20
23 | EP | 10 | a,b | Page 50 explains that the most influential factor in the CBA is the assumed level of “% share of flexible resources which have additional combined service offering to DNO and Capacity Market”. Please could you provide a simple explanation of what this means, and why it has such a influence on the CBA. | 2021-09-16 | 2021-09-20 | 2021-09-20
24 | EP | 2 | g | Pg7/8 states “the high-level architecture proposed by BiTraDER will be easily transferrable across the UK DNO population.” This is important (otherwise the solution is just applicable to ENW), so how will you ensure this? | 2021-09-16 | 2021-09-20 | 2021-09-20
25 | EP | 2,3 | d | Ofgem’s RIIO-ED2 DSO baseline requirements include a baseline requirement that “DNOs shall facilitate secondary trading of distribution flexibility services and curtailment obligations. In this context, facilitating means providing the relevant operational data, ensuring the DNO has processes in place to collect the relevant data about the trade, and making the operational parameters clear (and justified in the context of network reliability and efficiency).” Given this, it is reasonable to expect that ENW and other DNOs have already included funding in their RIIO-ED2 Business Plan submissions to deliver this baseline requirement. How is the Bitrader project different to this baseline ED2 requirement? Will you already be delivering any parts of this project in ED2 under this baseline requirement? | 2021-09-16 | 2021-09-20 | 2021-09-20
26 | OF | 2,3,4 | g | Does the proposed ElectronConnect platform have existing independent security accreditation (eg. ISO27001, SOC2 or analogous)? | 2021-09-23 | 2021-09-27 | 2021-09-27
27 | OF | 2,3,4 | g | Does the project plan to undertake any discrete security work during build (e.g. pentesting) to provide project specific assurance on the as-built security of the system? | 2021-09-23 | 2021-09-27 | 2021-09-27
28 | OF | 2,3,4 | g | Has a cyber security reference standard(s) been identified that the project will be delivered in accordance with to systematically manage cyber security risk? | 2021-09-23 | 2021-09-27 | 2021-09-27
29 | OF | 2,3,4 | g | Will the design / simulation phase look at the potential impact that erroneous (either intentionally malicious or genuine error) data submitted to the trading system could result in? And what safeguards could be designed / tested to identify such an event. | 2021-09-23 | 2021-09-27 | 2021-09-27
30 | OF | 2,3,4 | g | Has an assessment been made on impact of the live network trial phase in the context of NIS? I.e. If actively involved in the delivery of essential service would the trading platform be considered in scope of NIS and who would be responsible under NIS? | 2021-09-23 | 2021-09-27 | 2021-09-27
31 | OF | 2,3,4 | g | Do you expect to require customer participants in a live trial to demonstrate / provide assurance of their cyber security status. E.g. setting a demonstratable baseline expectation for participants so that the system / data integrity risks (ingress and egress) from participants are mitigated. | 2021-09-23 | 2021-09-27 | 2021-09-27
32 | OF | 2,3,4 | g | To help us consider and manage any conflicts of interest arising as a result of Afry’s involvement in the BiTraDER project (Afry also contract with Ofgem on other innovation work), can you name the individuals at Afry who are involved / may be involved in the project? | 2021-10-07 | 2021-10-11
33 | OF | 4,5 | c | Please can you explain how BiTraDER differs from and builds on other projects that Electron has been involved in with government funding including the Manchester Local Energy Market, Coventry Regional SO and TraDER? | 2021-10-13 | 2021-10-15
34 | EP | 3,4 | a | Building on information provided in your answers to SQs 6,7 and 9, and in Slide 7 in Bilateral 2, what further reassurance can you provide to the Panel that, at GB scale, the occurrence of curtailed and/or demand side customers is sufficient to justify the scaling up of benefits in the manner described? | 2021-10-13 | 2021-10-15
35 | EP | 3,4 | a | In what circumstances, taking a GB view, could a more economic selection of resources for curtailment lead to increased use of non-RES (higher carbon) sources? | 2021-10-13 | 2021-10-15
36 | CO | 3,4 | a | Have you considered the impact of energy storage on the requirement to manage constraints, in particular against the backdrop of rapidly dropping BESS costs? If not, how sensitive is your CBA to the emergence of other mechanisms that influence availability to participate in these markets such as energy price fluctuations and management of flexibility through ESS? | 2021-10-19 | 2021-10-21
37 | CO | 6 | g | In follow up to SQ17, have you carried out any analysis of remote DER (mostly solar farms in this context) to determine if they have remote telecoms facility that allow active management beyond all/nothing control through disconnection of connecting circuit breakers or disconnectors? | 2021-10-19 | 2021-10-21