## Key
Question by:
Initials | Name
CO | Consultants
EP | Expert Panel
OF | Ofgem
| Letter | Criterion
| a) | Low carbon/environmental and net financial benefits
| b) | Value for money
| c) | Generates new knowledge
| d) | Is innovative
| e) | Involvement of other partners and external funding
| f) | Relevance and timing
| g) | Robust methodology and readiness to implement

## EQUINOX
Question No. | From | Proforma section | Criteria | Question | Date question asked | Date response required | Date received | Follow up to Question # | Confidential (y/n) | Attachments | Links to Answers | Ofgem comments
1 | EP | 2 | g | P7 - Does the supplier dispatch/instruct customers in different ways between Method 1 and Method 2, or is the same method used for both? | 2021-08-24 | 2021-08-26 | 2021-08-26
2 | EP | 10 | a,b,d | P60 – please could you explain how method 3 combines M1 and M2, or give an example of what it might look like, appreciating that the design is part of the trial? | 2021-08-24 | 2021-08-26 | 2021-08-26
3 | EP | 10 | a | P61 – what parts of Figure 15 are existing and which are new developments for Equinox? | 2021-08-24 | 2021-08-26 | 2021-08-26
4 | EP | 4 | b | What is the cost per household of the equipment needed to deliver the responses? | 2021-08-26 | 2021-08-31 | 2021-08-28
5 | EP | 4 | b | What would be the payments per household per year for offering flexibility? | 2021-08-26 | 2021-08-31 | 2021-08-28
6 | EP | 4 | b | How would the payments and incentives interact with possible time-of-use tariffs designed to reflect peak costs better (currently under investigation by the BEIS’ Alternative Energy Markets programme)? | 2021-08-26 | 2021-08-31 | 2021-08-28
7 | EP | 2 | a,b | Can you explain how WPD’s flexibility platform (Flexible Power) works and what are its capabilities for this project and more generally for procuring flexibility? | 2021-08-26 | 2021-08-31 | 2021-08-28
8 | EP | 3 | a,b,g | How likely is it that fuel-poor customers will have heat pumps? | 2021-08-26 | 2021-08-31 | 2021-08-28
9 | EP | 2 | b | Please comment on the difference between your choice of data for the embedded carbon of traditional reinforcement (the C2C project, 2015) and that provided in other sources e.g. https://www.enwl.co.uk/globalassets/innovation/smart-street/smart-street-key-docs/final-report-on-carbon-accounting.pdf | 2021-09-07 | 2021-09-09 | 2021-09-09
10 | EP | 4 | c | How, if at all, will you address the differences in customer attitude to flexibility that might be expected to occur depending on the degree of heat insulation installed and whether they use HPs in conjunction with traditional home heating (e.g. radiators) or newer techniques such as underfloor heating? | 2021-09-07 | 2021-09-09 | 2021-09-09
11 | EP | 2 | e | How will you address the risk that customers recruited to the trials via the Welsh Government retrofitting programme and the WMCA programme will not be representative because of the policy objectives underlying the choice of homes to be included in these programmes? (This includes the possibility that customers receiving “free” HPs will react differently from those who have chosen to install them) | 2021-09-07 | 2021-09-09 | 2021-09-09
12 | EP | 10 | b | Please provide estimates of capacity release and carbon savings corresponding to your “low HP uptake scenario” (page 55). | 2021-09-07 | 2021-09-09 | 2021-09-09
13 | EP | 4 | b | How will you address the possibility that the winters in which trials are to take place will not include periods of intense cold likely to prompt customers’ use of supplementary heating (especially customers with heat pumps)? | 2021-09-07 | 2021-09-09 | 2021-09-09
14 | CO | 3 | b | Please explain how the flexibility of the heat pumps will manifest in kW savings? Your CBA is based on a 35-50% reduction in peak demand. Can you please provide details of this (the underlying Watt/VA values) including the pre-HP peak demand, the pre-HP diversified peak demand and the assumptions regarding the coincidence of the HP and non-HP demand. Can you also provide details of how this was applied to the network and what assumptions were applied concerning the growth of individual networks, i.e. was uniform scaling applied across the network, was it applied differently to different types of networks and what are the assumptions regarding the underlying headroom. | 2021-09-14 | 2021-09-16 | 2021-09-16
15 | CO | 2 | a | Is the heat pump load binary, and for each heat pump it is either on or off, and the savings are achieved solely by the time shifting of the on/off periods? Or is some modulation of the active power consumption of each heat pump attainable? In both cases what are the effects (or likely effects) on customer perception and also on the longevity of the heat pump. Are there grounds for seeking manufacturers’ comments on the operating regimes? | 2021-09-14 | 2021-09-16 | 2021-09-16
16 | CO | 3 | f | Can you please confirm the time allowed in your programme to recruit participants for the trials and the timing of this relative to trials and surveys? | 2021-09-14 | 2021-09-16 | 2021-09-16
17 | CO | 2 | b | What is the estimated cost for rollout of Equinox as BaU to other licencees? How long did you assume implementation as BaU will take other licencees? | 2021-09-14 | 2021-09-16 | 2021-09-16
18 | CO | 2 | b | What is the anticipated ongoing cost for maintaining the WPD portion of the Equinox systems and platforms? Do you expect the Energy Supplier/retailer and Customer costs to be recovered through the flexibility payments? | 2021-09-14 | 2021-09-16 | 2021-09-16
19 | CO | 3 | a | Your submission implies that the Equinox solution will only defer conventional network reinforcement and you anticipate Equinox not being used post-reinforcement. What is the reason for this assumption as it would reduce (by 35-50% by your estimating) the additional capacity that is required? In your CBA, how long do you anticipate reinforcement to be avoided through the use of Equinox. | 2021-09-14 | 2021-09-16 | 2021-09-16
20 | CO | 3 | b | In Section 3.2 you estimate that the annual market is worth £290k in the WPD licence areas. Can you please give an indication of what proportion of the flexibility cost will flow to the customer and the proportion that will flow to the retailer/aggregator? | 2021-09-14 | 2021-09-16 | 2021-09-16
21 | CO | 2 | b | Your project budget allows £7m for equipment (Table 4, p.22). Can you please clarify what equipment this is and what the procurement process will be. | 2021-09-14 | 2021-09-16 | 2021-09-16
22 | CO | 3 | 4 | Can you please confirm how a constraint instruction to a HP customer will be verified (i.e. how will you measure the extent of the response): through smart meter data, smart heat pump controller monitoring or HP demand monitoring metering? If it is through smart meters only, how will other loads picking up (in the same 30min window) be distinguished from a failure to comply, especially where turn down is preferred to turn off. | 2021-09-14 | 2021-09-16 | 2021-09-16
23 | EP | 4 | e | The development of the in-home automation and the mobile app etc is the province of Equinox’s partners, and will not be funded by NIC. Nevertheless what assurance can you give that these developments will be appropriately interoperable and therefore can be available from other energy service providers as part of future wider adoption? What safeguards and/or standards will the project be adopting to ensure this? | 2021-09-14 | 2021-09-16 | 2021-09-16
24 | EP | 10 | c | Pg 53 states that “the CBA model assumes that…flexibility is unlocked from across all customers with HPs within the areas of constraint.” Given low customer switching levels (a one-off activity with a clear financial incentive) please explain why you consider customer 100% engagement with Equinox is a reasonable CBA assumption. Please explain the CBA sensitivity to lower participation levels | 2021-09-16 | 2021-09-20 | 2021-09-20
25 | EP | 2 | g | In the first bilateral you explained that you would develop and own the APIs that suppliers would then use to communicate with you on a BAU basis. How will ensure that they are cyber secure? How will you ensure that they are suitable for suppliers and don’t present a barrier to supplier participation? | 2021-09-16 | 2021-09-20 | 2021-09-20
26 | EP | 3 | g | How will you respond if a customer doesn’t deliver a contracted service? | 2021-09-16 | 2021-09-20 | 2021-09-20
27 | EP | 2 | a | The UK building stock will become more energy efficient out to 2050, both through retrofit of existing buildings and higher efficiency new builds. This will affect the level of heating customers require. Please explain how you have accounted for this variable. | 2021-09-16 | 2021-09-20 | 2021-09-20
28 | EP | 3 | b | How will you determine what price to pay customers for their flexible response? | 2021-09-16 | 2021-09-20 | 2021-09-20
29 | EP | 2,3 | a,b | Part of the financial and carbon benefits arise due to the project method deferring network reinforcement. Does the analysis consider that a proportion of these network assets will need to be replaced regardless (i.e. even if the project method is deployed) due to poor condition and reaching end-of-life? | 2021-09-16 | 2021-09-20 | 2021-09-20
30 | EP | 10 | a | The carbon calcs “are based on the embedded carbon of the equipment” (top of p19 and p57), i.e. they don’t consider the ongoing/operational carbon impact. If this is correct, can you please set out why you have adopted this approach and quantify the operational carbon impact for confirmation. | 2021-09-16 | 2021-09-20 | 2021-09-20
31 | EP | 3 | a | In particular in relation to Q22 how would you identify if secondary (direct electric) heating was being used when the heat pump was turned down? | 2021-09-16 | 2021-09-20 | 2021-09-20
32 | EP | 8 | f | Equinox will engage with current HP customers to establish levels of response. How representative do you expect these early HP adopters to be of the wider customer base? | 2021-09-16 | 2021-09-20
33 | EP | 4 | f | In general, the social housing sector is adopting a “fabric first” approach to meeting their Net Zero obligations. This is consistent with advice from the Climate Change Committee and has a number of benefits from both providers’ and tenants’ perspectives. It is expected that installation of new heating installations in social housing will follow. What are the particular circumstances applying to your partners, the Welsh Government and WMCA, which give you confidence that they will be able to offer sufficient customers with HPs to your project within the required timescale? | 2021-09-16 | 2021-09-20
34 | OF | 2,3 | g | Can further information be provided on the end-to-end (customer, supplier / aggregator, DNO) security approach / reference framework adoption that will be applied during the project to provide assurance of security resiliency. Reference Figure 3 conceptual architecture. | 2021-09-16 | 2021-09-20
35 | OF | 2,3,4 | g | Does the referenced existing platform “Flexible Power” have independent security accreditation (eg. ISO27001, SOC2 or analogous)? | 2021-09-16 | 2021-09-20 | 2021-09-20
36 | OF | 2,3,4 | g | Does the project plan to undertake any discrete security work (e.g. pentesting) to provide project specific assurance on the as-built security of the system? | 2021-09-16 | 2021-09-20 | 2021-09-20
37 | OF | 2,3,4 | g | On the potential need to install additional equipment directly into consumer homes as part of the project. Who would be responsible for providing assurance that the equipment selected is designed and installed in a secure way? | 2021-09-16 | 2021-09-20 | 2021-09-20
38 | OF | 2,3,4 | g | Excluding data loss, the risk register doesn’t cover any potential cyber security risks. Does the project plan include a requirement to evaluate related security risks? For example, the potential impact that erroneous data submitted to the flexibility platform could have and the safeguards that could be designed / tested to detect / prevent such an event. | 2021-09-16 | 2021-09-20 | 2021-09-20
39 | OF | 2,3,4 | g | Has an assessment been made on in the context of NIS? I.e. If actively involved in the delivery of essential service would the platform be considered in WPD NIS scope? | 2021-09-16 | 2021-09-20 | 2021-09-20
40 | OF | 2,3,4 | g | Do you expect to require participants (supplier / aggregators) to demonstrate / provide assurance of their cyber security status. E.g. setting a demonstratable baseline expectation for participants so that the system / data integrity risks (ingress and egress) from participants are mitigated. | 2021-09-16 | 2021-09-20 | 2021-09-20
41 | EP | 4 | g | In our second bilateral we discussed the likely impact of weather on the availability/provision of flexibility from customer heating systems, and therefore the importance of having this data when assessing the trial results. Please explain what weather metrics you are recording/measuring, how you plan to record/measure them, and at what geographic and time granularity. | 2021-10-13 | 2021-10-15