## SpC 4.8
Licence number and name: |  | SpC 4.8 (Distribution System Operation output delivery incentive)
Ofgem contact: |  | Mike Duncan / Emily Bottoni
No. | Date raised | Comment from | Reference (Part X, Para Y) | Comment | Suggested alternative drafting (if necessary) | Due Date | Response | Issue closed?
1 | 2022-07-27 | SSEN | Part A | Question on whether the formula should incorporate the % weightings for each term. Ofgem clarified that these would be accounted for in the £m values in the relevant tables in the Appendices | No alternative drafting required |  | No change needed | Closed
2 | 2022-07-27 | ENWL | Part B / Part C | Suggestion that upper and lower targets terminology is confusing and they would better be described as deadband parameters. Acknowledgment that comment applies to all the ODIs in the licence | Ofgem to consider alternative drafting for deadbands and standardise across all the ODIs | September LDWG | Amended to "upper deadband" and "lower deadband" instead | Closed
3 | 2022-07-27 | UKPN | Part H | Request for DSO incentive licence condition to be brought back to September LDWG once DSO Incentive Governance Document made available and Outturn Performance Metrics finalised | Ofgem to consider alternative drafting for Outturn Performance metrics, in line with policy working group discussions | September LDWG | Ofgem to share DSO incentive governance document with DSO working group and discuss at 1 September meeting before coming back to September LDWG | Closed
4 | 2022-07-27 | ENWL | Part H | Question on whether the DSO Incentive Governance Document would include the baseline expectations for DSO. Ofgem confirmed this would be the case | No alternative drafting required |  | No change needed | Closed
5 | 2022-08-04 | ENWL | General | The meaning of 'Upper target.' may be misleading It actually has the effect of start of reward but could be confused with the target to meet max reward. | Same as issue 2 listed above | September LDWG | Amended to "upper deadband" and "lower deadband" instead | Closed
6 | 2022-08-04 | ENWL | General | The meaning of Lower target.' may be misleading It actually has the effect of start of penalty but could be confused with the target to meet max penalty. | Same as issue 2 listed above | September LDWG | Amended to "upper deadband" and "lower deadband" instead | Closed
7 | 2022-08-04 | ENWL | General | We welcome early sight of this guidance document, however consider it needs to be added to, and reviewed by DSO WG ahead of substantive comments being provided to LDWG. | Ofgem to take DSO governance document to the DSO WG before going back to the September LDWG | September LDWG | Ofgem to share DSO incentive governance document with DSO working group and discuss at 1 September meeting before coming back to September LDWG | Closed
8 | 2022-08-04 | ENWL | Part B | To simplify the tables in the Appendices the adjustment factors (ie DSOSAUt and DSOSADt) could point to one table with the words amended in DSOSADt for the value to be negative. The same applies to the incentive rates (DSORIRt and DSOPIRt). | No alternative wording suggested, just raising the point that the volume of table could be reduced, with slight wording changes. | September LDWG | Keep as is to ensure licence condition is future proofed if any changes are needed further down the line | Closed
9 | 2022-08-04 | ENWL | Part C | The logic described above for Part B also applies to Part C. | As above for Part B | September LDWG | Keep as is to ensure licence condition is future proofed if any changes are needed further down the line | Closed
10 | 2022-08-04 | ENWL | 4.8.8 | Capital required for consistency for 'Part G' in Curtailment Metric definition. | "and is derived in accordance with Part G." | September LDWG | Change made as suggested | Closed
11 | 2022-08-04 | ENWL | Part E, F & G | The logic described above for Part B also applies to Part E, F & G. | As above for Part B | September LDWG | Keep as is to ensure licence condition is future proofed if any changes are needed further down the line | Closed
12 | 2022-08-04 | SPEN | Part I 4.8.19 (h) | This para is extremely wide and almost renders the previous paras redundant if Ofgem retains this ability within the condition. Suggest this should be deleted - the scope of the guidance document should be prescriptive rather than open-ended in this way. | Suggest deleting paragraph | September LDWG | Paragraph has been amended to remove 4.8.19 (h) in favour of adding "but not limited to" at the start of the paragraph | Closed
13 | 2022-08-05 | NPg | 4.8.5 | In DSOSASt term, measurement is in accordance with the guidance document, not the RIGs | Change to "as measured in accordance with the Distribution System Operation Guidance Document;" | September LDWG | Change made as suggested | Closed
14 | 2022-08-05 | NPg | 4.8.6 | Why is modification under S11A of the Act only mentioned once in SpC4 regarding DSOSDTLt and DSOSDTUt? |  | September LDWG | The wording has now been included in Parts E, F and G relating to the outturn performance metrics | Closed
15 | 2022-08-05 | NPg | 4.8.10 | In FTASt term, measurement is in accordance with the guidance document, not the RIGs | Change to "as measured in accordance with the Distribution System Operation Guidance Document;" | September LDWG | Change made as suggested | Closed
16 | 2022-08-05 | NPg | 4.8.12 | In NVASt term, measurement is in accordance with the guidance document, not the RIGs | Change to "as measured in accordance with the Distribution System Operation Guidance Document;" | September LDWG | Change made as suggested | Closed
17 | 2022-08-05 | NPg | 4.8.14 | In CEASt term, measurement is in accordance with the guidance document, not the RIGs | Change to "as measured in accordance with the Distribution System Operation Guidance Document;" | September LDWG | Change made as suggested | Closed
18 | 2022-08-05 | NPg | 4.8.15 | The first Distribution System Operation Performance Panel Submission will be in in Regulatory Year 2024/25 in respect of Regulatory Year 2023/24 so the obligation cannot be "Each Regulatory Year" | Change "Each Regulatory Year, the licensee must prepare …" to "With effect from the Regulatory Year beginning on 1 April 2024, the licensee must prepare …" | September LDWG | Change made as suggested | Closed
19 | 2022-08-05 | NPg | 4.8.19(c) | "licensee" is singular | Change "their" to "its" | September LDWG | Change made as suggested | Closed
20 | 2022-09-21 | ENWL | Part C 4.8.6 | Question on intent to include drafting that "The Authority will keep DSOSDLt and DSOSDUt under review …". Ofgem clarified, in line with Draft Determinations, the purpose is to review sector performance again target and consider downward/upward adjustment if necessary | No alternative drafting required | 2022-12-01 | No change needed - in line with Draft Determinations Core Document para 4.72, the purpose is to review sector performance against target and consider downward/upward adjustment if necessary | Closed
21 | 2022-09-21 | ENWL | Part H 4.8.23 (f) | Reference to role of the Distribution System Operation Performance Panel is quite broad | Change to make more specific reference to terms of reference under which the panel will operate | 2022-12-01 | No change needed - further information set out in DSO Incentive Governance Document | Closed
22 | 2022-09-21 | UKPN | Part B, C, E, F, G | Request to check maximum negative adjustments formula (eg max (-DSOSADt, …) aligned with signs given to values in the Appendices | Absolute values will be set out in the Appendices, hence the formula will be (-1 * £[x]m). For these reasons, we do not believe any amendments are required | 2022-12-01 | All figures provided in the Appendices will be in absolute values. This will avoid double negatives | Closed
23 | 2022-09-21 | UKPN, ENWL, SPEN | Part A | Consider whether % weighting of the Stakeholder Satisfaction Survey, Performance Panel assessment and Distribution System Operation outturn performance metrics term should be included in the formula (currently weighting only set out in Governance document and reflected in values in the Appendices) | Change to be considered - but not drafted yet as requires more substantial edits | 2022-12-01 | This is one of several possible drafting approaches, we have preferred the one in our proposed modifications. | Closed
24 | 2022-10-14 | SPEN | General | The development of the DSO ODI is furthest behind all of the new ODIs, both in terms of policy finalisation and licence drafting. Despite requests by DNOs to simplify this ODI, there are more layers of assessment than other incentives like BMCS where the reward/penalty associated is double the size. Ofgem’s determination to mirror the ESO incentive as far as possible will result in significant resource burden for all DNOs and also for Ofgem. We have doubts as to whether details like the metric targets, benefits calculations, survey mechanics and Panel selection will all be ready in time for 1st April 2023. WE therefore believe that Ofgem should make provision in the licence to switch off this condition for 2023 if that happens. |  | 2022-12-01 | This point relates to the policy decision in question rather than drafting, please see Final Determinations for our decision on this policy. | Closed
25 | 2022-10-19 | NGED | 4.8.13 | One of the formulae could usefully include “equals to” to make sure that scenario is covered. It doesn’t matter which. They would both return zero. |  | 2022-12-01 | This text has been deleted. No longer applicable. | Closed
26 | 2022-10-21 | UKPN | 4.8.20 | Please see our common wording on DNOs publishing documents on their websites |  | 2022-12-01 | 'Website' capitalised to reflect Definition. | Closed
27 | 2022-10-21 | UKPN | 4.8.5 DSOSADt and other elements of formulas in this condition which set max downside/penalty | With the minus in the formula and "negative" in the description this could be seen to be double negative - use formulation in BMoCS which is along lines of "maximum penalty" |  | 2022-12-01 | All figures provided in the Appendices will be in absolute values. This will avoid double negatives. | Closed
28 | 2022-10-21 | UKPN | Paras 4.88/12/15 | These paragraphs refer to the incentive being switched off for the first year of RIIO-ED2. We do not believe that this reflects the latest policy position from Ofgem on this and these paragraphs should therefore be removed and the opening wording of each subsequent paragraph amended i.e. deleting “For subsequent Regulatory Years,” |  | 2022-12-01 | This point relates to the policy decision in question rather than drafting, please see Final Determinations for our decision on this policy. | Closed
29 | 2022-10-26 | NPg | Paragraph 4.8.2 | The incentive includes a deadband so the statement "The effect of this condition is to reward or penalise the licensee …" is not strictly correct | Change "The effect of this condition is to reward or penalise the licensee …" to "The effect of this condition is to reward or penalise the licensee’s performance of its Distribution System Operation functions unless such performance falls within the deadband." | 2022-12-01 | Agreed; licence text amended. | Closed
30 | 2022-10-26 | NPg | Part B heading, paragraph 4.8.5, Part C heading, paragraph 4.8.7, Part E heading, Part F heading, Part G heading | Consistency | Change "formulae" to "formula" | 2022-12-01 | Noun declension amended to match number of formulae each Part referred to. | Closed
31 | 2022-10-26 | NPg | Part F, paragraph 4.8.13 | Reference to each Appendix number is incorrect | Change to 12, 13, 14, 15 and 16 respectively | 2022-12-01 | This text has been deleted. No longer applicable. | Closed
32 | 2022-10-26 | NPg | Part F, paragraph 4.8.13 | Clarification | One of the formulas could usefully include “equals to” to cater for that scenario | 2022-12-01 | This text has been deleted. No longer applicable. | Closed
33 | 2022-10-26 | NPg | Part G, paragraph 4.8.16 | Reference to each Appendix number is incorrect | Change to 17, 18 and 19 respectively | 2022-12-01 | This text has been deleted. No longer applicable. | Closed
34 | 2022-10-26 | NPg | Part H, paragraph 4.8.19 | Consistency | Change "a" to "its" | 2022-12-01 | A' is consistent with other licence areas such as 4.5.9 / 4.6.16. No change deemed necessary. | Closed
35 | 2022-10-26 | NPg | Part H, paragraph 4.8.20 | "Website" is a defined term in the standard conditions | Capitalise "website" and insert definition of "Website" as "has the meaning given to that term in Standard Condition 1 (Definitions for the standard conditions)." | 2022-12-01 | Agreed; licence text amended to reflect this. | Closed
36 | 2022-10-27 | SSEN | General | Comments will be provided to Ofgem separately as requested. |  | 2022-12-01 | No further comments relevant to the Licence were provided. | Closed
37 | 2022-10-27 | ENWL | 4.8.14 | Notwithstanding our comment that 4.8.14 should be deleted - if it is to remain it is NVT that is under review, not NV |  | 2022-12-01 | This point relates to the policy decision in question rather than drafting, please see Draft Determinations 4.72. | Closed
38 | 2022-10-27 | ENWL | 4.8.5 DSOSAS | Issues log item 13 says a change has been made to correct this from RIGs to governance document, but change is still outstanding |  | 2022-12-01 | Agreed; licence text amended. | Closed
39 | 2022-10-27 | ENWL | 4.8 DSO | We note that there are targets and values included throughout this condition - all these numbers are provisional and subject to FD |  | 2022-12-01 | This point relates to the policy decision in question rather than drafting, please see Final Determinations for our decision on this policy. | Closed
40 | 2022-10-27 | ENWL | 4.8 throughout | We suggest that the word positive adjustment change to reward - this improves readability |  | 2022-12-01 | Agreed; licence text amended to reflect this. | Closed
41 | 2022-10-27 | ENWL | 4.8 throughout | We suggest that the word negative adjustment change to penalty - this improves readability |  | 2022-12-01 | Agreed; licence text amended to reflect this. | Closed
42 | 2022-10-27 | ENWL | Defined term - Flexibility Market Testing Outturn Performance Metric | We have reviewed the definition of the term set out in column D and provide detailed comments on this in Annex 5 to our response 'Annex 5: Definitions'. Please refer here for ENWL definitional views and comments. |  | 2022-12-01 | Agreed; DSO Incentive Governance document will be amended to include this as a defined term. | Closed
43 | 2022-10-27 | ENWL | Defined term - Network Visibility Outturn Performance Metric | We have reviewed the definition of the term set out in column D and provide detailed comments on this in Annex 5 to our response 'Annex 5: Definitions'. Please refer here for ENWL definitional views and comments. |  | 2022-12-01 | Agreed; DSO Incentive Governance document will be amended to include this as a defined term. | Closed
44 | 2022-10-27 | ENWL | Defined term - Curtailment Efficiency Outturn Performance Metric | We have reviewed the definition of the term set out in column D and provide detailed comments on this in Annex 5 to our response 'Annex 5: Definitions'. Please refer here for ENWL definitional views and comments. |  | 2022-12-01 | Agreed; DSO Incentive Governance document will be amended to include this as a defined term. | Closed
45 | 2022-10-27 | ENWL | 4.8.8 CE term | part should be capitalised - Part G |  | 2022-12-01 | Agreed; licence text amended to reflect this. | Closed
46 | 2022-10-27 | ENWL | 4.8.10 FTT | This target is stated both here in the condition and in Appendix 9 - it should be in one or the other but not both. | Delete appendix 9 and include target in condition | 2022-12-01 | This text has been deleted. No longer applicable. | Closed
47 | 2022-10-27 | ENWL | 4.8.10 FTAD | This target is stated both here in the condition and in Appendix 10 - it should be in one or the other but not both. | Delete appendix 10 and include target in condition | 2022-12-01 | This text has been deleted. No longer applicable. | Closed
48 | 2022-10-27 | ENWL | 4.8.11 | We disagree with this para - there is nothing in DD that referred to targets being reviewed |  | 2022-12-01 | This point relates to the policy decision in question rather than drafting, please see Draft Determinations 4.72. | Closed
49 | 2022-10-27 | ENWL | 4.8.13 NVT | This target is stated both here in the condition and in Appendix 14 - it should be in one or the other but not both. Also, from here onwards the appendices cross-referencing is incorrect | Delete appendix and include target in condition | 2022-12-01 | This text has been deleted. No longer applicable. | Closed
50 | 2022-10-27 | ENWL | 4.8.13 NVAU | This target is stated both here in the condition and in Appendix 15 - it should be in one or the other but not both. | Delete appendix and include target in condition | 2022-12-01 | This text has been deleted. No longer applicable. | Closed
51 | 2022-10-27 | ENWL | 4.8.13 NVAD | This target is stated both here in the condition and in Appendix 17 - it should be in one or the other but not both. | Delete appendix and include target in condition | 2022-12-01 | This text has been deleted. No longer applicable. | Closed
52 | 2022-10-27 | ENWL | 4.8.14 | We disagree with this para - there is nothing in DD that referred to targets being reviewed |  | 2022-12-01 | This point relates to the policy decision in question rather than drafting, please see Draft Determinations 4.72. | Closed
53 | 2022-10-27 | ENWL | 4.8.16 CET | We think the word "target score" should be re-worded as this particular metric incentivises being under the target |  | 2022-12-01 | This text has now been deleted however this is one of several possible drafting approaches. We welcome suggestions for alternatives. | Closed
54 | 2022-10-27 | ENWL | 4.8.16 CET | This target is stated both here in the condition and in Appendix 19 - it should be in one or the other but not both. | Delete appendix and include target in condition | 2022-12-01 | This text has been deleted. No longer applicable. | Closed
55 | 2022-10-27 | ENWL | 4.8.16 CEAU | This target is stated both here in the condition and in Appendix 20 - it should be in one or the other but not both. | Delete appendix and include target in condition | 2022-12-01 | This text has been deleted. No longer applicable. | Closed
56 | 2022-10-27 | ENWL | 4.8.17 | We disagree with this para - there is nothing in DD that referred to targets being reviewed |  | 2022-12-01 | This point relates to the policy decision in question rather than drafting, please see Draft Determinations 4.72. | Closed
57 | 2022-10-27 | ENWL | Part H | Can Ofgem please check the timing of this submission, the wording currently is unclear |  | 2022-12-01 | This point relates to the policy decision in question rather than drafting, please see DSO Incentive Governance Document for our decision on this policy. | Closed
58 | 2022-10-27 | ENWL | Part H | The wording around preparing an annual report seems overly complicated. We suggest this is simplified and a standard form of wording is used for condition 4.5, 4.6, 4.8 and 9.1 |  | 2022-12-01 | Agreed; licence text amended to reflect this. | Closed
59 | 2022-10-27 | ENWL | 4.8.22 g | We prefer this to be more explicit and include a terms of reference for the performance panel |  | 2022-12-01 | This point relates to guidance which will be addressed in the DSO Incentive Governance Document, please see this document for our proposed guidance. | Closed
60 | 2022-10-27 | ENWL | Appendices | We suggest that the word positive adjustment change to reward - this improves readability |  | 2022-12-01 | Agreed; licence text amended to reflect this. | Closed
61 | 2022-10-27 | ENWL | Appendices | We suggest that the word negative adjustment change to penalty - this improves readability |  | 2022-12-01 | Agreed; licence text amended to reflect this. | Closed