## A - SpC 3.3
Licence number and name: |  | SpC 3.3 - Evaluative PCDs
Ofgem contact: |  | Laura Dye
No. | Date raised | Comment from | Reference (Part X, Para Y) | Comment | Suggested alternative drafting (if necessary) | Due Date | Response | Issue closed?
1 | 2021-12-13 | UKPN | 3.3.12 | Aside from the "all" element which is covered elsewhere, why is this steps and not endeavours? |  |  | We think the current drafting is appropriate and conveys the same meaning | Closed
2 | 2021-12-13 | UKPN | 3.3.1(c ) | Costs up to the point of cancellation should also include committed costs as there will be costs which cannot be avoided as they are committed but will only land after the cancellatoin |  |  | Current wording says 'the costs of undertaking reasonable and necessary work until the decision to not deliver the output was made" - covers licensee's point. | Closed
3 | 2021-12-13 | UKPN | 3.3.1(e) | Why wil the Authoity only "consider" an adjustment using this formula? Does it mean another formula could be used or that any adjustment wont always be made? |  |  | Wording removed | Closed
4 | 2021-12-13 | UKPN | 3.3.1(f) | This appears to give the Authority free range to not follow what is in the licence |  |  | We consider there is sufficient detail in the licence and in the AD that sets out how an adjustment will be made. | Closed
5 | 2021-12-15 | NPg | 3.3 | Price Control Deliverable is a defined term of itself but there are various references in each condition to PCD | Either use Price Control Deliverable in full in each case or define Price Control Deliverable as PCD at the first opportunity in each condition |  | Defined term is Price Control Deliverable. | Closed
6 | 2021-12-15 | NPg | 3.3.3 | Minor drafting point | Insert "the " before "Evaluative" for consistency |  | Superseded by later changes | Closed
7 | 2021-12-15 | NPg | Part D onwards | Paragraph numbering goes wrong | Reset paragraph numbering from 3.3.8 |  | Superseded by later changes | Closed
8 | 2021-12-15 | NPg | Part D 3.3.1 | Minor drafting point | ".. until the date of the decision ..." as clarification |  | Superseded by later changes | Closed
9 | 2021-12-15 | SSEN | SpC 3.3/ SpC9.3 Part D | Post-CMA review drafting - please see feedback from SSEN transmission on this issue in particular with reference to (i) specificity of assessment criteria to ensure assessment is objective and robust, (ii) partial delivery formula must recognise that project spend profile is not always going to be linear. We do not consider that a self-modification process is appropriate as the current licence drafting allows significant discretion on assessment process and criteria. |  |  | disagree that process leaves room for discretion, 3.3 Part C describes the process clearly and in detail. | Closed
10 | 2022-02-23 | WPD | Part D | Numbering error (3.3.1 should be 3.3.8) |  |  | Addressed numbering error. | Closed
11 | 2022-02-23 | WPD | Part D | What is meant by considered Fully Delivered and then with a subsequent Alternative Specification |  |  | As defined in licence, this "means where the licensee has delivered a different specification to that set out in the relevant special condition, while achieving a Consumer Outcome that is materially equivalent or better than what would have been achieved if the licensee had delivered the output as set out in the relevant special condition." | Closed
12 | 2022-02-23 | ENWL |  | AIP text in Visual Amenity/ PCDs |  |  | Not being used in the licence but putting it in the Handbook, not individual conditions | Closed
13 | 2022-02-23 | WPD | 3.3.3 c | publish and send a notification - make language consistent across the licence |  |  | Current drafting is appropariate. | Closed
14 | 2022-02-23 | SPEN |  | What is the process for obtaining access to the confidential documents? |  |  | These will be provided directly to the relevant licensees. | Closed
15 | 2022-02-23 | SPEN |  | What is the difference between Mock and Other PCDs? |  |  | Mock PCDs are where there is an output that has to be delivered (eg, cyber). Other PCDs are discretionary with allowance recovered if not delivered with no other consequence. TBC whether this is actually needed in ED. | Closed
16 | 2022-02-23 | ENWL, WPD | Part D | Care needed around the language with the potential for a high degree of subjectivity in current drafting |  |  | Noted | Closed
17 | 2022-02-23 | SSEN |  | Does the current drafting account for any investment that is not uniform across the period? |  |  | It should do - each licence condition should specify whether the assessment of the output happens annually or at the end of the period, and how adjustments to the allowances in each year would be made | Closed
18 | 2022-03-01 | SSEN | 3.3.2(b) | How would DNOs demonstrate that the costs were necessary and incurred efficiently in the event that an output is Not Delivered? |  |  | This describes a case where, e.g., the DNO had to invest resources into preparation, but other circumstances later led to the failure to deliver the output, this could also include circumstances outside the DNOs' control. The preparatory works could still have been justified and efficient, and the DNO would have to submit evidence to show this. | Closed
19 | 2022-03-01 | SSEN | 3.3.2(c) | Definition of 'material impact'? |  |  | This will vary depending upon the scale and cost of each PCD, therefore discretion is required to determine materiality for individual circumstances. | Closed
20 | 2022-03-01 | SSEN | 3.3.2(d)(ii) | How would the 'proportion of output delivered' be determined? Should this be the justified estimate that the licensee is required to provide under (ii)? |  |  | How the proportion will be determined depends on the output in question - please see Appendix 2 for examples. Where there is no appropriate methodology to determine the proportion delivered, we would then determine the efficient cost of what was actually delivered, and adjust the allowance accordingly, as set out in licence condition 3.1. | Closed
21 | 2022-03-01 | SSEN | General | No timescale for the Ofgem assessment and direction - this would be helpful to provide certainty and transparency for DNOs. |  |  | Timescales are outlined in the AD in chapter 7 - evaluative PCDs section - "We will seek to complete the assessment process within a period of 9 months or less" | Closed
22 | 2022-03-01 | SSEN / WPD | 3.3.9(g) | 'allocate' would be more appropriate than 'proportion'. |  |  | Change made (now 3.3.15(e)) | Closed
23 | 2022-03-11 | SPEN | Part D, 3.3.9 (f) | What if an output has been fully delivered with an alternative specification which has a better outcome for customers - presumably under this drafting there would be no increase in allowance. Would there be circumstances where Ofgem would consider an upward adjustment for a much better outcome? If so then this drafting would seem to restrict that possibility. |  |  | No, upward adjustments to allowances are not foreseen, except for cyber IT and OT PCDs. Otherwise, the PCD mechanism is to ensure outputs are delivered for those allowances provided, the TIM is applied in most cases. As part of the cost assessment process, those cost that are associated with the baseline allowances for PCDs that were determined to be of high confidence, therefore we expect the activities and works associated with the allowances to have a higher degree of certitude. We recognise that for certain projects that there may be scope for delivering greater consumer benefits but at higher price. We have provided reopeners for certain PCDs to ensure that there remains a level of flexibility. We therefore reject the motion for an upside to total allowances for PCDs. | Closed
24 | 2022-03-11 | SPEN | Part E, 3.3.10 and 11 | Until more detail is provided on ED2 PCD licence drafting, it is not possible to arrive at a firm view on whether it is appropriate for PCD modifications to be done by Ofgem direction rather than through a Section 11 process. We would like to revisit this point once more detail on PCD drafing is available. |  |  | Noted | Closed
25 | 2022-03-11 | WPD | 3.3.11(a) | The delivery status could be any status not just “not Fully Delivered” |  |  | Agreed, therefore alternative delivery statuses are set out and defined. | Closed
26 | 2022-06-07 | DNO joint paper | Part C | Process for evaluative PCDs and allowance changes is incomplete and difficult to follow - the categories that have been identified are not all specified correctly, leading to several predictable, efficient circumstances ending up in the ‘catch all’ bespoke expost review category |  |  | Disagree that a change is needed - categories do cover all possible outcomes. It may be that licensees are referring to a point raised elsewhere - that upward adjustments should be possible where the output was delivered with alternative specification but at a higher cost that was nonetheless efficient. However, this outcome is accommodated in the categories as currently drafted. The PCD process does not provide for upward adjustments. | Closed
27 | 2022-06-07 | DNO joint paper | 3.3.14 (g) | Sub-paragraph 3.3.14(g) sets out that “any adjustment to an associated allowance will proportion that allowance to Regulatory Years in accordance with the profile of actual expenditure reported by the licensee”. It is unclear whether the “actual expenditure” referred to here relates to an individual output, the full programme of cyber OT/cyber IT expenditure or all expenditure. It is also unclear whether this sub-paragraph refers to the apportionment of the allowance adjustment, or whether this is intended to allow that the entire allowance can be reapportioned in accordance with the profile of actual expenditure. We assume that the original allowances (whether baseline or reopener) will remain untouched and that this is only intended to refer to the apportionment of the allowance adjustment. |  |  | No changes to AD required, it is clear as drafted. In response to the query: "actual expenditure" refers to the allowances associated with an output that has not been fully delivered. Licensee's assumption is not correct - the adjustment will reallocate allowances associated with the output, not just the adjustments. | Closed
28 | 2022-06-07 | DNO joint paper | 3.3.14 (a) | The fact that an output has been assessed as meeting the definition of Fully Delivered With An Alternative Specification should be sufficient to justify no allowance adjustment being made. If expenditure on the alternative solution did not exactly match the original allowance, any overspend against the original allowance would be subject to TIM. Any cyber IT underspend would also be subject to TIM and would be shared with customers. In the case of cyber OT, any underspend would likely be given back to customers via UIOLI. | Sub-paragraph 3.3.14(a) should be amended to read “where an output is Fully Delivered With An Alternative Specification and the licensee demonstrates that any underspends against the associated allowances are attributable to Efficiency or Innovation, the Authority will not make any adjustment to the associated allowance;” |  | No change made, original drafting meets policy intent. | Closed
29 | 2022-06-07 | DNO joint paper | definitions | The definition of Delayed fails to include instances where a PCD has been delivered in line with the original scope, but after the specified date | The definition of Delayed should be expanded “where the licensee has not delivered the output set out in the relevant special condition in full by the relevant delivery date, but has delivered or intends to deliver the output at a later date.” |  | Change made in ED sector - if Licensees find this adds clarity. | Closed
30 | 2022-06-07 | DNO joint paper | definitions | there is a conflict between the expectation that partial delivery can be justified by efficiency and the definition of Efficiency. (...) It means that Efficiency cannot be used to justify Partially Delivered or Partially Delivered With Alternative Specification |  |  | Change made to hypothetical example 3 to improve clarity, but not to definitions. The definition of efficiency works because it includes the reference to Conumser Outcome. Efficiency can be used to justify partial delivery of an output, if the Consumer Outcome (that is the expected benefits to consumers in terms of service quality over what would have been the whole life of the output specified in the relevant special condition had it been delivered as specified), is still equivalent or improved despite less of the output having been delivered. | Closed
31 | 2022-06-07 | DNO joint paper | 3.3.10 | #3: The proposed obligation in paragraph 3.3.10 to “take all reasonable steps to deliver the outputs specified” risks duplicating or even contradicting obligations elsewhere Fix To avoid unnecessary duplication and potential for contradiction and confusion, the words in paragraph 3.3.10 should be removed. If the cyber PCDs are to remain part of a wider evaluative PCD condition and other mechanisms require the inclusion of Part B, we suggest that the following, alternative form of standard words proposed by Ofgem could be used: “The licensee is funded to deliver the outputs specified in the Cyber Resilience OT PCD Table and the Cyber Resilience IT PCD Table in accordance with and by the delivery dates specified in those tables.” However, if a separate cyber condition was to be developed, we do not believe that Part B would be necessary as the revised words do not perform any operative function. |  |  | We consider that the drafting reflects the policy intention | Closed
32 | 2022-06-07 | DNO joint paper | Pa+A31+D31 | #5: There is not enough clarity in the drafting of Part D (UIOLI) to avoid double counting of any cyber OT evaluative PCD adjustment #5.1: The UIOLI adjustment under sub-paragraph 3.3.15(a) is not well articulated and may double count adjustments made under Part C Fix Paragraph 3.3.16 should be amended to make the intent clear: “The assessment under this Part will be made after the end of the Price Control Period and after any assessment under Part C. It will be made in such a way as to avoid double counting any adjustment to allowances made under Part C.” We believe that this adjustment can be set out algebraically relatively easily... #5.2: The purpose of sub-paragraph 3.3.15(b) is unclear, and may duplicate adjustments made under Part C Fix The purpose of sub-paragraph 3.3.15(b) is unclear, and may duplicate adjustments made under Part C |  |  | To clarify how the cyber UIOLI mechanism works, the following text has been documented in Section 3 of "RIIO-2 Cyber Resilience OT and IT PCD Reporting Guidance". This document will be issued as confidential Appendix 4 to the DNOs, as mentioned in the 'PCD_Reporting_Requirements_and_Methodology_Document_v3' document. The CROTt and CROTREt UIOLI mechanism is implemented with an asymmetrical approach as follows: • Overspend: TIM applies (costs shared between the operator and customer in accordance with the respective licensee’s TIM incentive rate). • Underspend: TIM does not apply, and unspent allowance will be recovered for customers. | Closed
33 | 2022-06-07 | DNO joint paper | 3.3.13 | #6: ...some of the allowance adjustment methodologies are not appropriate for cyber PCDs. Some will tend to provide inappropriately large allowance deductions. Others will mandate that Ofgem undertakes intrusive ex-post efficiency assessments that are neither consistent with policy nor likely to yield meaningful information about the efficiency or otherwise of cyber expenditure. Fix The general comprehensibility of Part C is probably better tackled once the other issues in it have been resolved, and once a decision has been made as to whether to create a separate cyber-specific condition.Inclusion of process diagrams and worked examples in the PCD Reporting Requirements and Methodology Document would also aid understanding. We identify solutions for some of the most material issues in the later sections of this note. |  |  | Cyber specific guidance documents have been updated to include worked examples. | Closed
34 | 2022-06-07 | DNO joint paper | Part C | #7 A number of PCD output delivery ‘categories’ and their associated allowance adjustment methodologies have not been specified correctly, are inconsistent with policy or are inappropriate for the assessment of cyber PCD delivery #7.1. Issues that are relevant to several or all PCD delivery ‘categories’ #7.1.1. It is unclear whether the definition of Consumer Outcome appropriately reflects the factors targeted by cyber activities The broad definition of Consumer Outcome can be quite widely interpreted and may be hard to relate to specific outputs, particularly in the case of activities such as cyber. In particular: • Distribution Network is not a defined term, so it is not clear how OT and IT resilience would be captured in part (a). A relevant pre-existing defined term may be Distribution System, but this would not encompass IT assets and may not include all OT assets. • In the case of parameter (b), cyber investment generally seeks to avoid deterioration in performance in the event of a cyber attack. Effectively, cyber projects target maintenance of existing levels of service quality by preventing very specific eventssuch as phishing or specific cyber attack. It is unclear how a DNO would be expected to quantify that an alternative cyber solution delivers a “materially equivalent or better” outcome against this aspect of the definition given the nature of the events the investment seeks to prevent. • The evolution of cyber guidance leads to an increasing blurring of the boundary between OT and IT outcomes, with cyber IT activities often being the ‘first line of defence’ against OT threats Fix Revisit the wording of the defined term Consumer Outcome, with other possible PCDs in mind as well as cyber, to ensure that all appropriate factors are included. Clarify how the quantification of delivery of Consumer Outcome will be undertaken for cyber activities. Consider whether reference to the defined term of Distribution System would be more appropriate than including the new and undefined term of Distribution Network in the definition of Consumer Outcome. (Note that this will not address the specific issue of some cyber assets not being included, but may be more useful for other PCDs). If the option of a separate condition covering cyber PCDs was considered, this could be differently achieved by referring to relevant criteria in the guidance issued under the NIS Regulations or CAF Assessment Framework as a means of assessing delivery. |  |  | 7.1.1 Consumer Outcome- means the benefits to existing and future consumers in terms of maintenance of existing levels of, or improvements in the network’s capability or resilience including cyber resilience, or benefits to consumers in terms of service quality, or reduction in risk delivered, that would have been delivered by the PCD output over the whole life of the PCD output as specified in the relevant licence condition. In the context of works delivered by the licensee, this means the benefits to customers or consumers in terms of maintenance of existing levels of, or improvements in the network’s capability or resilience including cyber resilience, or benefits to consumers in terms of service quality, or reduction in risk delivered, that can be attributed to the works delivered by the licensee over the whole life of the works delivered. This has been addded to the definitions. 7.1.1 Distribution network- is not a defined term. proposed updates to Consumer Outcome will address the definition of distribution networks and information systems which has both physical and logical components 7.1.1 Materially equivalent or better- hypothetical example to be included in Cyber specific guidance covering delivery with an alternate solution. It is unclear what the challenge is based on the "cyber solution" from a technical perspective there are a number of technologies able to deliver the same or similar levels of outcomes and similarly for people there are a number of consultancy or third party contractors that could be used to provide the "materially equivalent or better" outcome | Closed
35 | 2022-06-07 | DNO joint paper | Part C | #7.2. Issues relating to ‘Fully Delivered With An Alternative Specification’ #7.2.1. Issues with the definition of Consumer Outcome inappropriately lead to DNOs being unable to demonstrate that PCDs are Fully Delivered With An Alternative Specification Fix Revisit the wording of the defined term Consumer Outcome to ensure it covers cyber outcomes. |  |  | Consumer Outcome definition updated to include terms 'cyber resilience' and 'risk reduction'. | Closed
36 | 2022-06-07 | DNO joint paper | Part C | #7.4.2. The possible justifications for an output being Partially Delivered or Partially Delivered With Alternative Specification need to be extended to include changes to external requirements and external factors Fix The wording of sub-paragraph 3.3.14(d)(i) should be amended to become: “the licensee demonstrates that any underspend against the associated allowance are attributable to Efficiency, or Innovation, or changes to external requirements or external factors; and” |  |  | No change made, original drafting meets policy intent. | Closed
37 | 2022-06-07 | DNO joint paper | 3.3.14e | #7.5. Issues relating to the bespoke ex-post assessment undertaken in subparagraph 3.3.14e #7.5.1. The ex-post assessment anticipated in sub-paragraph 3.3.14(e) is not consistent with policy, and also proposes an ex-post efficiency assessment that will be difficult to implement for cyber activities Fix We think it is probable that this category of PCD assessment was introduced into the generic drafting for some GD and T PCDs and that a much simpler process can be implemented for cyber OT and cyber IT. If the ex-post assessment is to be retained in the condition, sub-paragraph 3.3.14(e)(iii) should be reworded to say “where none of the circumstances described in sub-paragraphs (b) to (d) apply, the Authority may direct an adjustment to the associated allowances such as to allow only the efficient costs of any work carried out that contributes to the delivery of the output. When deciding on the value of any such adjustment, the Authority will: i. have due regard to the particular characteristics of the output; and ii. have due regard to any factors that are outside of the licensee’s control and that may have affected the ability of the licensee to Fully Deliver the output.; |  |  | No change made - the ex post efficiency assessment is consistent with Ofgem's intent for PCD policy in the cases set out in the licence condition. | Closed
38 | 2022-06-07 | LDWG- Sept 2022 | NA | Review definitions for IT and OT to make more applicable to Cyber Security |  |  | Definition: IT means a licensee's information technology network and information systems that relate to the use of computers, software, hardware and other devices to perform business operations. Definition: OT means a licensee's operational technology network and information systems that interfaces with physical assets and processes of operations. | Closed
39 | 2022-06-07 | LDWG- Sept 2022 | 3.2.50 | Review definition of measured risk reduction in SpC 3.2: 3.2.50 |  |  | Removal of term "measured" will have no impact on the requirements set out by the Authority for IT Re-openers i.e. the DNO is required to demonstrate a quantifiable method for risk reduction Term- removed from clause | Closed
40 | 2022-06-07 | DNO joint paper | general | Not clear yet whether 3.3 will only apply to cyber or also other evaluative PCDs. Having 3.2+3.3+9.3 apply is hard to understand, need cross references | . |  | We have decided to retain the strucutre of the licence conditions as previously proposed. We have added cross-references between 3.3 and 9.3. | Closed
41 | 2022-06-08 | DNO joint paper | 3.3.14 | The possible justifications for an output being Partially Delivered or Partially Delivered With Alternative Specification need to be extended to include changes to external requirements and external factors | The wording of sub-paragraph 3.3.14(d)(i) should be amended to become: “the licensee demonstrates that any underspend against the associated allowance are attributable to Efficiency, or Innovation, or changes to external requirements or external factors; and” |  | No change made, original drafting meets policy intent. | Closed
42 | 2022-06-08 | DNO joint paper | general | need cross refs between 3.3+9.3. |  |  | See response for issue number 37 | Closed
43 | 2022-06-09 | DNO joint paper |  | The formula for determining allowances for Partially Delivered PCDs incorrectly assumes that output and Consumer Outcome delivery is likely to be proportional to expenditure incurred. (…) For cyber OT and cyber IT evaluative PCDs, it would be more appropriate for the revised allowance to take account of the costs that have been reasonably incurred |  |  | No change needed as this alternative approach is already reflected in the process set out in licence. In the case described, the licensee will not be able to satisfy 3.3.14 (d) ii) by submitting a well justified estimate of the proportion of the output or consumer outcome delivered, and Ofgem can use 3.3.15(a) - adjust to allow only efficient cost. | Closed
44 | 2022-06-10 | DNO joint paper | 3.3.14e - now 3.3.15 (a) | The ex-post assessment anticipated in sub-paragraph 3.3.14(e) is not consistent with policy, and also proposes an ex-post efficiency assessment that will be difficult to implement for cyber activities |  |  | No change made - the ex post efficiency assessment is consistent with Ofgem's intent for PCD policy in the cases set out in the licence condition. | Closed
45 | 2022-06-11 | DNO joint paper | parts A and E | The PCD adjustments for OT and IT are presented differently, which may confuse users into thinking that different processes apply | We suggest that the IT process is drafted to mirror the OT process (but without the UIOLI step). |  | No change made. This is one of several drafting options, we prefer present drafting. | Closed
46 | 2022-10-10 | SPEN | 3.1.13a | Fully delivered PCDS to an alternative spec, that have not overspent, should NOT be required to undergo a separate review of efficiency to determine if downward adjustments to allowance should be made. We understood the policy to be that such underspends should be shared with customers and subject to the TIM. If there is now a risk that licensees could fail such efficiency review by Ofgem this is not the case then the incentive to drive efficiencies is diluted. In addition to this, the phrase 'may' should be replaced with 'shall' given the context. | where an output is Fully Delivered With An Alternative Specification and the licensee demonstrates that any underspends against the associated allowances are attributable to Efficiency or Innovation, the Authority may shall not make any adjustment to the associated allowance |  | This point relates to the policy decision in question rather than drafting, please see Final Determinations for our decision on this policy. | Closed
47 | 2022-10-10 | SPEN | 3.1.13d | Evidence permitted for Partially Delivered or Partially Delivered with Alternative spec should also allow demonstration of underspends due to external factors and not just Efficiency or Innovation. Ofgem closed this issue in the log saying 'No change made, original drafting meets policy intent: allowances may be adjusted if there are changes to external factors that lead to an output not being fully delivered.' We believe that changing the drafting as we have proposed would ALSO meet policy intent but it would streamline the process further. | where the output is Partially Delivered or Partially Delivered With Alternative Specification, and the licensee demonstrates that any underspend against the associated allowance is attributable to Efficiency or Innovation or factors that are outside of the licensee’s control and that may have affected the underspend. |  | This is one of several possible drafting approaches, we think the proposed darfting is appropriate. No change made, original drafting meets policy intent: allowances may be adjusted if there are changes to external factors that lead to an output not being fully delivered. | Closed
48 | 2022-10-10 | SPEN, UKPN | Spc 3.3 Evaluative PCDs | Ofgem’s issues log (row 25) sets out that in the event of a Partially Delivered output where costs are “front end loaded” Ofgem would be able to fund the efficiently incurred costs via the processes in 3.3.13(a) (we think it means (e)). We do not understand how Ofgem would be able to use this branch of 3.3.13 instead of 3.1.13(d). We also do not understand what approach the DNO should take to reporting the delivery status of a PCD in this situation. Paragraph 1.12 of PCD Reporting Requirements and Methodology Document does not permit the DNOs an option to indicate that assessment under 3.3.13(e) is appropriate. It would be helpful if Ofgem could include a “hypothetical example” in the Associated Document explaining this process. |  |  | Please see hypothetical examples in Appendices 2 and 4. | Closed
49 | 2022-10-10 | SPEN | 3.3.13e | The cyber threats faced and external best practice around addressing these are also fast-moving. As a consequence, DNOs may be required to amend their cyber work programmes during RIIO-ED2. These programme changes may sometimes lead to DNOs deciding to only partially deliver previously agreed outputs and to focus on new outputs instead. While a decision to cease the delivery of planned cyber outputs in such circumstances would be sensible as it would be inappropriate to incur unnecessary expenditure, DNOs are at risk of being penalised because such decisions would not meet the definition of Efficiency proposed in the licence. This is because many changes will arise due to “factors beyond the reasonable control of the licensee” and also result in “lower Consumer Outcome than would have been achieved if the licensee had delivered the output as specified” both of which are explicitly excluded from the definition of Efficiency. In addition, it is possible that some outputs may be partially delivered as a result of innovative alternatives being deployed. However, it may often be the case that the reasons for ceasing an output may not meet the definition of Innovation as the application of technology, systems or processes may well have been proven (in other relevant contexts) as at the time of submission of the Business Plan. This leaves DNOs with a risk that any cyber outputs that are ceased for good reason during the price control, would be subject to ex-post efficiency review. We urge Ofgem to reconsider the assessment and allowance adjustment process and the associated wording of the licence and to introduce a practical, workable approach to adjustment of allowances for cyber projects that are cancelled before the associated output is fully delivered |  |  | Current drafting meets policy intent and therefore no changes are made. In response to the comment please refer, Part G clause 3.2.42 to clause 3.2.49 of licence condition which covers the situations where a cyber resilience OT re-opener can be triggered including the following: (a) new activities, including new technology, capable of improving cyber resilience in relation to OT, including risk reduction and improved status of the licensee’s OT network and information systems with respect to CAF Outcomes; (b) changes to levels of risks or threats relating to cyber resilience in relation to OT, that take the licensee outside of its organisational risk appetite; (c) changes to statutory or regulatory requirements relating to cyber resilience in relation to OT; or Please also refer Part H clause 3.2.50 to 3.2.57 which explains the criteria where a cyber resilience IT re-opener can be triggered. | Closed
50 | 2022-10-10 | SPEN | Appendix 1 | We are unclear what the term NSEt for SPEN only relates to. Is this an error? |  |  | Updated drafting to Appendix 1 of 3.3 superseded this point. | Closed
51 | 2022-10-10 | SPEN | 3.3.10 | The proposed obligation in paragraph 3.3.10 to “take all reasonable steps to deliver the outputs specified” risks duplicating or even contradicting obligations elsewhere. The Ofgem issues log suggested this has been addressed, but the published version of the licence still has the original text |  |  | We do not agree and think the current drafting is appropriate to reflect the policy intention. | Closed
52 | 2022-10-10 | SPEN | general | Is Ofgem no longer applying a UIOLI regulatory mechanism to the cyber OT spend? The drafting in Spc3.3 has had earlier drafting on this removed. If Ofgem does still intend to apply a UIOLI then this needs to be set out in licence clearly so that any adjustments are applied after PCD assessment |  |  | This point relates to the policy decision in question rather than drafting, please see Final Determinations for our decision on this policy. Cyber Resilience OT allowance is not subject to the TIM and therefore any underspend would be recovered | Closed
53 | 2022-10-10 | SPEN | general | The condition does not make it clear that Ofgem will assess PCD delivery based on evidence that was reasonably available at the time that the decisions were made. This important principle was enshrined in the DPCR5 and RIIO-ED1 close out processes and should be continued for RIIO-ED2. The DNOs have previously suggested drafting that would achieve this. We cannot see reference on the issues log to understand Ofgem’s rationale for not including this extra drafting. |  |  | We do not think the proposed wording is requied. It would be unreasonable for the Authority to expect the licensee to have taken into consideration information that was not aware of or could not have been reasonably aware of at the time the relevant investment decision was taken. To require otherwise would be against the principles of fair regulation. | Closed
54 | 2022-10-21 | UKPN | Cyber conditions (3.2, 3.3,9.3) | Fundamentally, we think that it is most important to address the issues with the operation of the licence conditions in respect of cyber OT and cyber IT as outlined earlier in this response. Once those issues have been resolved, we would also support the creation of a single condition that covers all aspects of the regulation of cyber OT and cyber IT allowance adjustments. However, but this objective is secondary to ensuring that the various components operate correctly. We set out our proposal for how this could be achieved in our consultation response. |  |  | We have taken all consultation responses into considertaion in arriving at our Final Determinations. | Closed
55 | 2022-10-21 | UKPN | 3.3.16(b) | The wording presupposes that there will always be a reduction in allowances where a PCD is not fully delivered. There are scenarios where Ofgem may choose to make no downward adjustment e.g. a delayed output but where delay is not material |  |  | Disagree that the wording proposes the outcome as stated. No change made. | Closed
56 | 2022-10-21 | UKPN | 3.3.16 | The second half of (b) commencing "and in relation to…"feels like it should be a separate bullet with the current (c) being a closing sentence to that separate bullet | (b) the value of the reduction to allowances and the Regulatory Years to which that adjustment relates, and (c) in relation to: i. cyber resilience OT must specify the value of CROPCDt and CROPCDRt; and ii. cyber resilience IT must specify the value of CRIPPCDt and CRIPPCDRt; and the methodology and data that has been used to decide the matters required by sub-paragraphs (a) and (b). |  | Agreed. 3.3.19 now reflects the suggested alternative drafting. | Closed
57 | 2022-10-21 | UKPN | Part C, 3.3.13 (c ) | There is no definition for the term 'material'. This is ambiguous and should be defined in monetary terms. |  |  | Disagree that the term is ambigous. No change made. | Closed
58 | 2022-10-21 | UKPN | 3.3.4(d) | CRIREt should be CRITREt |  |  | Agreed and updated. | Closed
59 | 2022-10-21 | UKPN | 3.3.5 to 3.3.9 | Should the cross references to Part C in these paragraphs be to Part D? |  |  | No change required. The cross reference refers to the process followed by the Authority in adjusting allowances. | Closed
60 | 2022-10-21 | UKPN | 3.3.13(b) | Is the final wording on "not otherwise funded by the special conditions of this licence" superfluous bearing in mind this is about reducing allowances for a non-delivery? |  |  | Disagree. No change required, sentence is necessary. | Closed
61 | 2022-10-21 | UKPN | 3.3.13(f) | Should this paragraph be expanded to clarify our understanding of the Ofgem policy which is for no increase in allowances should an evaluative PCD be fully delivered |  |  | No change made. This is one of several valid drafting options, we prefer present drafting. | Closed
62 | 2022-10-21 | UKPN | 3.3.16(b)(ii) | CRIPPCD and CRIPPCDR should be CRIPCD and CRIPCDR |  |  | Agreed and updated. | Closed
63 | 2022-10-26 | NPg | Defintion of "Consumer Outcome" | "Customer" is the defined term | Change three references to "consumer" to "Customer", delete "or consumers" and capitalise "customer" |  | The term "Consumer Outcome" has been added to the definitions spreadsheet. | Closed
64 | 2022-10-26 | NPg | Part C, paragraph 3.3.13(c) | The treatment of a cyber OT or cyber IT PCD that is delayed into the RIIO-ED3 period is unclear. It would be helpful if Ofgem could confirm that the re-profiling of any allowances associated with Delayed PCD delivery set out in 3.3.13(c) would extend to any PCD that is delayed into the RIIO-ED3 period. A “hypothetic example” to confirm this treatment would be helpful. |  |  | Delayed is not assigned if it is delayed into the next price control period. In these cases, instead, these outputs would be classed as "Partially Delivered"or "Not Delivered". Also, please refer Hypothetical examples for cyber OT and cyber IT, which has been documented in "RIIO-2 Cyber Resilience OT and IT PCD Reporting Guidance". This document will be issued as confidential Appendix 4 to the DNOs, as mentioned in the 'PCD_Reporting_Requirements_and_Methodology_Document_v3' document | Closed
65 | 2022-10-26 | NPg/UKPN | Interaction between SpC 3.2, SpC 3.3 and PCFM | The treatment of allowances associated with cyber OT and cyber IT in the PCFM seems to create variant baseline allowances. This is quite different to the more familiar approach of creating fixed baseline allowances and/ or separate variable values, and is not consistent with how the draft PCFM operates. It would be helpful if Ofgem could explain how it envisages these allowances operating in the PCFM, and also provide guidance to DNOs on how it expects DNOs to adjust these values when setting network charges. This will help us to check whether the allowance adjustments envisaged in these conditions are being specified in a manner that is consistent with the intended operation of the PCFM. |  |  | Please refer Hypothetical examples for cyber OT and cyber IT, which has been documented in "RIIO-2 Cyber Resilience OT and IT PCD Reporting Guidance". This document will be issued as confidential Appendix 4 to the DNOs, as mentioned in the 'PCD_Reporting_Requirements_and_Methodology_Document_v3' document. | Closed
66 | 2022-10-26 | NPg/UKPN | Part C, paragraph 3.3.13 (Also see PCD Reporting Requirements and Methodology Document para 1.12) | Ofgem’s issues log (row 25) sets out that in the event of a Partially Delivered output where costs are “front end loaded” Ofgem would be able to fund the efficiently incurred costs via the processes in 3.3.13(a) (we think it means (e)). We do not understand how Ofgem would be able to use this branch of 3.3.13 instead of 3.1.13(d). We also do not understand what approach the DNO should take to reporting the delivery status of a PCD in this situation. Paragraph 1.12 of PCD Reporting Requirements and Methodology Document does not permit the DNOs an option to indicate that assessment under 3.3.13(e) is appropriate. It would be helpful if Ofgem could include a “hypothetical example” in the Associated Document explaining this process. |  |  | Please refer Hypothetical examples in Appendices 2 and 4. | Closed
67 | 2022-10-26 | NPg/UKPN | Part C | For the reasons set out in our consultation response, the assessment process is likely to result in inappropriately intrusive ex-post efficiency assessment of any partially delivered cyber outputs. We urge Ofgem to reconsider the assessment and allowance adjustment process and the associated wording of the licence and to introduce a practical, workable approach to adjustment of allowances for cyber projects that are cancelled before the associated output is fully delivered. |  |  | This issues relates to our policy decision for Cyber OT and IT. For full details of it please refer to our Final Determinations. Please refer Hypothetical examples for cyber OT and cyber IT, which has been documented in "RIIO-2 Cyber Resilience OT and IT PCD Reporting Guidance". This document will be issued as confidential Appendix 4 to the DNOs, as mentioned in the 'PCD_Reporting_Requirements_and_Methodology_Document_v3' document. | Closed
68 | 2022-10-26 | NPg/UKPN | Part C | The condition does not make it clear that Ofgem will assess PCD delivery based on evidence that was reasonably available at the time that the decisions were made. | Add an extra sub-paragraph early in paragraph 3.3.14 setting out that: “The Authority shall only have regard to information that could reasonably have been available to the DNO at the time of making the relevant investment decisions”. |  | We do not think the proposed wording is requied. It would be unreasonable for the Authority to expect the licensee to have taken into consideration infromation that was not aware of or could not have been reasonably aware of at the time the relevant investment decision was taken. To require otherwise would be against the principles of fair regulation. | Closed
69 | 2022-10-26 | NPg/UKPN | Part B, paragraph 3.3.10 | The proposed obligation in paragraph 3.3.10 to “take all reasonable steps to deliver the outputs specified” is an unnecessary obligation that effectively duplicates a sub-set of obligations contained in the extensive secondary legislation and guidance. There is also a chance that this paragraph could contradict the Network and Information Systems (NIS) Regulations 2018. | Changes to the drafting of SpC 3.2, 3.3 and the Load Related Expenditure Re-opener Guidance will be required to achieve this. |  | We do not agree and think the current drafting is appropriate to reflect the policy intention. | closed
70 | 2022-10-26 | NPg/UKPN | Part A, paragraph 3.3.4(e) and Appendix 1 (Also see SpC 3.2.80(b) and Load Related Expenditure Re-opener Guidance para 1.11) | It is premature to assume that all Strategic Investment projects should be subject to evaluative PCDs. We currently do not expect any DNO to be provided with a baseline allowance to deliver a load related project that has been designated as a Strategic Investment project. In discussions with Ofgem it has been suggested that targeted delivery assessment mechanisms are likely to be required, possibly through the modification of the licence to introduce a mechanistic PCD. It is therefore inappropriate for the licence to presume that an evaluative PCD will automatically be created. | The introduction of any PCDs associated with Strategic Investment should be introduced via a modification made under section 11A (modifications of conditions of licences) of the Act (following the drafting approach used in paragraph 3.6.10 for the Net Zero Re-opener). |  | Please refer the response against Issue no. 48. | Closed
71 | 2022-10-26 | NPg/UKPN | 3.3 - general | The process for the assessment of evaluative PCDs that is set out in Part C of special condition 3.3 is a generic process. Some aspects of this generic process are not appropriate for the assessment of cyber PCDs. The generic drafting of key defined terms that this condition relies on (such as Consumer Outcome, Efficiency and Innovation) makes it difficult for DNOs to understand how cyber PCDs will be assessed or the likely impact on future allowance modifications. As cyber PCDs are likely to be the only evaluative PCDs ascribed to DNOs at the start of RIIO-ED2, the fact that the generic wording of the condition is not appropriate to cyber activities is concerning. These key terms should be reviewed and better tailored to the assessment of cyber PCDs. |  |  | Please refer Hypothetical examples for cyber OT and cyber IT, which has been documented in "RIIO-2 Cyber Resilience OT and IT PCD Reporting Guidance". This document will be issued as confidential Appendix 4 to the DNOs, as mentioned in the 'PCD_Reporting_Requirements_and_Methodology_Document_v3' document. | Closed
72 | 2022-10-26 | NPg | 3.3 - general | It is unclear whether cyber OT is still subject to a potential additional Use It or Lose It (UIOLI) adjustment. SpC 3.3 does not include any UIOLI adjustment for cyber OT. We agree that the presence of the re-opener, PCD delivery mechanism and the PCD reporting provisions means that a UIOLI adjustment is not needed. However, we note from Ofgem’s issues log that a UIOLI mechanism is expected. The DNOs have previously submitted text and associated algebra that could enact this adjustment if it is required. |  |  | This point relates to the policy decision in question rather than drafting, please see Final Determinations for our decision on this policy. Cyber Resilience OT allowance is not subject to the TIM and therefore any underspend would be recovered | Closed
73 | 2022-10-26 | NPg/UKPN | 3.3 - Cyber conditions (Also see SpC 3.2 and SpC 9.3) | Fundamentally, we think that it is most important to address the issues with the operation of the licence conditions in respect of cyber OT and cyber IT as outlined earlier in this response. Once those issues have been resolved, we would also support the creation of a single condition that covers all aspects of the regulation of cyber OT and cyber IT allowance adjustments. However, but this objective is secondary to ensuring that the various components operate correctly. We set out our proposal for how this could be achieved in our consultation response. |  |  | We have taken all consultation responses into considertaion in arriving at our Final Determinations. | Closed
74 | 2022-10-27 | NGED | 3.2.44(d)(iii) 3.2.50(e) 3.2.52(d)(iii) 3.2.58(e) | These sub-paragraphs all allow the Authority to correct errors or make undefined "refinements". We do not believe that the condition should be drafted on the presumption that there may be errors in the licence. In any case, the Authority will already have powers to correct errors in the licence under SLC 3A. These sub-paragraphs should all be deleted. |  |  | No changes made. SLC 3A is the procedure for making Housekeeping Modifications to the licence. The PCDs, allowances, outputs and delivery dates set for Cyber OT and IT are not set out in the licence, but in our Final Determinations. SLC 3A cannot, therefore, be used to modify PCDs, allowances, outputs and delivery dates set at Final Determinations and that process is required to be provided through the re-opener. | Closed
75 | 2022-10-27 | NGED | 3.2.50(b) 3.2.58(b) | These sub-paragraphs refer to modifications being permitted "where the addition of new outputs would improve the licensee’s cyber resilience". We think the wording of this paragraph should be expanded to include preventing deterioration in cyber resilience. | … where the addition of new outputs would improve or prevent deterioration in the licensee’s cyber resilience … |  | We would not provide allowances under the re-opener for the purposes of funding DNOs to simply maintain their current IT / OT resilience arrangements or to prevent a deterioration in them. The re-opener is to provide additional allowances for the purposes of delivering improvements in those arrangements. | Closed
76 | 2022-10-27 | NGED | 3.3.4(e) 3.3 appendix 1 3.2.80(b) Load Related Expenditure Re-opener Guidance para 1.11 | It is premature to assume that all Strategic Investment projects should be subject to evaluative PCDs. We currently do not expect any DNO to be provided with a baseline allowance to deliver a load related project that has been designated as a Strategic Investment project. In discussions with Ofgem it has been suggested that targeted delivery assessment mechanisms are likely to be required, possibly through the modification of the licence to introduce a mechanistic PCD. It is therefore inappropriate for the licence to presume that an evaluative PCD will automatically be created. The introduction of any PCDs associated with Strategic Investment should be introduced via a modification made under section 11A (modifications of conditions of licences) of the Act (following the drafting approach used in paragraph 3.6.10 for the Net Zero Re-opener). Changes to the drafting of SpC 3.2, 3.3 and the Load Related Expenditure Re-opener Guidance will be required to achieve this. |  |  | No change made. The inclusion of the SI term does not presuppose that strategic investment PCDs will be evaluative - we agree that they could be mechanistic. We have included the term for transparency about how the licence will work, should an evaluative strategic investment PCD be introduced in future. The implementation of any future SI PCD will follow a modification process under S11A, but no changes are needed to clarify this. | Closed
77 | 2022-10-27 | NGED/ SSEN | 3.3 Part B 3.3.10 | The proposed obligation in paragraph 3.3.10 to “take all reasonable steps to deliver the outputs specified” is an unnecessary obligation that effectively duplicates a sub-set of obligations contained in the extensive secondary legislation and guidance. There is also a chance that this paragraph could contradict the Network and Information Systems (NIS) Regulations 2018. | If the cyber PCDs are to remain part of a wider evaluative PCD condition and other mechanisms require the inclusion of Part B, we suggest that the following, alternative form of standard words proposed by Ofgem could be used: “The licensee is funded to deliver the outputs specified in the Cyber Resilience OT PCD Table and the Cyber Resilience IT PCD Table in accordance with and by the delivery dates specified in those tables.” However, if a separate cyber condition was to be developed, we do not believe that Part B would be necessary as the revised words do not perform any operative function. |  | We do not agree and think the current drafting is appropriate to reflect the policy intention. | Closed
78 | 2022-10-27 | NGED | 3.3 Part C | The condition does not make it clear that Ofgem will assess PCD delivery based on evidence that was reasonably available at the time that the decisions were made. | Add an extra sub-paragraph early in paragraph 3.3.14 setting out that: “The Authority shall only have regard to information that could reasonably have been available to the DNO at the time of making the relevant investment decisions”. |  | We do not think the proposed wording is requied. It would be unreasonable for the Authority to expect the licensee to have taken into consideration infromation that was not aware of or could not have been reasonably aware of at the time the relevant investment decision was taken. To require otherwise would be against the principles of fair regulation. | Closed
79 | 2022-10-27 | NGED | 3.3 Part C | For the reasons set out in our consultation response, the assessment process is likely to result in inappropriately intrusive ex-post efficiency assessment of any partially delivered cyber outputs. We urge Ofgem to reconsider the assessment and allowance adjustment process and the associated wording of the licence and to introduce a practical, workable approach to adjustment of allowances for cyber projects that are cancelled before the associated output is fully delivered. |  |  | This issues relates to our policy decision for Cyber OT and IT. For full details of it please refer to our Final Determinations. Please refer Hypothetical examples for cyber OT and cyber IT, which has been documented in "RIIO-2 Cyber Resilience OT and IT PCD Reporting Guidance". This document will be issued as confidential Appendix 4 to the DNOs, as mentioned in the 'PCD_Reporting_Requirements_and_Methodology_Document_v3' document. | Closed
80 | 2022-10-27 | NGED | 3.3.13 PCD Reporting Requirements and Methodology Document para 1.12 | Ofgem’s issues log (row 25) sets out that in the event of a Partially Delivered output where costs are “front end loaded” Ofgem would be able to fund the efficiently incurred costs via the processes in 3.3.13(a) (we think it means (e)). We do not understand how Ofgem would be able to use this branch of 3.3.13 instead of 3.1.13(d). We also do not understand what approach the DNO should take to reporting the delivery status of a PCD in this situation. Paragraph 1.12 of PCD Reporting Requirements and Methodology Document does not permit the DNOs an option to indicate that assessment under 3.3.13(e) is appropriate. It would be helpful if Ofgem could include a “hypothetical example” in the Associated Document explaining this process. |  |  | Please refer Hypothetical examples in Appendices 2 and 4. | Closed
81 | 2022-10-27 | NGED/SSEN | SpC 3.3 general | The process for the assessment of evaluative PCDs that is set out in Part C of special condition 3.3 is a generic process. Some aspects of this generic process are not appropriate for the assessment of cyber PCDs. The generic drafting of key defined terms that this condition relies on (such as Consumer Outcome, Efficiency and Innovation) makes it difficult for DNOs to understand how cyber PCDs will be assessed or the likely impact on future allowance modifications. As cyber PCDs are likely to be the only evaluative PCDs ascribed to DNOs at the start of RIIO-ED2, the fact that the generic wording of the condition is not appropriate to cyber activities is concerning. These key terms should be reviewed and better tailored to the assessment of cyber PCDs. |  |  | Please refer Hypothetical examples for cyber OT and cyber IT, which has been documented in "RIIO-2 Cyber Resilience OT and IT PCD Reporting Guidance". This document will be issued as confidential Appendix 4 to the DNOs, as mentioned in the 'PCD_Reporting_Requirements_and_Methodology_Document_v3' document. | Closed
82 | 2022-10-27 | NGED | 3.3.13 (c) | The treatment of a cyber OT or cyber IT PCD that is delayed into the RIIO-ED3 period is unclear. It would be helpful if Ofgem could confirm that the re-profiling of any allowances associated with Delayed PCD delivery set out in 3.3.13(c) would extend to any PCD that is delayed into the RIIO-ED3 period. A “hypothetic example” to confirm this treatment would be helpful. |  |  | Please refer Hypothetical examples for cyber OT and cyber IT, which has been documented in "RIIO-2 Cyber Resilience OT and IT PCD Reporting Guidance". This document will be issued as confidential Appendix 4 to the DNOs, as mentioned in the 'PCD_Reporting_Requirements_and_Methodology_Document_v3' document. | Closed
83 | 2022-10-27 | NGED/SSEN | 3.3 general | It is unclear whether cyber OT is still subject to a potential additional Use It or Lose It (UIOLI) adjustment. SpC 3.3 does not include any UIOLI adjustment for cyber OT. We agree that the presence of the re-opener, PCD delivery mechanism and the PCD reporting provisions means that a UIOLI adjustment is not needed. However, we note from Ofgem’s issues log that a UIOLI mechanism is expected. The DNOs have previously submitted text and associated algebra that could enact this adjustment if it is required. |  |  | This point relates to the policy decision in question rather than drafting, please see Final Determinations for our decision on this policy. Cyber Resilience OT allowance is not subject to the TIM and therefore any underspend would be recovered | Closed
84 | 2022-10-27 | NGED/SSEN/ NPg | Cyber conditions (3.2, 3.3,9.3) | Fundamentally, we think that it is most important to address the issues with the operation of the licence conditions in respect of cyber OT and cyber IT as outlined earlier in this response. Once those issues have been resolved, we would also support the creation of a single condition that covers all aspects of the regulation of cyber OT and cyber IT allowance adjustments. However, but this objective is secondary to ensuring that the various components operate correctly. We set out our proposal for how this could be achieved in our consultation response. |  |  | We have taken all consultation responses into consideration in arriving at our final determinations | Closed
85 | 2022-10-27 | NGED/SSEN | Interaction between SpC 3.2, 3.3 and PCFM | The treatment of allowances associated with cyber OT and cyber IT in the PCFM seems to create variant baseline allowances. This is quite different to the more familiar approach of creating fixed baseline allowances and/ or separate variable values, and is not consistent with how the draft PCFM operates. It would be helpful if Ofgem could explain how it envisages these allowances operating in the PCFM, and also provide guidance to DNOs on how it expects DNOs to adjust these values when setting network charges. This will help us to check whether the allowance adjustments envisaged in these conditions are being specified in a manner that is consistent with the intended operation of the PCFM. |  |  | Please refer Hypothetical examples for cyber OT and cyber IT, which has been documented in "RIIO-2 Cyber Resilience OT and IT PCD Reporting Guidance". This document will be issued as confidential Appendix 4 to the DNOs, as mentioned in the 'PCD_Reporting_Requirements_and_Methodology_Document_v3' document. | Closed
86 | 2022-10-27 | ENWL - common | 3.3 Part B 3.3.10 | The proposed obligation in paragraph 3.3.10 to “take all reasonable steps to deliver the outputs specified” is an unnecessary obligation that effectively duplicates a sub-set of obligations contained in the extensive secondary legislation and guidance. There is also a chance that this paragraph could contradict the Network and Information Systems (NIS) Regulations 2018. | If the cyber PCDs are to remain part of a wider evaluative PCD condition and other mechanisms require the inclusion of Part B, we suggest that the following, alternative form of standard words proposed by Ofgem could be used: “The licensee is funded to deliver the outputs specified in the Cyber Resilience OT PCD Table and the Cyber Resilience IT PCD Table in accordance with and by the delivery dates specified in those tables.” However, if a separate cyber condition was to be developed, we do not believe that Part B would be necessary as the revised words do not perform any operative function. |  | We do not agree and think the current drafting is appropriate to reflect the policy intention. | Closed
87 | 2022-10-27 | ENWL - common | 3.3 Part C | The condition does not make it clear that Ofgem will assess PCD delivery based on evidence that was reasonably available at the time that the decisions were made. | Add an extra sub-paragraph early in paragraph 3.3.14 setting out that: “The Authority shall only have regard to information that could reasonably have been available to the DNO at the time of making the relevant investment decisions”. |  | We do not think the proposed wording is requied. It would be unreasonable for the Authority to expect the licensee to have taken into consideration infromation that was not aware of or could not have been reasonably aware of at the time the relevant investment decision was taken. To require otherwise would be against the principles of fair regulation. | Closed
88 | 2022-10-27 | ENWL - common | 3.3 Part C | For the reasons set out in our consultation response, the assessment process is likely to result in inappropriately intrusive ex-post efficiency assessment of any partially delivered cyber outputs. We urge Ofgem to reconsider the assessment and allowance adjustment process and the associated wording of the licence and to introduce a practical, workable approach to adjustment of allowances for cyber projects that are cancelled before the associated output is fully delivered. |  |  | This issues relates to our policy decision for Cyber OT and IT. For full details of it please refer to our Final Determinations. Please refer Hypothetical examples for cyber OT and cyber IT, which has been documented in "RIIO-2 Cyber Resilience OT and IT PCD Reporting Guidance". This document will be issued as confidential Appendix 4 to the DNOs, as mentioned in the 'PCD_Reporting_Requirements_and_Methodology_Document_v3' document. | Closed
89 | 2022-10-27 | ENWL - common | 3.3.13 PCD Reporting Requirements and Methodology Document para 1.12 | Ofgem’s issues log (row 25) sets out that in the event of a Partially Delivered output where costs are “front end loaded” Ofgem would be able to fund the efficiently incurred costs via the processes in 3.3.13(a) (we think it means (e)). We do not understand how Ofgem would be able to use this branch of 3.3.13 instead of 3.1.13(d). We also do not understand what approach the DNO should take to reporting the delivery status of a PCD in this situation. Paragraph 1.12 of PCD Reporting Requirements and Methodology Document does not permit the DNOs an option to indicate that assessment under 3.3.13(e) is appropriate. It would be helpful if Ofgem could include a “hypothetical example” in the Associated Document explaining this process. |  |  | Please refer Hypothetical examples in Appendices 2 and 4. | Closed
90 | 2022-10-27 | ENWL - common | SpC 3.3 general | The process for the assessment of evaluative PCDs that is set out in Part C of special condition 3.3 is a generic process. Some aspects of this generic process are not appropriate for the assessment of cyber PCDs. The generic drafting of key defined terms that this condition relies on (such as Consumer Outcome, Efficiency and Innovation) makes it difficult for DNOs to understand how cyber PCDs will be assessed or the likely impact on future allowance modifications. As cyber PCDs are likely to be the only evaluative PCDs ascribed to DNOs at the start of RIIO-ED2, the fact that the generic wording of the condition is not appropriate to cyber activities is concerning. These key terms should be reviewed and better tailored to the assessment of cyber PCDs. |  |  | Please refer Hypothetical examples in Appendices 2 and 4. | Closed
91 | 2022-10-27 | ENWL - common | 3.3.13 (c) | The treatment of a cyber OT or cyber IT PCD that is delayed into the RIIO-ED3 period is unclear. It would be helpful if Ofgem could confirm that the re-profiling of any allowances associated with Delayed PCD delivery set out in 3.3.13(c) would extend to any PCD that is delayed into the RIIO-ED3 period. A “hypothetic example” to confirm this treatment would be helpful. |  |  | APlease refer Hypothetical examples for cyber OT and cyber IT, which has been documented in "RIIO-2 Cyber Resilience OT and IT PCD Reporting Guidance". This document will be issued as confidential Appendix 4 to the DNOs, as mentioned in the 'PCD_Reporting_Requirements_and_Methodology_Document_v3' document. | Closed
92 | 2022-10-27 | ENWL - common | 3.3 general | It is unclear whether cyber OT is still subject to a potential additional Use It or Lose It (UIOLI) adjustment. SpC 3.3 does not include any UIOLI adjustment for cyber OT. We agree that the presence of the re-opener, PCD delivery mechanism and the PCD reporting provisions means that a UIOLI adjustment is not needed. However, we note from Ofgem’s issues log that a UIOLI mechanism is expected. The DNOs have previously submitted text and associated algebra that could enact this adjustment if it is required. |  |  | This point relates to the policy decision in question rather than drafting, please see Final Determinations for our decision on this policy. Cyber Resilience OT allowance is not subject to the TIM and therefore any underspend would be recovered. | Closed
93 | 2022-10-27 | ENWL - common | Cyber conditions (3.2, 3.3,9.3) | Fundamentally, we think that it is most important to address the issues with the operation of the licence conditions in respect of cyber OT and cyber IT as outlined earlier in this response. Once those issues have been resolved, we would also support the creation of a single condition that covers all aspects of the regulation of cyber OT and cyber IT allowance adjustments. However, but this objective is secondary to ensuring that the various components operate correctly. We set out our proposal for how this could be achieved in our consultation response. |  |  | Please see response to Issue 54 of this log. | Closed
94 | 2022-10-27 | ENWL - common | Interaction between SpC 3.2, 3.3 and PCFM | The treatment of allowances associated with cyber OT and cyber IT in the PCFM seems to create variant baseline allowances. This is quite different to the more familiar approach of creating fixed baseline allowances and/ or separate variable values, and is not consistent with how the draft PCFM operates. It would be helpful if Ofgem could explain how it envisages these allowances operating in the PCFM, and also provide guidance to DNOs on how it expects DNOs to adjust these values when setting network charges. This will help us to check whether the allowance adjustments envisaged in these conditions are being specified in a manner that is consistent with the intended operation of the PCFM. |  |  | Please refer Hypothetical examples for cyber OT and cyber IT, which has been documented in "RIIO-2 Cyber Resilience OT and IT PCD Reporting Guidance". This document will be issued as confidential Appendix 4 to the DNOs, as mentioned in the 'PCD_Reporting_Requirements_and_Methodology_Document_v3' document. | Closed
95 | 2022-10-27 | ENWL | SINV | As we highlight in our "load conditions" tab, we consider it is premature to assume that all Strategic Investment projects should be subject to evaluative PCDs. We suggest that any PCD associated with Strategic Investment are created separately by a modification under Section 11A of the Act (in the same way any arising from SpC3.6 would be) andd references to SINV should be removed from 3.3 at this point. The introduction of any PCDs associated with Strategic Investment should be introduced via a modification made under section 11A (modifications of conditions of licences) of the Act (following the drafting approach used in paragraph 3.6.10 for the Net Zero Re-opener). Changes to the drafting of SpC 3.2, 3.3 and the Load Related Expenditure Re-opener Guidance will be required to achieve this. |  |  | No change made. The inclusion of the SI term does not presuppose that strategic investment PCDs will be evaluative - we agree that they could be mechanistic. We have included the term for transparency about how the licence will work, should an evaluative strategic investment PCD be introduced in future. | Closed
96 | 2022-10-27 | ENWL | 3.3.13a | para states: (a) where an output is Fully Delivered With An Alternative Specification and the licensee demonstrates that any underspends against the associated allowances are attributable to Efficiency or Innovation, the Authority may not make any adjustment to the associated allowance; | Change may to will: (a) where an output is Fully Delivered With An Alternative Specification and the licensee demonstrates that any underspends against the associated allowances are attributable to Efficiency or Innovation, the Authority will not make any adjustment to the associated allowance; |  | No change - the curent drafting is appropriate. It does not permit an adjusment to be made in theose circumstances. | Closed
97 | 2022-10-27 | ENWL | General | We provide further information within our Annex 2 document as part of our consultation response. |  |  | We have conssdered the information submitted in all consultation responses when arriving at our Final Determinations. | Closed
98 | 2022-10-27 | ENWL | General | All comments relating to 9.3 and the PCD guidance document are shown in the relevant separate tabs. |  |  | No action proposed by licensee in this issue item, therefore, no change necessary. | Closed
99 | 2022-10-27 | SSEN | 3.3 Part C | The condition does not make it clear that Ofgem will assess PCD delivery based on evidence that was reasonably available at the time that the decisions were made. | Add an extra sub-paragraph early in paragraph 3.3.14 setting out that: “The Authority shall only have regard to information that could reasonably have been available to the DNO at the time of making the relevant investment decisions”. |  | We do not think the proposed wording is requied. It would be unreasonable for the Authority to expect the licensee to have taken into consideration infromation that was not aware of or could not have been reasonably aware of at the time the relevant investment decision was taken. To require otherwise would be against the principles of fair regulation. | Closed
100 | 2022-10-27 | SSEN | 3.3 Part C | For the reasons set out in our consultation response, the assessment process is likely to result in inappropriately intrusive ex-post efficiency assessment of any partially delivered cyber outputs. We urge Ofgem to reconsider the assessment and allowance adjustment process and the associated wording of the licence and to introduce a practical, workable approach to adjustment of allowances for cyber projects that are cancelled before the associated output is fully delivered. |  |  | This issues relates to our policy decision for Cyber OT and IT. For full details of it please refer to our Final Determinations. Please refer Hypothetical examples for cyber OT and cyber IT, which has been documented in "RIIO-2 Cyber Resilience OT and IT PCD Reporting Guidance". This document will be issued as confidential Appendix 4 to the DNOs, as mentioned in the 'PCD_Reporting_Requirements_and_Methodology_Document_v3' document. | Closed
101 | 2022-10-27 | SSEN | 3.3.13 PCD Reporting Requirements and Methodology Document para 1.12 | Ofgem’s issues log (row 25) sets out that in the event of a Partially Delivered output where costs are “front end loaded” Ofgem would be able to fund the efficiently incurred costs via the processes in 3.3.13(a) (we think it means (e)). We do not understand how Ofgem would be able to use this branch of 3.3.13 instead of 3.1.13(d). We also do not understand what approach the DNO should take to reporting the delivery status of a PCD in this situation. Paragraph 1.12 of PCD Reporting Requirements and Methodology Document does not permit the DNOs an option to indicate that assessment under 3.3.13(e) is appropriate. It would be helpful if Ofgem could include a “hypothetical example” in the Associated Document explaining this process. |  |  | Please refer Hypothetical examples in Appendices 2 and 4. | Closed
102 | 2022-10-27 | SSEN | 3.3.13 (c) | The treatment of a cyber OT or cyber IT PCD that is delayed into the RIIO-ED3 period is unclear. It would be helpful if Ofgem could confirm that the re-profiling of any allowances associated with Delayed PCD delivery set out in 3.3.13(c) would extend to any PCD that is delayed into the RIIO-ED3 period. A “hypothetic example” to confirm this treatment would be helpful. |  |  | Please refer Hypothetical examples for cyber OT and cyber IT, which has been documented in "RIIO-2 Cyber Resilience OT and IT PCD Reporting Guidance". This document will be issued as confidential Appendix 4 to the DNOs, as mentioned in the 'PCD_Reporting_Requirements_and_Methodology_Document_v3' document. | Closed
103 | 2022-10-27 | SPEN |  | Please see Appendix 5 for further comments in relation to SpC3.2 and 3.3 |  |  | Please refer to "SpC 3.2 Cyber Resilience OT and IT Issue Log". | Closed
104 | 2022-10-27 | SPEN | 3.3.4(e) 3.3 appendix 1 3.2.80(b) Load Related Expenditure Re-opener Guidance para 1.11 | It is premature to assume that all Strategic Investment projects should be subject to evaluative PCDs. We currently do not expect any DNO to be provided with a baseline allowance to deliver a load related project that has been designated as a Strategic Investment project. In discussions with Ofgem it has been suggested that targeted delivery assessment mechanisms are likely to be required, possibly through the modification of the licence to introduce a mechanistic PCD. It is therefore inappropriate for the licence to presume that an evaluative PCD will automatically be created. The introduction of any PCDs associated with Strategic Investment should be introduced via a modification made under section 11A (modifications of conditions of licences) of the Act (following the drafting approach used in paragraph 3.6.10 for the Net Zero Re-opener). Changes to the drafting of SpC 3.2, 3.3 and the Load Related Expenditure Re-opener Guidance will be required to achieve this. |  |  | Please refer to Issue no 48 of this sheet. | Closed
105 | 2022-10-27 | SPEN | 3.3 Part C | For the reasons set out in our consultation response, the assessment process is likely to result in inappropriately intrusive ex-post efficiency assessment of any partially delivered cyber outputs. We urge Ofgem to reconsider the assessment and allowance adjustment process and the associated wording of the licence and to introduce a practical, workable approach to adjustment of allowances for cyber projects that are cancelled before the associated output is fully delivered. |  |  | This issues relates to our policy decision for Cyber OT and IT. For full details of it please refer to our Final Determinations. Please refer Hypothetical examples for cyber OT and cyber IT, which has been documented in "RIIO-2 Cyber Resilience OT and IT PCD Reporting Guidance". This document will be issued as confidential Appendix 4 to the DNOs, as mentioned in the 'PCD_Reporting_Requirements_and_Methodology_Document_v3' document. | Closed
106 | 2022-10-27 | SPEN | SpC 3.3 general | The process for the assessment of evaluative PCDs that is set out in Part C of special condition 3.3 is a generic process. Some aspects of this generic process are not appropriate for the assessment of cyber PCDs. The generic drafting of key defined terms that this condition relies on (such as Consumer Outcome, Efficiency and Innovation) makes it difficult for DNOs to understand how cyber PCDs will be assessed or the likely impact on future allowance modifications. As cyber PCDs are likely to be the only evaluative PCDs ascribed to DNOs at the start of RIIO-ED2, the fact that the generic wording of the condition is not appropriate to cyber activities is concerning. These key terms should be reviewed and better tailored to the assessment of cyber PCDs. |  |  | No changes made. The cyber PCD reporitng guidance document has been updated to include illustrative examples. Please refer Hypothetical examples for cyber OT and cyber IT, which has been documented in "RIIO-2 Cyber Resilience OT and IT PCD Reporting Guidance". This document will be issued as confidential Appendix 4 to the DNOs, as mentioned in the 'PCD_Reporting_Requirements_and_Methodology_Document_v3' document. | Closed
107 | 2022-10-27 | SPEN/UKPN | 3.3.13 (c) | The treatment of a cyber OT or cyber IT PCD that is delayed into the RIIO-ED3 period is unclear. It would be helpful if Ofgem could confirm that the re-profiling of any allowances associated with Delayed PCD delivery set out in 3.3.13(c) would extend to any PCD that is delayed into the RIIO-ED3 period. A “hypothetic example” to confirm this treatment would be helpful. |  |  | No changes made. The cyber PCD reporitng guidance document has been updated to include illustrative example with treatment of a cyber OT or cyber IT PCD that is delayed. Please refer Hypothetical examples for cyber OT and cyber IT, which has been documented in "Appendix 4 - RIIO-2 Cyber Resilience OT and IT PCD Reporting Guidance". This document will be issued as confidential Appendix to the DNOs, as mentioned in the 'PCD_Reporting_Requirements_and_Methodology_Document_v3' document. | Closed
108 | 2022-10-27 | SPEN/UKPN | 3.3 general | It is unclear whether cyber OT is still subject to a potential additional Use It or Lose It (UIOLI) adjustment. SpC 3.3 does not include any UIOLI adjustment for cyber OT. We agree that the presence of the re-opener, PCD delivery mechanism and the PCD reporting provisions means that a UIOLI adjustment is not needed. However, we note from Ofgem’s issues log that a UIOLI mechanism is expected. The DNOs have previously submitted text and associated algebra that could enact this adjustment if it is required. |  |  | This point relates to the policy decision in question rather than drafting, please see Final Determinations for our decision on this policy. Cyber Resilience OT allowance is not subject to the TIM and therefore any underspend would be recovered No changes made. The cyber PCD reporitng guidance document has been updated to include illustrative examples. Please refer Hypothetical examples for cyber OT and cyber IT, which has been documented in "RIIO-2 Cyber Resilience OT and IT PCD Reporting Guidance". This document will be issued as confidential Appendix 4 to the DNOs, as mentioned in the 'PCD_Reporting_Requirements_and_Methodology_Document_v3' document. | Closed
109 | 2022-10-27 | SSEN | 3.3 Part B 3.3.10 | The proposed obligation in paragraph 3.3.10 to “take all reasonable steps to deliver the outputs specified” is an unnecessary obligation that effectively duplicates a sub-set of obligations contained in the extensive secondary legislation and guidance. There is also a chance that this paragraph could contradict the Network and Information Systems (NIS) Regulations 2018. | If the cyber PCDs are to remain part of a wider evaluative PCD condition and other mechanisms require the inclusion of Part B, we suggest that the following, alternative form of standard words proposed by Ofgem could be used: “The licensee is funded to deliver the outputs specified in the Cyber Resilience OT PCD Table and the Cyber Resilience IT PCD Table in accordance with and by the delivery dates specified in those tables.” However, if a separate cyber condition was to be developed, we do not believe that Part B would be necessary as the revised words do not perform any operative function. |  | We do not agree and think the current drafting is appropriate to reflect the policy intention. | Closed
110 | 4.3.22 | UKPN/ SPEN / WPD |  | As noted in the LDWG meeting, care will need to be taken to ensure that definitions and policies are clear and as intended by policy. We think this will be easiest to review once a specific PCD has been drafted. It would be helpful to revisit this condition and guidance in April once the WSC PCD has been incorporated to test whether the definitions might introduce issues. |  |  | Noted, definitions are clear and as intended in our view. | Closed

## B - SpC 9.3
Licence number and name: |  | SpC 3.3 and SpC 9.3 Evaluative PCDs, reporting and example methodology
Ofgem contact: |  | Laura Dye
No. | Date raised | Comment from | Reference (Part X, Para Y) | Comment | Suggested alternative drafting (if necessary) | Due Date | Response | Issue closed?
1 | 2021-12-13 | UKPN | 9.3.1 | Is "Evaluative PCD" a defined term? |  |  | This is now a defined term. | Closed
2 | 2021-12-13 | UKPN | 9.3.8 | The timescales for SQ response feels like something which sits better in the reporting/method doc and not the licence |  |  | Timescales for SQs are no longer in the licence. | Closed
3 | 2021-12-13 | UKPN | 9.3.12(i) | Add cross reference to where the licence sets out Fully Delivered etc in detail |  |  | Defined terms are in SpC 1.2 no need to cross reference. | Closed
4 | 2021-12-15 | SPEN | 9.3 Definitions | We note that various proposed terms require definitions e.g. Basic PCD Report, Evaluative PCD Report etc., we will also comment on these in due course. |  |  | Definitions completed. | Closed
5 | 2021-12-15 | SPEN | 9.3.9 | We note Ofgem's reference in the LDWG to the fact that we must comply with the PCD Reporting Requirements and Methodology Document and that there is a tab in the workplan spreadsheet which explains how Ofgem intends to progress with this AD and others. The workplan that we have had sight of explains what ADs are expected, but not when it is proposed that we will have sight of these. Please can Ofgem re-issue with timescales. |  |  | The AD has been published alongside the informal consultation. | Closed
6 | 2021-12-15 | NPg | 9.3.8 | Incorrect reference to 9.3.8 | Change to 9.3.7 |  | No longer applicable. | Closed
7 | 2021-12-15 | NPg | 9.3.8 | Five calendar days may give only three working days to respond so use Working Days as it is also a defined term | Change "days" to "Working Days" |  | No longer applicable. | Closed
8 | 2021-12-15 | NPg | Part B 9.3 | Will the PCD Reporting Requirements and Methodology Document be an Associated Document? |  |  | Yes | Closed
9 | 2022-02-23 | NPG | 9.3.3 | Do we have to produce a report every year even in 2023 |  |  | Only if the delivery date was in previous regulatory year (so none expected in 2023, but could have a requirement to do so from 2024). | Closed
10 | 2022-02-23 | ENWL | 9.3.7 | Last line isn't clear when you have multiple delivery statuses in the same output |  |  | The assessment status can have multiple tags (partially delivered and late). | Closed
11 | 2022-02-23 | ENWL | Part A | the use of Directed and Direct |  |  | Refers to administrative directions from Ofgem (simple directions across the licence) | Closed
12 | 2022-02-23 | WPD | Part A | Would be good for resource planning to have a timescale if or when Ofgem can request a Full PCD report |  |  | We will consider this within the development of the Guidance document. | Closed
13 | 2022-02-23 | WPD | Part A | what timeframe do we have to prepare the full PCD report |  |  | We will consider this within the development of the Guidance document. | Closed
14 | 2022-02-23 | SPEN | 9.3.11 | slight change from Transmission that Ofgem will issue the guidance on the methodology not just examples |  |  | 3.3 has the methodology in the Licence and not in the Guidance | Closed
15 | 2022-03-11 | WPD | 9.3.6 | There is no date of submission specified for the provision of a Full PCD Report. Will this be specified in the Authority direction to the licensee? It is unclear. Note that para 6.7 of the methodology suggests within 28 days of the direction with an option for the licensee to ask for more time. We would expect these timescales be in the licence. |  |  | Yes, the direction to provide a Full PCD report will specify the number of days the licensee has to submit it. Confirm that ordinarily the Authority will ask for the report within 28 days of the direction, but another period may be specified. If DNOs wish to ask for a different period they should provide reasons why they think this is necessary. Given that licensees may ask for more time, specifying the timeframe in the licence - which may be deviated from - does not add anything useful to the licence. | Closed
16 | 2022-03-11 | WPD | 9.3.9 | Suggest the "will issue and amend" is changed to a "will issue and may amend" in case there is no need to update. |  |  | This read previously "The Authority will issue and amend the PCD Reporting Requirements and Methodology Document by direction" - has been replaced with standard reference to standard procedure "9.3.14 The procedure for issuing and amending the PCD Reporting Requirements and Methodology Document is provided in Special Condition 1.3 (Common procedure). " | Closed
17 | 2022-09-07 | ENWL | 9.3.1 | "9.3.1 The purpose of this condition is to require the licensee to report to the Authority on the delivery of its Evaluative Price Control Deliverables." condition refers only to "Evaluative" PCDs | Widen to include mechanistic |  | No, the introduction section of the licence as drafted correctly describes SpC 9.3 which does not set out requirements for mechanistic PCDs The PCD reporting and methodology doc which this condition establishes does set out information and guidance relevant to all mechanistic and evaluative PCDs, unless it specifically excludes them (e.g. NARM PCD). (see also line 75 on sheet c) but REQUIREMENTS only for evaluative PCDs. | Closed
18 | 2022-09-09 | ENWL | 9.3 Part E | Whilst not specific to Smart Street 9.3.14 needs to be revised to reflect the what the "Price Control Deliverable Reporting Requirements and Methodology Document: Version 3" aims to set out in 1.3 and the sub bullets in this para. | Replace 9.3.14 (a) through (d) with: " • The principles that underpin our use of PCDs; • The types of PCDs we will use to hold network companies to account for price control funding; • Possible outcomes of our assessment of delivery of PCDs; • Information that the licensee is required to provide as part of PCD reporting; and, • The process and timelines for our assessment of PCD delivery and allowance adjustments. " |  | Disagree that the description of what the AD does in the licence and the description of what it does in the AD itself have to be identical verbatim. The text is not contradictory, so can remain as stated. | Closed
19 | 2022-10-11 | SPEN | 9.3.4 and 9.3.5 | Can these two paragraphs be combined? Having both seems a bit unnecessary. |  |  | No change made, combining the two paragraphs into one changes only the numbering, but makes no change meaning or drafting. | Closed
20 | 2022-10-11 | SPEN | 9.3.8 (f) | This is a report rather than an application – is this needed / correctly characterised? |  |  | No change made. Licensee suggests "detailed Supporting evidence" is not needed. Disagree - detailed supporting evidence is needed to support the Authority's decision whether or not to adjust allowances in accordance with SpC 3.3 Part C. | Closed
21 | 2022-10-21 | UKPN | 9.3.11 | Under bullet c, the sub bullets should be roman numerals |  |  | Agreed. licence text amended to reflect this. | Closed
22 | 2022-10-21 | UKPN | Cyber conditions (3.2, 3.3,9.3) | Fundamentally, we think that it is most important to address the issues with the operation of the licence conditions in respect of cyber OT and cyber IT as outlined earlier in this response. Once those issues have been resolved, we would also support the creation of a single condition that covers all aspects of the regulation of cyber OT and cyber IT allowance adjustments. However, but this objective is secondary to ensuring that the various components operate correctly. We set out our proposal for how this could be achieved in our consultation response. |  |  | See SpC 3.3 issue 73 for response. | Closed
23 | 2022-10-26 | NPg | Part A, paragraph 9.3.3 | Clarification that the reporting requirement applies to ED2 | Change "The licensee must by 31 July of each Regulatory Year, …" to "With effect from the Regulatory Year starting on 1 April 2024, the licensee must by 31 July of each Regulatory Year, …" |  | No change necessary, it is clear that it refers to ED2 as drafted. | Closed
24 | 2022-10-26 | NPg | Part B, paragraph 9.3.8 | "Distribution System" is the defined term, not "network" | Change "network" to "Distribution System" |  | Licence text amended to specify the word 'OT' to clarify. OT and IT are defined terms in the ED2 Definitions spreadsheet. | Closed
25 | 2022-10-26 | NPg | Definition of "Mechanistic Price Control Deliverable" | "formula" is singular | Change "formulae" to "formula" |  | Definition text has been amended. | Closed
26 | 2022-10-26 | NPg | 9.3 - Cyber conditions (Also see SpC 3.2 and SpC 3.3) | Fundamentally, we think that it is most important to address the issues with the operation of the licence conditions in respect of cyber OT and cyber IT as outlined earlier in this response. Once those issues have been resolved, we would also support the creation of a single condition that covers all aspects of the regulation of cyber OT and cyber IT allowance adjustments. However, but this objective is secondary to ensuring that the various components operate correctly. We set out our proposal for how this could be achieved in our consultation response. |  |  | This is one of several possible drafting approaches. We prefer our proposed approach. | Closed
27 | 2022-10-27 | ENWL | 9.3.2 | This does not establish the AD, nor is it estabished elsewhere in this condition. There is inconsistency throughout the licence how this is done for ADs. Ofgem need to consider and use consistent wording throughout the licence for establishing the ADs. |  |  | No change needed. Disagree that the licence contains inconsistent wording. Across it, the conditions say in several places "this condition establishes the AD…" then in a separate Part, "the licensee must comply with the [AD] when … [carrying out the relevant activity]." | Closed
28 | 2022-10-27 | ENWL | Part B & Appendix 1 | Please see our more general comments in Annex 2 on the structure of this condition relating to cyber |  |  | All points raised in Appendix 2 has been considered. Appendix 2, 2.1 response: This is one of several possible drafting approaches, we prefer our proposed approach. Appendix 2, 2.2 response: Drafting meeting policy intent. 2.2.1;2.2.2;2.2.3: Please refer Hypothetical examples for cyber OT and cyber IT, which has been documented in "RIIO-2 Cyber Resilience OT and IT PCD Reporting Guidance". This document will be issued as confidential Appendix 4 to the DNOs, as mentioned in the 'PCD_Reporting_Requirements_and_Methodology_Document_v3' document. 2.3 Please refer response against Issue 32 under SpC 3.3 log 2.4 Please see SpC 3.3 issue 73 for response. 2.5 Please see SpC 3.3 issue 65 for response. | Closed
29 | 2022-10-27 | ENWL | 9.3.11 | change may to will |  |  | No change made. This is standard wording across the licence with respect to ADs. | Closed
30 | 2022-10-27 | ENWL | 9.3.11 | Formatting needs correcting |  |  | corrected | Closed
31 | 2022-10-27 | ENWL | 9.3 | Please see separate tab for commonts on the AD |  |  | noted - however this tab did not contain new, open issues for us to consider in relation to the AD. | Closed
32 | 2022-11-14 | Ofgem | 9.3 Part A | addition needed to require licensees to submit reports for delayed PCDs - so far this was not provided for, Ofgem would need to direct licensee to submit this. |  |  | Addition made - 9.3.3 (b) | Closed

## C - Reporting & MethodologyDoc
Licence number and name: |  | SpC 3.3 and SpC 9.3 Evaluative PCDs, reporting and example methodology
Ofgem contact: |  | Laura Dye
No. | Date raised | Comment from | Reference (Part X, Para Y) | Comment | Suggested alternative drafting (if necessary) | Response | Issue closed?
1 | 2022-02-23 | NPG | Chapter 7 | including timeframes in table 7.2 would be helpful |  | The overall indicative timeframe is set out - 9 months - but each PCD will vary in complexity, so breaking down the timeframes further to cover all cases would risk setting out inaccurate information. | Closed
2 | 2022-02-23 | SPEN | Appendices | Illustrative examples should be extended to cover some ED examples |  | ED specific example added | Closed
3 | 2022-03-10 | SSEN | 1.3 | Consider language in second bullet point "The types of PCDs we will use to hold network companies to account for price control funding" | The types of PCDs we will use to measure whether network companies have delivered the required output in line with the funding they have received. | No change made - the current drafting is broad yet specific enough in our view. | Closed
4 | 2022-03-11 | WPD | PCD reporting guidance | There is a conflict between para 6.4 of the guidance and 9.3.3. of the licence. The licence refers to when the PCD was to be delivered. The guidance refers to when it has been delivered. |  | Amended AD "For each Evaluative PCD, licensees are required to submit a Basic PCD Report along with the RRP templates due in the regulatory year following the output delivery date specified in the relevant licence condition regulatory year in which the delivery date occurred" | Closed
5 | 2022-03-11 | WPD | PCD reporting guidance | Extra spaces/typos in 1.4 (appendices, ,", and 5.1 ("with the") |  | amended | Closed
6 | 2022-03-11 | WPD | PCD reporting guidance | Paragraph 5.2 - Note that there may be specific cases where allowances could go up (unlooping services, secondary reinforcement) which may need to be listed as exclusions as per the GD Repex example |  | These exclusions can in future be added to the document once a PCD requires it - currently there are no PCDs in the ED sector designed in a way that requires more volume or number of units than defined in the output. | Closed
7 | 2022-03-11 | WPD | PCD reporting guidance | Paragraph 5.7 - missing content/references |  | amended | Closed
8 | 2022-03-11 | WPD | PCD reporting guidance | Paragraph 7.2 - note the PCD tracker templates will need to be established once the ED PCDs are known. |  | noted | Closed
9 | 2022-03-11 | WPD | PCD reporting guidance | Appendix 4 - Need to confirm that the same end of period approach will be taken for ED |  | as specified in the separately issued confidential cyber appendix. | Closed
10 | workshop 07/09/2022 | SPEN | PCD reporting guidance | There are still oustanding concerns with the drafting of SpC3.3, and wider PCD assessment process concerns, which need to be answered before can fully comment on the guidance doc. |  | now addressed in issues log | Closed
11 | workshop 07/09/2022 | SPEN | PCD reporting guidance | Understand that Cyber and potentially LRE will be the only common PCDs. It would be helpful for this to be made explicit at the start of the document to set the context for which it sits. |  | Common and bespoke PCDs are set out in each companies' licence, the AD does not need to include an exhaustive list of PCDs. Also, specific PCDs should not be listed here because that would mean that this document would need to be re-directed each time a reopener decision removes or adds a PCD, even if this change does not require any substantial updates to guidance, and, or reporting requirements. However, agree that it should be made clearer what the AD provides guidance and information/ context on (all PCDs), and what it provides requirements for (evaluative PCDs only). We have therefore - renamed the title of SpC 9.3 "Special Condition 9.3 Evaluative Price Control Deliverable reporting requirements" - clarified in the licence and in the AD introduction that the Associated Document provides guidance on evaluative and mechanistic PCDs, and sets out requirements on evaluative PCDs only. - clarified in Chapter 6 of the AD, by inserting sub-headings, that the reporting requirements apply only to evaluative PCDs. Also agree that the document should clearly state what it does not apply to - so added a line to clarify that NARM is out of scope. | Closed
12 | workshop 07/09/2022 | UKPN | PCD reporting guidance | Has the PCD process been utilised in other sectors yet? Can we take any learnings from this and make any improvements on that? |  | Mechanistic PCDs have gone through the first cycle of regulatory reporting and there are lessons on how to best draft mechanistic PCDs which we have considered. The evaluative PCD reporting process has not yet been tested. | Closed
14 | workshop 07/09/2022 | ENWL | PCD reporting guidance | We should consider the operation fo any new PCDs that emerge within period (eg, when attaching new volumes and or outputs to reopeners). What is the process for adminstering these? |  | When a new PCD is established, this will require a licence condition, if not already in place. In the case of a new evaluative PCD, it may also require redirecting the AD with appendices for special reporting requirements, and in the case of a mechanistic PCD, changes to RIGs and RRPs. | Closed
15 | workshop 07/09/2022 | npg | PCD reporting guidance | We should be explicit that the document does not need to provide giodance on NARM if that is provided for elsewhere. |  | Agreed, added a line to 1.5 - "The reporting requirements set out in this document do not apply to the Network Asset Risk Metric (NARM)". | Closed
20 | workshop 07/09/2022 | ENWL | PCD reporting guidance | The licence should include a date by which the PCD is to be delivered. |  | Agreed, each licence condition must determine the date - spelled out or specified as "by the end of the Price Control Period". | Closed
21 | workshop 07/09/2022 | SPEN | PCD reporting guidance | Illustrative examples should include cyber and LRE. These should capture all the types of possible scenario (eg, PCD on its own, with reopener, with new outputs etc) |  | Some hypothetical examples have been added, but these cannot cover all possible scenarios exhaustively. | Closed
22 | 2022-09-07 | UKPN/ ENWL | All | Para numbering awry |  | Resolved | Closed
23 | 2022-09-07 | UKPN | All | on p6 in particular the superscript on the footnote is missing and the last two bullets should be tabbed in futher |  | amended | Closed
24 | 2022-09-07 | UKPN, SSEN, ENWL | p11 (1.16) | Missing "not" |  | amended | Closed
25 | 2022-09-07 | UKPN | p19 Table 7.2 | Row 5, draft direction - shouldn’t the decision on whether a direction be set out in the licence? |  | See 3.3.13 for the basis for issuing a direction. Part D then sets out procedure. | Closed
26 | 2022-09-07 | UKPN, SSEN | Appendix examples | Add one more specific to ED/ It would be helpful to include ED worked examples. |  | ED specific example added | Closed
27 | 2022-09-07 | UKPN | Appendix examples | Add example showing the interaciton of the cyber PCD, UIOLI and reopener |  | Examples have been added to the confidential Cyber PCD guidance | Closed
28 | 2022-09-07 | UKPN | Appendix examples | Add example which shows how a late delivered PCD must be in the delayed status as to be fully delivered it must have been done on time |  | In this case it would be assigned both the delayed and the fully delivered statuses. So a PCD could be assigned Delayed only, or Delayed & Fully Delivered, Delayed & Fully Delivered with Alternative Specification, or Delayed & Partially Delivered. Example 1 extended to reflect this - now 1 a and 1b | Closed
29 | 2022-09-07 | SSEN | General | Several issues were raised by the DNOs on the PCD licence condition when it was discussed at the LDWG. This was followed up with a joint paper. As we have not yet seen the responses to the issues raised, or if any changes have been implemented as a result, it is difficult to provide full feedback on the guidance document. These comments related specifically to cyber but also more widely to the PCD reporting requirements. |  | Cyber issues have been uploaded to Sheet A - SpC 3.3 | Closed
30 | 2022-09-07 | SSEN | 1.6 (third bullet) | This should reflect that delays may be outside a DNO's control. In these cases DNOs should not benefit financially but also should not be penalised for this. | "If the licensee does not deliver the PCD as specified in the licence on time, the Authority may make a downward adjustment to the price control allowance associated with the PCD so that consumers only pay the efficient costs of work that has been delivered. For the avoidance of doubt, the value of such downward adjustments will not exceed the value of the allowances associated with the relevant PCD and will not penalise the licensee for any delays that are outside of its control. " | Disagree that this is necessary. It is already clear that the downward adjustment will result in bringing the cost to consumers in line with the efficient cost incurred. So there is no scope for the Authority to levy an additional 'penalty' adjustment - whether the delay is in or outside of licensee's control. Therefore, there is no need for this addition, and it would introduce ambiguity (given that some PCDs come with the Licence Obligation to take all reasonable steps to deliver the output on time). | Closed
31 | 2022-09-07 | SSEN | 1.6 (last bullet) | "Efficiency" should not be a defined term. This is a well used regulatory term that is used throughout the licence and associated documents. Defining this term in the PCD methodology risks setting a precedent for interpretation of the licence elsewhere. An alternative would be to name this something else other than efficiency. | As per June-2022 DNO joint note, could call the term "Efficiency for PCD Assessment". | We recognise this risk, but believe that to maintain consistency and transparency across the sectors, it is preferable to keep the current term and definition | Closed
32 | 2022-09-07 | SSEN | 1.16 | See above comment on defining Efficiency |  | as above | Closed
33 | 2022-09-07 | SSEN | General comment | Is there guidance on how delayed a PCD would need to be to fall under 'Delayed'? |  | if not delivered by the day specified in the relevant licence condition, it will be delayed. The Authority will assess the impact in each case. | Closed
34 | 2022-09-06 | ENWL | 1.1 | RIIO-2 reference should be clear applies to RIIO-ED2 for the purposes of this guidance document as the 'Framework' has been developed separately and via a separate process | Footnote "RIIO-2" to state for purposes of this document "RIIO-2" also includes "RIIO-ED2" | Added "For the purposes of this document, RIIO-2 refers to the price controls of the Gas Transportation and Electricity Transmission Licensees, running from 1 April 2021 – 31 March 2026, and the price control of the Electricity Distribution Licensees, running from 1 April 2023 – 31 March 2028." | Closed
35 | 2022-09-06 | ENWL | 1.2 | Reference for ED is 9.3 not 3.3 as stated. |  | amended | Closed
36 | 2022-09-06 | ENWL | 1.3 - bullet 1 | original wording should be retained |  | No because this section has been removed from the document and moved to the licence. | Closed
37 | 2022-09-06 | ENWL | 1.5 | for bespoke mechanistic PCD - Smart Street - the reporting requirements are in the licence - this needs to be removed and added into the this document and/or contained in the RIGs |  | This was an error, as 9.3 provides reporting requirements only for evaluative PCDs and Smart Street is a mechanistic PCD. So this text has been moved to the Smart Street condition 3.11. | Closed
38 | 2022-09-06 | ENWL | 2. - Section summary | It is important that all definitions are consistent with those laid out in the licence and there are no conflicts. This needs to checked for consistency and potential conflicts by Ofgem. |  | Completed | Closed
39 | 2022-09-06 | ENWL | 1.6 (what we think should be 2.1, bullet 1.) | Ofgem needs to ensure this is the case and where a PCD is in the licence specific end dates are present in the licence conditions. |  | Agreed, each licence condition must determine the date - spelled out - or specified as "by the end of the Price Control Period". | Closed
40 | 2022-09-06 | ENWL | 1.6 (what we think should be 2.1, bullet 4.) | Bullets below may not be exhaustive and as such will needs to be changed to may to reflect that there could be circumstances in which an adjustment isnt made but isnt set out in the bullets below. Use of "may" also aligns with the wording in the licence. | "For Evaluative PCDs, licensees may deliver an alternative specification to the one in the relevant licence condition. In such cases we may will adjust allowances downwards to match the efficient cost of delivering the alternative, unless the licensee can demonstrate that" | No change as this introduces ambiguity - it's not clear under which circumstances besides those stated we would not adjust the allowances. | Closed
41 | 2022-09-07 | ENWL | 1.6 (what we think should be 2.1, bullets below 4.) | These should be sub bullets - formating issue. |  | amended | Closed
42 | 2022-09-06 | ENWL | 1.6 (what we think should be 2.1, bullet 4, sub bullet 1) | Should this apply to ED, the consumer outcome for each PCD needs to be defined in the Licence so equivalent or better consumer outcome can be determined. This may not apply to ED as we are unaware of any cases where this would apply and so if not applicable to ED it should state so here. |  | The Consumer Outcome is linked to the benefits case upon which the expenditure was initially accepted at Final Determination or reopener decision stage, so the licensee and the Authority will be aware of this and hence of what the benefit would have been had the output been delivered as specified. The Consumer Outcome will not generally always be defined in the licence. The Authority will determine whether the equivalent, less or a better Consumer Outcome has been achieved, using all relevant information, including information in the Final Business Plan submission and in associated SQs. The bullet referenced is applicable to every evaluative PCD, also those in ED. | Closed
43 | 2022-09-06 | ENWL | 1.6 ( what we think should be 2.1) | We would like the guidance cover off what is intended to happen when a more expensive (e.g.15% higher cost solution) can deliver much more benefit (e.g. 30% more). |  | see issue 18 sheet A of this issues log. | Closed
44 | 2022-09-06 | ENWL | 1.8 (what we think should be 2.3) | Currently this is too open/broad/unclear which incentive mechanisms are referred to here. We request that Ofgem clearly sets out which incentive mechanisms have links to which PCDs which apply or due to apply in ED. |  | This is set out in the licence and there is no need to repeat this in the guidance document across all PCDs and sectors. | Closed
45 | 2022-09-06 | ENWL | 1.9 (what we think should be 3.1) | The para starts "In general", should it be in general, or "In all" cases. |  | No change required. | Closed
46 | 2022-09-06 | ENWL | 1.11 (which we think should be 4.1) | Unecessary wording - drafting simplifcation | "The assessment of delivery status for Mechanistic PCDs are based on units or volumes delivered, based on the metric used to specify the PCD in the licence." | No change required - the additional words make the difference between mechanistic and evaluative PCDs more clear. | Closed
47 | 2022-09-06 | ENWL | 1.11 (which we think should be 4.1) | Additional para needed - add in a new para that says, some mechanistic PCDs will be assessed by delivery over the full price control period rather than on a year by year basis. E.g. Smart Street PCD for ENWL |  | Not needed, this is set out in the Smart Street LC. | Closed
48 | 2022-09-06 | ENWL | 1.12 in general (which we think should be 4.2) | We think there is a scenario missing. What about circumstances where the delivery is in full, but late? This scenario does not seem to be covered in the potential outcomes. Delayed seems to indicate that delivery will flow into a future price control. |  | No change required. The definition of the delayed status is clear in this regard - "means where the licensee has not delivered the output set out in the relevant special condition in full by the relevant delivery date, but has delivered or intends to deliver the output in full or in part at a later date." | Closed
49 | 2022-09-06 | ENWL | 1.14 (which we think should be 5.1) | Uncessary wording - drafting simplification | "For Mechanistic PCDs, where a licensee does not deliver the volumes or numbers of units of the outputs by the delivery date, as set out in the relevant licence condition, the value of adjustments to allowances will be calculated in accordance with the formula and parameters set out in the relevant licence condition." | No change required - the additional words make the difference between mechanistic and evaluative PCDs more clear. | Closed
50 | 2022-09-06 | ENWL | 1.15 (which we think should be 5.2) | We think there is a conflict with the licence here as it lists reporting requirements and a separate reporting date to RRP. We question what the need is for a separate PCD report on volumes each year to be supplied if the information is also provided in the annual reporting packs. For a mechanistic PCD, surely the RRP is sufficient, particularly if that is the source of data for any adjustment. The corresponding reporting requirement in SpC 9.3 should be removed in this instance, or if it is still needed, it should point to inclusion of reporting in annual reporting pack. Separate report is unecessary reporting burden for all involved and is not inline with the principles laid out in this document. |  | There is no requirement to submit a PCD report for mechanistic PCDs set out in 9.3. The condition sets out reporting requirements for evaluative PCDs, so there is no conflict. | Closed
52 | 2022-09-06 | ENWL | 1.20 (what we think should be 6.1) | Extra context needed | "For all PCDs, licensees are required to submit completed reporting templates and associated commentary as part of the RIIO-2 Regulatory Reporting Templates (RRP) as directed by the relevant Regulatory Instructions and Guidance (RIGs) and as set out in the licence (i.e. chapter 9)." | no change, the addition would be incorrect, as 9.3 does not set out reporting requirements for all PCDs, just for evaluative ones. | Closed
53 | 2022-09-06 | ENWL | 1.25 ( what we think should be 6.6) | When and by what mechanism Ofgem will share the feedback is missing and needs to be included here. |  | As set out in the paragraph below, this will be via direction: "1.26 [6.7] Where we have decided to undertake a Full PCD Report Review, we will direct the licensee to submit a Full PCD Report as set out below, which will generally be required within 28 days of the direction. Licensees may request a longer period if that is deemed to be necessary." What is to be included is set out in paragraphs 1.28 - 1.31. | Closed
54 | 2022-09-06 | ENWL | 1.27 (what we think should be 6.8) | Suggest addition of cross-reference to the relevant paragraphs rather than just "given below". As these are minimum requirements, there should be explicit linkage to which paras apply. |  | Cross-reference has been added. | closed
55 | 2022-09-06 | ENWL | 1.37 (what we think should be 7.4) | Footnote 7 is missing |  | formatting amended, renumbered. | Closed
56 | 2022-09-06 | ENWL | 1.38 (what we think should be 7.5) | We do not understand the first sentence, could this be explained? We are unclear when the delivery of a PCD would trigger a re-opener or be the substance of the re-opener submission. |  | This would be spedified in each individual case, see Appendix 5 for an example from the Gas Transmission sector. | Closed
57 | 2022-09-06 | ENWL | Table 7.2, part 4 [minded to decision] | We continue to set out that this step should not be optional and should be completed in all cases |  | The minded-to decision is not necessary in all cases and will remain an optional step. | Closed
58 | 2022-09-06 | ENWL | Table 7.2 part 5 | We note the words "if a direction is considered necessary". What is the steps if a direction is not considered necessary - the table and document is silent on this point. |  | Table 7.2 changed to explicitly include in steps 5 and 6 that Ofgem will consult on its draft decision, and then publish its final decision. A direction may or may not be issued. | Closed
59 | 2022-09-06 | ENWL | 1.40 (what we think should be 7.7) | Information submitted in business plans are superseded by the licence and FDs. Information in the FBP may or may not be allowed for in FD or achievable based on allowances or provisions set out in the FD. Therefore Business plans are not relevant in this context and these words should be removed from the para |  | Disagree - If the PCD is attached to allowances intended to deliver an output that was proposed in the FBP, it is not clear why the FBP information would not be relevant, alongside other information, to determine the delivery status of a PCD. | Closed
60 | 2022-09-06 | ENWL | 1.40 (what we think should be 7.7) | Footnote 10 missing |  | formatting amended, renumbered. | Closed
61 | 2022-09-06 | ENWL | Appendix 1 - removed definitions | We think they should be reinstated but state these are defined in SpC 1.1 of the licence. |  | We prefer not to duplicate definitions unless necessary because not all licences contain them. Readers should refer to the licence. A reference has been added. | Closed
62 | 2022-09-06 | ENWL | Appendix 1 - Mechanstic PCD definition | We think this should also be in the licence and not in AD as per evaluative PCD. |  | Added to ED licence as part of 9.3, but remains in AD for the benefit of the other sectors. | Closed
63 | 2022-09-06 | ENWL | Appendix 2 | Can Ofgem consider including an ED example for completeness? |  | ED example added | Closed
64 | 2022-09-06 | ENWL | Appendix 2 | As per comment on consumer outcome, can Ofgem add what the consumer outcome would be for the hypothetical example 1? |  | No change made, see response to issue 42 (line 40) | Closed
66 | 2022-09-06 | ENWL | Appendix 3 and Appendix 5 - NGGT appendices | A term "Equivalent Delivery" is used here that isnt used anywhere else, or defined - what is this? |  | This was an error, replaced this term with "Fully Delivered with Alternative Specification" | Closed
67 | 2022-09-06 | ENWL | Appendix 4 | We disagree with the need for both a PCD and a UIOLI assessment for Cyber OT. This is unecessary regulatory treatment for no consumer benefit. Our response to Draft Determination provides more information and we do not consider it to be appropriate for inclusion in ED2 |  | See response in issues log SpC 3.2 Cyber Resilience IT and OT Issue log #13 | Closed
68 | 2022-09-06 | ENWL | General | The document is silent on when a PCD is changed or established via a re-opener - what would happen in this scenario, this should be set out in the document. |  | Example added to Appendix 2 | Closed
69 | 2022-09-06 | ENWL | General | The word re-opener sometimes has a capital R and other time doesn't - can this be made consistently - suspect lower case as not a defined term |  | Amended where the term is used not as part of a name (for a specific PCD or document) | Closed
70 | 2022-09-06 | ENWL | General | A clear introduction is needed at the start of the document to state which mechanisms/licence conditions the methodology document is applicable to. |  | See response to issue 11 (line 14) of this sheet. | Closed
71 | 2022-09-06 | ENWL | General | ENWL supports all of the comments and issues raised by the ENA in relation to Cyber and evaluative PCDs more broadly (June 2022) and this needs to be considered in the context of this document and associated licence conditions. |  | Noted. | Closed
72 | 2022-09-06 | ENWL | General definition - Efficiency | We suggest an extra paragraph is inserted in the assessment section. | "the Authority shall only have regard to information that could reasonably have been available to the licensee at the time of making the relevant investment decisions" | Have added to AD "We will have regard to all relevant, including the most recently available, information." at 1.40/ should be 7.7). | Closed
73 | 2022-09-06 | ENWL | General - Consumer Outcome | This is an incredibly broad definition, particularly in its link to the whole life of the PCD output. Can Ofgem give an example of what a consumer outcome would be that will be stated in the licence - we have not seen any examples through the ED2 licence drafting yet and cannot fully understand how this will work in relation to the assessment of the PCD |  | See response to issue 42 (line 40) of this sheet. | Closed
74 | 2022-09-06 | ENWL | General - Innovation | It is unclear why the definition of innovation differs from that applied in ED1 and we propose that this definition continues to be fit for purpose for ED2 | 1 should include those as part of NIC and LCNF, and 2) should use the ED1 wording of "not in widespread use…" | No change required. The current definition includes in part b) "involves the application of technology, systems or processes that were not proven as at the time of submission of the Business Plan" and is hence broad enough to include the requested additional information. | Closed
75 | 2022-10-10 | SPEN | Spc 3.3 Evaluative PCDs | Ofgem’s issues log (row 25) sets out that in the event of a Partially Delivered output where costs are “front end loaded” Ofgem would be able to fund the efficiently incurred costs via the processes in 3.3.13(a) (we think it means (e)). We do not understand how Ofgem would be able to use this branch of 3.3.13 instead of 3.1.13(d). We also do not understand what approach the DNO should take to reporting the delivery status of a PCD in this situation. Paragraph 1.12 of PCD Reporting Requirements and Methodology Document does not permit the DNOs an option to indicate that assessment under 3.3.13(e) is appropriate. It would be helpful if Ofgem could include a “hypothetical example” in the Associated Document explaining this process. | 2 should include those as part of NIC and LCNF, and 2) should use the ED1 wording of "not in widespread use…" | Please see Appendix 2 and 4 for hypothetical examples. | closed
76 | 2022-11-16 | ENWL | Cyber appendix | cyber annex contains wording at the front that duplicates and contradicts the main pcd document. It isn't clear whether it is an annex to main document or not. |  | Yes it is an appendix, and this has been clarified. Duplications and contradiction have been removed. | Closed
77 | 2022-10-26 | NPg | PCD Reporting Requirements and Methodology Document - General | Consistency | Use "licensee" and "licensees" instead of "network company" and "network companies" | Agree, amended | closed
78 | 2022-10-26 | NPg | PCD Reporting Requirements and Methodology Document - paragraph 1.11 | "assessment" is singular | Change "are" to "is" | Agree, amended | closed
79 | 2022-10-26 | NPg | PCD Reporting Requirements and Methodology Document - paragraph 1.12 | Ofgem’s issues log (row 25) sets out that in the event of a Partially Delivered output where costs are “front end loaded” Ofgem would be able to fund the efficiently incurred costs via the processes in 3.3.13(a) (we think it means (e)). We do not understand how Ofgem would be able to use this branch of 3.3.13 instead of 3.1.13(d). We also do not understand what approach the DNO should take to reporting the delivery status of a PCD in this situation. Paragraph 1.12 of PCD Reporting Requirements and Methodology Document does not permit the DNOs an option to indicate that assessment under 3.3.13(e) is appropriate. It would be helpful if Ofgem could include a “hypothetical example” in the Associated Document explaining this process. |  | See Appendix 2 and 4 for illustrative examples. | closed
80 | 2022-10-26 | NPg | PCD Reporting Requirements and Methodology Document - paragraph 1.16 | "underspends" is plural | Change "is" to "are" | agree, amended on p. 13 | closed
81 | 2022-10-26 | NPg | PCD Reporting Requirements and Methodology Document - paragraph 1.23 | "due" is not needed | Delete "due" | amended | closed
82 | 2022-10-26 | NPg | PCD Reporting Requirements and Methodology Document - paragraph 1.25 | Make second sentence consistent with the licence | Change to "Where there is clear evidence and justification that the PCD is Fully Delivered we will not require the licensee to submit a Full PCD Report". | amended. | closed
83 | 2022-10-26 | NPg | PCD Reporting Requirements and Methodology Document - paragraph 1.26 | Clarify that "within 28 days of the direction" means by no later than 28 days after the direction is issued | Change to "Where we have decided to undertake a Full PCD Report Review, we will direct the licensee to submit a Full PCD Report so as set out below by no later than 28 days from the date of the direction. Licensees may request a longer period, if that is deemed to be necessary, and should provide reasons in support of such a request." | agree, amended | closed
84 | 2022-10-26 | NPg | PCD Reporting Requirements and Methodology Document - paragraph 1.27 | The second sentence is not required because each of paragraphs 1.28, 1.29. 1.30 and 1.31 refers to the requirements for the Full PCD Report | Delete the second sentence. | Now paragraphs from 6.9 onwards - no change made. Drafting preference for current verison. | Closed
85 | 2022-10-26 | NPg | PCD Reporting Requirements and Methodology Document - paragraph 1.42 | Clarification | Change to "Ofgem will specify the deadline by which licensees are required to respond to a SQ, which will usually be within 5 or 10 working days depending on the complexity of the query." | Drafting preference, not actioned | Closed
86 | 2022-10-26 | NPg | PCD Reporting Requirements and Methodology Document - Appendix 1 | The definition of "Basic PCD Report" in the licence is "has the meaning given to that term in the PCD Reporting Requirements and Methodology Document". Consequently, the definition is circular | Change to "means a report submitted in accordance with paragraph 1.23 of this document, which includes the information specified in paragraph 1.24 of this document." | Amended. | Closed
87 | 2022-10-26 | NPg | PCD Reporting Requirements and Methodology Document - Appendix 1 | The definition of "Full PCD Report" in the licence is "has the meaning given to that term in the PCD Reporting Requirements and Methodology Document". Consequently, the definition is circular | Change to "means a report submitted in accordance with paragraph 1.28, 1.29. 1.30 or 1.31, as applicable to the individual circumstances of the PCD concerned and its delivery status." | Amended. | Closed
88 | 2022-10-10 | SPEN | Para 1.4 | Typo - delete "and" in track change or make a "/" between "and" / "or". |  | Amended. | Closed
89 | 2022-10-10 | SPEN | Para 1.19 | Paragraph states that Ofgem will take account of representations in line with its legal duties. It should be recognised that Ofgem will also need to consider feedback in light licensees' legal duties as well as Ofgem's. |  | Now paragraph 5.6. We have amended the sentence to say "We will take account of all relevant information provided by licensees and other stakeholders". | closed
90 | 2022-10-21 | UKPN | 1.3/Cover | The scope on the cover is for evaluative PCDs but 1.3 states evaluative and mechanistic |  | No change made. Text on the cover provides high level context on the purpose of the document - requirements and methodology associated with Evaluative pcds. The introduction provides broader context about all the types of PCDs - which is additional to the core purpose of the document as established by Sp C 9.3. | Closed
91 | 2022-10-21 | UKPN | 1.6 | Paragraph numbering not resetting at each chapter |  | Amended | Closed
92 | 2022-10-21 | UKPN | 1.10 Mechanistic | Remove "intended to be" |  | Amended | Closed
93 | 2022-10-21 | UKPN | General | As this is a PCD reporting document then chapters 2-5 are superflous and consideration should be given to their removal (or if it is felt that they give useful context, be merged into one chapter to downplay their importance in this document as they are for info only) |  | Disagree, consider that the document provides helpful information requested by licensees | Closed
94 | 2022-10-21 | UKPN | 1.21 | Remove "intended to be" |  | Amended | Closed
95 | 2022-10-21 | UKPN | 1.22 | Remove "intended to be" |  | Amended | Closed
96 | 2022-10-21 | UKPN | 1.23 | This reporting is a licence obligation so should be reworded to avoid double jeopardy |  | Now paragraph 6.4. - no change made. Requirements are aligned with what is spelled out in the licence. | closed
97 | 2022-10-21 | UKPN | 1.24 | What is a "Scheme Name"? |  | Now paragraph 6.5. The name of the work programme, as identified in the licence condition. | closed
98 | 2022-10-21 | UKPN | 1.24 | Are the final two bullets just for those PCDs that are not Fully Delivered? If so this should be made clearer |  | Now paragraph 6.5 - No change made. Information in points f and g can be relevant to several PCD delivery statuses. Where the licensee considers that no potential adjustments are necessary, they can state this. | closed
99 | 2022-10-21 | UKPN | 1.32 | What other mechanisms and reporting is being referred to? It would benefit from clarity in this respect |  | Now 6.13. No change made. This will depend on the PCD in question, so adding specifity across all sectors will add unnecessary complication to this paragraph. | closed
100 | 2022-10-21 | UKPN | 1.37 | There is no corresponding footnote for the No.8 |  | Footnotes renumbered, formatting fixed. | Closed
101 | 2022-10-21 | UKPN | 1.37 | Delete the sentence allowing submission earlier as the licence sets the backstop date and inherently it can therefore be submitted earlier |  | Provides helful clarity. Have not actioned change | Closed
102 | 2022-10-21 | UKPN | 1.39 | "Or less" can be deleted as you have stated it will be done within nine months |  | Amended | Closed
103 | 2022-10-21 | UKPN | Table 7.2 No.5 Draft Direction | In what circumstances is a direction not required? Is this only for where Ofgem has following the Full PCD Report decided the PCD has been Fully Delivered? If so this ought to be made clear |  | No change made. Again - this table is intended to cover a range of cases and whether a direction is required depends on the outcome of the PCD review which will vary according to the status - delayed, fully delivered, partially delivered etc.. We don't consider it to be helpful to the reader to add additional information to this table that spells out the possible outcomes in each different case. | closed
104 | 2022-10-21 | UKPN | 1.4 | There is no footer text for No.11 |  | formatting fixed, footnote numbering amended. | Closed
105 | 2022-10-21 | UKPN | Definitions | Mechanistic PCD is defined in the ED licence so should be signposted accordingly |  | Have now used same definition as in licence | Closed
106 | 2022-10-21 | UKPN | Hypothetical Example 1b | Remove some of the detail of the scenario as it is not relevant to example e.g. the list of equipment being installed |  | Amended. | Closed
107 | 2022-10-21 | UKPN | Hypothetical Example 4 | Remove reference to wider scheme as this is not relevant to the example |  | Disagree, it is relevant | Closed
108 | 2022-10-21 | UKPN | pg 3 | ToC includes erroneous contents for section 7 |  | Issue resolved, edit included | Closed
109 | 2022-10-21 | UKPN | Section 6 summary | Missing the word 'the' before background | This section sets out the background on PCD reporting and the evaluative PCD reporting requirements for licensees. | Issue resolved, edit included | Closed
110 | 2022-10-21 | UKPN | 1.2 | Incorrect definition for RRP, it is not Templates, it is Packs. | For all PCDs, licensees are required to submit completed reporting templates and associated commentary as part of the RIIO-2 Regulatory Reporting Packs (RRP) as directed by the relevant Regulatory Instructions and Guidance (RIGs). | Issue resolved, edit included | Closed
111 | 2022-10-21 | UKPN | 1.24 (last bullet) | Inconsistent use of capitalisation of bullets. Check whole document for consistency |  | Issue resolved, edit included | Closed
112 | 2022-10-21 | UKPN | Whole document | Paragraph numbers not start with the number of each respective chapter? At the moment, they just run from 1. all the way through. |  | Issue resolved, edit included | Closed
113 | 2022-10-21 | UKPN | Pg 19 - Table 7.2 | Missing words under Preliminary Review | Following the submission of the Basic PCD Report, Ofgem will conduct an initial assessment of whether the delivery of the PCD output complies with the relevant licence condition, using information submitted. | Issue resolved, edit included | Closed
114 | 2022-10-21 | UKPN | Pg 24 - Hypothetical example 1b | Typo in last paragraph, first sentence. (too many 'the's) and a missing word | If by 31 July 2026, when the Basic PCD Report is due to be submitted, installation is complete, the licensee must nevertheless assign the PCD status to Delayed, as this was the PCDs’ status on the last day of the Regulatory Year the report refers to. | Issue resolved, edit included | Closed