## SpC 3.2 Part N
Licence number and name: |  | West Coast of Cumbria re-opener, 3.2 Part N
Ofgem contact: |  | Atalla Buretta
No. | Date raised | Comment from | Reference (Part X, Para Y) | Comment | Suggested alternative drafting (if necessary) | Due Date | Response | Issue closed?
1 | 2022-08-25 | Ofgem | 3.2.91 | Correction to references. | References to be updated to 3.2.86, 3.2.88, 3.2.89 | 2022-08-25 | References updated | Closed
2 | 2022-09-05 | ENWL | Title and throughout | Moorside' to be replaced with 'West Coast of Cumbria' | Update throughout | 2021-09-19 | Updated | Closed
3 | 2022-09-18 | ENWL | Inclusion of an early notification |  | 1. ENWL/NGET receive application for connection at Moorside, which ENWL considers warrants the commencement of early preparatory work for the connection 2. ENWL submit ‘early notification’ to Ofgem, setting out: a. Request for low materiality development funding for Moorside - @Darley, David, would be good to understand what sort of materiality you’d expect to see here, taking in to account later triggers for construction works b. Request for Ofgem to confirm future timing of triggering the Moorside re-opener 3. Ofgem confirms: a. Approval of £[y]m of development funding; and b. That it will trigger main re-opener if [x] happens (e.g. submission of LOTI Final Needs Case or some form of generator milestone such as FID – to be considered, would adapt depending on circumstances) 4. [x] happens, Ofgem triggers re-opener for ENWL to request full project construction costs |  | Early inclusion agreed and now Incorporated | Closed
4 | 2022-10-27 | ENWL | General comment | We note that this version of the licence condition does not currently reflect agreed directional changes discussed as part of our bilateral engagement with Ofgem. This is referred to in issues log item 3 and we will continue to liaise with Ofgem to enact these necessary changes in the coming weeks. |  |  | Update submitted 23/11 and changes dicussed have been incoroprated. | Closed
5 | 2022-10-27 | ENWL | 3.2.97 (a) - Definition of West Coast of Cumbria is missing | We have reviewed the definition of the term set out in column D and provide detailed comments on this in Annex 5 to our response 'Annex 5: Definitions'. Please refer here for ENWL definitional views and comments. |  |  | West Coast of Cumbria Reopener is now defined | Closed
6 | 2022-10-27 | ENWL | 3.2.97 (a) - Definition of "Initial Needs Case" and embedded definition of "Relevant Network Licensee" | We have reviewed the definition of the term set out in column D and provide detailed comments on this in Annex 5 to our response 'Annex 5: Definitions'. Please refer here for ENWL definitional views and comments. |  |  | Intial needs case is defined. Relavent network licensee also defined but no longer used in this chapter | Closed
7 | 2022-10-27 | ENWL | General | We provide further information within our Annex 2 document as part of our consultation response. |  |  | Noted and incorporated. | Closed
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25