## SpC8.1
Licence number and name: |  | SpC 8.1 Governance
Ofgem contact: |  | Penny Harandy
No. | Date raised | Comment from | Reference (Part X, Para Y) | Comment | Suggested alternative drafting (if necessary) | Due Date | Response | Issue closed?
1 | 2022-02-23 | LDWG | 8.1.3 | There were some concerns around the inclusion of a Materiality Threshold within this condition. There was a suggestion to reduce it to a de minimis level or to remove it entirely, and rely only on the categories in 8.1.5. |  |  | Materiality threshold has been removed. | Closed
2 | 2022-02-23 | LDWG | General | There was a suggestion that this isn't needed as it is covered by the Housekeeping condition |  |  | There are differences in the remit and operation that we think warrant two separate powers e.g. consequential additions of PCFM VV to the PCFM in 8.1.5(d), different working groups and the need for 8.1.8. | Closed
3 | 2022-02-23 | LDWG | 8.1.4 | There are concerns around the presumption that a correction of a manifest error would have no impact and would therefore not require a statutory consultation, by default. |  |  | This is no different from how the condition operated in ED1 and remains in force in the GD/T equivalent special conditions. We do not see any reason to remove this for ED2 and we consider the distinction between manifest errors and other types of modifications to be a pertinent one. | Closed
4 | 2022-02-23 | LDWG | 8.1.8 | There was a suggestion that we should remove the words "for the avoidance of doubt" from the face of the licence. | 8.1.8 The following do not constitute a modification of the ED2 Price Control Financial Model: |  | Drafting now matches the suggested | Closed
5 | 2022-02-23 | LDWG | 8.1.3 | There were some concerns over the use of multiple different materiality thresholds ie. There is also a materiality threshold in SLC 38B as it stands. |  |  | Materiality threshold has been removed. | Closed
6 | 2022-02-23 | SSEN | 8.1.3 | We have concerns with the use of 'materiality threshold' in this context. Our view is that this should either be removed entirely, on the basis that a housekeeping or formatting change should not have any impact on revenue in any case. We note that this has already been captured from the discussion at the LDWG. |  |  | Materiality threshold has been removed. | Closed
7 | 2022-03-10 | NPg | 8.1.3(b) | The modification should have no financial impact on the licensee and should not be subject to a materiality threshold | Delete 8.1.3(b)(ii) such that it reads "no impact on the licensee's Allowed Revenue" |  | Amendment made and materiality threshold removed | Closed
8 | 2022-03-10 | NPg | 8.1.4 | If there is a manifest error, that error should be assessed to confirm whether it meets the "no impact" test. | The modification process should only apply if it is confirmed that correcting the manifest error will have no impact the licensee's Allowed Revenue |  | We do not agree that a manifest error should be assessed for revenue impact. This is no different from how the condition operated in ED1 and remains in force in the GD/T equivalent special conditions. We do not see any reason to remove this for ED2 and we consider the distinction between manifest errors and other types of modifications to be a pertinent one. | Closed
9 | 2022-03-10 | NPg | 8.1.5(e) | See 8.1.4 |  |  | See response, above. | Closed
10 | 2022-03-11 | WPD | 8.1.9 | Wording should make clear it is the most up to date versions of FIs to be maintained. | Proposed wording: 8.1.9 The Authority will maintain on the Authority’s Website an up to date copy of the ED2 Price Control Instruments for Regulatory Years commencing on or after 1 April 2023. |  | Amendment made. | Closed
11 | 2022-03-11 | WPD | 8.1.9 and elsewhere | It would be helpful to see a plan from Ofgem which included all PCFM publications required by the AIP, RFPR and Charge setting process, and as a result of the changes under SpC8.1. |  |  | Noted - Ofgem to look into this | Open
12 | 2022-03-30 | ENWL | Part D | We believe Ofgem should publish a consolidated PCFM (following AIP) each year to enable existing and future external stakeholder requirements to be met. |  |  | Agreed - amendment made | Closed
13 | 2022-08-05 | NPg | 8.1.2 | The definition of "ED2 Financial Intruments" is "means the ED2 Price Control Financial Handbook and the ED2 Price Control Financial Model" so there is no need to mention them individually | Replace all of the current wording with "The ED2 Price Control Financial Instruments form part of this condition." |  | No amendment needed. Some of the provisions very specifically relate to the PCFM, only and it would not make sense to replace PCFM with PCFI in those instances, eg para 8.1.8 which relates only to the model. | Closed
14 | 2022-08-05 | NPg | 8.1.5 | Minor change | Change "renaming" to "re-naming" |  | Amendment made. | Closed
15 | 2022-08-05 | NPg | 8.1.6 | The paragraph does not include the timescale for the decision-making process following expiry of the 28-day period for making representations i.e. as drafted, the exercise may never be concluded | A reasonable timescale of actions to be taken following expiry of the 28-day period for making representations should be added |  | This is in line with our drafting on how the authority will publish a direction, elsewhere in the licence. The consultation notice period is specified but we do not specify a timeframe for decision-making following a consultation. No amendment needed. | Closed
16 | 2022-08-05 | NPg, ENWL | General point | There has only been very limited discussion of PCFH drafting at any forum to date. We are concerned that this key task may be ‘falling between’ working groups. To help with this, it would be helpful if a) Handbook chapters can be shared with the associated condition when it comes to LDWG; and b) Ofgem could provide a list of handbook chapters/sections that will not have associated licence conditions. |  |  | We have since brought relevant sections of the PCFH to the LDWG along with the relevant licence condition including the Pensions, Legacy and Tax chapters. The PCFH continues to be a work in progress however we do ensure to update the drafting of each relevant section alongside the relevant licence condition. Update: the ED2 PCFH is included as part of this statutory consultation and has now been updated. | Closed
17 | 2022-08-04 | ENWL | Part D | Further to your agreement to an amendment following our earlier comment ‘We believe Ofgem should publish a consolidated PCFM (following AIP) each year to enable existing and future external stakeholder requirements to be met’, we request that in the event of a material change in forecast that Ofgem re-publishes the consolidated PCFM |  |  | The process of calculating allowed revenue and setting tariffs will not be tied to the 30 November AIP publication so it does not require a specific provision on the face of the licence. In theory, nothing should change between the 30 November reporting process and the version of the PCFM which tariffs are based on but if something material does change, it should be highlighted and communicated to us with two weeks notice and then reflected in tariffs. This does not require a separate process or a separate provision in the special conditions as this is more of a charging issue than a PCFM issue. | Closed
18 | 2022-10-12 | SPEN | 8.1.5 part e | Description of manifest error has been removed, suggest this is reinstated to match RIIO-T2 licence | correction of manifest errors; such as discrepancies between the ED2 Price Control Financial Instruments and between the ED2 Price Control Financial Instruments and the other special conditions of this licence. |  | Amendment made | Closed
19 | 2022-10-19 | NGED | 8.1.7(a) | 8.1.7(a) refers to ED2 Price Control Finance Instruments. Correct term is to ED2 Price Control Financial Instruments |  |  | Amendment made | Closed
20 | 2022-10-26 | NPg | Part A, paragraph 8.1.4 | It is wrong to presume that a manifest error will have no impact on the licensee's Allowed Revenue. Whether it does or not will depend on the effect of the error. | Delete 8.1.4 and re-number subsequent paragraphs accordingly |  | We do not agree that a manifest error should be assessed for revenue impact. This is no different from how the condition operated in ED1 and remains in force in the GD/T equivalent special conditions. We do not see any reason to remove this for ED2 and we consider the distinction between manifest errors and other types of modifications to be a pertinent one. | Closed
21 | 2022-10-26 | NPg | Part B, paragraph 8.1.7(a) | Defined term is "ED2 Price Control Financial Instruments" | Change "ED2 Price Control Finance Instruments" toi "ED2 Price Control Financial Instruments" |  | Amendment made | Closed
22 | 2022-10-26 | NPg | Definition of "ED2 Price Control Financial Handbook" | Incorrect reference to "GD2" | Change "GD2" to "ED2" |  | Cannot see any reference to GD2 in either SpC 8.1 or the definitions list. | Closed
23 | 2022-10-12 | SPEN | 8.1.5 part e | Description of manifest error has been removed, suggest this is reinstated to match RIIO-T2 licence | correction of manifest errors; such as discrepancies between the ED2 Price Control Financial Instruments and between the ED2 Price Control Financial Instruments and the other special conditions of this licence. |  | Have added this back in | Closed
24 | 2022-10-27 | SPEN |  |  | In relation to special condition 8.1, we are in agreement with Ofgem on the proposals to move to “self-publication of Allowed Revenue” as opposed to the current direction approach in RIIO-ED1. However, as set out in our response to Question 6, we disagree with the need to provide a PCFM to Ofgem 14 days prior to the formal deadline for tariff setting as it will in effect pull forward the price setting timeline by 2 weeks. Furthermore, we believe that more work is required on the whole "Price Control Financial Instruments" linkages i.e. (Special Conditions, Price Control Financial Handbook, Regulatory Financial Reporting Guidance, Price Control Financial Model & Associated Guidance) to ensure that the various documents reflect all intended policy. We continue to work with Ofgem via the dedicated workstreams but believe that until DNOs can review all elements of the relevant documents we cannot provide our final views on suitability of the current drafting. |  | We have made considerable progress on the instruments. Please raise issues if there are specific concerns at this point. The 14 day notice period should not change much, considering the ED1 process involved directing MOD values on 30 November. | Closed
25 | 2022-10-27 | SSEN | General Point | There is limited drafting on the Annual Iteration Process and how the Financial Instrucments will be utilised during the process, including the timeline for both licencees and the Authority. Similar to that of SpC 8.2 in T2 |  |  | This drafting will be included in the PCFM Guidance, which will be drafted and consulted on following the ED2 licence modification. | Closed
26 | 2022-10-21 | UKPN | 8.16(a) | This should refer to 8.16a to e not a to d - the ED2 PCFM WG are industry experts and will have a view on the impact of an manifest errors and Ofgem should consider such views |  |  | Bullet e relates to a correction of manifest errors, which is covered by the presumption set out at paragraph 8.1.4. However our working practice is to discuss all modifications with the working group whether or not they are considered corrections of a manifest error. Amendment made. | Closed
27 | 2023-01-17 | DNO Common | Manifest error SpC 3.1 SpC 3.9 SpC 8.1 SpC 9.2 | The term “manifest error”, which is used in four special conditions, is not defined and so gives rise to uncertainty as to what is meant by the concept of “manifest error” and what is the nature and effect of the presumption in the relevant conditions. This uncertainty should be addressed by making “Manifest Error” a defined term. SpC 3.9.13 provides that, for the purposes of SpC 3.9.12 (which identifies by reference to SpC 3.9.14 the categories of change that can be made to the Governance Document by direction), “it is to be presumed that a modification which serves to correct a manifest error will have no impact on the licensee’s Allowed Revenue”. SpC 3.9.14(e) only provides an example as to the meaning of “manifest error” i.e. “discrepancies between the [Governance Document] and the other special conditions”. which leaves open the question as to when a discrepancy amounts to a “manifest error”, as opposed to merely an unintended outcome. The importance of the precise meaning of “manifest error” depends in part on the nature and effect of the presumption in SpC 3.9.13. If the condition gives rise to an irrebuttable presumption that the correction of a “manifest error” will have no impact on a licensee’s Allowed Revenue, that could only be potentially acceptable if the condition were to apply only to the correction of errors that the licensee must have known were drafting errors (such that it never in fact expected to receive allowed revenue in accordance with the erroneous provision). Stronger and clearer language is, therefore, required to establish an irrebuttable presumption that the correction of a “manifest error” will have no impact on a licensee’s Allowed Revenue. This would be achieved by including “Manifest Error” as a defined term in SpC 1.2, as follows: “Manifest Error means a drafting error that is so obvious that no licensee could have relied on the error and/or expected to receive Allowed Revenue in accordance with its effects.” It should also be made clear that the presumption is rebuttable by the addition of “(unless the licensee shows otherwise)” such that SpC 3.9.13 reads: “For the purposes of paragraph 3.9.12, it is to be presumed (unless the licensee shows otherwise) that a modification which serves to correct a Manifest Error will have no impact on the licensee’s Allowed Revenue”. As the term “manifest error” is also used in other special conditions, this change would bring clarity to each of those conditions. The term “manifest error” should, therefore, be capitalised in SpC 3.1.8(c), SpC 3.9.13, SpC 3.19.14(e), SpC 8.1.4, SpC 8.1.5(e) and SpC 9.2.20(e). The principle noted in paragraph 3.5 also applies to SpC 8.1.4, which should, therefore, read: “For the purposes of paragraph 8.1.3(b), it is to be presumed (unless the licensee shows otherwise) that a modification which serves to correct a Manifest Error will have no impact on the licensee’s Allowed Revenue”. | New defined term: Manifest Error means a drafting error that is so obvious that no licensee could have relied on the error and/or expected to receive Allowed Revenue in accordance with its effects 8.1.4 For the purposes of paragraph 8.1.3(b), it is to be presumed (unless the licensee shows otherwise) that a modification which serves to correct a Manifest Error will have no impact on the licensee’s Allowed Revenue |  | We have amended 8.1 in line with DNO suggestions to reinstate the paragraph giving DNOs the right to make representations to the Authority that a particular modification would be likely to have a significant impact (see issue # 30). As such, the presumption set out at 8.1.4 is not an irrebuttable one. We do not agree that manifest error needs to be a defined term as the words bear their natural, dictionary meaning. | Closed
28 | 2023-01-17 | SSEN | General Point | As per point 25, there is limited drafting on the Annual Iteration Process and how the Financial Instrucments will be utilised during the process, including the timeline for both licencees and the Authority. Similar to that of SpC 8.2 in T2. Ofgem advise this will be included in the PCFM Guidance and we welcome the opportunity to respond in due course. |  |  | Noted - this will be shared with DNOs through the RIGs drafting process. | Closed
29 | 2023-01-03 | UKPN | 8.1.4 | It is not correct (as Ofgem asserts in this para) that that the correction of a manifest error will not impact Allowed Revenue. Ofgem are correct that the current ED1 licence states that the presumption is that a correction of a manifest error would not impact allowed revenue. However, it is followed by the paragraph below. We suggest that Ofgem insert a similar paragraph in the ED2 licence condition. “- The presumption established by paragraph 4A.6 is without prejudice to the licensee’s right under paragraph 4A.13.11 to make representations to the Authority that a particular modification would be likely to have a significant impact of the type referred to in paragraph 4A.4 or 4A.5(a).” Possible wording for ED2 licence “ The presumption established by paragraph 8.1.4 is without prejudice to the licensee’s right under paragraph 8.1.6 to make representations to the Authority that a particular modification would be likely to have a significant impact.” |  |  | We have included alternative fording at 8.1.4 to achieve the same aim. | Closed
30 | 2023-01-04 | UKPN | 8.1.9 | It would be sensible for Ofgem to also include an archive set of previous versions of PCFIs on their website |  |  | Ofgem to look into setting up a webpage that contains archive copies of the PCFIs for ED2. This has been implemented in GD/T2 and so we intend to implement similar for ED2, in due course. | Closed