## SpC 3.2 Part P
Licence number and name: |  | Shetland Enduring Solution re-opener, 3.2 Part P
Ofgem contact: |  | Joe Slater
No. | Date raised | Comment from | Reference (Part X, Para Y) | Comment | Suggested alternative drafting (if necessary) | Due Date | Response | Issue closed?
1 | 2022-08-25 | LDWG | 3.2.96 | SSEN requested that dates be amended to reopener window dates be amended to June 2023 and September 2028 |  | 2022-08-26 | Drafting amended. Discussed this with Mark and we both agreed that January 2024 would be more appropriate than June 2023 as it would provide SSEN more time to finalise the project and allowances would still flow at the same time. | Closed
2 | 2022-08-25 | LDWG | 3.2.96 | SSEN requested that the 10% up/down condition be added to the second re-opener window |  | 2022-08-26 | Drafting amended. September 2028 wouldn’t allow time for allowances to be incorporated in Year 5 RIGs, so have gone with standard Y5 window in Jan 2028. | Closed
3 | 2022-09-05 | SSEN | 3.2.96 | Following on from comment 1 above and Ofgem's response. We appreciate that an earlier reopener window would not result in an earlier allowance, however as we intend to place a contract for the Shetland solution prior to the commencement of ED2, we would prefer the first reopener window to be as early as possible in ED2 to provide certainty that the costs will be recovered. |  | 2022-09-09 | Drafting has been amended consistent with our comments at issues 1 and 2 above. We do not see a justification for a non-standard re-opener window for this re-opener. | Closed
4 | 2022-09-05 | SSEN | 3.2.95 | We proposed that no materiality threhold should apply as we have currently not requested any allowance for this (due to the level of uncertainty), therefore all costs should be recoverable. | 3.2.95 The Shetland Enduring Solution Re-opener may be used where the licensee has incurred or expects to incur costs related to the Shetland Enduring Solution. (removing 'that exceed the Materiality Threshold') | 2022-09-09 | We do not agree that no materiality threshold should apply. | Closed
5 | 2022-09-05 | SSEN | 3.2.97(a) | The wording doesn't quite work as 3.2.95 doesn't set out criteria. | sets out how the requirement in paragraph 3.2.95 has been fulfilled. | 2022-09-09 | Drafting amended | Closed
6 | 2022-09-05 | SSEN | PCFH | We are not clear why all Shetland related items have been removed from the PCFH (with the exception of legacy items). Several of these items require to be added back in and a new entry will be required for the new uncertainty mechanism. |  | 2022-09-09 | Noted your comments and are considering this separately | Closed
7 | 2022-09-05 | SSEN | General | Note that we also need to retain the existing ED1 uncertainty mechanism relating to: PPA with SVT; capital and operating costs for LPS; and ANM costs. |  | 2022-09-09 | Will be at Sept LDWG | Closed
8 | 2022-09-05 | SSEN | General | Note that we also need to retain the existing ED1 pass through mechanism for fuel costs and environmental permits for LPS. |  | 2022-09-09 | Will be at Sept LDWG | Closed
INFORMAL LICENCE CONSULTATION RESPONSES BELOW THIS LINE
9 | 2022-10-27 | SSEN | 3.2.4 (o) and (p) | This should refer to SSEH rather than SSEN | Shetland Enduring Solution re-opener (SESt)– SSEH only | 2022-12-02 | Agree and updated for both Shetland re-opener licence conditions | Closed
10 | 2022-10-27 | SSEN | 3.2.112 (a) | No materiality threshold should apply to this reopener as we currently have now allowance for this. We note Ofgem's response above in terms of applying a consistent approach with other reopeners. However, our view is that this is different as we have removed all costs from baseline. |  | 2022-12-02 | We do not agree that no materiality threshold should apply in this instance. | Closed
11 | 2022-10-27 | SSEN | 3.2.112(b) | This should state greater than +/-10% so as to avoid having to meet exactly 10%. | (b)the licensee has incurred or expects to incur costs related to the Shetland Enduring Solution that are greater than 10% over or under the allowances set in response to an application under paragraph 3.2.112(a) | 2022-12-02 | Agree and licence text updated | Closed
12 | 2022-10-27 | SSEN | 3.2.113(a) | We note that Ofgem has not agreed to our proposal for a June 2023 reopener application window. Whilst we understand that this would not provide us with an earlier allowance, it would provide greater comfort given that we intend to place a ten year contract in early 2023 for a service provision. |  | 2022-12-02 | No change. | Closed
13 | 2022-10-27 | SSEN | Part P General | It would be helpful for this reopener to also have an Authority triggered option. This would allow Ofgem to trigger the reopener earlier (in advance of January 2028) should costs be significantly different than expected. |  | 2022-12-02 | 3.2.120 (a) and (b) allow for authority to direct out of window triggers, so no further change required. | Closed
14 | 2022-10-27 | SSEN | Definition of Shetland Enduring Solution | The current definition could be read as only applying to the projects that are ongoing to develop the ongoing security of supply for Shetland once the HVDC link is in place. This should be clear that it is also the costs for the ongoing arrangements themselves (as well as project costs). | means the various concurrent and related projects and ongoing arrangements to provide long-term security of supply to Shetland following completion of the project to construct and energise the Shetland HVDC Link, including costs associated with the ongoing service provision. | 2022-12-02 | Definition updated | Closed
15 | 2022-10-27 | SSEN | 3.2.119 Part Q | As we have an existing allowance for SEFECt, 3.2.119(a) is not relevant. The reopener is only applicable if we over or under spend on our allowance by >+/- 10% In addition, this should refer to greater than +/-10 % rather than exactly 10%. | 3.2.119 The Shetland Extension Fixed Energy Costs Re-opener may be used where: (a) the licensee has incurred or expects to incur Shetland Extension Fixed Energy Costs that are greater than 10% over or under the allowance provided for these costs. | 2022-12-02 | Structure of licence condition unchanged, but we have updated the text to read 'greater than 10%...' | Closed
16 | 2023-01-17 | ENWL | All | We don’t think this is necessary to be included in ENWL version of the specials. If this is formatting we suggest there are better way to keep formatting without having this in place. As a minimum the licence doesn’t need all the paragraph numbers again unless it is to maintain numbering consitnecy between specials. Limit to one if needed. |  |  | As per previous discussions, we agree that numbering consistency between Special Conditions between licensees is important to maintain readability. This does necessitate some compromises with the 'holding' paragraphs where bespoke conditions exist in other licences. | Closed
Formulas:
Date raised = [Date raised, row above]