## SpC 3.15
Licence number and name: |  | SpC3.15 LineSIGHT (ENWL)
Ofgem contact: |  | Thomas Leung
No. | Date raised | Comment from | Reference (Part X, Para Y) | Comment | Suggested alternative drafting (if necessary) | Due Date | Response | Issue closed?
1 | 2022-11-16 | ENWL | Part A, 3.15.3, Definition of LAt, Appendix 1 | Asked whether it is required to have an LAt allowance for each year if clawback is based on achievements at the end of Price Control Period | To replace annual LAt values in Appendix 1 with just a total allowance value of LA |  | We consider it reasonable to have yearly incidences of allowance required by ENWL to deliver required output for LineSIGHT and replacement by just a total allowance value would not be appropriate. | Closed
2 | 2022-11-25 | ENWL | Part A, 3.15.3, Definition of LAt, Appendix 1 | In relation to issue number 1, ENWL are considering the need to provide an update to the profile in appendix 1 and if needed will provide this as part of our response the the Statutory Consultation on the licence. This comment also applies to our other bespoke mechanistic PCD Smart Street SpC 3.13. |  |  | We have yet to receive the updated profile but are open to suggestions from ENWL. | Closed
3 | 2023-01-17 | ENWL | 3.15.3 | Include reference as to when the algebra will apply for transparency. | "The value of LMPt is derived at the end of the Price Control Period in accordance with the following formula |  | Agreed. Licence has been updated. | Closed
4 | 2023-01-17 | ENWL | Definition - LineSIGHT | There is a contradiction between the definition and the licence condition. Given that 3.15.2 sets out the detail around lineSIGHT context the uncessary and contradictory words in the defintion need deleting. | “means the overhead line safety management system project developed by Electricity North West. Limited to install 400 sensors to 800km of high risk high voltage circuits and 1,800 sensors to 7,200km of normal risk high voltage circuits and integrate them with its network management system as set out in its Engineering Justification Paper (Reference No. BA EJP 1 - Safety) dated 1 December 2021.” |  | The wording in the definition is required to distinguish LineSIGHT from other, if any, overhead line safety management system projects of Electricity North West Limited. It accurately describes the output of the project in the Engineering Justification Paper submitted to Ofgem. We consider the definition is consistent with the licence condition. | Closed