## SpC 3.4 VA UIOLI
Licence number and name: |  | SpC 3.4 Visual Amenity UIOLI
Ofgem contact: |  | Eilidh Alexander
No. | Date raised | Comment from | Reference (Part X, Para Y) | Comment | Suggested alternative drafting (if necessary) | Due Date | Response | Issue closed?
1 | 2022-02-23 | UKPN | 3.4.1. | Wider query on whether we refer to the Totex formula in the totex chapter. |  |  | No, there is no headline formula in Chapter 3. The licence is just outlining the value and the means by which it may be altered. | Closed
2 | 2022-02-23 | WPD | 3.4.1 | To carry forward the standard lines on where we are not applying the TIM |  |  | Accepted | Closed
INFORMAL CONSULTATION COMMENTS BELOW THIS LINE
3 | 2022-10-27 | NGED | 3.4.11 | Incorrect references to 3.4.5, should be 3.4.10 |  | 2022-11-20 | Agree, change made | Closed
4 | 2022-10-27 | ENWL | 3.4.11 | VAPTEt and VAPCAP - the reference to 3.4.5 should be to 3.4.10. |  | 2022-11-20 | Agree, change made | Closed
5 | 2022-10-27 | ENWL | Section header | The header Formuale for calculating the Visual Amenity Projects term has lost its Part letter | Correct formatting to include Part reference, and correct typo in header | 2022-11-20 | Part reinstated | Closed
6 | 2022-10-27 | NGED | 3.4 | Heading references for each of the parts needs updating. Visual Amenity should be Part C (no reference currently), and the EV Optioneering Projects should be Part D. |  | 2022-11-20 | Part reinstated | Closed
7 | 2022-10-27 | NGED | 3.4 | Seems illogical that the WSC cap is in Appendix 2 and Visual Amenity in Appendix 1, when WSC appears before Visual Amenity in 3.4. |  | 2022-11-20 | Agreed, flipped round appendices | Closed
8 | 2022-10-26 | NPg | 3.4.1 | "Price Control Variable Values" is capitalised in the definition of "Use It Or Lose It Allowance" but is not a defined term and is not used in the special conditions | Change definition of "Use It Or Lose It Allowance" to "means the Use It Or Lose It Allowances established by Special Condition 3.4 (Use It Or Lose It Allowances)" | 2022-11-20 | No change required: PCFM Variable Values are defined in SpC 1.1 "as means the values in the table of that name in the ED2 Price Control Financial Handbook". | Closed
9 | 2022-10-26 | NPg | Part B title, title before paragraph 3.4.10 | Consistency | Change "formulae" to "formula" | 2022-11-20 | Agree, change made | Closed
10 | 2022-10-26 | NPg | Title before paragraph 3.4.10 | Missing Part reference | Insert "Part C" and amend subsequent Part references accordingly | 2022-11-20 | Part reinstated | Closed
11 | 2022-10-06 | SPEN | 3.4.11 | Incorrect paragraph reference to 3.4.5 | Refer to 3.4.10 | 2022-11-20 | Agree, change made | Closed
12 | 2022-11-10 | SPEN | 3.4.10 | Definition of "Total Expenditure" required to allow full clarity on the calculation values to be used. | Provide definitIon for "Total Expenditure" | 2022-11-20 | Defintion not required. It's not a defined term, the words have their natural meaning. | Closed
13 | 2022-10-11 | SPEN | 3.4.2 | The wording of this paragraph is a little odd and could be improved. | Should we say "incorporated into the ED2 Price Control Financial Model…" rather than "terms are treated by". | 2022-11-20 | Agree, change made | Closed
14 | 2022-10-27 | SSEN | 3.4 General | It would make more sense for Visual Amenity to come first, follwed by WSC, as per the running order. The referencing numbering is also misaligned and needs updating. |  | 2022-11-20 | Flipped round appendices to correct ordering | Closed
15 | 2022-10-21 | UKPN | Heading after 3.4.9 | Is misformatted and missing its Part C reference (which will also cause the existing Part C to become Part D) |  | 2022-11-20 | Part reinstated | Closed
16 | 2022-10-21 | UKPN | SPC3.4.6 | Both references to paragraphs 3.4.7 seem to be incorrect. Should the correct references be to paragraph 3.4.5? |  | 2022-11-20 | Agree, change made | Closed
17 | 2022-10-21 | UKPN | General | PART A is in specifc order (Visual Amenity Projects, WSC, EV Optioneering) but PART B is in different order. These should be aligned, and with corrected headings. Visual Amenity is shown second but references the first Appendix. Note also appendix order needs to match chosen order for condition. Any changes will need reflecting through into WSC guidance document for paragraph number changes |  | 2022-11-20 | Flipped round appendices to correct ordering | Closed
18 | 2022-10-27 | ENWL | 3.4.6 | WSCCSEt and WSCCSC - the reference to 3.4.7 should be 3.4.5. |  | 2022-11-20 | Agree, change made | Closed
19 | 2022-10-27 | ENWL | 3.4.4a & b | It would make sense to swap these two around given that WSC then comes first in the condition. This also lines up with the appendices as UVA is app 1 and WSC is app 2 |  | 2022-11-20 | Changes made to reflect correct order | Closed
20 | 2022-10-27 | ENWL | 3.4.7 | This should be a new Part C as it is about the governance document, not the formula | Create new Part and change the definition of WSC Governance Document to point to the correct Part of the condition | 2022-11-20 | Part reinstated | Closed
21 | 2022-10-27 | ENWL | 3.4.8 | This para says "The WSC Governance Document may make provision about the governance and administration of the Worst Served Customers Use It Or Lose It Allowance, including" "may" should change to "will" to provide clarity of what the governance document will contain | The WSC Governance Document will make provision about the governance and administration of the Worst Served Customers Use It Or Lose It Allowance, including | 2022-11-20 | Agree, change made | Closed
22 | 2023-01-17 | ENWL | 3.4.10 | VAPCAP should refer to Appendix 2 NOT Appendix 1 |  |  | Agree, change made | Closed
23 | 2023-01-17 | NGED | 3.4.10 definition of VAPTEt | There is a superfluous ";and" at the end of the definition. Delete. | means the total expenditure on Visual Amenity Projects as reported in accordance with the RIGs; and |  | This is consistent with WSC. | Closed
24 | 2023-01-17 | NGED | 3.4.11 definition of VAPCAP | There is a superfluous ";and" at the end of the definition. Delete. | has the meaning given in paragraph 3.4.10; and |  | This is consistent with WSC. | Closed
25 | 2023-01-17 | NGED | 3.4.10 definition of VAPCAP | This references the wrong appendix. It should be appendix 2. | means the value of the licensee's expenditure cap for Visual Amenity Projects for the Price Control Period, as set out in Appendix 2. |  | Agree, change made | Closed
26 | 2023-01-17 | NPg | SpC 3.4, paragraph 3.4.10, definition of VAPCAP | Incorrect reference | Change "Appendix 1" to "Appendix 2" |  | Agree, change made | Closed
27 | 2023-01-17 | common | SpC 3.4 PCFM | There are inconsistencies in the application of RPEs associated with the UIOLI mechanisms (for example, in relation to the Worst Served Customers term (WSCt) and the Visual Amenity Projects term (VAPt)). There are two separate issues: 1. The UIOLI allowance determined via the calculations in SpC 3.4 (Use It Or Lose It Allowances) will be either the value of the cap (which does not have RPEs embedded) or the value of actual expenditure (which will have RPEs embedded). The PCFM then classifies UIOLI as ‘RPEs Apply’ which double-counts RPEs if actual expenditure is used. To avoid this inconsistency, we propose that UIOLI allowances are categorised as ‘RPEs Don’t’ Apply’ in the PCFM. This then avoids the double-counting of RPEs on actual costs. 2. The cap in the licence has been calculated without any consideration of RPEs. This means that RPEs could artificially constrain (or inflate) the amount licensees can spend on these cost areas. We suggest the values of the caps for each UIOLI allowance term in SpC 3.4 Appendices are uplifted by RPEs on an annual basis, using the updated annual RPE modelling assumptions. It would then also be correct that ‘RPEs don’t apply’ in the PCFM, as per the amendment proposed in point 1 above. |  |  | We agree with the change to "RPE Don't Apply" We will not update the cap in the licence; in considering our cost treatment of UIOLIs including OE treatment, we see the caps we have set to be appropriate on balance. | Closed
28 | 2023-01-04 | UKPN | All | The appendices need renumbering as the first one does not have a appendix number - the cross references to them then requires updating |  |  | Agree, change made | Closed