## SpC 3.2 Part N
Licence number and name: |  | West Coast of Cumbria re-opener, 3.2 Part N
Ofgem contact:
No. | Date raised | Comment from | Reference (Part X, Para Y) | Comment | Suggested alternative drafting (if necessary) | Due Date | Response | Issue closed?
1 | 2022-08-25 | Ofgem | 3.2.91 | Correction to references. | References to be updated to 3.2.86, 3.2.88, 3.2.89 |  | References updated | Closed
2 | 2022-09-05 | ENWL | Title and throughout | Moorside' to be replaced with 'West Coast of Cumbria' | Update throughout |  | Updated | Closed
3 | 2022-09-18 | ENWL | Inclusion of an early notification |  | 1. ENWL/NGET receive application for connection at Moorside, which ENWL considers warrants the commencement of early preparatory work for the connection 2. ENWL submit ‘early notification’ to Ofgem, setting out: a. Request for low materiality development funding for Moorside - @Darley, David, would be good to understand what sort of materiality you’d expect to see here, taking in to account later triggers for construction works b. Request for Ofgem to confirm future timing of triggering the Moorside re-opener 3. Ofgem confirms: a. Approval of £[y]m of development funding; and b. That it will trigger main re-opener if [x] happens (e.g. submission of LOTI Final Needs Case or some form of generator milestone such as FID – to be considered, would adapt depending on circumstances) 4. [x] happens, Ofgem triggers re-opener for ENWL to request full project construction costs |  | Early inclusion agreed and now Incorporated | Closed
4 | 2022-10-27 | ENWL | General comment | We note that this version of the licence condition does not currently reflect agreed directional changes discussed as part of our bilateral engagement with Ofgem. This is referred to in issues log item 3 and we will continue to liaise with Ofgem to enact these necessary changes in the coming weeks. |  |  | Update submitted 23/11 and changes dicussed have been incoroprated. | Closed
5 | 2022-10-27 | ENWL | 3.2.97 (a) - Definition of West Coast of Cumbria is missing | We have reviewed the definition of the term set out in column D and provide detailed comments on this in Annex 5 to our response 'Annex 5: Definitions'. Please refer here for ENWL definitional views and comments. |  |  | West Coast of Cumbria Reopener is now defined | Closed
6 | 2022-10-27 | ENWL | 3.2.97 (a) - Definition of "Initial Needs Case" and embedded definition of "Relevant Network Licensee" | We have reviewed the definition of the term set out in column D and provide detailed comments on this in Annex 5 to our response 'Annex 5: Definitions'. Please refer here for ENWL definitional views and comments. |  |  | Intial needs case is defined. Relavent network licensee also defined but no longer used in this chapter | Closed
7 | 2022-10-27 | ENWL | General | We provide further information within our Annex 2 document as part of our consultation response. |  |  | Noted and incorporated. | Closed
8 | 2023-01-17 | ENWL | 3.2.97 | Delete "where" at the end of first line, which is superflous | delete "where" |  | Edit updated | Closed
9 | 2023-01-17 | ENWL | 3.2.97(b)(i) | "West Coast of Cumbria" is not a defined term, we suggest this needs to be defined or decapitalised. |  |  | Edit updated | Closed
10 | 2023-01-17 | ENWL | 3.2.97(b)(iii) | "lead developer" needs to be defined for transparency around operability of the licence condition |  |  | Changed to developer. Disagree that this needs defining, intent is clear and defining the term now may create issues in future, given uncertainty around who/how many developers may work on Moorside | Closed
11 | 2023-01-17 | ENWL | 3.2.98 | There is no explanation of the process to ask Ofgem to trigger a reopener. There should be a clause before or after 3.2.98 setting out that, if one of the circumstances in 3.2.97 are met, ENWL submits evidence seeking approval to trigger (as per reopener guidance) As the FD confirms that the licensee can trigger the re-opener at any time, clause 3.2.98 requires Ofgem permission to apply under the reopener at a time it directs. However there is no provision in the licence to allow this to happen. In line with the issue number 2 raised on 1.3 Part B the option for a licensee to request a window should extend to this condition as we see no difference between this and any other re-opener condition where the licensee can request the Authority to direct a window. | “When determined by the Authority considering any request by the licensee“ This could be brought ahead of 3.2.98 to note the order of how things would work i.e. the licensee can request a window at any point in the price review and this should be considered by the authority. or 'Redraft to say "The process the Authority will follow in making a modification by direction or By reference to any additional wording which may be added to 1.3 in response to our issue |  | Disagree that a change is needed. This is an Authority triggered re-opener. We do not consider it is necessary to set out in licence how engagement may occur prior to that trigger, especially as this is detailed indicatively in Guidance and may vary. | Closed
12 | 2023-01-17 | ENWL | 3.2.99 | Uncessary wording as the wording is already set out in 3.2.97. Suggest delete “associated with new nuclear generation seeking to connect at Moorside Nuclear Site” | delete “associated with new nuclear generation seeking to connect at Moorside Nuclear Site” |  | deleted | Closed
13 | 2023-01-17 | ENWL | 3.2.100 | As above, uncessary wording as the wording is already set out in 3.2.97. Suggest delete “associated with new nuclear generation seeking to connect at Moorside Nuclear Site” | delete “associated with new nuclear generation seeking to connect at Moorside Nuclear Site” |  | deleted | Closed
14 | 2023-01-17 | ENWL | 3.2.101 | As above, uncessary wording as the wording is already set out in 3.2.97. Suggest delete “associated with new nuclear generation seeking to connect at Moorside Nuclear Site” | delete “associated with new nuclear generation seeking to connect at Moorside Nuclear Site” |  | deleted | Closed
15 | 2023-01-17 | ENWL | 3.2.102(b) | reference to 3.2.98 is needed here. | (b) if the modification has been requested by the licensee under paragraph 3.2.98, where the requirements in paragraphs 3.2.99 and 3.2.100 have been met; and |  | Edit updated | Closed