## Cover
We have published this workbook in conjuction with the RIIO-2 Re-opener Applications 2025 Draft Determinations. It contains the tables used in the core document and annexes.
Title | Information
Publisher | Ofgem - Small and Medium Sized Projects
Version | 1
Publication date | 2025-07-18
Filename | RIIO-2 Re-opener Applications 2025 Draft Determinations - Data File
Price Base For Costs (ET/GT/GD) | 2018/19
Price Base For Costs (ED) | 2020/21
Cover table Licencees
Sector_Group | Network Name | Sector Group Short | Sector | Network Short Name
National Grid Electricity Transmission | National Grid Electricity Transmission | ET_NGrid | ET | NGET
Scottish Hydro Electric Transmission | Scottish Hydro Electric Transmission | ET_SSE | ET | SHET
SP Transmission | SP Transmission | ET_SPEN | ET | SPT
National Gas Transmission | National Gas Transmission | GT_NGas | GT | NGT
Electricity North West | Electricity North West | ED_ENWL | ED | ENWL
Northern Powergrid | Northern Powergrid - Northern | ED_NPG | ED | NPGN
Northern Powergrid | Northern Powergrid - Yorkshire | ED_NPG | ED | NPGY
National Grid Electricity Distribution | National Grid Electricity Distribution - West Midlands | ED_NGrid | ED | WMID
National Grid Electricity Distribution | National Grid Electricity Distribution - East Midlands | ED_NGrid | ED | EMID
National Grid Electricity Distribution | National Grid Electricity Distribution - South Wales | ED_NGrid | ED | SWALES
National Grid Electricity Distribution | National Grid Electricity Distribution - South West | ED_NGrid | ED | SWEST
SP Energy Networks | SP Energy Networks - Distribution | ED_SPEN | ED | SPD
SP Energy Networks | SP Energy Networks - Manweb | ED_SPEN | ED | SPMW
Scottish and Southern Energy | SSEN Distribution - Hydro | ED_SSE | ED | SSEH
Scottish and Southern Energy | SSEN Distribution - Southern | ED_SSE | ED | SSES
UK Power Networks | UK Power Networks - East | ED_UKPN | ED | EPN
UK Power Networks | UK Power Networks - London | ED_UKPN | ED | LPN
UK Power Networks | UK Power Networks - South East | ED_UKPN | ED | SPN
Cadent | Cadent - East of England | GD_Cad | GD | EoE
Cadent | Cadent - London | GD_Cad | GD | Lon
Cadent | Cadent - North West | GD_Cad | GD | NW
Cadent | Cadent - West Midlands | GD_Cad | GD | WM
Northern Gas Networks | Northern Gas Networks | GD_NGN | GD | NGN
Scotia Gas Networks | Scotia Gas Networks - Scotland | GD_SGN | GD | Sc
Scotia Gas Networks | Scotia Gas Networks - Southern | GD_SGN | GD | So
Wales & West Utilities | Wales and West Utilities | GD_WWU | GD | WWU
Opex Escalator/Indirect Scaler rates
Sector_Group | OE_IS_Rate
National Grid Electricity Transmission | 16.89%
Scottish Hydro Electric Transmission | 10.81%
SP Transmission | 13.42%
National Gas Transmission
Electricity North West | 10.8%
Northern Powergrid | 10.8%
National Grid Electricity Distribution | 10.8%
SP Energy Networks | 10.8%
Scottish and Southern Energy | 10.8%
UK Power Networks | 10.8%
Cadent | 0%
Northern Gas Networks | 0%
Scotia Gas Networks | 0%
Wales & West Utilities | 0%

## Applications
Applications subject to this consultation/decision | Mechanism | Opex Escalator/Indirect Scaler
NGET MSIP 2025 | ET Medium Sized Investment Projects (MSIP) | Yes
SPT MSIP 2025 | ET Medium Sized Investment Projects (MSIP) | Yes
SHET MSIP 2025 | ET Medium Sized Investment Projects (MSIP) | Yes
ENWL Load Related Expenditure Re-opener 2025 | ED Load Related Expenditure Re-opener | Yes
SHET Gremista GSP 2024 | ET Large Onshore Transmission Investments (LOTI) | No
SSEN-D Orkney Whole System Uncertainty Mechanism (HOWSUM) 2025 | ED Hebrides and Orkney – (SSEN only) | No
Cadent HSE Policy Re-opener 2023 | GD HSE policy Re-opener | No
NGN HSE Policy Re-opener 2023 | GD HSE policy Re-opener | No
SGN HSE policy Re-opener 2023 | GD HSE policy Re-opener | No
WWU HSE policy Re-opener 2023 | GD HSE policy Re-opener | No
Cadent Specified Streetworks Costs Re-opener 2023 | GD Specified Streetworks Costs Re-opener | No
NGN Specified Streetworks Costs Re-opener 2023 | GD Specified Streetworks Costs Re-opener | No
SGN Specified Streetworks Costs Re-opener 2023 | GD Specified Streetworks Costs Re-opener | No
WWU Specified Streetworks Costs Re-opener 2023 | GD Specified Streetworks Costs Re-opener | No
Cadent Net Zero Pre-construction Work and Small Net Zero Projects Reopener | GD Net zero pre-construction works and small net zero projects re-opener | No

## Contents
Sheet | Tab Name | Worksheet Title | Link
1 | Cover | Cover Sheet | Click to go to worksheet
2 | Applications | Applications | Click to go to worksheet
3 | Contents | Contents | Click to go to worksheet
Tables and Figures in Overview Document
4 | Table1_Licensees | Table 1: Regulated network companies | Click to go to worksheet
5 | Table2_Reopener_Applications | Table 2: Re-opener applications subject to this consultation | Click to go to worksheet
6 | Table3_DDs_Summary | Table 3: Summary of Draft Determinations | Click to go to worksheet
7 | Table4_DD_Consumer_Cost | Table 4: Estimated total amount to be paid by customers through their bills for these Draft Determinations | Click to go to worksheet
8 | Table5_Consultation_Stages | Table 5: Consultation Stages | Click to go to worksheet
9 | Table6_DDReview | Table 6: Decision implementation overview | Click to go to worksheet
10 | Overview_A2 | Appendix 2: Re-opener mechanisms overview | Click to go to worksheet
11 | Overview_A3 | Appendix 3: Network companies published re-opener applications | Click to go to worksheet
Tables and Figures in ET Annex
12 | TableET1_DD_Summary | Table ET1 Draft Determinations on the ET Re-opener submissions in 2025 | Click to go to worksheet
13 | TableET2_MSIP_DD_Summary | Table ET2 Draft Determinations on the MSIP Projects in 2025 | Click to go to worksheet
14 | TableET3_NGET_Draft_Det | Table ET3 Draft Determinations on Needs Case and Optioneering on NGET's 2025 MSIPs | Click to go to worksheet
15 | TableET4_NGET_ET2 | Table ET4 Summary of Proposed ET2 Adjustments on NGET's 2025 MSIPs | Click to go to worksheet
16 | TableET5_NGET_ET3 | Table ET5 Summary of Proposed ET3 Adjustments on NGET's 2025 MSIPs | Click to go to worksheet
17 | TableET6_SHET_Draft_Det | Table ET6 Draft Determinations on Needs Case and Optioneering on SHET's 2025 MSIPs | Click to go to worksheet
18 | TableET7_SHET_ET2 | Table ET7 Summary of Proposed ET2 Adjustments on SHET's 2025 MSIPs | Click to go to worksheet
19 | TableET8_SHET_ET3 | Table ET8 Summary of Proposed ET3 Adjustments on SHET's 2025 MSIPs | Click to go to worksheet
20 | TableET9_SPT_Draft_Det | Table ET9 Draft Determinations on Needs Case and Optioneering on SPT's 2025 MSIPs | Click to go to worksheet
21 | TableET10_SPT_ET2 | Table ET10 Summary of Proposed ET2 Adjustments on SPT's 2025 MSIPs | Click to go to worksheet
22 | TableET11_SPT_ET3 | Table ET11 Summary of Proposed ET3 Adjustments on SPT's 2025 MSIPs | Click to go to worksheet
23 | TableET12_LOTI_1 | Table ET12 Summary of SHET’s Gremista GSP Total Project Costs | Click to go to worksheet
24 | TableET13_LOTI_2 | Table ET13 Summary of Proposed ET2 Adjustments on SHET’s Gremista GSP | Click to go to worksheet
25 | ET_A5_MSIP_Direction_NGET | Appendix 1 Medium Sized Investment Project Price Control Deliverable (£m) | Click to go to worksheet
26 | ET_A5_MSIP_Direction_SHET | Appendix 1 Medium Sized Investment Project Price Control Deliverable (£m) | Click to go to worksheet
27 | ET_A5_MSIP_Direction_SPT | Appendix 1 Medium Sized Investment Project Price Control Deliverable (£m) | Click to go to worksheet
28 | ET_A6_Appendix2 | Appendix 2 of Special Condition 3.13 Large onshore transmission investment Re-opener (LOTIAt and LOTIREt) | Click to go to worksheet
|  | Tables and Figures in ED Annex | Click to go to worksheet
29 | TableED1_DD_Summary | Table ED1: Draft Determinations for the re-openers in ED | Click to go to worksheet
30 | TableED2_HOWSUM_Projects | Table ED2: Draft Determinations on the Hebrides and Orkney Re-opener submissions in 2025 (£m, 2020/21) | Click to go to worksheet
31 | TableED3_ENWL_LRE_Request | Table ED3: Funding request from ENWL | Click to go to worksheet
32 | TableED4_LRE_EJP_Assessment | Table ED4: Draft Determinations on Needs Case on EJPs | Click to go to worksheet
33 | TableED5_LRE_DD_Summmary | Table ED5: Model Costs and Ofgem’s Draft Determinations | Click to go to worksheet
34 | ED_A5_LRE_Direction | Appendix 1: Uncertain Costs without Evaluative Price Control Deliverables allowances (£m) | Click to go to worksheet
35 | ED_A6_HOWSUM_Direction | Appendix 1: Uncertain Costs without Evaluative Price Control Deliverables allowances (£m) | Click to go to worksheet
|  | Tables and Figures in GD Annex | Click to go to worksheet
36 | TableGD1_GD_Reopeners | Table GD1: GD re-opener mechanisms subject to this decision | Click to go to worksheet
37 | TableGD2_DDs_Summary | Table GD2: Summary of our GD Draft Determinations | Click to go to worksheet
38 | TableGD3_HSE_DD_Summary | Table GD3: applications received and summary of our DDs | Click to go to worksheet
39 | TableGD3a_HSE_Benchmarking | Table GD3a: HSE Policy benchmarking | Click to go to worksheet
40 | TableGD4_Streetworks_DD_Summary | Table GD4: applications received and summary of our DDs | Click to go to worksheet
41 | TableGD4a_Cadent_Costs | Table GD4a: Summary of Cadent’s request under the Specified Streetworks Costs Re-opener and Ofgem’s DDs (£m, 2018/19 prices) | Click to go to worksheet
42 | TableGD4b_NGN_Costs | Table GD4b: Summary of NGN’s request under the Specified Streetworks Costs Re-opener and Ofgem’s DDs (£m, 2018/19 prices) | Click to go to worksheet
43 | TableGD4c_SGN_Costs | Table GD4c: Summary of SGN’s request under the Specified Streetworks Costs Re-opener and Ofgem’s DDs (£m, 2018/19 prices) | Click to go to worksheet
44 | TableGD4d_WWU_Costs | Table GD4d: Summary of WWU’s request under the Specified Streetworks Costs Re-opener and Ofgem’s DDs (£m, 2018/19 prices) | Click to go to worksheet
45 | TableGD5_NetZero_DD_Summary | Table GD5: applications received and summary of our DDs | Click to go to worksheet
46 | TableGD5a_NetZero_Cadent_Costs | Table GD5a: Cost assessment for Cadent's NZASP project (£m, 2018/19 prices) | Click to go to worksheet
47 | TableGD5b_NetZero_Deliverables | Table GD5b: Cadent's proposed project deliverables | Click to go to worksheet
48 | GD_A1_Annex1 | Annex 1: SpC 3.17 HSE Policy Re-opener REPt | Click to go to worksheet
49 | GD_A1_Annex2 | Annex 2: SpC 3.24 Specified Streetworks Costs Re-opener STWt | Click to go to worksheet
50 | GD_A2_Annex1 | Annex 1: SpC 3.9 Net Zero Pre-construction Work and Small Net Zero Projects (£m, 2018/19 prices) | Click to go to worksheet
51 | GD_A2_Annex2 | Annex 2: Project deliverables | Click to go to worksheet

## Overview_Document>>
The following worksheets contain the tables in the Overview Document

## Table1_Licensees
Table 1: Regulated network companies
Sector | Company Group | Sector Group | Network | Network Short Name
ET | National Grid | National Grid Electricity Transmission | National Grid Electricity Transmission | NGET
ET | Scottish and Southern Energy | Scottish Hydro Electric Transmission | Scottish Hydro Electric Transmission | SHET
ET | SP Energy Networks | SP Transmission | SP Transmission | SPT
GT | National Gas | National Gas Transmission | National Gas Transmission | NGGT
ED | Electricity North West | Electricity North West | Electricity North West | ENWL
ED | Northern Powergrid | Northern Powergrid | Northern Powergrid - Northern | NPGN
ED | Northern Powergrid | Northern Powergrid | Northern Powergrid - Yorkshire | NPGY
ED | National Grid | National Grid Electricity Distribution | National Grid Electricity Distribution - West Midlands | WMID
ED | National Grid | National Grid Electricity Distribution | National Grid Electricity Distribution - East Midlands | EMID
ED | National Grid | National Grid Electricity Distribution | National Grid Electricity Distribution - South Wales | SWALES
ED | National Grid | National Grid Electricity Distribution | National Grid Electricity Distribution - South West | SWEST
ED | SP Energy Networks | SP Energy Networks | SP Energy Networks - Distribution | SPD
ED | SP Energy Networks | SP Energy Networks | SP Energy Networks - Manweb | SPMW
ED | Scottish and Southern Energy | Scottish and Southern Energy | SSEN Distribution - Hydro | SSEH
ED | SSES | SSES | SSEN Distribution - Southern | SSES
ED | UK Power Networks | UK Power Networks | UK Power Networks - East | EPN
ED | UK Power Networks | UK Power Networks | UK Power Networks - London | LPN
ED | UK Power Networks | UK Power Networks | UK Power Networks - South East | SPN
GD | Cadent | Cadent | Cadent - East of England | EoE
GD | Cadent | Cadent | Cadent - London | Lon
GD | Cadent | Cadent | Cadent - North West | NW
GD | Cadent | Cadent | Cadent - West Midlands | WM
GD | Northern Gas Networks | Northern Gas Networks | Northern Gas Networks | NGN
GD | Scotia Gas Network | Scotia Gas Networks | Scotland Gas Network | Sc
GD | Scotia Gas Network | Scotia Gas Networks | Southern Gas Network | So
GD | Wales & West Utilities | Wales & West Utilities | Wales & West Utilities | WWU

## Table2_Reopener_Applications
Table 2: Re-opener applications subject to this consultation
Sector | Re-opener Mechanism | No. of companies | No. of projects | Price Base* | Company forecast cost £m
ET | ET Medium Sized Investment Projects (MSIP) | 0 | 24 | 2018/19 | 294.1338
ET | ET Large Onshore Transmission Investments (LOTI) | 0 | 1 | 2018/19 | 104.6153
ED | ED Hebrides and Orkney – (SSEN only) | 0 | 6 | 2020/21 | 158.59
ED | ED Load Related Expenditure Re-opener | 0 | 1 | 2020/21 | 201.6
GD | GD HSE policy Re-opener | 0 | 8 | 2018/19 | 122.2206
GD | GD Specified Streetworks Costs Re-opener | 0 | 4 | 2018/19 | 72.396
GD | GD Net zero pre-construction works and small net zero projects re-opener | 0 | 4 | 2018/19 | 20.48
Sector |  | Check: no. of projects | No. of projects | Check: company forecast | Company forecast cost £m
ET |  | OK | 25 | OK | 398.7491
ED |  | OK | 7 | OK | 360.19
GD |  | OK | 16 | OK | 215.0966
974.0357

## Table3_DDs_Summary
Table 3: Summary of our Draft Determinations | [8 empty] | Reconciliation against Mechanism Tables: Cost Adjustments
Sector | Sector Group | Company Requested Number of Projects | Company Requested Forecast costs £m | Ofgem’s DD - Projects Approved* | Ofgem’s DD - Projects Not Approved | Ofgem’s DD - Cost adjustment £m | Ofgem’s DD - Allowances £m |  | Total | ED Hebrides and Orkney – (SSEN only) | ED Load Related Expenditure Re-opener | ET Large Onshore Transmission Investments (LOTI) | ET Medium Sized Investment Projects (MSIP) | GD HSE policy Re-opener | GD Net zero pre-construction works and small net zero projects re-opener | GD Specified Streetworks Costs Re-opener
ET | National Grid Electricity Transmission | 13 | 204.7649 | 11 | 2 | -82.0985 | 122.6664 | OK | -82.0985 | N/A | N/A | N/A | -82.0985 | N/A | N/A | N/A
ET | Scottish Hydro Electric Transmission | 5 | 112.5277 | 5 | 0 | -27.5188 | 85.0089 | OK | -27.5192 | N/A | N/A | -25.266 | -2.2532 | N/A | N/A | N/A
ET | SP Transmission | 7 | 81.4565 | 7 | 0 | -7.1932 | 74.2633 | OK | -7.1932 | N/A | N/A | N/A | -7.1932 | N/A | N/A | N/A
ET | Total | 25 | 398.7491 | 23 | 2 | -116.8105 | 281.9386 | OK | -116.811 | 0 | 0 | -25.266 | -91.545 | 0 | 0 | 0
GT | National Gas Transmission | 0 | 0 | 0 | 0 | 0 | 0 | OK | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GT | Total | 0 | 0 | 0 | 0 | 0 | 0 | OK | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ED | Electricity North West | 1 | 201.6 | 1 | 0 | -108.495 | 93.105 | OK | -108.495 | N/A | -108.495 | N/A | N/A | N/A | N/A | N/A
ED | Northern Powergrid | 0 | 0 | 0 | 0 | 0 | 0 | OK | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ED | National Grid Electricity Distribution | 0 | 0 | 0 | 0 | 0 | 0 | OK | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ED | SP Energy Networks | 0 | 0 | 0 | 0 | 0 | 0 | OK | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ED | Scottish and Southern Energy | 6 | 158.59 | 4 | 2 | -150.7 | 7.89 | OK | -150.7 | -150.7 | N/A | N/A | N/A | N/A | N/A | N/A
ED | UK Power Networks | 0 | 0 | 0 | 0 | 0 | 0 | OK | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ED | Total | 7 | 360.19 | 5 | 2 | -259.195 | 100.995 | OK | -259.195 | -150.7 | -108.495 | 0 | 0 | 0 | 0 | 0
GD | Cadent | 9 | 65.7239 | 8 | 1 | -21.2379 | 44.486 | OK | -21.2379 | N/A | N/A | N/A | N/A | -1.4879 | -4.1 | -15.65
GD | Northern Gas Networks | 2 | 33.69 | 2 | 0 | -18.566 | 15.124 | OK | -18.566 | N/A | N/A | N/A | N/A | -5.2144 | N/A | -13.3516
GD | Scotia Gas Networks | 3 | 65.6198 | 3 | 0 | -25.2789 | 40.3409 | OK | -25.2789 | N/A | N/A | N/A | N/A | -20.2119 | N/A | -5.067
GD | Wales & West Utilities | 2 | 50.0628 | 2 | 0 | -23.485 | 26.5778 | OK | -23.485 | N/A | N/A | N/A | N/A | -1.042 | N/A | -22.443
GD | Total | 16 | 215.0966 | 15 | 1 | -88.5679 | 126.5287 | OK | -88.5679 | 0 | 0 | 0 | 0 | -27.9563 | -4.1 | -56.5116
* or partially approved

## Table4_DD_Consumer_Cost
Table 4: Estimated total amount to be paid by customers through their bills for these Draft Determinations
Sector | Company | Price Base | Paid by Consumers: Reopener Allowances (£m) | Paid by Consumers: Additional Allowances (£m) | Paid by Consumers: Company Debt Repayments | Paid by Consumers: Company Shareholder Return | Total Paid by Consumers | Present Value of Total Paid by Consumers
ET | National Grid Electricity Transmission | 2018/19 | 206.513 | 34.881 | 47.2395 | 85.3709 | 374.0045 | 216.8521
ET | Scottish Hydro Electric Transmission | 2018/19 | 90.086 | 1.161 | 15.5998 | 32.27 | 139.1169 | 82.8929
ET | SP Transmission | 2018/19 | 113.99 | 15.298 | 25.2905 | 45.7048 | 200.2833 | 115.3319
ET | Sector Total | 2018/19 | 410.589 | 51.34 | 88.1299 | 163.3458 | 713.4047 | 415.0769
GT | National Gas Transmission | 2018/19 | 0 | 0 | 0 | 0 | 0 | 0
GT | Sector Total | 2018/19 | 0 | 0 | 0 | 0 | 0 | 0
ED | Electricity North West | 2020/21 | 93.105 | 10.055 | 36.4234 | 42.1914 | 181.7748 | 103.764
ED | Northern Powergrid | 2020/21 | 0 | 0 | 0 | 0 | 0 | 0
ED | National Grid Electricity Distribution | 2020/21 | 0 | 0 | 0 | 0 | 0 | 0
ED | SP Energy Networks | 2020/21 | 0 | 0 | 0 | 0 | 0 | 0
ED | Scottish and Southern Energy | 2020/21 | 7.89 | 0 | 2.7857 | 3.2269 | 13.9026 | 7.6732
ED | UK Power Networks | 2020/21 | 0 | 0 | 0 | 0 | 0 | 0
ED | Sector Total | 2020/21 | 100.995 | 10.055 | 39.2091 | 45.4183 | 195.6774 | 111.4371
GD | Cadent | 2018/19 | 44.485 | 0 | 7.821 | 12.3188 | 64.6248 | 41.0993
GD | Northern Gas Networks | 2018/19 | 15.124 | 0 | 2.747 | 4.1887 | 22.0597 | 14.3074
GD | Scotia Gas Network | 2018/19 | 40.338 | 0 | 7.1513 | 11.1704 | 58.6597 | 38.172
GD | Wales & West Utilities | 2018/19 | 26.578 | 0 | 4.8268 | 7.36 | 38.7648 | 25.4026
GD | Sector Total | 2018/19 | 126.525 | 0 | 22.546 | 35.0379 | 184.1089 | 118.9814
All | All Sectors Total | 2018/19 | 634.3811 | 61.0238 | 148.4377 | 242.1254 | 1085.9681 | 641.382
All | All Sectors Total | 2020/21 | 658.6949 | 63.3627 | 154.1269 | 251.4054 | 1127.5899 | 665.9642
All | All Sectors Total | 2024/25 | 815.4672 | 78.4433 | 190.8098 | 311.241 | 1395.9613 | 824.4666

## Table5_Consultation_Stages
Table 5: Consultation Stages
Stage 1 | Stage 2 | Stage 3 | Stage 4
Consultation open (Draft Determinations) | Consultation closes (awaiting decision). Deadline for responses | Responses reviewed and published | Final Determinations
2025-07-18 | 2025-08-26 | Autumn 2025 | By the end of 2025

## Table6_DDReview
Table 6: Decision implementation overview
Sector | Network company | Licence condition/ Reopener applications subject to this decision | Direction/ licence modification
ET | NGET | SpC: 3.14 Medium Sized Investment Projects Re-opener and Price Control Deliverable (MSIPREt) | Licence modification
ET | SPT | SpC: 3.14 Medium Sized Investment Projects Re-opener and Price Control Deliverable (MSIPREt) | Licence modification
ET | SHET | SpC: 3.14 Medium Sized Investment Projects Re-opener and Price Control Deliverable (MSIPREt) | Licence modification
ED | SSEH | SpC: 3.2 (Hebrides and Orkney Re-opener) Part O | Direction
ED | ENWL | SpC: 3.2 (Load Related Expenditure Re-opener (LREt)) Part J | Licence modification
GD | Cadent | SpC: 3.17 (HSE policy Re-opener (REPt)) and SpC: 3.24 (Specified Streetworks Costs Re-opener) (STWt) | Direction
GD | Northern Gas Networks | SpC: 3.17 (HSE policy Re-opener (REPt)) and SpC: 3.24 (Specified Streetworks Costs Re-opener) (STWt) | Direction
GD | SGN (Scotland Gas Network) | SpC: 3.17 (HSE policy Re-opener (REPt)) and SpC: 3.24 (Specified Streetworks Costs Re-opener) (STWt) | Direction
GD | Southern Gas Networks | SpC: 3.17 (HSE policy Re-opener (REPt)) and SpC: 3.24 (Specified Streetworks Costs Re-opener) (STWt) | Direction
GD | WWU | SpC: 3.17 (HSE policy Re-opener (REPt)) and SpC: 3.24 (Specified Streetworks Costs Re-opener) (STWt) | Direction
GD | Cadent | SpC: 3.9 (Net Zero Pre-construction work and Small Net Zero Projects Re-opener) Part C | Direction

## Overview_A2
Appendix 2: Re-opener mechanisms overview
Re-opener Mechanism | Sector | Purpose | Benefits | Licence Condition | Chapter reference | Link to the relevant FD document
Medium Sized Investment Projects (MSIP) | ET | To ensure that ETOs are able to undertake necessary investments in the transmission network, funding for which has not been provided in RIIO baseline allowances. | Allows Ofgem to scrutinise, on behalf of consumers, the need for and cost of projects with more unusual characteristics. | Special condition 3.14 | 4.49 - 4.58 of RIIO-2 Final Determinations Electricity Transmission System Annex (REVISED) | RIIO-2 Final Determinations Electricity Transmission System Annex (REVISED) (ofgem.gov.uk)
Large Onshore Transmission Investment (LOTI) | ET | To ensure that TOs are funded to undertake necessary large investments on the transmission network. | Allows Ofgem to scrutinise, on behalf of consumers, large transmission investments at the point at which needs case and efficient costs can be scrutinised more effectively. | Special Condition 3.13 | 4.29 - 4.34 of RIIO-2 Final Determinations Electricity Transmission System Annex (REVISED) | RIIO-2 Final Determinations Electricity Transmission System Annex (REVISED) (ofgem.gov.uk)
Hebrides and Orkney - (SSEN only) | ED | To allow for upward adjustment of ex ante allowances after identification of customer needs once third-party uncertainties have reduced. | The consumer bears less risk of paying for over- or underinvestment in infrastructure needs for the islands. | Special Condition 3.2 | 4.6 - 4.9 of RIIO-ED2 Final Determinations SSEN Annex | RIIO-ED2 Final Determinations SSEN Annex (ofgem.gov.uk)
Load Related Expenditure Re-opener | ED | To enable additional investment in DNOs primary networks, if required. | Ensure networks have sufficient funding to enable net zero and protect consumers from paying higher costs than necessary. | Special Condition 3.2 | 3.21 - 3.32 of RIIO-ED2 Final Determinations Core Methodology | RIIO-ED2 Final Determinations Core Methodology (ofgem.gov.hk)
Health and Safety Executive (HSE) Policy Re-opener | GD | A common re-opener to account for changes in HSE-related policy areas that result in material changes to GDNs' costs during RIIO-GD2. | Provides appropriate protection for consumers, and GDNs, by adjusting funding (upwards or downwards) to account for changes to safety requirements that result from changes in HSE policy or to GDNs' Approved Programmes during the course of RIIO-GD2. | Special Condition 3.17 | 4.15 - 4.18 of the RIIO-2 Final Determinations - GD Sector Annex (REVISED) | RIIO-2 Final Determinations - GD Sector Annex (REVISED)
Net Zero Pre-Construction Work and Small Net Zero Projects (NZASP) Re-opener | GD | To allow GD and GT network companies to undertake design and pre-construction work that is too material for the UIOLI and also to progress Net Zero facilitation projects that aren't material enough for the Net Zero Re-opener. | Enables companies to progress small value, but high impact, Net Zero work in an agile way. | Special Condition 3.9 | 8.27 - 8.32 of RIIO-2 Final Determinations - Core Document | RIIO-2 Final Determinations - Core Document
Specified Streetworks Costs Re-opener | GD | An ongoing re-opener from RIIO-GD1 to recover the efficient costs of complying with new permit and lane rental schemes or new requirements introduced by public bodies after the RIIO-GD2 price control is set. | The mechanism protects customers and GDNs by avoiding the inclusion of uncertain streetworks spend in baseline allowances and providing an opportunity for GDNs to request funding for potential additional efficient costs within period, if they arise | Special Condition 3.24 | 4.52 - 4.55 of RIIO-2 Final Determinations - GD Sector Annex (REVISED) | RIIO-2 Final Determinations - GD Sector Annex (REVISED)

## Overview_A3
Appendix 3: Network companies published re-opener applications
Sector | Company | Re-opener Mechanism | Link to relevant publications
ET | NGET | Medium Sized Investment Projects (MSIP) | Our RIIO-2 business plan ¦ National Grid
ET | SHET | Medium Sized Investment Projects (MSIP) | Medium Sized Investment Projects (MSIP) - SSEN Transmission
ET | SPT | Medium Sized Investment Projects (MSIP) | MSIP Reopeners - SP Energy Networks
ET | SHET | Large Onshore Transmission Investment (LOTI) mechanism | Gremista GSP (Grid Supply Point) and 132kV Connection - SSEN Transmission
ED | SSEN | Hebrides and Orkney Whole System Uncertainty Mechanism (HOWSUM) | Whole system energy solutions for the Scottish Islands - SSEN
ED | ENWL | Load Related Expenditure Re-opener (LREt) | Public information
GD | Cadent | Health and Safety Executive (HSE) Policy Re-opener | Fatigue-Re-opener-Submission-September-2024.pdf
GD | NGN | Health and Safety Executive (HSE) Policy Re-opener | NGN-RIIO-GD2-HSE-Policy-Special-Condition-3.17-Re-opener-Submission-300924-redactedv2.0-2.pdf
GD | SGN | Health and Safety Executive (HSE) Policy Re-opener | SGN HSE Re-opener_30 September 2024_Redacted_0.pdf
GD | WWU | Health and Safety Executive (HSE) Policy Re-opener | Microsoft Word - WWU re-opener - Fatigue Final_03.10.2024 redacted revised
GD | Cadent | Net Zero Pre-Construction Work and Small Net Zero Projects (NZASP) Re-opener | Net-Zero-Pre-construction-Work-and-Small-Net-Zero-Projects-Re-opener-Cadent-Vehicle-Based-Advanc.pdf
GD | Cadent | Specified Streetworks Costs Re-opener | Streetworks-Re-opener-Submission-September-2024.pdf
GD | NGN | Specified Streetworks Costs Re-opener | NGN-RIIO-GD2-Specified-Streetworks-Special-Condition-3.24-Re-opener-Submission-300924-1.pdf
GD | SGN | Specified Streetworks Costs Re-opener | SGN Streetworks Re-opener_30 September 2024_Redacted_0.pdf
GD | WWU | Specified Streetworks Costs Re-opener | Microsoft Word - WWU Streetworks re-opener paper redacted revised

## ET_Annex>>
The following worksheets contain the tables and figures in the ET Annex

## TableET1_DD_Summary
Table ET1 Draft Determinations on the ET Re-opener submissions in 2025
Sector Group | Network | Company Requested Number of Projects | Company Requested Forecast costs £m | Ofgem’s DD - Projects Approved* | Ofgem’s DD - Projects Not Approved | Ofgem’s DD - Cost adjustment £m | Ofgem’s DD - Allowances £m
National Grid Electricity Transmission | NGET | 13 | 204.7649 | 11 | 2 | -82.0985 | 122.6664
Scottish Hydro Electric Transmission | SHET | 5 | 112.5277 | 5 | 0 | -27.5188 | 85.0089
SP Transmission | SPT | 7 | 81.4565 | 7 | 0 | -7.1932 | 74.2633
Total |  | 25 | 398.7491 | 23 | 2 | -116.8105 | 281.9386
* We refer to Draft Determinations as ‘Ofgem’s DD’. Projects approved also include partial approval.

## TableET2_MSIP_Projects
Table ET2 Draft Determinations on the MSIP Projects in 2025
Sector Group | Network | Company Requested Project | Company Requested Forecast costs £m | Ofgem’s DD* - Cost adjustment £m | Ofgem’s DD - Allowances £m
National Grid Electricity Transmission | NGET | NGET Central Reactive Voltage - Ironbridge | 8.1218 | -0.22465 | 7.8971
National Grid Electricity Transmission | NGET | NGET Central Reactive Voltage - Willington | 7.8385 | -0.44201 | 7.3965
National Grid Electricity Transmission | NGET | NGET Heysham OPS scheme for ENWL | 1.3229 | -0.62028 | 0.7026
National Grid Electricity Transmission | NGET | NGET Marston Vale (Millbrook) | 20.9419 | -20.9419 | 0
National Grid Electricity Transmission | NGET | NGET Necton 400kV site strategy | 45.0307 | -7.3889 | 37.6418
National Grid Electricity Transmission | NGET | NGET Norwich 400kV site strategy | 28.4517 | -28.4517 | 0
National Grid Electricity Transmission | NGET | NGET OTS - East Anglia | 1.6055 | 0.12042 | 1.7259
National Grid Electricity Transmission | NGET | NGET OTS - Lackenby | 2.8542 | -0.0583 | 2.7959
National Grid Electricity Transmission | NGET | NGET OTS Killingholme | 0.84776 | -0.02275 | 0.82501
National Grid Electricity Transmission | NGET | NGET Pathfinder - East Anglia OTS | 6.7997 | -1.6416 | 5.1581
National Grid Electricity Transmission | NGET | NGET Pathfinder - Yaxley | 6.0674 | -0.27457 | 5.7928
National Grid Electricity Transmission | NGET | NGET Penrhos 132kV site strategy | 17.0344 | -0.81361 | 16.2208
National Grid Electricity Transmission | NGET | NGET Wallend | 57.8484 | -21.3386 | 36.5097
Scottish Hydro Electric Transmission | SHET | SHET Constraint Management Pathfinder (B6) | 0.409 | -0.062 | 0.347
Scottish Hydro Electric Transmission | SHET | SHET Lochluichart and Corriemollie | 1.4855 | -0.46692 | 1.0186
Scottish Hydro Electric Transmission | SHET | SHET North of Beauly DLR (stage 2) | 1.0434 | -0.32232 | 0.72112
Scottish Hydro Electric Transmission | SHET | SHET Tealing bypass | 4.9745 | -1.402 | 3.5725
SP Transmission | SPT | SPT Branxton 400kV Substation | 51.029 | -2.8624 | 48.1666
SP Transmission | SPT | SPT Extension of Sub-Synchronous Oscillation (SSO) Detection Capabilities | 0.236 | -0.00158 | 0.23442
SP Transmission | SPT | SPT Inch Cape Offshore Wind Farm | 3.7702 | -0.06878 | 3.7015
SP Transmission | SPT | SPT SPT-RI-1742 Cockenzie Overload Protection Scheme | 0.406 | -0.0094 | 0.3966
SP Transmission | SPT | SPT-RI 282 Mark Hill SGT4 | 4.295 | 0 | 4.295
SP Transmission | SPT | SPT-RI-302 Glenglass 132kV Substation | 13.5393 | -0.52568 | 13.0136
SP Transmission | SPT | SPT-TOCO 2201 Kilmarnock South H1 | 8.181 | -3.7254 | 4.4556
*We refer to draft determinations as ‘Ofgem’s DD’.

## TableET3_NGET_Draft_Det
Table ET3 Draft Determinations on Needs Case and Optioneering on NGET's 2025 MSIPs
No. of Project assessed | Needs Case approved | Need case rejected or partially rejected | Optioneering approved | Optioneering rejected or partially rejected
12 | 12 | 0 | 9 | 3

## TableET4_NGET_ET2
Table ET4 Summary of Proposed ET2 Adjustments on NGET's 2025 MSIPs
Project Name | Funding Request £m | Adjustment – OE £m | Adjustment – RPE £m | Adjustment – Risk £m | Adjustment – Optioneering £m | Adjustment – Low Cost Confidence items £m | Adjustment – Eligibility £m | Ofgem’s DD* £m |  | Reconciliation
NGET Central Reactive Voltage - Ironbridge | 8.1218 | -0.25663 | -0.008823 | 0.040805 | 0 | 0 | 0 | 7.8971 | OK | 8.1218
NGET Central Reactive Voltage - Willington | 7.8385 | -0.062988 | -0.15831 | -0.22071 | 0 | 0 | 0 | 7.3965 | OK | 7.8385
NGET Heysham OPS scheme for ENWL | 1.3229 | 0 | 0 | -0.25542 | 0 | -0.36486 | 0 | 0.7026 | OK | 1.3229
NGET Marston Vale (Millbrook) | 20.9419 | 0 | 0 | 0 | -20.9419 | 0 | 0 | 0 | OK | 20.9419
NGET Necton 400kV site strategy | 45.0307 | -0.15506 | -0.11845 | -7.1155 | 0 | 0 | 0 | 37.6418 | OK | 45.0308
NGET Norwich 400kV site strategy | 28.4517 | 0 | 0 | 0 | 0 | 0 | -28.4517 | 0 | OK | 28.4517
NGET OTS - East Anglia | 1.6055 | 0 | 0 | 0.12041 | 0 | 0 | 0 | 1.7259 | OK | 1.6055
NGET OTS - Lackenby | 2.8542 | -0.0021276 | -0.017891 | -0.038282 | 0 | 0 | 0 | 2.7959 | OK | 2.8542
NGET OTS Killingholme | 0.84776 | -0.0020225 | 0 | -0.020722 | 0 | 0 | 0 | 0.82501 | OK | 0.84775
NGET Pathfinder - East Anglia OTS | 6.7997 | -0.024489 | -0.013845 | -1.6033 | 0 | 0 | 0 | 5.1581 | OK | 6.7997
NGET Pathfinder - Yaxley | 6.0674 | -0.00035816 | -0.036996 | -0.23722 | 0 | 0 | 0 | 5.7928 | OK | 6.0674
NGET Penrhos 132kV site strategy | 17.0344 | -0.48475 | -0.14047 | -0.18839 | 0 | 0 | 0 | 16.2208 | OK | 17.0344
NGET Wallend | 57.8484 | 0 | 0 | -3.0769 | -18.2617 | 0 | 0 | 36.5097 | OK | 57.8484
Total | 204.7649 | -0.98843 | -0.49478 | -12.5952 | -39.2036 | -0.36486 | -28.4517 | 122.666 | OK | 204.7646
RIIO-3
Project Name | Funding Request £m | Adjustment – OE £m | Adjustment – RPE £m | Adjustment – Risk £m | Adjustment – Optioneering £m | Adjustment – Low Cost Confidence items £m | Adjustment – Eligibility £m | Ofgem’s DD* £m
NGET Central Reactive Voltage - Ironbridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NGET Central Reactive Voltage - Willington | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NGET Heysham OPS scheme for ENWL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NGET Marston Vale (Millbrook) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
NGET Necton 400kV site strategy | 10.4004 | -0.020322 | -0.15141 | -3.4186 | 0 | 0 | 0 | 6.81
NGET Norwich 400kV site strategy | 1.7867 | 0 | 0 | 0 | 0 | 0 | -1.7867 | 0
NGET OTS - East Anglia | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NGET OTS - Lackenby | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NGET OTS Killingholme | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NGET Pathfinder - East Anglia OTS | 2.7291 | 0 | -0.016833 | -0.66059 | 0 | 0 | 0 | 2.0516
NGET Pathfinder - Yaxley | 0.28969 | 0 | -0.0042215 | 0 | 0 | 0 | 0 | 0.28547
NGET Penrhos 132kV site strategy | 56.1301 | -0.62516 | -0.90011 | -0.72192 | 0 | 0 | 0 | 53.8829
NGET Wallend | 34.1627 | 0 | 0 | -2.5368 | -10.7727 | 0 | 0 | 20.8156
Total | 105.4986 | -0.64548 | -1.0726 | -7.3379 | -10.7727 | 0 | -1.7867 | 83.8456
Total
Project Name | Funding Request £m | Adjustment – OE £m | Adjustment – RPE £m | Adjustment – Risk £m | Adjustment – Optioneering £m | Adjustment – Low Cost Confidence items £m | Adjustment – Eligibility £m | Ofgem’s DD* £m
NGET Central Reactive Voltage - Ironbridge | 8.1218 | -0.25663 | -0.008823 | 0.040805 | 0 | 0 | 0 | 7.8971
NGET Central Reactive Voltage - Willington | 7.8385 | -0.062988 | -0.15831 | -0.22071 | 0 | 0 | 0 | 7.3965
NGET Heysham OPS scheme for ENWL | 1.3229 | 0 | 0 | -0.25542 | 0 | -0.36486 | 0 | 0.7026
NGET Marston Vale (Millbrook) | 20.9419 | 0 | 0 | 0 | -20.9419 | 0 | 0 | 0
NGET Necton 400kV site strategy | 55.4311 | -0.17538 | -0.26986 | -10.5341 | 0 | 0 | 0 | 44.4518
NGET Norwich 400kV site strategy | 30.2384 | 0 | 0 | 0 | 0 | 0 | -30.2384 | 0
NGET OTS - East Anglia | 1.6055 | 0 | 0 | 0.12041 | 0 | 0 | 0 | 1.7259
NGET OTS - Lackenby | 2.8542 | -0.0021276 | -0.017891 | -0.038282 | 0 | 0 | 0 | 2.7959
NGET OTS Killingholme | 0.84776 | -0.0020225 | 0 | -0.020722 | 0 | 0 | 0 | 0.82501
NGET Pathfinder - East Anglia OTS | 9.5288 | -0.024489 | -0.030678 | -2.2639 | 0 | 0 | 0 | 7.2098
NGET Pathfinder - Yaxley | 6.3571 | -0.00035816 | -0.041218 | -0.23722 | 0 | 0 | 0 | 6.0783
NGET Penrhos 132kV site strategy | 73.1645 | -1.1099 | -1.0406 | -0.91031 | 0 | 0 | 0 | 70.1037
NGET Wallend | 92.0111 | 0 | 0 | -5.6137 | -29.0344 | 0 | 0 | 57.3254
Total | 310.2635 | -1.6339 | -1.5674 | -19.9332 | -49.9763 | -0.36486 | -30.2384 | 206.5116

## TableET5_NGET_ET3
Table ET5 Summary of Proposed ET3 Adjustments on NGET's 2025 MSIPs
Project Name | Funding Request £m | Adjustment – OE £m | Adjustment – RPE £m | Adjustment – Risk £m | Adjustment – Optioneering £m | Adjustment – Low Cost Confidence items £m | Adjustment – Eligibility £m | Ofgem’s DD* £m
NGET Central Reactive Voltage - Ironbridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NGET Central Reactive Voltage - Willington | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NGET Heysham OPS scheme for ENWL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NGET Marston Vale (Millbrook) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NGET Necton 400kV site strategy | 10.4004 | -0.020322 | -0.15141 | -3.4186 | 0 | 0 | 0 | 6.81
NGET Norwich 400kV site strategy | 1.7867 | 0 | 0 | 0 | 0 | 0 | -1.7867 | 0
NGET OTS - East Anglia | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NGET OTS - Lackenby | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NGET OTS Killingholme | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NGET Pathfinder - East Anglia OTS | 2.7291 | 0 | -0.016833 | -0.66059 | 0 | 0 | 0 | 2.0516
NGET Pathfinder - Yaxley | 0.28969 | 0 | -0.0042215 | 0 | 0 | 0 | 0 | 0.28547
NGET Penrhos 132kV site strategy | 56.1301 | -0.62516 | -0.90011 | -0.72192 | 0 | 0 | 0 | 53.8829
NGET Wallend | 34.1627 | 0 | 0 | -2.5368 | -10.7727 | 0 | 0 | 20.8156
Total | 105.4986 | -0.64548 | -1.0726 | -7.3379 | -10.7727 | 0 | -1.7867 | 83.8456

## TableET6_SHET_Draft_Det
Table ET6 Draft Determinations on Needs Case and Optioneering on SHET's 2025 MSIPs
No. of Project assessed | Needs Case approved | Need case rejected or partially rejected | Optioneering approved | Optioneering rejected or partially rejected
4 | 4 | 0 | 4 | 0

## TableET7_SHET_ET2
Table ET7 Summary of Proposed ET2 Adjustments on SHET's 2025 MSIPs
Project Name | Funding Request £m | Adjustment – OE £m | Adjustment – RPE £m | Adjustment – Risk £m | Adjustment – Optioneering £m | Adjustment – Low Cost Confidence items £m | Adjustment – Eligibility £m | Ofgem’s DD* £m |  | Reconciliation
SHET Constraint Management Pathfinder (B6) | 0.409 | -0.078 | 0 | 0.016 | 0 | 0 | 0 | 0.347 | OK | 0.409
SHET Lochluichart and Corriemollie | 1.4855 | -0.47204 | 0 | 0.0051301 | 0 | 0 | 0 | 1.0186 | OK | 1.4855
SHET North of Beauly DLR (stage 2) | 1.0434 | -0.29422 | 0 | -0.028111 | 0 | 0 | 0 | 0.72112 | OK | 1.0434
SHET Tealing bypass | 4.9745 | -1.3726 | 0 | -0.029362 | 0 | 0 | 0 | 3.5725 | OK | 4.9745
Total | 7.9124 | -2.2169 | 0 | -0.036343 | 0 | 0 | 0 | 5.6592 | OK | 7.9124
RIIO-3
Project Name | Funding Request £m | Adjustment – OE £m | Adjustment – RPE £m | Adjustment – Risk £m | Adjustment – Optioneering £m | Adjustment – Low Cost Confidence items £m | Adjustment – Eligibility £m | Ofgem’s DD* £m
SHET Constraint Management Pathfinder (B6) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SHET Lochluichart and Corriemollie | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SHET North of Beauly DLR (stage 2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SHET Tealing bypass | 6.169 | -1.0646 | 0 | -0.027808 | 0 | 0 | 0 | 5.0765
Total | 6.169 | -1.0646 | 0 | -0.027808 | 0 | 0 | 0 | 5.0765
Total
Project Name | Funding Request £m | Adjustment – OE £m | Adjustment – RPE £m | Adjustment – Risk £m | Adjustment – Optioneering £m | Adjustment – Low Cost Confidence items £m | Adjustment – Eligibility £m | Ofgem’s DD* £m
SHET Constraint Management Pathfinder (B6) | 0.409 | -0.078 | 0 | 0.016 | 0 | 0 | 0 | 0.347
SHET Lochluichart and Corriemollie | 1.4855 | -0.47204 | 0 | 0.0051301 | 0 | 0 | 0 | 1.0186
SHET North of Beauly DLR (stage 2) | 1.0434 | -0.29422 | 0 | -0.028111 | 0 | 0 | 0 | 0.72112
SHET Tealing bypass | 11.1434 | -2.4373 | 0 | -0.057171 | 0 | 0 | 0 | 8.649
Total | 14.0814 | -3.2815 | 0 | -0.064151 | 0 | 0 | 0 | 10.7357

## TableET8_SHET_ET3
Table ET8 Summary of Proposed ET3 Adjustments on SHET's 2025 MSIPs
Project Name | Funding Request £m | Adjustment – OE £m | Adjustment – RPE £m | Adjustment – Risk £m | Adjustment – Optioneering £m | Adjustment – Low Cost Confidence items £m | Adjustment – Eligibility £m | Ofgem’s DD* £m
SHET Constraint Management Pathfinder (B6) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SHET Lochluichart and Corriemollie | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SHET North of Beauly DLR (stage 2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SHET Tealing bypass | 6.169 | -1.0646 | 0 | -0.027808 | 0 | 0 | 0 | 5.0765
Total | 6.169 | -1.0646 | 0 | -0.027808 | 0 | 0 | 0 | 5.0765

## TableET9_SPT_Draft_Det
Table ET9 Draft Determinations on Needs Case and Optioneering on SPT's 2025 MSIPs
No. of Project assessed | Needs Case approved | Need case rejected or partially rejected | Optioneering approved | Optioneering rejected or partially rejected
6 | 6 | 0 | 5 | 1

## TableET10_SPT_ET2
Table ET10 Summary of Proposed ET2 Adjustments on SPT's 2025 MSIPs
Project Name | Funding Request £m | Adjustment – OE £m | Adjustment – RPE £m | Adjustment – Risk £m | Adjustment – Optioneering £m | Adjustment – Low Cost Confidence items £m | Adjustment – Eligibility £m | Ofgem’s DD* £m |  | Reconciliation
SPT Branxton 400kV Substation | 51.029 | -2.0584 | 0 | -0.804 | 0 | 0 | 0 | 48.1666 | OK | 51.029
SPT Extension of Sub-Synchronous Oscillation (SSO) Detection Capabilities | 0.236 | 0 | 0 | -0.001575 | 0 | 0 | 0 | 0.23442 | OK | 0.236
SPT Inch Cape Offshore Wind Farm | 3.7702 | 0 | 0 | -0.068775 | 0 | 0 | 0 | 3.7015 | OK | 3.7702
SPT SPT-RI-1742 Cockenzie Overload Protection Scheme | 0.406 | 0 | 0 | -0.0094 | 0 | 0 | 0 | 0.3966 | OK | 0.406
SPT-RI 282 Mark Hill SGT4 | 4.295 | 0 | 0 | 0 | 0 | 0 | 0 | 4.295 | OK | 4.295
SPT-RI-302 Glenglass 132kV Substation | 13.5393 | -0.52031 | 0 | -0.0053655 | 0 | 0 | 0 | 13.0136 | OK | 13.5393
SPT-TOCO 2201 Kilmarnock South H1 | 8.181 | 0 | 0 | -0.21038 | -3.515 | 0 | 0 | 4.4556 | OK | 8.181
Total | 81.4565 | -2.5787 | 0 | -1.0995 | -3.515 | 0 | 0 | 74.2633 | OK | 81.4565
RIIO-3
Project Name | Funding Request £m | Adjustment – OE £m | Adjustment – RPE £m | Adjustment – Risk £m | Adjustment – Optioneering £m | Adjustment – Low Cost Confidence items £m | Adjustment – Eligibility £m | Ofgem’s DD* £m
SPT Branxton 400kV Substation | 33.575 | -0.3748 | 0 | -0.90647 | 0 | 0 | 0 | 32.2937
SPT Extension of Sub-Synchronous Oscillation (SSO) Detection Capabilities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPT Inch Cape Offshore Wind Farm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPT SPT-RI-1742 Cockenzie Overload Protection Scheme | 0.258 | 0 | 0 | 0 | 0 | 0 | 0 | 0.258
SPT-RI 282 Mark Hill SGT4 | 4.114 | 0 | 0 | -0.037975 | 0 | 0 | 0 | 4.076
SPT-RI-302 Glenglass 132kV Substation | 1.6077 | 0 | 0 | -0.027823 | 0 | 0 | 0 | 1.5799
SPT-TOCO 2201 Kilmarnock South H1 | 2.812 | 0 | 0 | -0.20585 | -1.087 | 0 | 0 | 1.5192
Total | 42.3667 | -0.3748 | 0 | -1.1781 | -1.087 | 0 | 0 | 39.7268
Total
Project Name | Funding Request £m | Adjustment – OE £m | Adjustment – RPE £m | Adjustment – Risk £m | Adjustment – Optioneering £m | Adjustment – Low Cost Confidence items £m | Adjustment – Eligibility £m | Ofgem’s DD* £m
SPT Branxton 400kV Substation | 84.604 | -2.4332 | 0 | -1.7105 | 0 | 0 | 0 | 80.4603
SPT Extension of Sub-Synchronous Oscillation (SSO) Detection Capabilities | 0.236 | 0 | 0 | -0.001575 | 0 | 0 | 0 | 0.23442
SPT Inch Cape Offshore Wind Farm | 3.7702 | 0 | 0 | -0.068775 | 0 | 0 | 0 | 3.7015
SPT SPT-RI-1742 Cockenzie Overload Protection Scheme | 0.664 | 0 | 0 | -0.0094 | 0 | 0 | 0 | 0.6546
SPT-RI 282 Mark Hill SGT4 | 8.409 | 0 | 0 | -0.037975 | 0 | 0 | 0 | 8.371
SPT-RI-302 Glenglass 132kV Substation | 15.147 | -0.52031 | 0 | -0.033189 | 0 | 0 | 0 | 14.5935
SPT-TOCO 2201 Kilmarnock South H1 | 10.993 | 0 | 0 | -0.41623 | -4.602 | 0 | 0 | 5.9748
Total | 123.8233 | -2.9535 | 0 | -2.2776 | -4.602 | 0 | 0 | 113.9901

## TableET11_SPT_ET3
Table ET11 Summary of Proposed ET3 Adjustments on SPT's 2025 MSIPs
Project Name | Funding Request £m | Adjustment – OE £m | Adjustment – RPE £m | Adjustment – Risk £m | Adjustment – Optioneering £m | Adjustment – Low Cost Confidence items £m | Adjustment – Eligibility £m | Ofgem’s DD* £m
SPT Branxton 400kV Substation | 33.575 | -0.3748 | 0 | -0.90647 | 0 | 0 | 0 | 32.2937
SPT Extension of Sub-Synchronous Oscillation (SSO) Detection Capabilities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPT Inch Cape Offshore Wind Farm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPT SPT-RI-1742 Cockenzie Overload Protection Scheme | 0.258 | 0 | 0 | 0 | 0 | 0 | 0 | 0.258
SPT-RI 282 Mark Hill SGT4 | 4.114 | 0 | 0 | -0.037975 | 0 | 0 | 0 | 4.076
SPT-RI-302 Glenglass 132kV Substation | 1.6077 | 0 | 0 | -0.027823 | 0 | 0 | 0 | 1.5799
SPT-TOCO 2201 Kilmarnock South H1 | 2.812 | 0 | 0 | -0.20585 | -1.087 | 0 | 0 | 1.5192
Total | 42.3667 | -0.3748 | 0 | -1.1781 | -1.087 | 0 | 0 | 39.7268

## TableET12_Gremista_Costs
Table ET12 Summary of SHET’s Gremista GSP Total Project Costs
Categories Cost Breakdown | Total Project Cost (£m)
Project Management | 5.465
Regulatory and Consent | 2.105
Engineering | 10.386
Equipment Procurement | 0.471
Construction – Main and Ancillary Contracts | 78.034
Commissioning and Operations | 0.425
Risk and Contingency | 7.037
Other Direct Costs | 0.692
RIIO-ET2 Total | 104.615
RIIO-ET1 Costs | 0.465
Project Total | 105.08
Reclassified costs
Cost Re-classification | Total Project Cost (£m)
Pre-construction costs | 2.705
Direct costs | 78.506
Risk and contingency | 7.037
Indirect costs | 16.832
Total | 105.08 | OK

## TableET13_Gremista_DD_Adjustm
Table ET13 Summary of Proposed ET2 Adjustments on SHET’s Gremista GSP
Cost Category | Submitted Cost £m | Proposed Adjustment £m | Proposed DD* Allowance £m
Project management | 5.465 | -5.465 | 0
Regulatory and consent | 2.105 | -2.105 | 0
Engineering | 10.386 | -3.136 | 7.25
Equipment Procurement | 0.471 | 0 | 0.471
Construction – Main and Ancillary Contracts | 78.034 | -11.436 | 66.598
Commissioning and Operations | 0.425 | -0.425 | 0
Risk and Contingency | 7.037 | -2.007 | 5.03
Other Direct Costs | 0.692 | -0.692 | 0
RIIO-ET2 Total | 104.615 | -25.266 | 79.349
RIIO-ET1 Costs | 0.465 | -0.465 | 0
Project Total | 105.08 | -25.731 | 79.349
COAE | 2% | 8% | 10%

## ET_A5_MSIP_Direction_NGET
MSIP project | Output | Delivery date | 2021 /22 | 2022 /23 | 2023 /24 | 2024 /25 | 2025 /26 | Total
2025 MSIP Project Total |  |  | 0.001 | 4.006 | 12.539 | 50.771 | 55.351 | 122.668 | OK
[7 empty] | Check against summary total: | 122.666 | OK
NGET Appendix 1
MSIP project | Output | Delivery date | 2021 /22 | 2022 /23 | 2023 /24 | 2024 /25 | 2025 /26 | Total | OK
Sulphur hexafluoride (SF6) Asset Intervention | a) Refurbishment at Barking 400kV Substation | By 31 March 2026 | 0 | 0.058 | 0.956 | 1.449 | 2.005 | 4.468 | OK
Sulphur hexafluoride (SF6) Asset Intervention | b) Refurbishment at Seabank 400kV Substation | By 31 March 2026 | 0 | 0.391 | 1.904 | 2.03 | 1.777 | 6.102 | OK
Sulphur hexafluoride (SF6) Asset Intervention | c) Refurbishment at Sellindge 400kV I Substation | By 31 March 2026 | 0 | 0.405 | 0.762 | 1.344 | 0.034 | 2.545 | OK
Sulphur hexafluoride (SF6) Asset Intervention | d) Refurbishment at West Ham 400kV Substation | By 31 March 2026 | 0 | 0.286 | 1.06 | 2.755 | 2.966 | 7.067 | OK
Sulphur hexafluoride (SF6) Asset Intervention | e) Replacement with HV cable at Monk Fryston 275kV GIB | By 31 March 2026 | 0 | 0.034 | 0.093 | 4.662 | 0.018 | 4.807 | OK
Sulphur hexafluoride (SF6) Asset Intervention | f) Replacement of 427 SF6 filled current transformer listed in the NGET Redacted Information Document | By 31 March 2026 | 0 | 0 | 6.467 | 7.831 | 9.544 | 23.842 | OK
Extreme Weather Resilience | Complete flood protections at 33 sites listed in the NGET Redacted Information Document | By 31 March 2026 | 0 | 0.5 | 0.8 | 0.9 | 0.8266 | 3.0266 | OK
Cellarhead Customer Connection | Complete Cellarhead Customer Connection | By 31 March 2023 | 0.1858 | 0.2494 | 0.0062 | 0 | 0 | 0.4414 | OK
Frodsham Customer Connection | Complete Frodsham Customer Connection | By 31 March 2023 | 0.3385 | 0.1051 | 0 | 0 | 0 | 0.4436 | OK
Lister Drive Customer Connection | Complete Lister Drive Customer Connection | By 31 March 2023 | 0.6056 | 0.0905 | 0 | 0 | 0 | 0.6961 | OK
Melksham Operational Tripping Scheme Phase 2 Project | Complete Melksham Operational Tripping Scheme Phase 2 Project | By 31 March 2025 | 0.1145 | 1.612 | 4.174 | 1.259 | 1.647 | 8.8065 | OK
Pennine Pathfinders | (a) complete 200MVAr shunt reactor project at Stalybridge 400kV substation | (a) By 31 August 2024 | 0 | 1.368 | 3.343 | 0.391 | 0 | 5.102 | OK
Pennine Pathfinders | (b) complete 200MVAr shunt reactor project at Stocksbridge 400kV substation | (b) By 31 August 2024 | 0 | 1.621 | 3.294 | 0.721 | 0 | 5.636 | OK
Pennine Pathfinders | (c) complete 100MVAr shunt reactor project at Bradford West 275kV substation | (c) By 31 August 2024 | 0 | 0.806 | 3.543 | 0.389 | 0 | 4.739 | OK
Leiston 132kV Substation Connection | Complete demand connection for Sizewell C at Leiston 132kV Substation | By 30 June 2026 | 0 | 0 | 0 | 3.526 | 1.557 | 5.083 | OK
Elland 132kV Substation Connection | Complete connection to Northern Powergrid at Elland 132kV Substation | By 24 October 2023 | 0 | 0.036 | 0.041 | 0 | 0 | 0.077 | OK
Willesden 66kV SEPD Connection | Complete demand connection to SEPD at Willesden 66kV substation | By 30 November 2024 | 2.169 | 0.503 | 1.464 | 0.095 | 0 | 4.231 | OK
Willesden Microsoft Data Centre Connection | Complete demand connection to Microsoft Data Centre at Kensal Green 400kV and Willesden 400kV and 66kV substations | By 30 August 2027 | 0 | 0 | 0.811 | 0.845 | 0 | 1.656 | OK
Central Pathfinders – Yaxley | Installation of a substation bay and associated works at Yaxley to connect Conrad Energy’s NESO Pathfinder solutions | By 30 November 2026 | 0 | 0.454 | 0.75 | 0.654 | 3.935 | 5.793 | OK
Central Reactive Voltage Compliance – Ironbridge | Installation of a new 200MVAr shunt reactor unit at Ironbridge | By 31 July 2025 | 0 | 0 | 0.467 | 5.754 | 1.676 | 7.897 | OK
Central Reactive Voltage Compliance – Willington | Installation of a new 200MVAr shunt reactor unit at Willington | By 28 February 2026 | 0 | 0 | 0.448 | 3.428 | 3.521 | 7.397 | OK
Heysham Overload Protection Scheme | Deliver upgrades at Heysham GSP to facilitate the connection of 130.5MW of embedded generation via ENWL’s network | By 31 August 2026 | 0 | 0 | 0.082 | 0.208 | 0.413 | 0.703 | OK
Necton 400kV Substation Connection | Extend the existing 400kV Necton substation by 12 bays and amend the OHL from a double-tee to double turn-in arrangement to connect three offshore windfarms | By 30 April 2027 | 0.001 | 2.983 | 9.288 | 17.876 | 7.494 | 37.642 | OK
East Anglia Operational Tripping System | Deliver upgrades to the East Anglia OTS to facilitate tripping of Viking Link interconnector | By 31 December 2024 | 0 | 0.532 | 0.961 | 0.233 | 0 | 1.726 | OK
Lackenby Operational Tripping System | Deliver a new OTS in the area to facilitate tripping of Dogger Bank C and Sofia windfarms | By 31 January 2026 | 0 | 0.037 | 0.045 | 0.721 | 1.993 | 2.796 | OK
Killingholme Operational Tripping System | Deliver upgrades to the Killingholme OTS to trip the Open Cycle Gas Turbine (OCGT) at VPI Immingham | By 31 October 2025 | 0 | 0 | 0 | 0.411 | 0.414 | 0.825 | OK
Pathfinder East Anglia Operational Tripping System | Deliver upgrades to East Anglia OTS to trip/de-load generation customers at multiple sites as well as upgrade monitoring across the region | By 31 June 2026 | 0 | 0 | 0.078 | 2.029 | 3.051 | 5.158 | OK
Penrhos 132kV Substation Connection | Construct a new 132kV 8-bay substation for installing at Penrhos for connecting both Eclipse Power Networks and Mentor Mon | By 31 June 2028 | 0 | 0 | 0.076 | 0.894 | 15.251 | 16.221 | OK
Wallend 400kV Substation Connection | Construct a new 10-bay 400kV substation and a double circuit turn in off the 4TK OHL route via two new towers to connect two interconnector customers and one BESS facility | By 21 November 2027 | 0 | 0 | 0.344 | 18.563 | 17.603 | 36.51 | OK

## ET_A5_MSIP_Direction_SHET
MSIP project | Output | Delivery date | 2021 /22 | 2022 /23 | 2023 /24 | 2024 /25 | 2025 /26 | Total
2025 MSIP Project Total |  |  | 0 | 0 | 0.136 | 0.606 | 4.916 | 5.658 | OK
[7 empty] | Check against summary total: | 5.6592 | OK
SHET Appendix 1
MSIP project | Output | Delivery date | 2021 /22 | 2022 /23 | 2023 /24 | 2024 /25 | 2025 /26 | Total | OK
B6 constraint management pathfinder | Connection of Corriemoillie, Griffin and Dorenell sites to the B6 Operational Tripping Scheme. | 2026-03-31 | 0 | 0 | 0.136 | 0.173 | 0.038 | 0.347 | OK
Lochluichart and Corriemoillie Connection | Completion of shared works required to connect Lochluichart Extension II Windfarm | 2026-03-31 | 0 | 0 | 0 | 0.015 | 1.003 | 1.019 | OK
North of Beauly Dynamic Line Rating | Completion of the DLR system on the 275kV overhead line circuits from Beauly to Loch Buidhe to Dounreay | 2026-03-31 | 0 | 0 | 0 | 0.418 | 0.303 | 0.721 | OK
Tealing Phase Shifting Transformers Bypass | Installation of a bypass around the Phase Shifting Transformers (PST) on the XT1 feeder and XT2 feeder at Tealing substation | 2027-06-30 | 0 | 0 | 0 | 0 | 3.572 | 3.572 | OK

## ET_A5_MSIP_Direction_SPT
MSIP project | Output | Delivery date | 2021 /22 | 2022 /23 | 2023 /24 | 2024 /25 | 2025 /26 | Total
2025 MSIP Project Total |  |  | 0.043 | 0.065 | 6.486 | 15.036 | 52.633 | 74.263 | OK
[7 empty] | Check against summary total: | 74.2633 | OK
SPT Appendix 1
MSIP project | Output | Delivery date | 2021 /22 | 2022 /23 | 2023 /24 | 2024 /25 | 2025 /26 | Total | OK
Coalburn SGT4 | Installation of Coalburn SGT4 (360MVA) and associated works at Coalburn 400/132kV Substation | 2025-12-31 | 2.124 | 4.314 | 5.147 | 2.09 | 0 | 13.675 | OK
Constraint Management Pathfinder – Line End Open (LEO) Modifications and Operational Tripping Scheme (OTS) Modifications | Completion of the extension of the LEO and OTS systems. | 2023-12-31 | 0 | 0.298 | 1.003 | 0 | 0 | 1.301 | OK
Wishaw-Eccles- Torness- Smeaton Operational Intertrip Scheme (WETSS Scheme) | Completion of the WETSS Scheme, including the associated LEO Scheme extension. | 2023-12-31 | 0.412 | 0.087 | 0.184 | 0 | 0 | 0.683 | OK
Constraint Management OTS | Completion of the OTS at Strathaven 400kV Substation, Middlemuir 132kV Substation, Linnmill 132kV Substation, Moffat 132kV Substation and Arecleoch 132kV Substation | 2025-03-31 | 0 | 0 | 0.245 | 0.755 | 0 | 1 | OK
Enoch Hill Collector Substation and associated 132kV circuit | Completion of the Enoch Hill 132/33kV Collector Substation and associated 132kV circuit | 2026-03-31 | 0.041 | 0.718 | 5.352 | 4.271 | 0.146 | 10.529 | OK
Branxton 400kV Substation Connection | Installation of Branxton 400kV Substation and provision of connection to Eastern HVDC Link | 2032-02-28 | 0.043 | 0.013 | 5.166 | 6.517 | 36.428 | 48.167 | OK
Glenglass 132kV Substation Connection | Delivery of the works required to facilitate the GIS Extension to the existing Glenglass 132/33kV Substation | 2026-07-31 | 0 | 0.052 | 0.734 | 3.811 | 8.417 | 13.014 | OK
Inch Cape Offshore Wind Farm Connection | Delivery of the works required to facilitate the Inch Cape Offshore Wind Farm connections | 2025-12-31 | 0 | 0 | 0.2 | 0.78 | 2.72 | 3.7 | OK
Cockenzie Load Management Scheme | Installation of Load Management Scheme to manage network conditions in the Cockenzie area | 2026-12-31 | 0 | 0 | 0 | 0 | 0.397 | 0.397 | OK
Kilmarnock 400kV substation Connection | Commissioning of Kilmarnock South GIS Bay to feed TOCO-2201 Kilmarnock BESS facility | 2027-03-31 | 0 | 0 | 0.36 | 1.755 | 2.341 | 4.456 | OK
Mark Hill 275kV Substation Connection | Installation of Mark Hill SGT4 (240MVA) and associated works at Mark Hill 275/132kV Substation | 2027-12-31 | 0 | 0 | 0.026 | 2.061 | 2.208 | 4.295 | OK
Sub-Synchronous Oscillation Detection | Completion of the extension of Sub-Synchronous Oscillation (SSO) detection facilities | 2025-12-31 | 0 | 0 | 0 | 0.112 | 0.122 | 0.234 | OK

## ET_A6_Appendix2
Appendix 2 of Special Condition 3.13 Large onshore transmission investment Re-opener (LOTIAt and LOTIREt)
Regulatory Year
LOTI Output | Delivery date | 2020/21 | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26
Construct, energise and make freely and fully available to the ISOP the Shetland HVDC Link | 2024-12-31 | 109.3 | 203.5 | 170.2 | 105.1 | 24.2 | 5.7
Delivery of a demand connection to Gremista GSP from Kergord. The connection will be capable of delivering 49.3MW of demand. | 2026-03-31 |  | 0.2 | 2.3 | 24.6 | 35.2 | 17.1

## ED_Annex>>
The following worksheets contain the tables and figures in the ED Annex

## TableED1_DD_Summary
Table ED1: Draft Determinations for the re-openers in ED
Sector Group | Network | Company Requested Number of Projects | Company Requested Forecast costs £m | Ofgem’s DD - Projects Approved* | Ofgem’s DD - Projects Not Approved | Ofgem’s DD - Cost adjustment £m | Ofgem’s DD - Allowances £m
Electricity North West | ENWL | 1 | 201.6 | 1 | 0 | -108.495 | 93.105
Scottish and Southern Energy | SSEH | 6 | 158.59 | 4 | 2 | -150.7 | 7.89

## TableED2_HOWSUM_Projects
Table ED2: Draft Determinations on the Hebrides and Orkney Re-opener submissions in 2025 (£m, 2020/21)
Company Proposed Project | Company requested - Forecast costs (£m) | Ofgem’s DD - Cost adjustment (£m) | Ofgem’s DD -Allowances (£m)
SSEN Inner Hebridean Islands of Islay and Jura development costs | 104.01
SSEN Inner Hebridean Islands of Mull, Coll and Tiree development costs | 2.07
SSEN Orkney Islands development costs | 17.04
SSEN Outer Hebrides and Skye development costs | 24.62
SSEN Total whole system analysis development costs - HOWSUM | 1.36
SSEN CAI costs development costs - HOWSUM | 9.49
Total | 158.59 | -150.7 | 7.89
Application
SSEN-D Orkney Whole System Uncertainty Mechanism (HOWSUM) 2025

## TableED3_ENWL_LRE_Request
Table ED3: Funding request from ENWL
Template | Cost Category | Funding Request (£m)
CV1 | Primary reinforcement | 113.7
CV2 | Secondary reinforcement | 25.8
CV3 | Fault level reinforcement | 5.5
CV4 | New Transmission Capacity Charges | -
C2 | Connections | 56.6
| Load Related Strategic Investment | -
| Total | 201.6

## TableED4_LRE_EJP_Assessment
Table ED4: Draft Determinations on Needs Case on EJPs
No. of EJPs assessed | Needs Case approved | Needs case rejected or partially rejected | Optioneering approved | Optioneering rejected or partially rejected
18 | 15 | 3 | 15 | 3

## TableED5_LRE_DD_Summmary
¦
Table ED5: Model Costs and Ofgem’s Draft Determinations
Template | Cost Category | Model Costs for ENWL LRE Plan (£m) | Ex ante Funding in ED2 (£m) | Ofgem’s DD (£m)
CV1 | Primary reinforcement | 104.9377 | 44.5 | 60.4377
CV2 | Secondary reinforcement | 3.9 | 6 | -2.1
CV3 | Fault level reinforcement | 19.4899 | 26.1 | -6.6101
CV4 | New Transmission Capacity Charges | - | 0 | -
C2 | Connections | 78.1774 | 36.8 | 41.3774
| Load Related Strategic Investment | - | - | -
| Total | 206.505 | 113.4 | 93.105
| DD Funding Adjustment |  |  | -108.495

## ED_A5_LRE_Direction
Appendix 1: Uncertain Costs without Evaluative Price Control Deliverables allowances (£m)
Column1 | 23/24 | 24/25 | 25/26 | 26/27 | 27/28 | Total allowance (all years)
PSUPt | 0 | 0 | 0 | 0 | 0 | 0
RECt | 0 | 0 | 0 | 0 | 0 | 0
ESRt | 0 | 0 | 0 | 0 | 0 | 0
EVRt | 0 | 0 | 0 | 0 | 0 | 0
SWRt | 0 | 0 | 0 | 0 | 0 | 0
DIGIt | 0 | 0 | 0 | 0 | 0 | 0
SARt | 0 | 0 | 0 | 0 | 0 | 0
LREt | 0 | 0 | 0 | 0 | 0 | 0 |  | Check
|  | 11.894 | 21.913 | 28.604 | 30.694 | 93.105 | OK | 93.105
HVPt | 0 | 0 | 0 | 0 | 0 | 0
WDVt | 0 | 0 | 0 | 0 | 0 | 0
HOt | 0 | 0 | 0 | 0 | 0 | 0
SESt | 0 | 0 | 0 | 0 | 0 | 0
SEFECt | 0 | 0 | 0 | 0 | 0 | 0

## ED_A6_HOWSUM_Direction
Appendix 1: Uncertain Costs without Evaluative Price Control Deliverables allowances (£m)
Column1 | 23/24 | 24/25 | 25/26 | 26/27 | 27/28 | Total allowance (all years)
PSUPt | 0 | 0 | 0 | 0 | 0 | 0
RECt | 0 | 0 | 0 | 0 | 0 | 0
ESRt | 0 | 0 | 0 | 0 | 0 | 0
EVRt | 0 | 0 | 0 | 0 | 0 | 0
SWRt | 0 | 0 | 0 | 0 | 0 | 0
DIGIt | 0 | 0 | 0 | 0 | 0 | 0
SARt | 0 | 0 | 0 | 0 | 0 | 0
LREt | 0 | 0 | 0 | 0 | 0 | 0
HVPt | 0 | 0 | 0 | 0 | 0 | 0
WDVt | 0 | 0 | 0 | 0 | 0 | 0
HOt | 34.67 | 0 | 6.22 | 64.4 | 3.13 | 108.42 |  | Check
Appendix 1: Uncertain Costs without Evaluative Price Control Deliverables allowances (£m) 25/26: 6.67; Appendix 1: Uncertain Costs without Evaluative Price Control Deliverables allowances (£m) 26/27: 64.81; Appendix 1: Uncertain Costs without Evaluative Price Control Deliverables allowances (£m) 27/28: 10.16 | 116.31 | OK | 7.89 | 7.89
SESt | 0 | 0 | 0 | 0 | 0 | 0
SEFECt | 0 | 0 | 0 | 0 | 0 | 0

## GD_Annex>>
The following worksheets contain the tables and figures in the GD Annex

## TableGD1_GD_Reopeners
Table GD1: GD re-opener mechanisms subject to this decision
Reopener Mechanism | Special Condition
HSE Policy Re-opener | 3.17
Specified Streetworks Costs Re-opener | 3.24
Net Zero Pre-Construction Work and Small Net Zero Projects Re-opener | 3.9

## TableGD2_DDs_Summary
Table GD2: Summary of our GD Draft Determinations
Sector Group | Network | Company Requested Number of Projects | Company Requested Forecast costs £m | Ofgem’s DD - Projects Approved* | Ofgem’s DD - Projects Not Approved | Ofgem’s DD - Cost adjustment £m | Ofgem’s DD - Allowances £m
Cadent | EoE | 2 | 21.803 | 2 | 0 | -5.986 | 15.817
Cadent | Lon | 3 | 21.4103 | 2 | 1 | -12.0743 | 9.336
Cadent | NW | 2 | 13.6582 | 2 | 0 | -2.3862 | 11.272
Cadent | WM | 2 | 8.8525 | 2 | 0 | -0.79151 | 8.061
Northern Gas Networks | NGN | 2 | 33.69 | 2 | 0 | -18.566 | 15.124
Scotia Gas Networks | Sc | 1 | 19.9358 | 1 | 0 | -9.6939 | 10.2419
Scotia Gas Networks | So | 2 | 45.684 | 2 | 0 | -15.585 | 30.099
Wales & West Utilities | WWU | 2 | 50.0628 | 2 | 0 | -23.485 | 26.5778
Total |  | 16 | 215.0966 | 15 | 1 | -88.5679 | 126.5287
Check
GD Totals from DD Summary Sheet |  | 16 | 215.0966 | 15 | 1 | -88.5679 | 126.5287
|  | OK | OK | OK | OK | OK | OK

## TableGD3_HSE_DD_Summary
Table GD3: applications received and summary of our DDs
Sector Group | GDN submitted costs (RIIO-2 only) | Ofgem adjustments | Ofgem DD allowance | Sector_Group | Modelled allowance
Cadent | 29.5939 | -1.4879 | 28.106 | Cadent | 28.106 | OK
NGN | 16.214 | -5.2144 | 10.9996 | Northern Gas Networks | 11 | OK
SGN | 50.6598 | -20.2119 | 30.4479 | Scotia Gas Networks | 30.448 | OK
WWU | 25.7528 | -1.042 | 24.7108 | Wales & West Utilities | 24.711 | OK
Total | 122.2206 | -27.9563 | 94.2643
Mechanism | GD HSE policy Re-opener

## TableGD3a_HSE_Benchmarking
Table GD3a: HSE Policy benchmarking
Network | Avg FTE | Unit rate (75th percentile) | Total efficient cost (£m) | GD2 allowance (£m)
EoE | 566.2386 | 0.067445 | 38.1897 | 8.127
Lon | 493.7788 | 0.067445 | 33.3027 | 8.446
NW | 472.7583 | 0.067445 | 31.885 | 6.962
WM | 271.6645 | 0.067445 | 18.3223 | 4.571
NGN | 542.0663 | 0.067445 | 36.5595 | 11
Sc | 451.986 | 0.067445 | 30.484 | 10.242
So | 878.2521 | 0.067445 | 59.2334 | 20.206
WWU | 366.3896 | 0.067445 | 24.711 | 24.711

## TableGD4_Streetworks_DD_Summary
Table GD4: applications received and summary of our DDs
Sector Group | GDN submitted costs (RIIO-2 only) | Ofgem adjustments | Ofgem DD allowance | Sector_Group
Cadent | 15.65 | -15.65 | 0 | Cadent
NGN | 17.476 | -13.3516 | 4.1244 | Northern Gas Networks
SGN | 14.96 | -5.067 | 9.893 | Scotia Gas Networks
WWU | 24.31 | -22.443 | 1.867 | Wales & West Utilities
Total | 72.396 | -56.5116 | 15.8844
Mechanism | GD Specified Streetworks Costs Re-opener

## TableGD4a_Cadent_Costs
Table GD4a: Summary of Cadent’s request under the Specified Streetworks Costs Re-opener and Ofgem’s DDs (£m, 2018/19 prices)
| Cadent submitted costs | Schemes after 1 April 2021 | Ofgem adjustments | Ofgem DD allowance
PBS | 13.67 | Nil | -13.67 | 0
Traffic light management | 1.98 | Nil | -1.98 | 0
Total | 15.65 | - | -15.65 | 0

## TableGD4b_NGN_Costs
Table GD4b: Summary of NGN’s request under the Specified Streetworks Costs Re-opener and Ofgem’s DDs (£m, 2018/19 prices)
| NGN submitted costs | Schemes after 1 April 2021 | Ofgem adjustments | Ofgem DD allowance
Permits | 5.898 | 2 out of 15 | -5.409 | 0.489
Traffic management | 11.578 | 2 out of 15 | -7.943 | 3.635
Total | 17.476 | - | -13.352 | 4.124

## TableGD4c_SGN_Costs
Table GD4c: Summary of SGN’s request under the Specified Streetworks Costs Re-opener and Ofgem’s DDs (£m, 2018/19 prices)
| SGN submitted costs | Schemes after 1 April 2021 | Ofgem adjustments | Ofgem DD allowance
Lane rental | 11.43 | 5 out of 6 | -2.42 | 9.01
ULEZ | 0.883 | Yes | 0 | 0.883
Traffic management | 2.644 | Nil | -2.644 | 0
Total | 14.957 | - | -5.064 | 9.893

## TableGD4d_WWU_Costs
Table GD4d: Summary of WWU’s request under the Specified Streetworks Costs Re-opener and Ofgem’s DDs (£m, 2018/19 prices)
| WWU submitted costs | Schemes after 1 April 2021 | Ofgem adjustments | Ofgem DD allowance
Permits | 6.85 | 3 out of 14 | -5.974 | 0.876
Traffic management | 14.36 | 3 out of 14 | -13.493 | 0.867
Road closure costs | 3.1 | 3 out of 14 | -2.976 | 0.124
Total | 24.31 | - | -22.443 | 1.867

## TableGD5_NetZero_DD_Summary
Table GD5: applications received and summary of our DDs
Sector Group | GDN submitted costs (RIIO-2 only) | Ofgem adjustments | Ofgem DD allowance | Sector_Group
Cadent | 20.48 | -4.1 | 16.38 | Cadent
NGN | 0 | 0 | 0 | Northern Gas Networks
SGN | 0 | 0 | 0 | Scotia Gas Networks
WWU | 0 | 0 | 0 | Wales & West Utilities
Total | 20.48 | -4.1 | 16.38
Mechanism | GD Net zero pre-construction works and small net zero projects re-opener

## TableGD5a_NetZero_Cadent_Costs
Table GD5a: Cost assessment for Cadent's NZASP project (£m, 2018/19 prices)
Cost category | Cadent submitted costs | Ofgem adjustments | Draft allowances
Efficient project costs | 20.48 | 0 | 20.48
Cadent NZASP contribution (10%) | 0 | -2.05 | -2.05
TIM impact adjustment | - | -2.05 | -2.05
Total | 20.48 | -4.1 | 16.38

## TableGD5b_NetZero_Deliverables
Table GD5b: Cadent's proposed project deliverables
Reference | Proposed project deliverable | Indicative deadline | Evidence
1 | Interim vehicle-based ALD roll out report | 31/11/2025 | The report should set out:
1. Current vehicle-based ALD capacity:
a) Number of units purchased,
b) Number of units mobilised,
c) Length of network surveyed,
d) Follow on interventions commissioned.
2. Roadmap for the next 5 months of roll out.
2 | Final vehicle-based ALD roll out report | 2026-03-31 | The report should set out:
1. Vehicle-based ALD capacity vs re-opener targets:
a) Number of units purchased,
b) Number of units mobilised,
c) Length of network surveyed,
d) Follow on interventions commissioned.
2. Progress update on emissions estimation method capability.
3 | Mobilisation of full LP/MP network coverage capacity | 2026-03-31 | Evidence showing survey capacity.

## GD_A1_Annex1
Annex 1: SpC 3.17 HSE Policy Re-opener REPt
Distribution Network/Regulatory Year | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26 | Total
EoE | 0.27 | 0.291 | 0.176 | 0.746 | 6.644 | 8.127
Lon | 0.391 | 0.42 | 0.25 | 1.339 | 6.046 | 8.446
NW | 0.228 | 0.246 | 0.142 | 0.747 | 5.599 | 6.962
WM | 0.248 | 0.266 | 0.16 | 0.627 | 3.27 | 4.571
Northern Gas Networks plc | 0.497 | 1.298 | 1.113 | 1.113 | 6.979 | 11
Scotland Gas Networks plc | 0 | 0.047 | 3.151 | 3.346 | 3.698 | 10.242
Southern Gas Networks plc | 0 | 0.067 | 6.455 | 6.584 | 7.1 | 20.206
Wales and West Utilities plc | 2.102 | 4.261 | 6.42 | 5.844 | 6.084 | 24.711

## GD_A1_Annex2
Annex 2: SpC 3.24 Specified Streetworks Costs Re-opener STWt
Distribution Network/Regulatory Year | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26 | Total
EoE | 0 | 0 | 0 | 0 | 0 | 0
Lon | 0 | 0 | 0 | 0 | 0 | 0
NW | 0 | 0 | 0 | 0 | 0 | 0
WM | 0 | 0 | 0 | 0 | 0 | 0
Northern Gas Networks plc | 0.824 | 0.825 | 0.825 | 0.825 | 0.825 | 4.124
Scotland Gas Networks plc | 0 | 0 | 0 | 0 | 0 | 0
Southern Gas Networks plc | 2.622 | 2.542 | 1.813 | 1.353 | 1.563 | 9.893
Wales and West Utilities plc | 0.167 | 0.28 | 0.572 | 0.424 | 0.424 | 1.867

## GD_A2_Annex1
Annex 1: SpC 3.9 Net Zero Pre-construction Work and Small Net Zero Projects (£m, 2018/19 prices)
Distribution Network/Regulatory Year | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26 | Total
EoE | 0 | 0 | 0 | 0 | 7.69 | 7.69
Lon | 0 | 0 | 0 | 0 | 0.89 | 0.89
NW | 0 | 0 | 0 | 0 | 4.31 | 4.31
WM | 0 | 0 | 0 | 0 | 3.49 | 3.49

## GD_A2_Annex2
Annex 2: Project deliverables
Reference | Proposed project deliverable | Indicative deadline | Evidence
1 | Interim vehicle-based ALD roll out report | 31/11/2025 | The report should set out:
1. Current vehicle-based ALD capacity:
a) Number of units purchased,
b) Number of units mobilised,
c) Length of network surveyed,
d) Follow on interventions commissioned.
2. Roadmap for the next 5 months of roll out.
2 | Final vehicle-based ALD roll out report | 2026-03-31 | The report should set out:
1. Vehicle-based ALD capacity vs re-opener targets:
a) Number of units purchased,
b) Number of units mobilised,
c) Length of network surveyed,
d) Follow on interventions commissioned.
2. Progress update on emissions estimation method capability.
3 | Mobilisation of full LP/MP network coverage capacity | 2026-03-31 | Evidence showing survey capacity.

## Supporting_Data>>
The following worksheets contain supporting data and calculations that feed into the document tables.

## HSE_Policy_Assessment
HSE POLICY REOPENER BENCHMARKING
| Step 1: FTE data source: RIIO-3 BPDTs | [9 empty] | Step 2: GDN cost submissions | [5 empty] | Step 3: Benchmarking
|  |  |  | RIIO-GD2 | [7 empty] | GD2 | GD3 | [5 empty] | GD2 & GD3
|  |  |  | 2022 | 2023 | 2024 | 2025 | 2026 | GD2 re-opener request (£m) | GD2 re-opener request (£) | (18/19) | re-opener | baseline | Total (£m) | GDN total (£m) | % in GD2 | Company | Network | Avg FTE | GD2&3 total/FTE
| EoE | employee FTE | emergency | 280.273 | 281.703 | 283.7799 | 231.9539 | 227.1877 |  |  | EoE | 12.753 | 47.172 | 59.925 |  | 0.21282 | Cadent | EoE | 566.2386 | 105829.9788
|  |  | repairs | 261.5418 | 277.7822 | 251.2575 | 302.6282 | 313.2249 |  |  | Lon | 4.8702 | 14.3335 | 19.2037 |  | 0.25361 | Cadent | Lon | 493.7788 | 38891.2101
|  | apprentices FTE | emergency | 0 | 0 | 0 | 0 | 0 |  |  | NW | 7.9782 | 28.5633 | 36.5414 |  | 0.21833 | Cadent | NW | 472.7583 | 77294.1243
|  |  | repairs | 0 | 0 | 0 | 0 | 0 |  |  | WM | 3.9925 | 12.0124 | 16.0049 | 131.675 | 0.24946 | Cadent | WM | 271.6645 | 58914.0814
|  | contract FTE | emergency | 3.0105 | 7.1065 | 0.24366 | 0 | 27 |  |  | NGN | 16.214 | 37.6722 | 53.8862 | 53.8862 | 0.30089 | NGN | NGN | 542.0663 | 99408.9151
|  |  | repairs | 2.3434 | 4.4996 | 12.4058 | 21.2639 | 41.9873 |  |  | Sc | 19.936 | 39.4031 | 59.3391 |  | 0.33597 | SGN | Sc | 451.986 | 131285.2546
|  | related FTE | emergency | 0 | 0 | 0 | 0 | 0 |  |  | So | 30.724 | 59.3439 | 90.0679 | 149.407 | 0.34112 | SGN | So | 878.2521 | 102553.619
|  |  | repairs | 0 | 0 | 0 | 0 | 0 |  |  | WWU | 25.7528 | 0 | 25.7528 | 25.7528 | 1 | WWU | WWU | 366.3896 | 70288.1316
|  |  | total | 547.1687 | 571.0913 | 547.6869 | 555.846 | 609.3999 | 12.753 | 12752973.7451
| Lon | employee FTE | emergency | 198.8541 | 202.8641 | 189.8469 | 189.9297 | 187.328 |  |  | Conversion: | 0.79763 | [5 empty] | 75th percentile: |  | 67444.619
|  |  | repairs | 232.2003 | 248.187 | 225.7813 | 211.7447 | 210.3861
|  | apprentices FTE | emergency | 0 | 0 | 0 | 0 | 0
|  |  | repairs | 0 | 0 | 0 | 0 | 0 | [9 empty] | GDNs benchmarked to 75th percentile
|  | contract FTE | emergency | 8.4051 | 24.3056 | 20.5284 | 16.4779 | 16.4779 | [8 empty] | Network | Avg FTE | rate | Total efficient cost (£m) | GD2 allowance (£m)
|  |  | repairs | 16.8789 | 47.5591 | 61.2283 | 71.9551 | 87.9551 | [8 empty] | EoE | 566.2386 | 0.067445 | 38.1897 | 8.127
|  | related FTE | emergency | 0 | 0 | 0 | 0 | 0 | [8 empty] | Lon | 493.7788 | 0.067445 | 33.3027 | 8.446
|  |  | repairs | 0 | 0 | 0 | 0 | 0 | [8 empty] | NW | 472.7583 | 0.067445 | 31.885 | 6.962
|  |  | total | 456.3384 | 522.9157 | 497.3849 | 490.1075 | 502.1472 | 4.8702 | 4870180.6055 | [6 empty] | WM | 271.6645 | 0.067445 | 18.3223 | 4.571
| NW | employee FTE | emergency | 183.0627 | 209.9199 | 212.688 | 202.9681 | 200.2974 | [8 empty] | NGN | 542.0663 | 0.067445 | 36.5595 | 11
|  |  | repairs | 242.4482 | 260.027 | 252.7315 | 258.2507 | 255.1854 | [8 empty] | Sc | 451.986 | 0.067445 | 30.484 | 10.242
|  | apprentices FTE | emergency | 0 | 0 | 0 | 0 | 0 | [8 empty] | So | 878.2521 | 0.067445 | 59.2334 | 20.206
|  |  | repairs | 0 | 0 | 0 | 0 | 0 | [8 empty] | WWU | 366.3896 | 0.067445 | 24.711 | 24.711
|  | contract FTE | emergency | 0.58987 | 0 | 7.2835 | 4.4511 | 21.4511
|  |  | repairs | 0.21918 | 11.2528 | 8.2364 | 5.3643 | 27.3643 | [8 empty] | Allowances by Sector Group
|  | related FTE | emergency | 0 | 0 | 0 | 0 | 0 | [8 empty] | Sector Group | GDN GD2 allowance (£m)
|  |  | repairs | 0 | 0 | 0 | 0 | 0 | [8 empty] | Cadent | 28.106
|  |  | total | 426.32 | 481.1998 | 480.9395 | 471.034 | 504.2981 | 7.9782 | 7978184.3458 | [6 empty] | NGN | 11
| WM | employee FTE | emergency | 122.6617 | 122.8009 | 127.4104 | 129.2383 | 126.6362 | [8 empty] | SGN | 30.448
|  |  | repairs | 146.6148 | 143.9061 | 130.2471 | 146.2859 | 145.5213 | [8 empty] | WWU | 24.711
|  | apprentices FTE | emergency | 0 | 0 | 0 | 0 | 0
|  |  | repairs | 0 | 0 | 0 | 0 | 0
|  | contract FTE | emergency | 0 | 0 | 0 | 0 | 9
|  |  | repairs | 0 | 0 | 0 | 0 | 8
|  | related FTE | emergency | 0 | 0 | 0 | 0 | 0
|  |  | repairs | 0 | 0 | 0 | 0 | 0
|  |  | total | 269.2764 | 266.707 | 257.6575 | 275.5242 | 289.1575 | 3.9925 | 3992506.9648
| NGN | employee FTE | emergency | 190 | 205 | 210 | 201 | 198
|  |  | repairs | 318 | 307 | 319 | 312 | 260
|  | apprentices FTE | emergency | 0 | 0 | 0 | 0 | 0
|  |  | repairs | 0 | 0 | 0 | 0 | 0
|  | contract FTE | emergency | 0 | 0 | 0 | 0 | 0
|  |  | repairs | 38.0663 | 38.0663 | 38.0663 | 38.0663 | 38.0663
|  | related FTE | emergency | 0 | 0 | 0 | 0 | 0
|  |  | repairs | 0 | 0 | 0 | 0 | 0
|  |  | total | 546.0663 | 550.0663 | 567.0663 | 551.0663 | 496.0663 | 16.214 | 16214000
| Sc | employee FTE | emergency | 215.0435 | 224.3782 | 175.4505 | 233.1 | 233.1
|  |  | repairs | 170.4414 | 196.3979 | 179.0006 | 281.1 | 281.1
|  | apprentices FTE | emergency | 0 | 0 | 0 | 0 | 0
|  |  | repairs | 0 | 0 | 0 | 0 | 0
|  | contract FTE | emergency | 14.6125 | 46.3152 | 9.8899 | 0 | 0
|  |  | repairs | 0 | 0 | 0 | 0 | 0
|  | related FTE | emergency | 0 | 0 | 0 | 0 | 0
|  |  | repairs | 0 | 0 | 0 | 0 | 0
|  |  | total | 400.0975 | 467.0912 | 364.3411 | 514.2 | 514.2 | 19.936 | 19936000
| So | employee FTE | emergency | 349.2407 | 436.7142 | 425.3222 | 468 | 468
|  |  | repairs | 255.8304 | 308.667 | 327.0007 | 410.8 | 410.8
|  | apprentices FTE | emergency | 0 | 0 | 0 | 0 | 0
|  |  | repairs | 0 | 0 | 0 | 0 | 0
|  | contract FTE | emergency | 27.1376 | 86 | 173.2634 | 129.1204 | 115.3637
|  |  | repairs | 0 | 0 | 0 | 0 | 0
|  | related FTE | emergency | 0 | 0 | 0 | 0 | 0
|  |  | repairs | 0 | 0 | 0 | 0 | 0
|  |  | total | 632.2087 | 831.3812 | 925.5863 | 1007.9204 | 994.1637 | 30.724 | 30724000
| WWU | employee FTE | emergency | 179.0459 | 180.9242 | 184.9739 | 184.9739 | 184.9739
|  |  | repairs | 153.947 | 175.5072 | 185.7284 | 185.7284 | 185.7284
|  | apprentices FTE | emergency | 0 | 0 | 0 | 0 | 0
|  |  | repairs | 0 | 0 | 0 | 0 | 0
|  | contract FTE | emergency | 0 | 0 | 9.6433 | 9.6433 | 9.6433
|  |  | repairs | 0 | 0 | 0.49558 | 0.49558 | 0.49558
|  | related FTE | emergency | 0 | 0 | 0 | 0 | 0
|  |  | repairs | 0 | 0 | 0 | 0 | 0
|  |  | total | 332.9929 | 356.4315 | 380.8413 | 380.8413 | 380.8413 | 25.7528 | 25752842.2246

## Look_up_Tables>> (hidden)
O
The following are lookup tables and not published in the Draft Determinations.

## Project_Data (hidden)
Sector | Sector_Group | Licensee | Reopener_mechanism | Assessment_Group | Project_Name | Date | Status | Price_base | Units | Submitted_Cost_Submission | Allowance_Draft | Approved_DD | Opex Escalator/Indirect Scaler | OE_IS_Rate | OE_IS_Allowances
ED | Scottish and Southern Energy | SSEH | ED Hebrides and Orkney – (SSEN only) | SSEN-D Orkney Whole System Uncertainty Mechanism (HOWSUM) 2025 | SSEN CAI costs development costs - HOWSUM | 2025-07-01 | Current | 2020/21 | £m | 9.49 | 0 | 0 | No | 0.108 | 0
ED | Scottish and Southern Energy | SSEH | ED Hebrides and Orkney – (SSEN only) | SSEN-D Orkney Whole System Uncertainty Mechanism (HOWSUM) 2025 | SSEN Inner Hebridean Islands of Islay and Jura development costs | 2025-07-01 | Current | 2020/21 | £m | 104.01 | 0 | 0 | No | 0.108 | 0
ET | National Grid Electricity Transmission | NGET | ET Medium Sized Investment Projects (MSIP) | NGET MSIP 2025 | NGET Pathfinder - Walpole | 2024-11-21 | Current | 2018/19 | £m | 0 | 0 | 0 | Yes | 0.1689 | 0
ET | National Grid Electricity Transmission | NGET | ET Medium Sized Investment Projects (MSIP) | NGET MSIP 2025 | NGET Pitsmoor | 2024-11-21 | Current | 2018/19 | £m | 0 | 0 | 0 | Yes | 0.1689 | 0
ET | National Grid Electricity Transmission | NGET | ET Medium Sized Investment Projects (MSIP) | NGET MSIP 2025 | NGET SSEPD - Minety | 2024-11-21 | Current | 2018/19 | £m | 0 | 0 | 0 | Yes | 0.1689 | 0
ET | National Grid Electricity Transmission | NGET | ET Medium Sized Investment Projects (MSIP) | NGET MSIP 2025 | NGET Swansea North Greener Grid | 2024-11-21 | Current | 2018/19 | £m | 0 | 0 | 0 | Yes | 0.1689 | 0
ET | National Grid Electricity Transmission | NGET | ET Medium Sized Investment Projects (MSIP) | NGET MSIP 2025 | NGET Pathfinder - Upper Boat | 2024-11-21 | Current | 2018/19 | £m | 0 | 0 | 0 | Yes | 0.1689 | 0
ET | National Grid Electricity Transmission | NGET | ET Medium Sized Investment Projects (MSIP) | NGET MSIP 2025 | NGET Pathfinder - Sellindge | 2024-11-21 | Current | 2018/19 | £m | 0 | 0 | 0 | Yes | 0.1689 | 0
ET | National Grid Electricity Transmission | NGET | ET Medium Sized Investment Projects (MSIP) | NGET MSIP 2025 | NGET Willington rebuild (132kv - NGED) | 2024-11-21 | Current | 2018/19 | £m | 0 | 0 | 0 | Yes | 0.1689 | 0
ET | National Grid Electricity Transmission | NGET | ET Medium Sized Investment Projects (MSIP) | NGET MSIP 2025 | NGET Pathfinder - Landulph | 2024-11-21 | Current | 2018/19 | £m | 0 | 0 | 0 | Yes | 0.1689 | 0
ET | National Grid Electricity Transmission | NGET | ET Medium Sized Investment Projects (MSIP) | NGET MSIP 2025 | NGET - Amersham | 2024-11-21 | Current | 2018/19 | £m | 0 | 0 | 0 | Yes | 0.1689 | 0
ET | National Grid Electricity Transmission | NGET | ET Medium Sized Investment Projects (MSIP) | NGET MSIP 2025 | NGET Marston Vale (Millbrook) | 2025-07-18 | Current | 2018/19 | £m | 20.9419 | 0 | 0 | Yes | 0.1689 | 0
ET | National Grid Electricity Transmission | NGET | ET Medium Sized Investment Projects (MSIP) | NGET MSIP 2025 | NGET Pathfinder - Richborough | 2024-11-21 | Current | 2018/19 | £m | 0 | 0 | 0 | Yes | 0.1689 | 0
ET | National Grid Electricity Transmission | NGET | ET Medium Sized Investment Projects (MSIP) | NGET MSIP 2025 | NGET Norwich 400kV site strategy | 2025-07-18 | Current | 2018/19 | £m | 28.4517 | 0 | 0 | Yes | 0.1689 | 0
ET | National Grid Electricity Transmission | NGET | ET Medium Sized Investment Projects (MSIP) | NGET MSIP 2025 | NGET OTS - Humber Refinery | 2024-11-21 | Current | 2018/19 | £m | 0 | 0 | 0 | Yes | 0.1689 | 0
ET | National Grid Electricity Transmission | NGET | ET Medium Sized Investment Projects (MSIP) | NGET MSIP 2025 | NGET Pathfinder - Cilfynydd | 2024-11-21 | Current | 2018/19 | £m | 0 | 0 | 0 | Yes | 0.1689 | 0
ET | National Grid Electricity Transmission | NGET | ET Medium Sized Investment Projects (MSIP) | NGET MSIP 2025 | NGET Pathfinder - Hartmoor | 2024-11-21 | Current | 2018/19 | £m | 0 | 0 | 0 | Yes | 0.1689 | 0
ET | National Grid Electricity Transmission | NGET | ET Medium Sized Investment Projects (MSIP) | NGET MSIP 2025 | NGET OTS - Anglo Scottish |  | Current |  | £m | 0 | 0 | 0 | Yes | 0.1689 | 0
ET | SP Transmission | SPT | ET Medium Sized Investment Projects (MSIP) | SPT MSIP 2025 | VSRE-Strathaven - Smeaton OHL Conductor Replacement | 2024-07-31 | Current | 2018/19 | £m | 0 | 0 | 0 | Yes | 0.1342 | 0
GD | Cadent | EoE | GD Specified Streetworks Costs Re-opener | Cadent Specified Streetworks Costs Re-opener 2023 | EoE Cadent Specified Streetworks Costs Re-opener 2023 | 2024-09-30 | Current | 2018/19 | £m | 0 | 0 | 0 | No | 0 | 0
GD | Cadent | Lon | GD Specified Streetworks Costs Re-opener | Cadent Specified Streetworks Costs Re-opener 2023 | Lon Cadent Specified Streetworks Costs Re-opener 2023 | 2025-06-02 | Current | 2018/19 | £m | 15.65 | 0 | 0 | No | 0 | 0
GD | Cadent | NW | GD Specified Streetworks Costs Re-opener | Cadent Specified Streetworks Costs Re-opener 2023 | NW Cadent Specified Streetworks Costs Re-opener 2023 | 2024-09-30 | Current | 2018/19 | £m | 0 | 0 | 0 | No | 0 | 0
GD | Cadent | WM | GD Specified Streetworks Costs Re-opener | Cadent Specified Streetworks Costs Re-opener 2023 | WM Cadent Specified Streetworks Costs Re-opener 2023 | 2024-09-30 | Current | 2018/19 | £m | 0 | 0 | 0 | No | 0 | 0
GD | Scotia Gas Networks | Sc | GD Specified Streetworks Costs Re-opener | SGN Specified Streetworks Costs Re-opener 2023 | SGN Sc Specified Streetworks Costs Re-opener 2023 | 2024-09-30 | Current | 2018/19 | £m | 0 | 0 | 0 | No | 0 | 0
ET | SP Transmission | SPT | ET Medium Sized Investment Projects (MSIP) | SPT MSIP 2025 | SPT Extension of Sub-Synchronous Oscillation (SSO) Detection Capabilities | 2025-07-18 | Current | 2018/19 | £m | 0.236 | 0.23442 | 1 | Yes | 0.1342 | 0.031
ET | Scottish Hydro Electric Transmission | SHET | ET Medium Sized Investment Projects (MSIP) | SHET MSIP 2025 | SHET Constraint Management Pathfinder (B6) | 2025-07-18 | Current | 2018/19 | £m | 0.409 | 0.347 | 1 | Yes | 0.1081 | 0.038
ET | SP Transmission | SPT | ET Medium Sized Investment Projects (MSIP) | SPT MSIP 2025 | SPT SPT-RI-1742 Cockenzie Overload Protection Scheme | 2025-07-18 | Current | 2018/19 | £m | 0.406 | 0.3966 | 1 | Yes | 0.1342 | 0.053
ET | National Grid Electricity Transmission | NGET | ET Medium Sized Investment Projects (MSIP) | NGET MSIP 2025 | NGET Heysham OPS scheme for ENWL | 2025-07-18 | Current | 2018/19 | £m | 1.3229 | 0.7026 | 1 | Yes | 0.1689 | 0.119
ET | Scottish Hydro Electric Transmission | SHET | ET Medium Sized Investment Projects (MSIP) | SHET MSIP 2025 | SHET North of Beauly DLR (stage 2) | 2025-07-18 | Current | 2018/19 | £m | 1.0434 | 0.72112 | 1 | Yes | 0.1081 | 0.078
ET | National Grid Electricity Transmission | NGET | ET Medium Sized Investment Projects (MSIP) | NGET MSIP 2025 | NGET OTS Killingholme | 2025-07-18 | Current | 2018/19 | £m | 0.84776 | 0.82501 | 1 | Yes | 0.1689 | 0.139
GD | Cadent | Lon | GD Net zero pre-construction works and small net zero projects re-opener | Cadent Net Zero Pre-construction Work and Small Net Zero Projects Reopener | Cadent Lon Network Emissions Management | 2025-06-02 | Current | 2018/19 | £m | 0.89 | 0.89 | 1 | No | 0 | 0
ET | Scottish Hydro Electric Transmission | SHET | ET Medium Sized Investment Projects (MSIP) | SHET MSIP 2025 | SHET Lochluichart and Corriemollie | 2025-07-18 | Current | 2018/19 | £m | 1.4855 | 1.0186 | 1 | Yes | 0.1081 | 0.11
ED | Scottish and Southern Energy | SSEH | ED Hebrides and Orkney – (SSEN only) | SSEN-D Orkney Whole System Uncertainty Mechanism (HOWSUM) 2025 | SSEN Inner Hebridean Islands of Mull, Coll and Tiree development costs | 2025-07-01 | Current | 2020/21 | £m | 2.07 | 1.16 | 1 | No | 0.108 | 0
ED | Scottish and Southern Energy | SSEH | ED Hebrides and Orkney – (SSEN only) | SSEN-D Orkney Whole System Uncertainty Mechanism (HOWSUM) 2025 | SSEN Total whole system analysis development costs - HOWSUM | 2025-07-01 | Current | 2020/21 | £m | 1.36 | 1.23 | 1 | No | 0.108 | 0
ET | National Grid Electricity Transmission | NGET | ET Medium Sized Investment Projects (MSIP) | NGET MSIP 2025 | NGET OTS - East Anglia | 2025-07-18 | Current | 2018/19 | £m | 1.6055 | 1.7259 | 1 | Yes | 0.1689 | 0.292
GD | Wales & West Utilities | WWU | GD Specified Streetworks Costs Re-opener | WWU Specified Streetworks Costs Re-opener 2023 | WWU Specified Streetworks Costs Re-opener 2023 | 2025-06-02 | Current | 2018/19 | £m | 24.31 | 1.867 | 1 | No | 0 | 0
ED | Scottish and Southern Energy | SSEH | ED Hebrides and Orkney – (SSEN only) | SSEN-D Orkney Whole System Uncertainty Mechanism (HOWSUM) 2025 | SSEN Orkney Islands development costs | 2025-07-01 | Current | 2020/21 | £m | 17.04 | 2.46 | 1 | No | 0.108 | 0
ET | National Grid Electricity Transmission | NGET | ET Medium Sized Investment Projects (MSIP) | NGET MSIP 2025 | NGET OTS - Lackenby | 2025-07-18 | Current | 2018/19 | £m | 2.8542 | 2.7959 | 1 | Yes | 0.1689 | 0.472
ED | Scottish and Southern Energy | SSEH | ED Hebrides and Orkney – (SSEN only) | SSEN-D Orkney Whole System Uncertainty Mechanism (HOWSUM) 2025 | SSEN Outer Hebrides and Skye development costs | 2025-07-01 | Current | 2020/21 | £m | 24.62 | 3.04 | 1 | No | 0.108 | 0
GD | Cadent | WM | GD Net zero pre-construction works and small net zero projects re-opener | Cadent Net Zero Pre-construction Work and Small Net Zero Projects Reopener | Cadent WM Network Emissions Management | 2025-06-02 | Current | 2018/19 | £m | 4.86 | 3.49 | 1 | No | 0 | 0
ET | Scottish Hydro Electric Transmission | SHET | ET Medium Sized Investment Projects (MSIP) | SHET MSIP 2025 | SHET Tealing bypass | 2025-07-18 | Current | 2018/19 | £m | 4.9745 | 3.5725 | 1 | Yes | 0.1081 | 0.386
ET | SP Transmission | SPT | ET Medium Sized Investment Projects (MSIP) | SPT MSIP 2025 | SPT Inch Cape Offshore Wind Farm | 2025-07-18 | Current | 2018/19 | £m | 3.7702 | 3.7015 | 1 | Yes | 0.1342 | 0.497
GD | Northern Gas Networks | NGN | GD Specified Streetworks Costs Re-opener | NGN Specified Streetworks Costs Re-opener 2023 | NGN Specified Streetworks Costs Re-opener 2023 | 2025-06-02 | Current | 2018/19 | £m | 17.476 | 4.1244 | 1 | No | 0 | 0
ET | SP Transmission | SPT | ET Medium Sized Investment Projects (MSIP) | SPT MSIP 2025 | SPT-RI 282 Mark Hill SGT4 | 2025-07-18 | Current | 2018/19 | £m | 4.295 | 4.295 | 1 | Yes | 0.1342 | 0.576
GD | Cadent | NW | GD Net zero pre-construction works and small net zero projects re-opener | Cadent Net Zero Pre-construction Work and Small Net Zero Projects Reopener | Cadent NW Network Emissions Management | 2025-06-02 | Current | 2018/19 | £m | 5.68 | 4.31 | 1 | No | 0 | 0
ET | SP Transmission | SPT | ET Medium Sized Investment Projects (MSIP) | SPT MSIP 2025 | SPT-TOCO 2201 Kilmarnock South H1 | 2025-07-18 | Current | 2018/19 | £m | 8.181 | 4.4556 | 1 | Yes | 0.1342 | 0.598
GD | Cadent | WM | GD HSE policy Re-opener | Cadent HSE Policy Re-opener 2023 | WM Cadent HSE Policy Re-opener 2023 | 2025-06-02 | Current | 2018/19 | £m | 3.9925 | 4.571 | 1 | No | 0 | 0
ET | National Grid Electricity Transmission | NGET | ET Medium Sized Investment Projects (MSIP) | NGET MSIP 2025 | NGET Pathfinder - East Anglia OTS | 2025-07-18 | Current | 2018/19 | £m | 6.7997 | 5.1581 | 1 | Yes | 0.1689 | 0.871
ET | National Grid Electricity Transmission | NGET | ET Medium Sized Investment Projects (MSIP) | NGET MSIP 2025 | NGET Pathfinder - Yaxley | 2025-07-18 | Current | 2018/19 | £m | 6.0674 | 5.7928 | 1 | Yes | 0.1689 | 0.978
GD | Cadent | NW | GD HSE policy Re-opener | Cadent HSE Policy Re-opener 2023 | NW Cadent HSE Policy Re-opener 2023 | 2025-06-02 | Current | 2018/19 | £m | 7.9782 | 6.962 | 1 | No | 0 | 0
ET | National Grid Electricity Transmission | NGET | ET Medium Sized Investment Projects (MSIP) | NGET MSIP 2025 | NGET Central Reactive Voltage - Willington | 2025-07-18 | Current | 2018/19 | £m | 7.8385 | 7.3965 | 1 | Yes | 0.1689 | 1.249
GD | Cadent | EoE | GD Net zero pre-construction works and small net zero projects re-opener | Cadent Net Zero Pre-construction Work and Small Net Zero Projects Reopener | Cadent EoE Network Emissions Management | 2025-06-02 | Current | 2018/19 | £m | 9.05 | 7.69 | 1 | No | 0 | 0
ET | National Grid Electricity Transmission | NGET | ET Medium Sized Investment Projects (MSIP) | NGET MSIP 2025 | NGET Central Reactive Voltage - Ironbridge | 2025-07-18 | Current | 2018/19 | £m | 8.1218 | 7.8971 | 1 | Yes | 0.1689 | 1.334
GD | Cadent | EoE | GD HSE policy Re-opener | Cadent HSE Policy Re-opener 2023 | EoE Cadent HSE Policy Re-opener 2023 | 2025-06-02 | Current | 2018/19 | £m | 12.753 | 8.127 | 1 | No | 0 | 0
GD | Cadent | Lon | GD HSE policy Re-opener | Cadent HSE Policy Re-opener 2023 | Lon Cadent HSE Policy Re-opener 2023 | 2025-06-02 | Current | 2018/19 | £m | 4.8703 | 8.446 | 1 | No | 0 | 0
GD | Scotia Gas Networks | So | GD Specified Streetworks Costs Re-opener | SGN Specified Streetworks Costs Re-opener 2023 | SGN So Specified Streetworks Costs Re-opener 2023 | 2025-06-02 | Current | 2018/19 | £m | 14.96 | 9.893 | 1 | No | 0 | 0
GD | Scotia Gas Networks | Sc | GD HSE policy Re-opener | SGN HSE policy Re-opener 2023 | SGN Sc HSE Policy Re-opener 2023 | 2025-07-18 | Current | 2018/19 | £m | 19.9358 | 10.2419 | 1 | No | 0 | 0
GD | Northern Gas Networks | NGN | GD HSE policy Re-opener | NGN HSE Policy Re-opener 2023 | NGN HSE Policy Re-opener | 2025-06-02 | Current | 2018/19 | £m | 16.214 | 10.9996 | 1 | No | 0 | 0
ET | SP Transmission | SPT | ET Medium Sized Investment Projects (MSIP) | SPT MSIP 2025 | SPT-RI-302 Glenglass 132kV Substation | 2025-07-18 | Current | 2018/19 | £m | 13.5393 | 13.0136 | 1 | Yes | 0.1342 | 1.746
ET | National Grid Electricity Transmission | NGET | ET Medium Sized Investment Projects (MSIP) | NGET MSIP 2025 | NGET Penrhos 132kV site strategy | 2025-07-18 | Current | 2018/19 | £m | 17.0344 | 16.2208 | 1 | Yes | 0.1689 | 2.74
GD | Scotia Gas Networks | So | GD HSE policy Re-opener | SGN HSE policy Re-opener 2023 | SGN So HSE Policy Re-opener 2023 | 2025-07-18 | Current | 2018/19 | £m | 30.724 | 20.206 | 1 | No | 0 | 0
GD | Wales & West Utilities | WWU | GD HSE policy Re-opener | WWU HSE policy Re-opener 2023 | WWU HSE Policy Re-opener 2023 | 2025-06-02 | Current | 2018/19 | £m | 25.7528 | 24.7108 | 1 | No | 0 | 0
ET | National Grid Electricity Transmission | NGET | ET Medium Sized Investment Projects (MSIP) | NGET MSIP 2025 | NGET Wallend | 2025-07-18 | Current | 2018/19 | £m | 57.8484 | 36.5097 | 1 | Yes | 0.1689 | 6.166
ET | National Grid Electricity Transmission | NGET | ET Medium Sized Investment Projects (MSIP) | NGET MSIP 2025 | NGET Necton 400kV site strategy | 2025-07-18 | Current | 2018/19 | £m | 45.0307 | 37.6418 | 1 | Yes | 0.1689 | 6.358
ET | SP Transmission | SPT | ET Medium Sized Investment Projects (MSIP) | SPT MSIP 2025 | SPT Branxton 400kV Substation | 2025-07-18 | Current | 2018/19 | £m | 51.029 | 48.1666 | 1 | Yes | 0.1342 | 6.464
ET | Scottish Hydro Electric Transmission | SHET | ET Large Onshore Transmission Investments (LOTI) | SHET Gremista GSP 2024 | SHET Gremista GSP 2024 | 2025-07-01 | Current | 2018/19 | £m | 104.6153 | 79.3498 | 1 | No | 0.1081 | 0
ED | Electricity North West | ENWL | ED Load Related Expenditure Re-opener | ENWL Load Related Expenditure Re-opener 2025 | ENWL Load Related Expenditure Re-opener 2025 | 2025-07-18 | Current | 2020/21 | £m | 201.6 | 93.105 | 1 | Yes | 0.108 | 10.055