## Cover
`
`
`
RIIO-GT2 - Supplementary Data File (Years 1-4)

## Perf Dashboard
NGT Performance Dashboard
Operational Costs | [5 empty] | RIIO2 Outputs
Totex Performance including Uncertain Mechanism Expenditure | [5 empty] | Annual Gas Outputs |  | 2021- 22 | 2022- 23 | 2023- 24 | 2024- 25
[6 empty] | Annual gas output: |  | 81.0567 | 93.5834 | 75.6546 | 74.2377
| Expenditure | RIIO 2 - Years 1-4 (18/19 Prices) |  |  |  | - GB gas output (BCM) |  | 67.6493 | 62.2639 | 56.5892 | 56.852
|  | 2021- 22 | 2022- 23 | 2023- 24 | 2024- 25 | - Interconnector Exports (BCM) |  | 9.679 | 25.889 | 14.1428 | 12.026
Transmission Owner | Allowed | 311.7631 | 407.544 | 446.8292 | 492.3918 | - Storage & Shrinkage (BCM) |  | 3.7284 | 5.4306 | 4.9226 | 5.3597
| Actual | 291.1973 | 341.0961 | 396.5268 | 507.054 | GB Peak Daily output (GWh/day) |  | 4029.2098 | 4577.5 | 4294 | 4315.1
| Overspend (underspend) | -20.5658 | -66.4479 | -50.3024 | 14.6622
[6 empty] | Environment |  | 2021- 22 | 2022- 23 | 2023- 24 | 2024- 25
System Operator | Allowed | 91.46 | 91.0436 | 105.1607 | 107.4008 | Greenhouse gas emissions (venting) | Tonnes | 2031.2664 | 2286.6192 | 2293.0612 | 1982.2151
| Actual | 71.4207 | 66.0007 | 80.0708 | 84.6538 | NTS Shrinkage (Amount and the cost of the energy used to run the network) | GWH Cost | 3,506 GWh £190m | 6,795 GWh £578m | 3,090 GWh £108m | 2782 GWh £96.5m
| Overspend (underspend) | -20.0393 | -25.0429 | -25.0899 | -22.747 | Total Business Carbon Footprint | (tonnes of CO2 equivalent) | 296779.6421 | 405834.8011 | 381412.528 | 328970.7579
Total | Allowed | 403.2231 | 498.5877 | 551.9899 | 599.7926 | Customer & Stakeholder |  | 2021- 22 | 2022- 23 | 2023- 24 | 2024- 25
| Actual | 362.6179 | 407.0968 | 476.5976 | 591.7078 | Customer satisfaction | RIIO1 Target 6.9/10 RIIO 2 Target 7.8/10 | 8.6306 | 8.6035 | 8.5586 | 8.89
| Overspend (underspend) | -40.6051 | -91.4909 | -75.3923 | -8.0849 | Stakeholder satisfaction | RIIO1&2 Target 7.4/10 | 8.5423 | 8.6867 | 8.752 | 7.93
Operational Data & Outputs
GB Gas Transmission Network Length | c5000 miles
NGT Power sites |  | Main Gas Terminals
1. Didcot | 17. Damhead Creek | Natural Gas Entry Terminals | Liquid Natural Gas (LNG) Import | Interconnectors (Export)
2. Great Yarmouth | 18. Rye House | St Fergus | Isle of Grain | Moffat - To Ireland
3. Little Barford | 19. Coryton | Teeside | Milford Haven (2 x Terminals) | Bacton - To Netherlands
4. Pembroke | 20. Rocksavage | Barrow |  | Bacton - To Belgium
5. Staythorpe | 21. *Spalding (1&2) | Burton Point
6. Kings Lynn | 22. Langage | Easington
7. *Keadby (1&2) | 23. *South Humber (1&2) | Bacton
8. Medway | 24. Sutton Bridge
9. Peterhead | 25. West Burton
10. Seabank | 26. Carrington | Industrial Connections
11. Connah's Quay | 27. Corby | Blackburn Mill | Centrax | Seal Sands
12. Cottam | 28. Saltend PS | BOC Teesside | Fordoun | Shell Backhaul
13. Enfield | 29. Marchwood | INEOS Grangemouth | Goole Glass | Fellside
14. Grain | 30. Brigg | BP Saltend | INOVYN Runcorn | Winnington
15. Killingholme B | 31. Peterborough | Bridgewater | Palm Paper | ICI Billingham
16. VPI Immingham | 32. Saltholme
*3 sites (Keadby, Spalding and South Humber) that have 2 power stations so 35 in total is correct
Main Compressor Stations |  | Storage sites
Aberdeen | Hatton | Holford | Humbly Grove | Holehouse Farm
Alrewas | Huntingdon | Aldbrough | Hilltop
Avonbridge | Kings Lynn | Stublach | Rough
Aylesbury | Kirriemuir | Hornsea | Hatfield
Bishop Auckland | Lockerley
Cambridge | Nether Kellet | Connections to Gas Distribution Networks
Carnforth | Peterborough | Cadent (London, West Midlands and East of England) | Northern Gas Networks (North of England) | SGN (Scotland and South of England)
Chelmsford | St Fergus | Wales & West Utilities (Wales and South West England)
Churchover | Wisbech
Diss | Wooler
Felindre | Wormington

## Index
RIIO-GT2 - Supplementary Data File (Years 1-4) - Index
LINKS
Reference | Cover
Index
Performance Dashboard
Outputs | Outputs - Consumers
Outputs - Networks
Outputs - Environmental
Total Expenditure (Totex) | Totex Performance
Totex Breakdown (TO)
Totex Breakdown (SO)
Totex Incentive Mechanism | Totex Incentive Mechanism
Incentive Performance (TO & SO)
Surveys | Stakeholder Satisfaction
Customer Satisfaction
Gas Activity Output | Consolidated gas output Local output Interconnectror Export Storage Shrinkage
Business Carbon Footprint | BCF Emission
Innovation | Innovation Activity

## Outputs- Consumers
Meeting the needs of consumers and network users
Outputs | Description | Output Type | RIIO2 Target | RIIO2 Data (Years 1-4)
|  |  |  | 2021- 22 | 2022- 23 | 2023- 24 | 2024- 25
Customer satisfaction | Undertake annual satisfaction survey with customers | ODI-F | 7.8/10 | 8.63 | 8.6 | 8.56 | 8.89
Stakeholder satisfaction | Undertake annual satisfaction survey with stakeholders | ODI-R | 7.4/10 | 8.54 | 8.69 | 8.75 | 7.93
Quality of Demand Forecast | Deliver accurate day ahead demand forecasting (D-1) | ODI-F | 8.45 mcm average forecast error | 8.52 mcm average forecast error | 8.97 mcm average forecast error | 7.86 mcm/d average forecast error | 7.91 mcm/d average forecast error
Quality of Demand Forecast | Deliver accurate demand forecasting at the two to five days ahead stage (D2 to D5) | LO | 13.70 mcm average forecast error | 12.37 mcm average forecast error | 13.95 mcm average forecast error | 12.89 mcm/d average forecast error | 12.65 mcm/d average forecast error
Maintenance | Deliver benchmark performance for maintenance outage day and minimise driven changes to maintenance planning | ODI-F | 11 days or less | 1 maintenance day called | 1 maintenance day called | 1 maintenance day called | 0 maintenance days called
Maintenance | Deliver benchmark performance for maintenance outage day (excluding valve operations) | ODI-F | 75% of NGT driven customer impacting works aligned with customer outages | 95% of NG driven customer impacting works aligned with customer outages | 92% of NG driven customer impacting works aligned with customer outages | 100% of NGT driven customer impacting works aligned with customer outages | 94.6% of NGT driven customer impacting works aligned with customer outages
Maintenance | Minimise National Grid driven changes to maintenance planning | ODI-F | 7.25% of all Maintenance Days and Advice Notice Days called | 0 changes initiated by NGT | 0 changes initiated by NGT | 0 changes initiated by NGT | 10 change days initiated by NGT
Entry and Exit capacity constraint management | Meet constraint management target | ODI-F | £8.5m | £0 costs | £0 costs | £0 costs | £0 costs
Residual Balancing | Meet residual balancing linepack performance measure (LPM) target | ODI-F | <2.8 mcm average daily change | 2.0 mcm average daily change | 2.5 mcm average daily change | 1.8 mcm average daily change | 1.6 mcm average daily change
Residual Balancing | Meet residual balancing price performance measure (PPM) target | ODI-F | Difference 1.5% of SAP | Difference 1.8% of SAP | Difference 4.0% of SAP
Residual Balancing | Meet residual balancing price performance measure (PPM) target | ODI-F | Difference 1.5% of SAP | Difference 1.84% of SAP | Difference 3.96% of SAP | Difference 0.9% of SAP | Difference 0.5% of SAP
Modernising energy data (digitalisation strategy and action plan) | Set out our approach to using data and digitalisation to deliver benefit for our stakeholders and society | LO | Publish Digitalisation Strategy and action plan | Gas Transmission Digitalisation Strategy published March 2022. | Gas Transmission Digitalisation Strategy published March 2022. Updated Action Plan published June 2023 | Digitalisation Strategy Action Plan published in June 2023 and December 2023 Independent Digitalisation Strategy published March 2024 | Digitalisation Strategy Action Plan published in December 2024 Independent Digitalisation Strategy published March 2025
Colour Coding
On track to achieve target
Medium risk of non-achievement of target
High risk of non-achievement of target
Completed or target achieved

## Outputs - Network
Maintaining a safe and resilient network
Outputs | Description | Output Type | RIIO2 Target |  | RIIO2 (Years 1-4)
|  |  |  | 2021- 22 | 2022- 23 | 2023- 24 | 2024- 25
Network Asset Risk Metric (NARM) | Deliver Baseline Network Risk Outputs (measured as Long Term Risk Benefits (LTRB)) as a result of asset health investment into our lead secondary assets using Baseline NARM allowances. | PCD | Deliver our Baseline Network Risk Outputs (across three risk sub-categories) by the end of RIIO-T2. | Slower than anticipated ramp up in 2021/22. In aggregate, on track to deliver 5 year output | Increase in NARMs work delivered in 2022/23 in comparison to 2021/22. On track to deliver 5 year output | Projects delivered in 2023/24 have been at the lower end of LTRB scale however projects with large amounts of LTRB are forecast to be closed out across 2024/25 to ensure National Gas remain on target to deliver the overall NARMs target | Asset health delivery was ramped up in 24/25 across a number of themes including projects with higher associated LTRB values. Looking forward to 25/26 NGT forecasts to be on track to achieve the LTRB target
Cyber resilience OT | Deliver cyber resilience programme related to Cyber Operational Technology | PCD UIOLI | Deliver PCD deliverables | Year 1 cyber programme complete. | Year 2 cyber programme complete. Delivery of Control Systems impacted by global market conditions | Year 3 programme delivered. Majority of PCD outputs on track but delivery of control systems is behind target. | Year 4 programme delivered. Majority of PCD outputs on track but some deliverables rephased and aim to be delivered by year 5
Cyber resilience IT | Deliver cyber resilience programme related to Cyber Information Technology | PCD | Deliver PCD deliverables | Year 1 cyber programme complete. | Year 2 cyber programme complete. Some elements are behind the original schedule but overall NGT expect to complete existing outputs within the RIIO-T2 period | Year 3 programme delivered. Majority of PCD outputs on track but some deliverables rephased to year 4 | Year 4 programme delivered. Majority of PCD outputs on track but some deliverables rephased and aim to be delivered by year 5
Physical resilience | Deliver physical security upgrades at sites designated as Critical National Infrastructure (CNI). | PCD | Deliver PSUP requirements by 2026 | Slower progress against year 1 deliverables as we further develop delivery strategy and identify efficiency opportunities. On track for 5 year output | Delivery of 4 out of 9 sites in progress and on track for completion by Q3 2023/24. Remaining 5 sites on track for delivery in 2024/25. On track for 5 year output. | Asset Refresh and Major Asset Health upgrades are progressing well On track for 5 year output | Commissioning of the first four sites was delayed due to the separation from National Grid. We mobilised four of five additional sites, with the fifth delayed by late legal approvals from the shared site owner. Design for four non-baseline sites slipped into 2025/26 due to delays in procuring site-specific operational requirements (SSORs).
Annual Network Capability Report | Publish annual ANCAR document | LO | Publish report for each RIIO2 year | Published 29th June 2021 | Published June 2022 | Published in June 2023, with an update published in September 2023 | This is no longer an NG license obligation and is now completed by NESO as under the Gas Network Capability Needs Report (GNCNR)
Exit Capacity | Run the annual exit capacity process in accordance with the Exit Capacity Planning Guidance (ECPG) | LO | Run annual exit capacity process and submit Exit Capacity Allocation Report | Process ran Apr 2021 - Jan 2022. Report published Oct 2021 | Process ran Apr 2022- Jan 2023. Report published 31st Oct 2022 | Report published October 2023 | Run the annual exit capacity process in accordance with the ECPG
Asset health non-lead assets | Delivery of agreed AH non-lead assets volumes | PCD | 3047 volume interventions - mainly pipeline, civils, plant & equipment | Slower progress on some deliverables as we further refine delivery approach. Some deliverables tracking ahead of total volumes. On track for 5 year output | Slower progress on some deliverables as we further refine delivery approach. Some deliverables tracking ahead of total volumes. On track for 5 year output | Delivered a significant increase in non-lead PCD volumes. On track for the year 5 output. | Delivered an increase in non-lead PCD volumes. On track for the year 5 output.
Bacton terminal site redevelopment | Deliver a Final Options Selection Report (FOSR) and Re-opener submission | PCD | FOSR Delivery date Feb 2022, Reopener date Sep 2023 | New FOSR and reopener dates of no later than Feb 2024 and August 2025 respectively, as agreed with Ofgem. Further investigation is needed on the condition of below ground pipework to inform final options selection. | New FOSR and reopener dates of no later than Feb 2024 and August 2025 respectively, as agreed with Ofgem. All work is on track for FOSR submission in February 2024 or earlier. | FOSR submitted in February 2024 in line with Ofgem agreement. Cost reopener due to be submitted in September 2024, in line with Ofgem agreement of not later than August 2025 | 50% of the PCD competed in Feb 24' with FOSR submission being made on time. 50% of PCD completed in October 24' with cost submission being made on time / in agreement with the directed license date agreed with Ofgem.
King's Lynn subsidence | Delivery of Re-opener submission | PCD | Delivery date 31/03/2022 | Close-out Reopener submission delivered. Subsidence needs case driver no longer valid so no request for major project funding at this time | Output Fully delivered with alternative specification - Close-out Reopener submission delivered. Subsidence needs case driver no longer valid so no request for major project funding at this time | PCD complete | PCD complete
Colour Coding
On track to achieve target
Medium risk of non-achievement of target
High risk of non-achievement of target
Completed or target achieved

## Outputs -Environmental
Delivering an environmentally sustainable network
Outputs | Description | Output Type | RIIO2 Target |  | RIIO2 (Years 1-4)
|  |  |  | 2021- 22 | 2022- 23 | 2023- 24 | 2024- 25
Greenhouse gas emissions (venting) | Meet greenhouse gas emissions venting targets | ODI-F | <2,897 tonnes | 2031 | 2287 | 2293 | 1982
NTS Shrinkage | Meet our targets for the amount and the cost of the energy we use to run the network | ODI-R | NGT to report on the costs of procured energy compared to ‘perfect foresight’ and ‘pure on the day’ purchases scenarios | 3,506 GWh £190m | 6,795 GWh £578m | 3,090 GWh £108m | 2782 GWh £96.5m
Annual Environmental Report | Publish an Annual Environmental Report | LO | Annual publication | Submitted Oct 2022 | Submitted Oct 2023 | Submitted Oct 2024 | Submitted Oct 2025
Deliver our Baseline Environmental Incentive targets | Reduce operational transport emissions | ODI-F | 12% reduction in operational transport emissions against baseline level of 1748 tCO2e | 0.2% increase in operational transport emissions against baseline to 1751.25 tCO2e | 2.8% increase in operational transport emissions against baseline to 1797 tCO2e | -0.3% decrease in operational transport emissions compared to baseline levels (1742.8 tCO2e) | 8% increase of operational transport emissions to 1895.62 tCO2e compared to baseline levels (1748 tCO2e)
| Reduce business mileage emissions | ODI-F | 3% reduction in business mile emissions against baseline level of 1608 tCO2e | 62.3% decrease in business mile emissions against baseline to 605.89 tCO2e | 53.9% decrease in business mile emissions against baseline to 741 tCO2e | 47.1% decrease in business mile emissions to 850.1 tCO2e | 52% decrease of business mileage emissions to 776 tCO2e
| Reduce office and operational waste recycling | ODI-F | 52% of office and operational waste recycled | 32.6% recycled | 37.6% recycled | 49.2% recycled | 50% recycled
| Reduce office waste | ODI-F | An increasing % reduction in office waste against baseline level of 54.6 tonnes- target % values within license | NGT achieved a 48.72% decrease in office waste. This resulted in NGT being between the reward target threshold and of 52% but above the penalty threshold of 44%; 28 tonnes of office waste with 14.81 tonnes recycled | NGT achieved a 40.44% decrease in office waste against baseline; This represents an increase of 16.14% in total waste compared to the previous years performance meaning NGT fell below the starting penalty threshold of 46%; 32.52 tonnes of office waste with 12.26 tonnes recycled. | NGT achieved a 63.81% decrease in office waste against their baseline exceeding the reward threshold level 57%. This represents an decrease of 39.24% in total waste compared to the previous years performance; 19.76 tonnes of office waste with 9.36 tonnes recycled | NGT achieved a 58.92% decrease in office waste against baseline. However this does represent an increase of 13.51% in total waste compared to the previous years performance and is between the reward and penalty thresholds for reward (61%)and penalty (53%) this year; 22.43 tonnes of office waste with 9.38 tonnes recycled
| Reduce office water use | ODI-F | 3% reduction in water use against baseline level of 7,380 m3 | 77% decrease in water use against baseline to 1,699 m3 | 47% decrease in water use against baseline to 3,910 m3 | 57.7% decrease in water use to 3,124 m3 | 64.1% decrease in water use to 2648 m4
| Increase the environmental value of non-operational land | ODI-F | 1.4% increase in natural capital valuation against baseline level of £32.92m | 2.2% increase in natural capital valuation | 4.5% increase in natural capital valuation | 3.2% increase in natural capital valuation | 3.4% increase in natural capital valuation |  | 0 | 0 | 0 | 0 | 0
| Increase the biodiversity net gain on new network projects | ODI-F | N/A | Not triggered in 2021/22 | Not triggered in 2022/23 | Not triggered in 2023/24 | Not triggered in 2024/25
Redundant assets | Decommission 80 redundant assets/asset sites, five customer sites and four compressors | PCD | Delivery date Mar 2026 | 5 Redundant Asset outputs have been physically delivered in year 1. 3 outputs are no longer redundant due to an external customer impact. All remaining outputs are on track to be delivered by year 5. | 9 Redundant Asset outputs have been physically delivered in total, pending project close out. 3 outputs are no longer redundant due to an external customer impact, 13 condensate tank outputs are being reassessed to determine the most appropriate intervention due to a change in risk. All remaining outputs are on track to be delivered by year 5. | 15 Redundant Asset outputs have been physically delivered in total. 8 outputs have a provisional classification of not progressing due to changing circumstances and customer requirements. Remaining outputs are on track to be delivered by year 5. | 16 Redundant asset outputs delivered. 11 no longer progressing due to changes in customer requirements or site circumstances. Seven outputs currently experiencing delays, with a risk that some may extend into the RIIO-GT3 period. The remaining 50 outputs on track for delivery by end of year five.
Incremental Capacity | Needs case submission and FIOC Project Direction submission (Re-opener allowance request) for in-flight Western Gas Network project (Milford Haven PARCA) | Re-opener | Needs Case submission June 2021 | Needs Case submitted June 2021 (approved Dec 2021), FIOC Project Direction submission on track for June 2023 | Needs Case submitted June 2021 (approved Dec 2021), FIOC Project Direction submission on track for June 2023 | Needs Case submitted June 2021 (approved Dec 2021). FIOC Project Direction submitted May 2023. Updated consultation response on track for July 2024 | Need Case submission in June 2021. FIOC Project Direction sub May 2023. Consultation response July 2024. Customer terminated PARCA in 2024 and original project no longer prepressing via this UM. RIIO-GT3 BP resubmitted the West Import Resilience Project which is a combination of Baseline and UM funded requests.
Compressor emissions - (Wormington, Peterborough and Huntingdon, Kings Lynn and St Fergus, | Deliver a Final Options Selection Report, long lead items and Reopener submission for Wormington | PCD | FOSR delivery date May 2022, Reopener date Nov 2024 | Agreed Reopener timelines on track | Agreed Reopener timelines on track | Agreed Reopener timelines on track | Agreed Reopener timelines on track
Hatton - emissions compliance | Deliver emissions compliance at Hatton with a new unit scoped and procured to deliver 41MW mechanical output power. | PCD | Delivery date Mar 2025 | On track for delivery Mar 2025 | On track for delivery Mar 2025 | On track for delivery Mar 2025 Except Hatton Project experiencing slippage but is expected to complete in RIIO2 | Project experienced programme slippage and is expected to gain operational acceptance in September 2025 with asset acceptance being achieved by end of February 2026 | Updated
Colour Coding
On track to achieve target
Medium risk of non-achievement of target
High risk of non-achievement of target
Completed or target achieved
Note on F11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I have 32.6% as per cell E84 in table 8.3 Reply: Updated in line with this
Note on G11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I have 37.6 as per cell L84 in *.3 Reply: Updated in line with this
Note on H11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I have 49.2 as per cell S84 in 8.3 Reply: Updated in line with this
Note on I13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Incorrect total Reply: Total should be 2648 Reply: Agreed this has been updated
Note on I19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Acceptance is stated as February 2026

## Totex Performance
Totex Performance (Core and Uncertain Mechanisms)
|  | Expenditure |  | RIIO 2 - Years 1-4 (18/19 Prices)
|  |  | 2021- 22 | 2022- 23 | 2023- 24 | 2024- 25 | Cumulative
| Transmission Owner | Allowance | 311.7631 | 407.544 | 446.8292 | 492.3918 | 1658.5281
|  | Actual | 291.1973 | 341.0961 | 396.5268 | 507.054 | 1535.8741
|  | Overspend (underspend) | -20.5658 | -66.4479 | -50.3024 | 14.6622 | -122.654
| System Operator | Allowance | 91.46 | 91.0436 | 105.1607 | 107.4008 | 395.0652
|  | Actual | 71.4207 | 66.0007 | 80.0708 | 84.6538 | 302.146
|  | Overspend (underspend) | -20.0393 | -25.0429 | -25.0899 | -22.747 | -92.9192
| Total | Allowance | 403.2231 | 498.5877 | 551.9899 | 599.7926 | 2053.5933
|  | Actual | 362.6179 | 407.0968 | 476.5976 | 591.7078 | 1838.0201
|  | Overspend (underspend) | -40.6051 | -91.4909 | -75.3923 | -8.0849 | -215.5732

## Totex Breakdown (TO)
Totex Performance including Uncertain Mechanism Expenditure (Transmission Operator) -18/19 Prices
| Cost category | Cost type | Cost Description |  | RIIO 2 (Actual) Years 1-4 |  |  |  |  | RIIO 2 (Allowance) Years 1-4 |  |  |  |  | RIIO 2 (Variance) Years 1-4
|  |  |  | 2021- 22 | 2022- 23 | 2023- 24 | 2024- 25 | Cumulative | 2021- 22 | 2022- 23 | 2023- 24 | 2024- 25 | Cumulative | 2021- 22 | 2022- 23 | 2023- 24 | 2024- 25 | Cumulative
| Capex | Load Related Capex | Entry & Exit/Offtakes/Network capabilities/Customer Contributions/Net Zero | 5.0852 | 4.038 | 2.3511 | 3.8212 | 15.2955 | 1.9998 | 3.0394 | 2.3948 | 1.9866 | 9.4207 | 3.0854 | 0.99856 | -0.043754 | 1.8347 | 5.8748
|  | Non-load related | Compressor emissions | 16.7777 | 26.491 | 32.4715 | 47.2823 | 123.0225 | 12.4407 | 36.521 | 68.2589 | 33.6047 | 150.8252 | 4.337 | -10.03 | -35.7874 | 13.6776 | -27.8027
|  |  | Asset Health | 61.3152 | 81.6657 | 100.9908 | 141.9797 | 385.9513 | 89.6587 | 105.1758 | 108.2287 | 139.7176 | 442.7808 | -28.3435 | -23.5101 | -7.2379 | 2.2621 | -56.8295
|  |  | Other Non-load | 43.5104 | 46.3674 | 27.5383 | 31.8536 | 149.2697 | 26.16 | 40.7544 | 31.2614 | 23.6606 | 121.8364 | 17.3504 | 5.6129 | -3.7231 | 8.193 | 27.4332
|  |  |  | 121.6033 | 154.5241 | 161.0006 | 221.1155 | 658.2435 | 128.2593 | 182.4512 | 207.749 | 196.9829 | 715.4424 | -6.656 | -27.9272 | -46.7484 | 24.1326 | -57.199
|  | Non operational & other capex | Non-operational capex | 31.4205 | 8.6014 | 20.7825 | 25.443 | 86.2474 | 28.0224 | 27.2324 | 24.452 | 22.1043 | 101.8111 | 3.3981 | -18.631 | -3.6695 | 3.3387 | -15.5637
|  |  | Other | 31.7169 | 59.5674 | 83.2148 | 116.4452 | 290.9443 | 35.8267 | 64.8896 | 85.976 | 132.6518 | 319.3442 | -4.1098 | -5.3222 | -2.7612 | -16.2066 | -28.3999
|  |  |  | 63.1374 | 68.1688 | 103.9973 | 141.8882 | 377.1917 | 63.8491 | 92.1221 | 110.4279 | 154.7562 | 421.1553 | -0.71167 | -23.9532 | -6.4307 | -12.868 | -43.9635
| Opex | Indirect Opex | Business support/Closely associated/Other costs | 60.1371 | 71.5375 | 88.0577 | 102.9128 | 322.645 | 75.3 | 87.7918 | 84.2889 | 94.9251 | 342.3058 | -15.1629 | -16.2543 | 3.7688 | 7.9877 | -19.6607
|  | Direct Opex | Network operating cost | 41.2343 | 42.8277 | 41.1201 | 37.3162 | 162.4983 | 42.3548 | 42.1396 | 41.9685 | 43.7411 | 170.204 | -1.1206 | 0.68813 | -0.84837 | -6.4248 | -7.7056
|  |  |  | 101.3713 | 114.3652 | 129.1778 | 140.229 | 485.1434 | 117.6549 | 129.9313 | 126.2574 | 138.6662 | 512.5097 | -16.2835 | -15.5661 | 2.9204 | 1.5628 | -27.3664
|  |  | Total Totex | 291.1973 | 341.0961 | 396.5268 | 507.054 | 1535.8741 | 311.7631 | 407.544 | 446.8292 | 492.3918 | 1658.5281 | -20.5658 | -66.4479 | -50.3024 | 14.6622 | -122.654
Note: Brackets denote underspend

## Totex Breakdown (SO)
Totex Performance including Uncertain Mechanism Expenditure (System Operator) -18/19 Prices
| Cost category | Cost type | Cost Description |  | RIIO 2 (Actual) Years 1-4 |  |  |  |  | RIIO 2 (Allowance) Years 1-4 |  |  |  |  | RIIO 2 (Variance) Years 1-4
|  |  |  | 2021- 22 | 2022- 23 | 2023- 24 | 2024- 25 | Cumulative | 2021- 22 | 2022- 23 | 2023- 24 | 2024- 25 | Cumulative | 2021- 22 | 2022- 23 | 2023- 24 | 2024- 25 | Cumulative
| Capex | Non-operational capex | Non-operational capex | 16.1779 | 16.743 | 24.9632 | 28.6443 | 86.5284 | 24.8388 | 26.881 | 42.9894 | 36.2641 | 130.9733 | -8.6608 | -10.138 | -18.0262 | -7.6197 | -44.4448
|  | Other | Resilience | 1.7576 | 0.25958 | 1.1136 | 1.9259 | 5.0567 | 1.7637 | 0.25958 | 0.62707 | 7.6541 | 10.3045 | -0.00616 | 0 | 0.48655 | -5.7282 | -5.2478
|  |  |  | 17.9355 | 17.0026 | 26.0769 | 30.5702 | 91.5851 | 26.6025 | 27.1406 | 43.6165 | 43.9182 | 141.2778 | -8.667 | -10.138 | -17.5397 | -13.3479 | -49.6926
| Opex | Indirect Opex | Business support/Closely associated/Other costs | 28.7435 | 26.2375 | 31.6416 | 32.7516 | 119.3741 | 35.6062 | 34.298 | 32.1017 | 34.3189 | 136.3248 | -6.8627 | -8.0606 | -0.4601 | -1.5673 | -16.9507
|  | Direct Opex | Network operating costs Opex | 24.7417 | 22.7607 | 22.3524 | 21.332 | 91.1868 | 29.2513 | 29.605 | 29.4426 | 29.1637 | 117.4626 | -4.5096 | -6.8443 | -7.0902 | -7.8318 | -26.2758
|  |  |  | 53.4852 | 48.9982 | 53.9939 | 54.0836 | 210.5609 | 64.8575 | 63.9031 | 61.5442 | 63.4827 | 253.7874 | -11.3723 | -14.9049 | -7.5503 | -9.3991 | -43.2266
|  |  | Total Totex | 71.4207 | 66.0007 | 80.0708 | 84.6538 | 302.146 | 91.46 | 91.0436 | 105.1607 | 107.4008 | 395.0652 | -20.0393 | -25.0429 | -25.0899 | -22.747 | -92.9192
Note: Brackets denote underspend

## Totex Incentive Mechanism
Totex Incentive Mechanism: RIIO2 -18/19 Prices
| Transmission Owner |  |  | RIIO 2 (Years 1-4)
|  |  | 2021- 22 | 2022- 23 | 2023- 24 | 2024- 25 | Cumulative
|  | Total allowed expenditure | 311.7631 | 407.544 | 446.8292 | 492.3918 | 1658.5281
|  | Actual expenditure | 291.1973 | 341.0961 | 396.5268 | 507.054 | 1535.8741
|  | Overspend (underspend) | -20.5658 | -66.4479 | -50.3024 | 14.6622 | -122.654
|  | Totex incentive mechanism (company share) | -8.0207 | -25.9147 | -19.6179 | 5.7182 | -47.8351
|  | Allowed expenditure after sharing | 299.218 | 367.0108 | 416.1447 | 501.3357 | 1583.7091
| System Operator | Total allowed expenditure | 91.46 | 91.0436 | 105.1607 | 107.4008 | 395.0652
|  | Actual expenditure | 71.4207 | 66.0007 | 80.0708 | 84.6538 | 302.146
|  | Overspend (underspend) | -20.0393 | -25.0429 | -25.0899 | -22.747 | -92.9192
|  | Totex incentive mechanism (company share) | -7.8153 | -9.7667 | -9.7851 | -8.8713 | -36.2385
|  | Allowed expenditure after sharing | 79.236 | 75.7675 | 89.8559 | 93.5252 | 338.3845
| Total | Total allowed expenditure | 403.2231 | 498.5877 | 551.9899 | 599.7926 | 2053.5933
|  | Actual expenditure | 362.6179 | 407.0968 | 476.5976 | 591.7078 | 1838.0201
|  | Overspend (underspend) | -40.6051 | -91.4909 | -75.3923 | -8.0849 | -215.5732
|  | Totex incentive mechanism (company share) | -15.836 | -35.6814 | -29.403 | -3.1531 | -84.0736
|  | Allowed expenditure after sharing | 378.4539 | 442.7782 | 506.0006 | 594.8609 | 1922.0936

## TO + SO Incentive Performance
Incentive Performance: : RIIO2 (Years 1-4)
Earned1 all in 2018/19 prices
|  | 2021- 22 | 2022- 23 | 2023- 24 | 2024- 25 | Total Earned | RIIO2 Incentive cap (yrs 1-4)
Transmission Owner
| Customer satisfaction output | 3.645 | 3.645 | 3.645 | 3.645 | 14.58 | 14.6
| Baseline Environmental Incentive Targets | 0.051611 | 0.11575 | 0.11587 | 0.1 | 0.4 | 1.4
System Operator
| Greenhouse gas emissions | 1.5 | 1.1 | 1.2 | 1.5 | 5.3 | 6
| Quality of demand forecasting | 0.17439 | -0.19183 | 0.25649 | 0.2 | 0.5 | 6
| Residual balancing | 0.5798 | -0.042091 | 0.83522 | 1.1 | 2.4 | 6.4
| Maintenance | 0.5 | 0.5 | 0.5 | 0.5 | 2 | 2
| Entry and Exit capacity constraint management | 5.2 | 4.5848 | 3.7082 | 3.8 | 17.3 | 20.8
| Total incentives | 11.6508 | 9.7116 | 10.2607 | 10.845 | 42.48 | 57.2
1 There is a 2 year lag for earned incentives so 2021-22 performance will be paid in 2023-24

## Stakeholder Satisfaction Survey
Stakeholder Satisfaction Survey Results (out of 10)
RIIO2 (Years 1-4)
|  | 2021- 22 | 2022- 23 | 2023- 24 | 2024- 25
| NGT | 8.5423 | 8.6867 | 8.752 | 7.93

## Customer Satisfaction Survey
Customer Satisfaction Survey Results (out of 10)
RIIO2 (Years 1-4)
|  | 2021- 22 | 2022- 23 | 2023- 24 | 2024- 25
| NGT | 8.6306 | 8.6035 | 8.5586 | 8.89

## BCF Emissions
Business Carbon Footprint by Scope (tonnes of CO2 equivalent)
RIIO2 (Years 1-4)
| Scope | 2021- 22 | 2022- 23 | 2023- 24 | 2024- 25
| Scope 1 | 262911.8421 | 367497 | 343148.614 | 294647.194
| Scope 2 | 33611.82 | 37733 | 37394.11 | 33537
| Scope 3 | 255.98 | 604.8011 | 869.804 | 786.5639
| Total BCF | 296779.6421 | 405834.8011 | 381412.528 | 328970.7579

## Gas Activity
NGT Gas outputs
[18 empty] | RIIO2 (Years 1-4) | [5 empty] | RIIO2 (Years 1-4)
|  |  | Spare2 | Spare3 | Spare4 | Spare5 | Spare6 | Spare7 | Spare8 | Spare9 | Spare10 | Spare11 | Spare12 | Spare13 | Unit |  | 2021- 22 | 2022- 23 | 2023- 24 | 2024- 25 | Unit |  | 2021- 22 | 2022- 23 | 2023- 24 | 2024- 25
Total Annual Gas Output | [14 empty] | GWh |  | 889372.2218 | 1026818.37 | 830099.34 | 814552.8266 | BCM |  | 81.0567 | 93.5834 | 75.6546 | 74.2377
|  | GB Output | [14 empty] | 742263.39 | 683172.89 | 620909.61 | 623792.8571 |  |  | 67.6493 | 62.2639 | 56.5892 | 56.852
|  | Export Output | [14 empty] | 106200.5 | 284060 | 155177.43 | 131952.46 |  |  | 9.679 | 25.889 | 14.1428 | 12.026
|  | Storage & Shrinkage | [14 empty] | 40908.3318 | 59585.48 | 54012.3 | 58807.5095 |  |  | 3.7284 | 5.4306 | 4.9226 | 5.3597
Total Annual Gas Output _ Breakdown
Actual NTS output (by LDZ)
|  | Scotland | [12 empty] | GWh |  | 46896.18 | 41921.02 | 41950.48 | 41667.36 | BCM |  | 4.2741 | 3.8206 | 3.8233 | 3.7975
|  | Northern | [12 empty] | GWh |  | 30754.97 | 27134.06 | 26174.76 | 26837.3 | BCM |  | 2.803 | 2.473 | 2.3855 | 2.4459
|  | North West | [12 empty] | GWh |  | 67466.88 | 59279.76 | 57733.8 | 59768.16 | BCM |  | 6.1489 | 5.4027 | 5.2618 | 5.4472
|  | North East | [12 empty] | GWh |  | 35990.32 | 31482.26 | 31205.81 | 31898.89 | BCM |  | 3.2801 | 2.8693 | 2.8441 | 2.9072
|  | East Midlands | [12 empty] | GWh |  | 57404.66 | 49519.91 | 48718.8 | 51010.42 | BCM |  | 5.2318 | 4.5132 | 4.4402 | 4.6491
|  | West Midlands | [12 empty] | GWh |  | 44550.28 | 39150.93 | 37199.43 | 39591.18 | BCM |  | 4.0603 | 3.5682 | 3.3903 | 3.6083
|  | Wales North | [12 empty] | GWh |  | 6581.03 | 5753.62 | 5584.31 | 5826.72 | BCM |  | 0.59979 | 0.52438 | 0.50895 | 0.53104
|  | Wales South | [12 empty] | GWh |  | 21106.11 | 18649.23 | 18571.74 | 20519.51 | BCM |  | 1.9236 | 1.6997 | 1.6926 | 1.8701
|  | Eastern | [12 empty] | GWh |  | 42273.91 | 37042.41 | 36084.68 | 38185.29 | BCM |  | 3.8528 | 3.376 | 3.2887 | 3.4802
|  | North Thames | [12 empty] | GWh |  | 51003.62 | 44806.87 | 43823.82 | 45693.92 | BCM |  | 4.6484 | 4.0837 | 3.9941 | 4.1645
|  | South East | [12 empty] | GWh |  | 42951.88 | 35946.75 | 35058.61 | 38349.55 | BCM |  | 3.9146 | 3.2762 | 3.1952 | 3.4951
|  | southern | [12 empty] | GWh |  | 39691.89 | 34500.08 | 33581.42 | 35665.83 | BCM |  | 3.6175 | 3.1443 | 3.0606 | 3.2506
|  | South West | [12 empty] | GWh |  | 29146.99 | 25476.19 | 24547.56 | 25526.12 | BCM |  | 2.6564 | 2.3219 | 2.2372 | 2.3264
[15 empty] | GWh | Total | 515818.72 | 450663.09 | 440235.22 | 460540.25 | BCM | Total | 47.0113 | 41.0731 | 40.1227 | 41.9733
Interconnector export
|  | Moffat | [12 empty] | GWh |  | 57290.79 | 61902.88 | 58621.88 | 64364.19 | BCM |  | 5.2214 | 5.6418 | 5.3428 | 5.8661
|  | IUK | [12 empty] | GWh |  | 48909.71 | 222157.12 | 96555.55 | 67588.27 | BCM |  | 4.4576 | 20.2472 | 8.8 | 6.1599
[15 empty] | GWh | Total | 106200.5 | 284060 | 155177.43 | 131952.46 | BCM | Total | 9.679 | 25.889 | 14.1428 | 12.026
NTS direct connect industrials (by LDZ)
|  | Scotland | [12 empty] | GWh |  | 4028.19 | 4509.5 | 3746.09 | 2677.61 | BCM |  | 0.36713 | 0.41099 | 0.34142 | 0.24404
|  | Northern | [12 empty] | GWh |  | 6151.76 | 2977.2 | 967.55 | 957.63 | BCM |  | 0.56067 | 0.27134 | 0.088182 | 0.087278
|  | North West | [12 empty] | GWh |  | 3897.49 | 2139.98 | 2027.62 | 1664.41 | BCM |  | 0.35521 | 0.19504 | 0.1848 | 0.15169
|  | North East | [12 empty] | GWh |  | 1867.03 | 1578.33 | 1647.72 | 1769.37 | BCM |  | 0.17016 | 0.14385 | 0.15017 | 0.16126
|  | East Midlands | [12 empty] | GWh |  | 12069.25 | 11538 | 10641.58 | 8686.02 | BCM |  | 1.1 | 1.0516 | 0.96987 | 0.79164
|  | West Midlands | [12 empty] | GWh |  | 0 | 0 | 0 | 0 | BCM |  | 0 | 0 | 0 | 0
|  | Wales North | [12 empty] | GWh |  | 0 | 0 | 0 | 0 | BCM |  | 0 | 0 | 0 | 0
|  | Wales South | [12 empty] | GWh |  | 0 | 0 | 0 | 0 | BCM |  | 0 | 0 | 0 | 0
|  | Eastern | [12 empty] | GWh |  | 0 | 0 | 0 | 0 | BCM |  | 0 | 0 | 0 | 0
|  | North Thames | [12 empty] | GWh |  | 0 | 0 | 0 | 0 | BCM |  | 0 | 0 | 0 | 0
|  | South East | [12 empty] | GWh |  | 0 | 0 | 0 | 0 | BCM |  | 0 | 0 | 0 | 0
|  | southern | [12 empty] | GWh |  | 0 | 0 | 0 | 0 | BCM |  | 0 | 0 | 0 | 0
|  | South West | [12 empty] | GWh |  | 9.96 | 5.74 | 4.77 | 1.69 | BCM |  | 0.00090775 | 0.00052314 | 0.00043473 | 0.00015403
[15 empty] | GWh | Total | 28023.68 | 22748.75 | 19035.33 | 15756.73 | BCM | Total | 2.5541 | 2.0733 | 1.7349 | 1.4361
NTS direct connect power stations (by LDZ)
|  | Scotland | [12 empty] | GWh |  | 4671.78 | 7359.54 | 2892.04 | 3771.53 | BCM |  | 0.42578 | 0.67074 | 0.26358 | 0.34373
|  | Northern | [12 empty] | GWh |  | 940.14 | 764.02 | 737.42 | 804.03 | BCM |  | 0.085684 | 0.069632 | 0.067208 | 0.073279
|  | North West | [12 empty] | GWh |  | 14671.81 | 10848.18 | 8492.97 | 10918.33 | BCM |  | 1.3372 | 0.98869 | 0.77404 | 0.99509
|  | North East | [12 empty] | GWh |  | 13587.84 | 12667.46 | 9044.44 | 9015.71 | BCM |  | 1.2384 | 1.1545 | 0.8243 | 0.82168
|  | East Midlands | [12 empty] | GWh |  | 52723.53 | 60035.03 | 52211.3 | 45353.2371 | BCM |  | 4.8052 | 5.4715 | 4.7585 | 4.1335
|  | West Midlands | [12 empty] | GWh |  | 0 | 0 | 0 | 0 | BCM |  | 0 | 0 | 0 | 0
|  | Wales North | [12 empty] | GWh |  | 5328.46 | 7337.06 | 3722.08 | 4014.32 | BCM |  | 0.48563 | 0.66869 | 0.33923 | 0.36586
|  | Wales South | [12 empty] | GWh |  | 29542.45 | 29811.98 | 23523.97 | 21642.5 | BCM |  | 2.6925 | 2.717 | 2.144 | 1.9725
|  | Eastern | [12 empty] | GWh |  | 18849.87 | 19940.23 | 15061.22 | 8377.72 | BCM |  | 1.718 | 1.8173 | 1.3727 | 0.76354
|  | North Thames | [12 empty] | GWh |  | 2748.48 | 2457.72 | 1493.01 | 2699.28 | BCM |  | 0.25049 | 0.22399 | 0.13607 | 0.24601
|  | South East | [12 empty] | GWh |  | 17006.6 | 18257.91 | 16740.46 | 15989.59 | BCM |  | 1.55 | 1.664 | 1.5257 | 1.4573
|  | southern | [12 empty] | GWh |  | 24171.95 | 24893.34 | 15421.34 | 14777.31 | BCM |  | 2.203 | 2.2688 | 1.4055 | 1.3468
|  | South West | [12 empty] | GWh |  | 14178.08 | 15388.58 | 12298.81 | 10132.32 | BCM |  | 1.2922 | 1.4025 | 1.1209 | 0.92345
[15 empty] | GWh | Total | 198420.99 | 209761.05 | 161639.06 | 147495.8771 | BCM | Total | 18.0839 | 19.1175 | 14.7317 | 13.4427
Storage
|  | Storage | [12 empty] | GWh | Total | 37402.1 | 52790.33 | 50926.65 | 56025.93 | BCM | Total | 3.4088 | 4.8113 | 4.6414 | 5.1062
Shrinkage
|  | Shrinkage | [12 empty] | GWh | Total | 3506.2318 | 6795.15 | 3085.65 | 2781.5795 | BCM | Total | 0.31956 | 0.6193 | 0.28122 | 0.25351

## Innovation Activity
Network Innovation Allowance
RIIO2 (Years 1-4)
|  | 2021- 22 | 2022- 23 | 2023- 24 | 2024- 25 | Cumulative
| NIA Expenditure (£m) | 2.0046 | 4.0228 | 7.5814 | 6.6152 | 20.224
| Number of projects completed | 6 | 9 | 29 | 19 | 63
Strategic Innovation Fund
RIIO2 (Years 1-4)
|  | 2021- 22 | 2022- 23 | 2023- 24 | 2024- 25 | Cumulative
| SIF Expenditure (£m) | 0.10778 | 2.2957 | 6.7013 | 6.3373 | 15.4421
| Number of projects completed | 0 | 29 | 11 | 5 | 45
Total Innovation Fund
RIIO2 (Years 1-4)
|  | 2021- 22 | 2022- 23 | 2023- 24 | 2024- 25 | Cumulative
| NIA & SIF Expenditure (£m) | 2.1124 | 6.3185 | 14.2828 | 12.9525 | 35.6661
| Number of projects completed | 6 | 38 | 40 | 24 | 108