## GD Responses
Associated Document | Paragraph | Comment | Proposed alternative drafting | Comment Raised by | Date raised | Additional Notes | Ofgem Comment | Status
GD2/GD3 Crossover Condition Guidance Document | General | Ensure principles and processes set out in this draft guidance document are mirrored for RIIO-GD2 close out. Ofgem describes the provisions for GD2/GD3 crossover, as set out in this draft guidance document, to be “complementary to the process for closing out the RIIO-GD2 price control […] the methodology for which will be set out separately by Ofgem.” (section 2.5) Ofgem must ensure consistent treatment of costs and rigour of assessment for items that transect price control periods (e.g. from GD2 to GD3), irrespective of whether there are mechanisms in the GD3 licence to fund any remaining costs (i.e. via close out) or not (i.e. via GD2/GD3 crossover). |  | Cadent | 2026-03-11 |  | The close out methodology is expected to be consulted on in January 2027. As clarified at the working group on 26 March, Ofgem do not intend to use this condition to make all final adjustments to the RIIO-2 outputs. The crossover condition is intended to be used for exceptionally delayed delivery, beyond close out, for which the GDNs would otherwise not be reimbursed. We will ensure that the principles of close out and the cross-over condition adjustments are as aligned as possible (taking the purpose of this condition into consideration). | Closed
GD2/GD3 Crossover Condition Guidance Document | 3.1 | Remove fifth principle - negative adjustment and clawback of RIIO-GD2 allowances. From the way this principle is currently set out, it is unclear to us as to why this is needed. Should Ofgem deem a clawback appropriate, we would expect Ofgem to be able to execute this under the relevant provision of the GD2 allowance at close out and not require an additional provision to use a negative crossover item. Ofgem's intention may be to provide for a mechanism to adjust allowances identified for crossover because Ofgem may take the view there are some inefficiencies in the costs (however this seems to be covered by principle 2 - appropriate remuneration of efficient cost - although not specifically referenced). If Ofgem's intention is to provide for a mechanism to clawback any allowances that have been carried from GD2 to GD3 as a crossover in case of under or non-delivery during GD3, then this should be clearer in the description of the principles. |  | Cadent | 2026-03-11 |  | We expect the crossover condition to only be used for exceptionally delayed delivery. Where appropriate and in line with the principles set out in the guidance document, RIIO2/RIIO3 Crossover adjustments could be negative or positive and could have the effect of clawing back allowances associated with the RIIO2/RIIO3 Crossover item. | Closed
GD2/GD3 Crossover Condition Guidance Document | 4.1 (Evaluative PCDs and reopeners) | Amend cutoff date for GD2 reopener submissions to 31 July 2026 or in line with Ofgem's close out timelines. We do not agree with Ofgem's proposal in regard to reopener submissions made before 31 March 2026. The cut-off date needs to provide for a sufficient period of advanced notification to companies, which is not the case for the proposed date. This is a consultation on a draft guidance document; this cannot conceivably constitute notification to companies given Ofgem may amend both dates and policy in this document ahead of final publication. More perversely, given Ofgem seeks to publish final GD3 associated documents (of which this guidance is part of) on 1 April 2026, the 31 March 2026 date is proposing a deadline for response to Ofgem before this guidance document would take effect. Companies must not be penalised because Ofgem only sought to publish the consultation for this guidance document on 12 February 2026, only 33 working days before the GD3 controls commence. Ofgem must ensure sufficient time is given to companies to consider, compile and put forward a valid application for additional funding or adjustments to outputs under a reopener mechanism under their RIIO-GD2 licence. | We propose a cutoff date for reopener submissions under the GD2 licences should be made before 31 July 2026 (to align with RRP) or in line with Ofgem's close out timelines. | Cadent | 2026-03-11 |  | As of the 1st of April, the reopeners included in the crossover condition will no longer be active in the licence, thus meaning that applications will not be possible under those reopener mechanisms. If an alternative reopener mechanism is identified that exists in the RIIO-3 licence, licensees can apply under said reopener instead. | Closed
GD2/GD3 Crossover Condition Guidance Document | 4.1 (MOBs safety reopener) | With reference to the issue of re-assessment of our MOBs safety reopener application set out below, we note that we operate on the basis that Ofgem's initial position on this query still stands, which is to re-review our application as part of closeout. We previously engaged with Ofgem on this in July 2025 where it was indicated for this to be considered as part of RIIO-GD2 close out. However, the provision in this GD2/GD3 guidance document in section 4.1 suggest Ofgem seeks an alternative route through which this issue may be handled (including a cutoff date) to making a formal application. |  | Cadent | 2026-03-11 |  | If delivery of this output falls under close out, the crossover condition will not apply and no further adjustments will be made. | Closed
GD2/GD3 Crossover Condition Guidance Document | 5.5/5.6 | We object to this provision. Ofgem must set out a process of notification and engagement with companies to accompany the intention of making any such adjustments (analogous to the process set out for adjustments initiated by GDNs in section 5.9). With reference to the illustrative example noted in 5.6, by 31 March 2026 Ofgem must have a complete list of any such funding decisions which it has already made for which there is not a suitable alternative mechanism available in the GD3 licence. This list must be included in the guidance document to set out to licensees the adjustments Ofgem seeks to make under this provision of the guidance document. |  | Cadent | 2026-03-11 |  | We expect this condition to apply for RIIO2 conditions with delayed delivery beyond close-out. The re-opener submission dates for RIIO-2 reopeners will not be affected – the 31 March 2026 still applies unless stated otherwise in the condition or unless there is an alternative re-opener in RIIO-3 to cover the work planned. | Closed
GD2/GD3 Crossover Condition Guidance Document | 5.8 | We ask Ofgem to clarify whether the provisions in this section are also to accommodate possible mid-period adjustments to allowances which had previously been agreed to crossover from GD2 to GD3. |  | Cadent | 2026-03-11 |  | Yes, the provisions in this condition also allow for midterm adjustments if necessary. | Closed
GD2/GD3 Crossover Condition Guidance Document | 5.14 | Ofgem must set realistic, but binding timelines, for this assessment and decision for applications under this guidance document to support the much-sought acceleration of regulatory decision-making processes. In line with Ofgem’s decision to amend the consultation period of self-modifications to our licence from “not less than 28 days” to “up to 28 days”, we encourage Ofgem to extend the same spirit to accelerating regulatory decisions for assessment of applications under this guidance document. As Ofgem set out in its Decision RIIO-3 Licence Drafting modifications, “[…] stakeholders have previously expressed that they value quick decisions from Ofgem. It is important that we are in a position to make those quick decisions […]”. Our view is that Ofgem’s position in this draft in unambitious and not in line with its clear desire to accelerate regulatory decisions, a position we fully support. We propose Ofgem sets out clear timelines for assessment and decisions for applications under this guidance document. Specifically, we suggest setting out in the guidance documents a timeframe of 28 working days for simple decisions, and 56 working days for complex decisions. It is our view that these are adequate timeframes for Ofgem to make a decision. We recognise that Ofgem is reliant on information from companies – and the quality of such information should not impair Ofgem’s ability to meet the aforementioned timelines for decision-making. Should Ofgem identify any shortfalls in quality of information they have received from companies, Ofgem should exercise a ‘stop the clock’ mechanism, with the clock restarting one working day after Ofgem have received updated correspondence from the relevant company. |  | Cadent | 2026-03-11 |  | We will consider this feedback and aim to reach decisions promptly. This will depend on a number of factors including the networks' provision of data. | Closed
GD2/GD3 Crossover Condition Guidance Document | General | Whilst this consultation refers directly to the GD2/GD3 cross-over period, we think that it is important that such principles are clearly defined and can be applied to the eventual GD3/GD4 cross-over period. |  | SGN | 2026-03-16 |  | Ths document will provide suitable guidance for the GD2/GD3 transition and may be updated accordingly to reflect the GD3/GD4 transition. The principles and scope of the guidance will likely remain similar for future price control periods if this crossover mechanism is required in the GD4 licence. | Closed
GD2/GD3 Crossover Condition Guidance Document | Observations on crossover mechanism | Alignment between close-out process and crossover mechanism. Where projects and outputs are delivered shortly after the GD3 period but before the close-out consultation process is finalised, then we consider that utilising the close-out process is the preferable process to the crossover mechanism. It is our view that accommodation through the GD2/GD3 crossover mechanism should be for those projects that are extending significantly beyond the close out consultation period and its use should be kept to a minimum. |  | SGN | 2026-03-16 |  | Drafting has been included in the document to set out when the crossover mechanism should be used, and acknowledges that close-out or an alternative reopener mechanism may be more appropriate for GDNs to use. | Closed
GD2/GD3 Crossover Condition Guidance Document | Observations on crossover mechanism | Programmes of work. Where there are programmes of work that are carried across price control periods (ie. There is an output in GD2 and there is an updated output in GD3 for the same workload), then any adjustment in workload should be accounted for in the GD3 business plan and should not need to be accommodated through the GD2/GD3 mechanism. |  | SGN | 2026-03-16 |  | We have noted this comment. | Closed
GD2/GD3 Crossover Condition Guidance Document | PCD delivery | There are valid reasons why PCD outputs may not be delivered in the anticipated timeline (such as unanticipated planning requirements or delivery restrictions imposed by third parties). It is important that these should be accommodated, within reason, without the network being penalised. While we anticipate that all our outputs should be delivered by the 1st of April, there may be a few that are delivered shortly afterwards, we do not anticipate any will extend beyond the close out consultation and are likely to require the GD2/GD3 cross-over mechanism, but there are still project delivery risks and as such it cannot be ruled out. |  | SGN | 2026-03-16 |  | We agree. The crossover mechanism is in place to act as a backstop in case projects are delayed and neither the close-out process, nor another alternative reopener mechanism, are suitable to extend funding into the GD3 period. | Closed
GD2/GD3 Crossover Condition Guidance Document | 2.12 | This paragraph identifies where a PCD is assessed as not being fully delivered, there could be a reduction in allowances through the GD2 close-out process and that these allowances may then be reinstated through the crossover mechanism. If an adjustment is to take place in this manner it is very important that this is completed at the same time, to avoid uncertainty. There is a risk that any delay between the close-out adjustment and the implementation of the crossover adjustment could lead to uncertainty and even project stoppage that could then increase costs of demobilisation and remobilisation. Careful consideration will also need to be given to inflation and real price effect adjustments during that adjustment process. |  | SGN | 2026-03-16 |  | We have noted this comment. We will, to the extent possible, align the close-out methodology with the cross-over condition assessment process. The close-out methodology is currently still under development, and will be confirmed in due course. | Closed
GD2/GD3 Crossover Condition Guidance Document | 3.1 | Section 3.1 identifies the process of where a negative adjustment could be applied. It is important to clarify the context in which a negative adjustment would be implemented. Our understanding is that under an evaluative PCD, there is the option under a partial completion to clawback an element of the funding associated with non-delivery for the part that was not delivered. It is important to be clear that it is only in these circumstances (mirroring the associated documents) that a claw back would be applied and then to establish the process for clawback. There would be two immediate examples, firstly if a project was not fully completed in GD2, in the GD2 close-out process it was determined that it was no longer in consumer interests to fully complete the project as intended and the output is therefore recalibrated. Or secondly, if a project was not fully complete in GD2, however, in the GD2 close-out process it was determined that the full deliverable remained in consumer interests and the stated intention going into the GD2 / GD3 crossover mechanism is for a full completion after which it was later determined that full completion was not in consumer interests and an adjustment needed to be made. We do not see the basis for other negative adjustments. |  | SGN | 2026-03-16 |  | The PCD evaluation is deferred until the claw back is in place. | Closed
GD2/GD3 Crossover Condition Guidance Document | Unused UIOLI | In terms of UIOLI funds (NIA, NZARD and VCMA) it is important that networks are able to close out projects in a robust manner recognising that these funding mechanisms are often in place with third parties and due to the innovative nature of the work and the close dependency on third parties, may not be within the networks control, or effectively risks sterilising the last months of the price control for further investment due to delivery risk. This is recognised for NIA with the CNIA, this should also be extended to NZARD and VCMA for a limited time period |  | SGN | 2026-03-16 |  | NZARD is accounted for in the crossover condition under the term 'RDFt'. As agreed at the Working Group, please provide the additional RIIO2 Crossover Items that should be included in the licence condition. | Closed
GD2/GD3 Crossover Condition Guidance Document | Application to GD3/GD4 | As set out above we think that it is important to have the mechanism for GD3/4 defined in advance. Particularly with Cyber PCDs and reopeners that come relatively late in the price control process, they have been constrained by not having a mechanism to provide confidence in funding in the next price control period. Having such a mechanism in place early provides for an opportunity to remove this uncertainty and provide continuity of funding for large delivery projects over a price control border. |  | SGN | 2026-03-16 |  | We will continue to monitor and update the crossover guidance as appropriate throughout the price control period. | Closed
GD2/GD3 Crossover Condition Guidance Document | Submission of request | Whilst we appreciate the flexibility of submitting a request at any point within the price control period, we would suggest that the natural time for a request to be submitted would be during the close-out process, and then if required, then we would anticipate that it would be at the point of RRP reporting in July. We would anticipate however, that the majority of these requests would be for the GD3/GD4 crossover. |  | SGN | 2026-03-16 |  | We would expect the same. Please highlight any areas that might not apply. | Closed
GD2/GD3 Crossover Condition Guidance Document | Consultation | Given that this will be a licence modification, we assume that this will require a consultation and associated statutory consultation before the change can come into effect. It would be good to clarify this process. |  | SGN | 2026-03-16 |  | Document will be pubilshed for further consultation on the 1st of April. The consultation is to make adjustments to the guidance document. Any further changes to the licence condition will take place under statutory consultation. | Closed

## GT responses
Associated Document | Paragraph | Comment | Proposed alternative drafting | Comment Raised by | Date raised | Additional Notes | Ofgem Comment | Status
GT2/GT3 Crossover condition guidance document | General | 1. NGT needs to understand the circumstances in which Ofgem envisage using the crossover condition. NGT would like to avoid a scenario where all final adjustments will be made via the crossover condition, and our understanding to date is that this is also Ofgem’s view. We note that Ofgem has stated it will use its discretion in applying the crossover mechanism. We consider that Ofgem should adopt a principles-based approach to establishing the circumstances in which the crossover condition may be relevant, and we welcome the opportunity to discuss this. NGT would like to avoid a scenario where all final adjustments will be made via the crossover condition, and our understanding to date is that this is also Ofgem’s view. |  | NGT | 2026-03-12 |  | As clarified at the working group on 26 March, Ofgem do not intend to use this condition to make all final adjustments to the RIIO-2 outputs. The crossover condition is intended to be used for exceptionally delayed delivery, beyond close out, for which NGT would be otherwise not be reimbursed. | Closed
GT2/GT3 Crossover condition guidance document | General | 2. NGT needs sight of the closeout procedure, and how this crossover condition will link to this. Please could Ofgem confirm when this information will be available. |  | NGT | 2026-03-12 |  | Ofgem will consult on the close-out methodology and conditions early in 2027. | Closed
GT2/GT3 Crossover condition guidance document | General | a. General: why does Ofgem consider it necessary / expedient to look afresh at the question of whether to continue an investment and what consumer benefit is attached simply because delivery spans two price control periods? |  | NGT | 2026-03-12 |  | The intention is not to look afresh at consumer benefit for the RIIO-2 outputs. However, in case of a severely delayed delivery of an output (i.e. beyond close out), Ofgem consider it necessary to consider consumer benefit in light of such a delayed delivery. As discussed at the Working Group, we will reconsider the inclusion of consumer benefit in the assessment process. Please provide alternative drafting as part of your response to the guidance consultation. | Closed
GT2/GT3 Crossover condition guidance document | General | b. Reference to ‘beneficial to consumer’ (throughout): if the work has already been started in RIIO-2, then Ofgem will have already assessed the benefit to the consumer in setting the PCD. Why does the end of the price control period immediately lend itself to a re-evaluation of consumer benefit? |  | NGT | 2026-03-12 |  | The intention is not to look afresh at consumer benefit for the RIIO-2 outputs. However, in case of a severely delayed delivery of an output (i.e. beyond close out), Ofgem consider it necessary to consider consumer benefit in light of such a delayed delivery. As discussed at the Working Group, we will reconsider the inclusion of consumer benefit in the assessment process. Please provide alternative drafting as part of your response to the guidance consultation. | Closed
GT2/GT3 Crossover condition guidance document | General | c. Reference to ‘anticipatory basis’ (‘NARM Outputs’ section of the table): We request clarification as to meaning. Does this mean that if the allowances are directed after the NARM output is delivered then output or PCDs will not be introduced? |  | NGT | 2026-03-12 |  | The PCD provission in the crossover is there to hold NGT to account for delivery. However, just because the provision to create an output exists, it does not mean a PCD will be set. We will only introduce new outputs where it is necessary to produce a PCD. | Closed
GT2/GT3 Crossover condition guidance document | General | d. Reference to ‘adjustment to allowances’ (para. 5.9, bullet point 2): Ofgem will have already agreed the spend and Ofgem already has mechanisms in place to claw back allowances so why does it also consider it necessary / expedient to require financial evidence at this point simply because the deliverable spans two price control periods. |  | NGT | 2026-03-12 |  | This condition will not be used where outputs have been delivered and adjustments have been made as part of close-out. | Closed
GT2/GT3 Crossover condition guidance document | General | 4. General principles (section 3): a. The final two bullet points do not appear to be principles. |  | NGT | 2026-03-12 |  | Amended the drafting to separate the last two bullet points from the principles. | Closed
GT2/GT3 Crossover condition guidance document | General | 4. General principles (section 3): b. ‘Negative adjustments and clawback of RIIO-GT2 allowances’ requires clarification. It is unclear how Ofgem could clawback allowances for RIIO-3 spend when no allowances have been directed under RIIO-3 for RIIO-2 PCDs and UIOLI. |  | NGT | 2026-03-12 |  | In case of delayed delivery, for the outputs that are delayed beyond close-out, Ofgem may claw back the spend for the RIIO-2 PCDs and UIOLIs if appropriate. | Closed
GT2/GT3 Crossover condition guidance document | General | c. The inclusion of ‘aim to’ within the drafting provides no certainty for NGT. The guidance specifies that Ofgem must only ‘have regard’ to the principles and it is unreasonable to layer ‘aim to’ on top of this. |  | NGT | 2026-03-12 |  | Removed "aim to" throughout the document, except in para 5.14 where it would be inappropriate to do so. | Closed
GT2/GT3 Crossover condition guidance document | General | 5. The guidance document can be more succinctly drafted: ensuring alignment with the licence condition and removing repetition, unnecessary drafting (e.g. reference to mechanistic PCDs which NGT doesn’t have in RIIO-2) and overly long sentences. |  | NGT | 2026-03-12 |  | We have removed the references to the mechanistic PCD. We will continue to tighten the drafting following further consultation and based on the specific comments we will receive from NGT. | Open