## Sheet1
Ofgem Reference | Date Received | Document | Question | Response
SCL-001 | 2026-03-30 | Draft Licence | Is the intention that the decommissioning fund acts like an escrow or would other instruments (eg bonds) be suitable? We note that there is potential duplication between this requirement under the C&F and obligations planning authorities places on developers to ensure funds for agreed decommissioning will be available. | There is no specification of fund legal form, such as escrow, trust, sinking fund, or similar. The restrictions require strict segregation, but not any particular financial instrument. Requirements affects governance and sufficiency, not the instrument type.
The draft licence requires a ring‑fenced Decommissioning Fund holding dedicated assets, but does not specify that it must operate as an escrow, nor does it explicitly mandate or exclude other financial instruments such as bonds, letters of credit, or surety instruments. It simply requires a segregated, ring‑fenced fund that cannot be used as security or for other purposes.
There is no text addressing interactions with planning‑authority decommissioning security requirements,
Not all planning authorities will require a decommissioning fund: planning policy and practice varies across the UK. The licence must apply consistently across jurisdictions and technology types, so it cannot rely on variable planning outcomes. The licence therefore includes its own decommissioning plan and ring‑fenced fund requirements.
SCL-002 | 2026-03-30 | Draft Licence | We understand that grid connection delays are neither explicitly included nor explicitly excluded from the definition of Force Majeure. We understand that this is to ensure FM remains for truly uncontrollable and unmanageable event; whereas grid connection delays impacting COD may or may not meet this threshold and therefore need to be assessed on case-by-case basis. Can you confirm this is the intended position? | Under the current consultation draft, Force Majeure is intended to be a narrow, evidence‑based route for genuinely uncontrollable events outside the licensee’s reasonable control, with relief conditional on notice, causation and mitigation consistent with Good Industry Practice. The draft does not create an automatic Force Majeure entitlement for grid‑connection delays. Whether a particular delay qualifies would depend on the specific facts and the evidence against the licence definition and process. The draft also includes other routes to address system or network constraints (for example, deemed availability and the Exceptional Event route within the availability framework), which are separate from Force Majeure
SCL-003 | 2026-03-30 | Draft Licence | We note the proposed arrangements for the Delay Penalty Charge where projects overspend the P50 and area delayed beyond the Backstop. We welcome and acknowledge the additional risk mitigation afforded by the introduction of a Longstop date. Our understanding is that Backstop Penalty Charge will be calculated an applied in every year where floor payments are required, meaning that for projects expecting to be regularly at or below the Floor the balance will likely accrue continuously over the regime period, and that as a result equity distributions will be locked up for the period of the regime. We note that this effect would appear to be triggered (with loss of 20% of floor payments) by projects spending £1 over the P50 and going 1 day beyond the Backstop. This appears to be a stark cliff edge, with significant (and potentially unworkable) implications for investability. Are you able to confirm whether this is an intended consequence. | In the draft licence, the Backstop Delay Charge (BDC) does not reduce Floor Support straight away. If a project reaches Full Commissioning after its Backstop Date and later receives Floor Support, the BDC is calculated as a proportion of that Floor Support and added to a running Backstop Delay Repayment Balance. That balance is repaid only from future surpluses above the Floor Level, and while it remains outstanding, distributions are restricted.
The Backstop Delay Factor (BDF), recorded in the FSPR, sets the proportion and is stepped: 20% for commissioning up to one year late, rising by 20 percentage points for each additional year of delay, up to 100% at five years late or more. The draft licence is also clear that the BDC amount is not determined by reference to construction costs or P50/P90 outcomes. We recognise the financeability point you raise, and we are explicitly seeking evidence on whether the overall backstop and delay package is clear, proportionate and avoids avoidable financeability risk.
SCL-004 | 2026-03-30 | Draft Licence | Can you confirm the purpose and intent of the “short cycling” provisions including in Special Condition 12 (Part I). We understand that this is intended to ensure that assets receiving LDES C&F operate as LDES across the full range of durations required by the system, and do not operate exclusively in short duration markets (mimicking existing 2/4-hr batteries on the system). We support this objective, but note potential unintended consequences and need for carefully balanced obligations/prohibitions to ensure that assets operate as intended by the scheme, but are also free to responded effectively to market price signals to deliver where the system needs them most. It would be helpful in shaping our detail consultation response, if you can confirm your intention for this clause. | The draft licence confirms that the “short‑cycling” restrictions are intended to:
Prevent LDES facilities from routinely operating through repeated short‑duration cycles or other cycling patterns that effectively mimic short‑duration/fast‑cycling batteries.
Ensure each LDES facility operates “within the long‑duration envelope” on which it was assessed and approved, including meeting the minimum duration and usable energy capability that was the basis for its selection.
Preserve the integrity of the LDES scheme, i.e. ensuring supported projects genuinely provide long‑duration flexibility and system value, rather than shifting into high‑frequency short‑duration arbitrage behaviour.
We set out the context and questions in the call for input (Section 4.6) and welcome evidence on the right practical balance.
SCL-005 | 2026-03-30 | Draft Licence | Would you agree that the ‘haircut mechanism’ is not required at all given the existing controls already included in other licence conditions? Payments to affiliates are already restricted through the ‘Excluded Costs’ definition (excluded unless the contract is written on arm’s length terms). We have to follow the procurement rules of benchmarking/proving value for money. And Ofgem has full audit rights over all revenues, margins and optimiser fees, so it’s very transparent. We believe that our proposal for Trading & Optimisation is within market level costings and follows arms-length principles, so to penalise further by capping those costs seems unnecessarily punitive. | The draft licence includes additional safeguards where optimiser arrangements involve an Associate or Related Undertaking. This reflects residual consumer‑protection and auditability risks that can remain even with procurement, arm’s‑length expectations and information rights. Under the draft approach, claimed optimiser remuneration is subject to a related‑party adjustment (haircut) before the cap is applied. This is intended as a structural safeguard rather than a case‑by‑case judgement on a particular firm’s pricing. We welcome evidence through the consultation on whether the approach is proportionate and how any parameters should be calibrated to reflect market practice while protecting consumers.
SCL-006 | 2026-03-30 | Draft Licence | Can you be please expand on the new definition of Construction Longstop Date. We can see the intention and interaction with other points, but its definition in terms of time is less clear. | Under the draft licence, the Construction Longstop Date is a project‑specific date recorded in the FSPR. It operates as a final cut‑off for achieving the Full Commissioning Date. If the project has not achieved Full Commissioning by the Longstop Date (as recorded and as may be extended in accordance with the draft licence), a Construction Longstop Event occurs. A Construction Longstop Event can enable Ofgem to revoke the special licence conditions (in whole or in part) following the due‑process steps in the draft.
SCL-007 | 2026-03-30 | Draft Licence | The CFFM produces a total NPV-based cap and floor output across the full regime duration that is then spread across years with a fixed annuity factor, but developers and lenders require a single annualised floor figure, usually expressed as £/MW/year, analogous to the Capacity Market auction and similar long-duration auctions (e.g. MACSE in Italy to make reach FID and support lender credit approval. Will Ofgem commit to confirming at regime award a fixed, annualised floor level per MW that is locked in pre-Financial Close that can be used as the floor reference for financing decisions? +J18 | Under the LDES cap and floor framework, cap and floor levels are set as annual real‑terms revenue annuities for the facility, calculated using the cap and floor financial model. At award, the draft licence proposes that a Preliminary Administrative Floor Level is recorded in the FSPR. For projects using the ACOD approach, the draft licence proposes that a Preliminary ACOD Floor Level is determined following Financial Close using the ACOD parameters and recorded in the FSPR. The framework does not define a separate regulatory parameter in £/MW/year. Where helpful for financing analysis, developers can derive an indicative £/MW/year figure by reference to accredited capacity, but that is not a separate value recorded by Ofgem under the draft.
SCL-008 | 2026-03-30 | Draft Licence | BESS project finance debt will be shorter than a 25-year tenor. The ACOD floor is currently annualised against the actual (shorter) debt tenor in CFFM1, producing a higher annual floor level than the administrative floor annualised over the full 25-year regime duration. How will Ofgem normalise the two approaches so that ACOD projects with shorter debt tenors are not systematically disadvantage relative to the administrative benchmark? | The standard LDES cap and floor regime duration is 25 years, and a shorter duration of no less than 20 years would only be allowed by exception, so our starting point is that supported assets remain in the regime for the approved regime period. The ACOD floor annuity factor is calculated using the debt tenor, which we expect to be broadly the same as the regime length approved for the project, so if a project chooses (or can only secure) a shorter debt tenor than its approved regime length, the annualised ACOD floor during the debt period will, all else equal, be higher. Our concern is consumer exposure: if a shorter debt tenor (without an approved shorter regime duration) would increase floor support, we would expect clear evidence of why that structure is necessary and how it is in consumers’ interests. Ofgem is not proposing to adjust the administrative benchmark to match individual financing choices; any departure from the standard approach would need to be justified as in consumers’ interests.
SCL-009 | 2026-03-30 | Draft Licence | There is no industry precedent for large-scale BESS decommissioning, and battery residual value at the end of regime life is uncertain, resulting in a net cost that could range from a positive terminal value (where battery resale/component value exceeds dismantling and recycling costs) to a material cost. Whilst the DCCt/DCFt mechanism addresses legislative change, it does not address the fundamental uncertainty in predicting decommissioning value or cost at project inception. What methodology is Ofgem using to assess and validate the net decommissioning cost for projects for the Decommissioning Plan specified in SC23, and what is the provision for projects to revise decommissioning cost estimates following regime award outside of DCCt /DCFt? | Under the draft licence, the Licensee must prepare and keep up to date a Decommissioning Plan, including its best estimate of decommissioning costs and any assumptions about residual value, with regard to Good Industry Practice. The licence does not prescribe a specific methodology (for example, P50 or P80 estimates), allowable cost categories, or assumptions on residual value; however, the Decommissioning Plan should reflect the licensee’s reasonable and evidence‑based view of expected costs and values at the time it is prepared, including how uncertainty has been addressed, and how assumptions align with Good Industry Practice. Although Good Industry Practice may not be established within a specific sector, we would expect Projects to have regard to Good Industry Practice in related sectors. The draft licence does not include a routine mechanism to re‑set decommissioning estimates after regime award solely because uncertainty has reduced. Ofgem welcomes consultation evidence on whether additional mechanisms are needed to manage material uncertainty in a clear and enforceable way.
SCL-010 | 2026-03-30 | Draft Licence | The TDD confirmed a limited cost update opportunity in Q2 2026 which is absent from the draft SLC. While this may be due to the SLC only applying post regime award, could we please confirm that this cost update window applies and what the timeline for this will be? | The intention is that projects listed on the Decision List will have an opportunity to submit updated cost information ahead of Final Cap and Floor / Licence Awards. This update window is intended to allow projects to reflect limited changes since the Project Assessment Data submissions and is not an opportunity to reopen or reassess costs.
While this process is not reflected in the draft SLC (which applies post‑regime award), the cost update window confirmed at TDD stage will apply. Further detail on the timing and mechanics of this update window will be provided in due course, ahead of Final Awards.
SCL-011 | 2026-03-30 | Draft Licence | At which point post-regime award, prior to project FID, will Ofgem determine whether the P50 costs are considered efficient to be used to determine the Preliminary cap and floor level? A window for cost update between Q2 2026 and post-regime award, pre-FID is required as capex can shift within that time horizon. | Ofgem will assess whether project capex and cost estimates are economic, efficient and effective at the point it determines the Preliminary Cap and Floor Levels at regime award, based on the best available evidence submitted by the project at that time.
The draft licence process does not define a separate, fixed window for routine cost updates after regime award and before FID. Applicants are therefore expected to submit updated and evidenced cost information up to regime award where costs have materially changed.
After regime award, cost updates are only reflected through the defined post‑award adjustment mechanisms set out in the licence, rather than through a further re‑setting of preliminary cap and floor levels prior to FID.
SCL-012 | 2026-03-30 | Draft Licence | Our interpretation of SC9 para 75 is that project cost overrun between the P50 and P90 will be passed through to calculated Adjusted Cost for the revised Post-Construction cap and floor calculations. Can Ofgem confirm whether there will be a methodology to determine whether cost overruns within this range are economic and efficient at PCR, and what that methodology would be? | At PCR, Ofgem determines a PCR Cost Baseline using audited actual costs and forecasts to completion, net of excluded costs, on the same scope and price basis as the original P50/P90. This baseline is the starting point for judging overruns. Ofgem determines the economic, efficient and effective cost of the project by assessing the evidence submitted and applying the methodologies in the Cap and Floor Cost Assessment Guidance. Where the PCR Cost Baseline is above P50 but ≤ P90, the difference between P50 and the PCR Cost Baseline is passed through in full in the PCR adjustment after removing any costs found not to be economic/efficient/effective.
SCL-013 | 2026-03-30 | Draft Licence | We would like some clarification on the Backstop Delay Charges: | 1.The Backstop Delay Charge (BDC) is defined as a proportion of floor support received in any relevant year and added to the Backstop Delay Repayment Balance.
|  |  | o Does the Backstop Delay Factor apply to every floor support year against the annualised floor as recorded in the FSPR? | The amount is calculated as a percentage of Floor Support (based on how late the project is). The balance is repaid only if and when the project earns surplus revenues above the Floor, and only after other consumer-support balances have been cleared; while that balance is outstanding, distributions are restricted.
|  |  | o Is a project's floor duration shortened if it starts delivery late? i.e. If a project has a 25-year cap and floor for delivery in 2030, and it does not deliver until 2035, will the cap and floor duration be shortened to 22 years (i.e. deducting the 3 years following the backstop date) to hold the end date unchanged, or will the 25 year contract start from the point of start of project commercial operations? | 2. No, regime duration is set at the default 25 year, unless a regime duration request is approved. It will not be altered due to delay.
|  |  | o In the event a project is delayed reaching commercial operations beyond the backstop date, does the Conditional Floor Accrual balance also build up because the project is not available to deliver against the Minimum Availability Target? Please confirm whether the CFAc balance and BDC balance accumulate simultaneously. | 3. They can accumulate simultaneously but are triggered by different conditions.
SCL-014 | 2026-03-30 | Draft Licence | Please confirm whether a standard third-party optimiser contract constitutes Relinquishing Operational Control or a Structured Transaction requiring prior Ofgem consent. Can licensees change optimisers mid-regime without Ofgem involvement? Optimiser agreements are generally much shorter than 25 years so this will be required. | A standard third‑party optimiser contract would not, in itself, be treated as Relinquishing Operational Control or as a Structured Transaction, provided the Licensee retains overall control of the asset, remains responsible for compliance with the licence, and bears the commercial and operational risks of operation. Using an external optimiser to provide dispatch or trading services is therefore generally permitted under the draft licence.
Relinquishing Operational Control would arise only where control of core operational decisions is transferred away from the Licensee in a way that undermines its ability to comply with licence obligations. Whether this threshold is met depends on the substance of the arrangement, not the commercial label applied to it.
The draft licence does not require prior Ofgem consent for entering into, amending, or replacing a standard optimiser contract, provided the arrangement does not amount to a Structured Transaction or relinquishment of control. Licensees remain fully accountable for performance, availability, market behaviour, and compliance at all times.
Licensees may therefore change optimisers during the regime without routine Ofgem involvement. Any such change would, however, remain subject to the existing information, reporting, and audit requirements in the licence, and Ofgem may review arrangements where necessary for assurance or enforcement purposes.
This reflects the expectation that optimiser contracts may be shorter than the regime duration, while maintaining clear accountability and consumer protection.
SCL-015 | 2026-03-30 | Draft Licence | Please confirm whether assets under the LDES cap and floor regime are permitted to secure tolling agreements (as per SLC23). A toll will only be required and signed where the toll fee exceeds the Ofgem floor, i.e. where the floor is insufficient to provide a 'bankable' level of contracted revenue for the asset size. | Assets supported under the LDES cap and floor regime are not prohibited from entering into tolling agreements. A tolling arrangement would not automatically be treated as a Structured Transaction or require prior Ofgem consent, provided that the Licensee retains overall operational control of the asset, remains exposed to performance and availability risk, and continues to be fully responsible for compliance with the licence, including revenue reporting and revenue netting requirements under SLC23.
Whether a tolling agreement raises concerns depends on its substance rather than its form. In particular, arrangements that transfer long‑term control of dispatch or materially insulate the Licensee from market and operational risk could be considered a Structured Transaction or a relinquishment of operational control, in which case the relevant licence protections would apply.
The draft licence does not restrict tolling agreements to circumstances where the toll fee exceeds the Ofgem floor, nor does it link permissibility to whether the floor is “bankable”. Where a tolling arrangement is entered into, revenues received under the toll would be treated in accordance with the assessed revenue and revenue netting provisions of the licence.
Ofgem recognises that developers may seek tolling arrangements for financing reasons and welcomes consultation evidence on how such arrangements are structured in practice, while ensuring accountability, consumer protection, and enforceability remain clear.
SCL-016 | 2026-03-30 | Draft Licence | In relation to the above, where a toll is in place, the draft SLC requires all market revenues to be reported in Gross Revenue with the toll offtaker's retained margin treated as an Optimiser Fee capped at y% margin and the delta being Assessed Revenue. Could we confirm whether this is the right interpretation of SC4? This creates a cap sharing liability for the duration the project is under a toll, on revenues the licensee never receives, where Ofgem has no floor exposure. Please confirm whether Gross Revenue should instead be reported against the toll fee rather than the toller's full market revenues as this is a more accurate view of the licensee's revenues. | Under the draft licence, Gross Revenue is intended to capture the market revenues attributable to the operation of the LDES asset, before third‑party charges are deducted. This applies regardless of whether the Licensee routes the asset to market directly or via a tolling arrangement.
Payments made to third parties, including tolling counterparties acting in a similar role to an optimiser, are treated as Market‑Related Costs and are netted off in calculating Assessed Revenue, subject to the relevant caps and evidence requirements. The cap and floor is therefore designed to apply to the underlying economic performance of the asset, rather than the Licensee’s contractual structure.
The draft licence does not intend to create disproportionate cap sharing exposure where the Licensee has no material economic exposure to upside, nor to allow revenues or risks to be re‑characterised in a way that undermines the integrity of the regime. Whether a particular tolling arrangement achieves this will depend on its substance and supporting evidence.
Ofgem welcomes consultation feedback on whether the current drafting provides sufficient clarity on the treatment of tolling arrangements, including whether additional clarification is needed on the distinction between toll revenues receivable by the Licensee and wider market revenues generated by the asset.