## Project Registration
Tier1
| First Tier LCN Project Registration |  | Yes | No
DNO(s)
Scottish Hydro Electric Power Distribution
Registration date
Project description
| Project title | Trial Evaluation of Domestic Demand Management Solutions (DDMS)
| Project background | As part of SHEPD's Tier 2 submission there is provision for large quantities of domestic responsive demand. As a precursor to this, SHEPD propose to trial a small number of these solutions in the same geographic area as the Tier 2 submission. By working with our partners at Glen Dimplex, Hjatland Housing Association and Smarter Grid Solutions this is seen as the first step towards a larger roll out of the solutions under the auspices of Tier 2
| Scope and objectives | This submission seeks to install DDMS in 6 houses with suitable control and signalling back to a central control hub. The aim being to control domestic electrical heat demand during times of network strain such as exceptionally low or high demand periods. Heat storage devices (immersion water heaters & space storage heaters) will be installed with control systems enabling them to become inertial energy storage devices on the electrical network, thus allowing the local DNO to have a degree of control over local demand response and frequency response.
| Success criteria | Any information gathered during this project will inform the larger Tier 2 proposal along with other modelling/projects/products around the UK regarding DDMS. The project success criteria will be to prove the integration of the technologies in order to provide knowledge and learning for the Tier 2 project and wider UK DNO rollout.
| TRL(s) | 6
| Predicted end date | Q4 2011
| External Collaborators and external funding | Glen Dimplex Smarter Grid Solutions Hjaltland House Association Shetland Islands' Coucil
| Solutions | New electrical heat storage devices (electrical immersion heaters and bespoke low loss storage heaters) with a custom designed communication systems back to a central control hub enabling demand control and frequency response.
| Potential for new learning | The project will detail the challenges facing a larger roll out of such technologies along with an insight into the actual levels of controllability that are achievable within a domestic setting. The project will inform SHEPD about customer comfort levels within homes. System cost savings maybe extrapolated for larger groups and modelling used to identify customer behaviours and minimum heating comfort levels.
| Risks | Customers may be inconvenienced/disrupted with the equipment installation and may not accept additional equipment within their home. There is a risk that the control system wouldn't work as planned and would have to be changed, however customers will have the ability to manually bypass the control system and revert to the original operating mode.
| Scale of Project | 6 houses were chosen as a manageable sample size where sufficient learning could be achieved and the basic principle of the concept proven.
| Geographic area | Shetland Mainland,Lerwick
| Does the Project involve customer engagement? | Yes
Funding
| Revenue allowed for within the DPCR5 settlement (£) | 0
| Indication of the total Allowable First Tier Project Expenditure (£) | 280000
Publication
| Does the DNO provide Ofgem with consent to publish its First Tier LCN Project Registration Pro-forma in full? | Yes
If not, please justify which parts the DNO considers to be confidential
Related Undertakings
| Payments to Related Undertakings (£) | Nil
If a payment is to be made to any Related Undertaking that is a Distribution System User, have the same terms been offered to similar Distribution System Users of the part of the network that is within the project boundary?
Has the DNO used reasonable endeavours to make the opportunity available to similar Distribution System Users of the part of the network that is within the project boundary?
IPR arrangements
| If IPRs are generated, will they conform to the default IPR arrangements set out in the LCN Fund Governance Document? | Yes
If no, then please provide a compelling justification for the project being approved
Increase row height
Decrease row height

## Project Changes
Tier1
| First Tier LCN Project Changes |  | Yes | No
DNO(s)
Scottish Hydro Electric Power Distribution
Change date
| Project description | Registration details | Updated details | Reason for changes
| Project title | Trial Evaluation of Domestic Demand Management Solutions (DDMS) | Trial Evaluation of Domestic Demand Management Solutions (DDMS) | N/A
| Project background | As part of SHEPD's Tier 2 submission there is provision for large quantities of domestic responsive demand. As a precursor to this, SHEPD propose to trial a small number of these solutions in the same geographic area as the Tier 2 submission. By working with our partners at Glen Dimplex, Hjatland Housing Association and Smarter Grid Solutions this is seen as the first step towards a larger roll out of the solutions under the auspices of Tier 2 | As part of SHEPD's Tier 2 submission there is provision for large quantities of domestic responsive demand. As a precursor to this, SHEPD propose to trial a small number of these solutions in the same geographic area as the Tier 2 submission. By working with our partners at Glen Dimplex, Hjatland Housing Association and Smarter Grid Solutions this is seen as the first step towards a larger roll out of the solutions under the auspices of Tier 2 | N/A
| Scope and objectives | This submission seeks to install DDMS in 6 houses with suitable control and signalling back to a central control hub. The aim being to control domestic electrical heat demand during times of network strain such as exceptionally low or high demand periods. Heat storage devices (immersion water heaters & space storage heaters) will be installed with control systems enabling them to become inertial energy storage devices on the electrical network, thus allowing the local DNO to have a degree of control over local demand response and frequency response. | This submission seeks to install DDMS in 6 houses with suitable control and signalling back to a central control hub. The aim being to control domestic electrical heat demand during times of network strain such as exceptionally low or high demand periods. Heat storage devices (immersion water heaters & space storage heaters) will be installed with control systems enabling them to become inertial energy storage devices on the electrical network, thus allowing the local DNO to have a degree of control over local demand response and frequency response. | N/A
| Success criteria | Any information gathered during this project will inform the larger Tier 2 proposal along with other modelling/projects/products around the UK regarding DDMS. The project success criteria will be to prove the integration of the technologies in order to provide knowledge and learning for the Tier 2 project and wider UK DNO rollout. | Any information gathered during this project will inform the larger Tier 2 proposal along with other modelling/projects/products around the UK regarding DDMS. The project success criteria will be to prove the integration of the technologies in order to provide knowledge and learning for the Tier 2 project and wider UK DNO rollout. | N/A
| TRL(s) | 6
| Predicted end date | Q4 2011
| External Collaborators and external funding | Glen Dimplex Smarter Grid Solutions Hjaltland House Association Shetland Islands' Coucil
| Solutions | New electrical heat storage devices (electrical immersion heaters and bespoke low loss storage heaters) with a custom designed communication systems back to a central control hub enabling demand control and frequency response.
| Potential for new learning | The project will detail the challenges facing a larger roll out of such technologies along with an insight into the actual levels of controllability that are achievable within a domestic setting. The project will inform SHEPD about customer comfort levels within homes. System cost savings maybe extrapolated for larger groups and modelling used to identify customer behaviours and minimum heating comfort levels.
| Risks | Customers may be inconvenienced/disrupted with the equipment installation and may not accept additional equipment within their home. There is a risk that the control system wouldn't work as planned and would have to be changed, however customers will have the ability to manually bypass the control system and revert to the original operating mode.
| Scale of Project | 6 houses were chosen as a manageable sample size where sufficient learning could be achieved and the basic principle of the concept proven.
| Geographic area | Shetland Mainland,Lerwick
| Does the Project involve customer engagement? | Yes
| Funding | Registration details | Updated details | Reason for changes
| Revenue allowed for within the DPCR5 settlement (£) | 0 | 0 | N/A
| Indication of the total Allowable First Tier Project Expenditure (£) | 280000 | 280000 | N/A
| Publication | Registration details | Updated details | Reason for changes
| Does the DNO provide Ofgem with consent to publish its First Tier LCN Project Changes Pro-forma in full? | Yes
If not, please justify which parts the DNO considers to be confidential
| Related Undertakings | Registration details | Updated details | Reason for changes
| Payments to Related Undertakings (£) | Nil
If a payment is to be made to any Related Undertaking that is a Distribution System User, have the same terms been offered to similar Distribution System Users of the part of the network that is within the project boundary?
Has the DNO used reasonable endeavours to make the opportunity available to similar Distribution System Users of the part of the network that is within the project boundary?
| IPR arrangements | Registration details | Updated details | Reason for changes
| If IPRs are generated, will they conform to the default IPR arrangements set out in the LCN Fund Governance Document? | Yes | Yes | N/A
| If no, then please provide a compelling justification for the project being approved |  |  | N/A
Increase row height
Decrease row height
Increase row height
Decrease row height
Increase row height
Decrease row height
Increase row height
Decrease row height
Increase row height
Decrease row height