## Sheet1
Question No. | Project No. | Box number / spreadsheet tab | Topic | Question | Date question asked | Date response required | Date received | Follow up to Question # | Attachments
ENWL001 | ENWT2001 | Appendix A | Project Costs | Please provide, in electronic (spreadsheet) form, any underlying calculations supporting the figures presented in the Second Teir Funding Request tab of Appendix A, specifically the Total Project Costs, External Funding (where applicable), DNO Extra Contribution (where applicable) and DNO compulsory contribution (if not the default 10%). | 2010-09-14 | c.o.p 15/09/2010 | 2010-09-15 |  | Northern Gateway Full Submission Workbook WIP.xls
ENWL002 | ENWT2001 | Appendix A | Net Benefits | Please provide, in electronic (spreadsheet) form, any underlying calculations supporting the figures presented in the Net Benefits tab of Appendix A, ie, where applicable, and Costs, Direct Benefits, Carbon Benefits or Other Benefits. | 2010-09-14 | c.o.p 15/09/2010 | 2010-09-15 |  | ENWL002 - Northern Gateway Net Benefits.xls,
ENWL003 | ENWT2002 | Appendix A | Project Costs | Please provide, in electronic (spreadsheet) form, any underlying calculations supporting the figures presented in the Second Teir Funding Request tab of Appendix A, specifically the Total Project Costs, External Funding (where applicable), DNO Extra Contribution (where applicable) and DNO compulsory contribution (if not the default 10%). | 2010-09-14 | c.o.p 15/09/2010 | 2010-09-15 |  | Corridor Manchester Full Submission Workbook WIP.xls
ENWL004 | ENWT2002 | Appendix A | Direct Benefits | Please provide, in electronic (spreadsheet) form, any underlying calculations of direct benefits presented in the Direct Benefits tab of Appendix A. | 2010-09-14 | c.o.p 15/09/2010 | 2010-09-15 |  | ENWL004 – Direct Benefits.xls
ENWL005 | ENWT2002 | Appendix A and E | Net Benefits | Please provide, in electronic (spreadsheet) form, any underlying calculations supporting the figures presented in the Net Benefits tab of Appendix A and as set out in Appendix E, ie, where applicable, and Costs, Direct Benefits, Carbon Benefits or Other Benefits. | 2010-09-14 | c.o.p 15/09/2010 | 2010-09-15 |  | ENWL005 Corridor – net benefits spreadsheet.xls
ENWL006 | ENWT2001 | Box 4 | ER P2/6 | Please give an example of the type of the type of "technical infringement" envisiaged and explain why a derogation would be needed if there is no "material deviation". | 2010-09-14 | c.o.p 15/09/2010 | 2010-09-15
ENWL007 | ENWT2001 | Box 1 |  | If the project does not secure LCN funding, How will initiatives related to PV, CHP plant etc progress? | 2010-09-16 | midday 20/09/2010 | 2010-09-20
ENWL008 | ENWT2001 | Box 3, Box 22 |  | Box 3 introduces Electrolink as a key consortium member. Why have they not been included as external collaborators or partners and please provide appropriate details on them? | 2010-09-16 | midday 20/09/2010 | 2010-09-20
ENWL009 | ENWT2001 | Box 17 |  | For each of the items under new learning, can you provide further detail on the specific outcomes from each area? | 2010-09-16 | midday 20/09/2010 | 2010-09-20
ENWL010 | ENWT2001 | Box 18 |  | Can you provide more detail on how the Joule Centre will work with core project team? | 2010-09-16 | midday 20/09/2010 | 2010-09-20
ENWL011 | ENWT2001 | Box 23 |  | Why has the Joule Centre not been identified as a project partner? | 2010-09-16 | midday 20/09/2010 | 2010-09-20
ENWL012 | ENWT2001 | Box 22 |  | Can you provide specific details on SAIC's track record in managing similar projects in the past? | 2010-09-16 | midday 20/09/2010 | 2010-09-20
ENWL013 | ENWT2001 | Box 26 |  | Associated with the delivery of "Manchester: A certain Future" - what are the existing plans in place to ensure the network is able to support the introduction of low-carbon enabling technologies? | 2010-09-16 | midday 20/09/2010 | 2010-09-20
ENWL014 | ENWT2001 | Appendix E |  | Can you provide further detail on the underlying assumptions on DSM carbon savings (rationale for customer behaviour; source of energy/carbon saving)? | 2010-09-16 | midday 20/09/2010 | 2010-09-20
ENWL015 | ENWT2002 | Box 1, Box 3 |  | Can you describe what interface arranagements with an IDNO network may be explored? When do you expect the Coop to decide its preferred approach in this area? | 2010-09-16 | midday 20/09/2010 | 2010-09-20
ENWL016 | ENWT2002 | Box 1 |  | If you are not awarded funds from the LCN, how will connections to the biomass/ new Coop building be met? | 2010-09-16 | midday 20/09/2010 | 2010-09-20
ENWL017 | ENWT2002 | Box 5 |  | The date for the initial public seminar is 12/2011; Please confirm that this is the first planned engagement. | 2010-09-16 | midday 20/09/2010 | 2010-09-20
ENWL018 | ENWT2002 | Box 15 |  | Can you provide rationale behind the identification of 9 urban centres for biomass projects? Also explain why 10 (rather than 9) cities are included in dissemination etc? | 2010-09-16 | midday 20/09/2010 | 2010-09-20
ENWL019 | ENWT2002 | Box 17 |  | The proposal mentions a number of communication methods being explored; At the same time the collaborator Arqiva has specific strengths in particular solutions. What measures do you have in place to ensure a balanced review of alternative approaches? | 2010-09-16 | midday 20/09/2010 | 2010-09-20
ENWL020 | ENWT2002 | Box 18 |  | Can you please provide further details of numbers and timing for dissemination learning from the project? | 2010-09-16 | midday 20/09/2010 | 2010-09-20
ENWL021 | ENWT2002 | Box 18 |  | Can you provide further information on the support proposed for the proposed Smart Grid Development Centre? | 2010-09-16 | midday 20/09/2010 | 2010-09-20
ENWL022 | ENWT2002 | Box 22 |  | Can you provide further detail on the level of effort committed to the project by the Joule Centre? | 2010-09-16 | midday 20/09/2010 | 2010-09-20
ENWL023 | ENWT2002 | Box 22 |  | Can you provide specific details on SAIC's track record in managing similar projects in the past? | 2010-09-16 | midday 20/09/2010 | 2010-09-20
ENWL024 | ENWT2001 | Box 7 | super conducting Fault limiter | Will £2M be the roll out cost for super conducting fault limiters and if so can you confirm there use is cost effective. If not is this research and development? | 2010-09-17 | c.o.p 21/09/2010 | 2010-09-21
ENWL025 | ENWT2001 | Box 2 |  | Why will the connection of 17MW of generation directly onto the 33kV network create a problem that will require redefinition of current planning tools? | 2010-09-17 | c.o.p 21/09/2010 | 2010-09-21
ENWL026 | ENWT2001 | Box 8 |  | Please provide a breakdown of the cost items provided byy SAIC, Alcatel-Lucent and GE | 2010-09-17 | c.o.p 21/09/2010 c.o.p 22/09/2010 | 2010-09-22
ENWL027 | ENWT2001 | Box 13 |  | Please confirm why the specific "Cyber Security Solution" is critical to this proposal and that this is not BAU for such applications? Is this a propertiary system | 2010-09-17 | c.o.p 21/09/2010 | 2010-09-21
ENWL028 | ENWT2001 | Box 18 |  | Box 3 indicated that support for the Smart Grid Development Centre has been dropped. Please confirm why this is still included in Box 18 | 2010-09-17 | c.o.p 21/09/2010 | 2010-09-21
ENWL029 | ENWT2001 | Box 22 |  | Please confirm the Contribution Value of the funding from the Joule Centre. | 2010-09-17 | c.o.p 21/09/2010 | 2010-09-21
ENWL030 | ENWT2002 |  | General | It is not clear whether the interface with consumers is direct or via third parties, contractural/commercial or control. Please clarify | 2010-09-17 | c.o.p 21/09/2010 | 2010-09-21
ENWL031 | ENWT2001 | Box 4 | IIS Exemption | Please provide more description of the circumstances under which generation failures might cause unplaned outages, an estimate of risk of this happening, and potential impact in terms of number of customers and outage duration. The submission states that temporary suspension of the IIS may be cheaper than designing in expensive features to reduce the risk - please provide more detail on these expensive features, and confirm that they are not included in the amount of LCN Funding currently requested. As per the Governance Document, please set out whether you would withdraw the request for Second Tier Funding in the event that Ofgem would not support the change to the regulatory arrangements requested | 2010-09-21 | c.o.p 24/09/2010
ENWL032 | ENWT2002 | Box 4 | IIS Exemption | Please provide an estimate of the number of customers who will be affected by planned shutdowns required to install the new equipment. Please also provide the potential duration of the outages. Please indicate whether similar interruptions would be required in order to roll-out the project if the trial was successful. As per the Governance Document, please set out whether you would withdraw the request for Second Tier Funding in the event that Ofgem would not support the change to the regulatory arrangements requested. | 2010-09-21 | c.o.p 24/09/2010
ENWL033 | ENWT2002 | Box 4 | IIS Exemption | Please provide more description of what equipment failures might cause unplanned outages, an estimate of risk of this happening, and potential impact in terms of number of customers and outage duration. Also please describe any mitigation measures you have considered. As per the Governance Document, please set out whether you would withdraw the request for Second Tier Funding in the event that Ofgem would not support the change to the regulatory arrangements requested | 2010-09-21 | c.o.p 24/09/2010
ENWL034 | ENWT2001 & ENWT2002 | Box 13 | Second Tier Successful Delivery Reward Criteria: QUESTION TO ALL DNOS | We consider that many of the Second Tier Successful Delivery Reward Criteria set out in Box 13 do not meet the requirements of the Governance Document and the proforma guidance. For clarity, each criteria should be SMART (specific, measurable, attainable, relevant and time-bounded) - meaning each should linked directly to the intended milestones (i.e. identify a date of achievement against each criteria) and outputs of the project. As stated in the Governance Document the criteria must be linked to meeting the identified project milestones on at least an annual basis and must be linked to achieving the Full Submission proposals on the sharing of knowledge. We would also stress the importance of specifying the evidence that the DNO would present to us to demonstrate the achievement of each criteria. We recognise that Box 13 was limited to two sides and we have therefore decided to allow all DNOs to resubmit Box 13 using a maximum of four sides if required. A revised Box 13 has been provided that allows flexibility of space allocation between the criteria, and should be used to resubmit the criteria. | 2010-09-21 | c.o.p 24/09/2010
ENWL035 | ENWT2002 | Appendix A | Second Tier Funding Request tab | Please can you resubmit the Second Tier Funding Request tab of Appendix A, with only the Direct Benefits table completed (This is because, as stated in the spreadsheet - if the Direct Benefits are greater than 10% of the Initial Net Funding Required you should complete the Direct Benefits table only. If the Direct Benefits are less than 10% of the Initial Net Funding you should complete the DNO Compulsory Contribution table only.) This should not change the Second Tier Funding Request amount. | 2010-09-24 | c.o.p 28/09/2010
ENWL036 | ENWT2001 | Expert Panel Question |  | What would be the 'business as usual' (BAU) solution and subsequent costs for connecting the 17MW biomass generation plant at the same location as outlined in trial? | 2010-10-11 | N/A - To be answered at Expert Panel meeting
ENWL037 | ENWT2001 & ENWT2002 | Expert Panel Question |  | Can you provide a summary of the techincal approach that the project is testing? | 2010-10-11 | N/A - To be answered at Expert Panel meeting
ENWL038 | ENWT2001 & ENWT2002 | Expert Panel Question |  | How will a successful project change the behaviour of other UK DNOs? | 2010-10-11 | N/A - To be answered at Expert Panel meeting
ENWL039 | ENWT2001 | Expert Panel Question |  | We note that you state the trial is replicable to nine other sites. Is this purely in terms of sites with exactly the same characteristics i.e. Biomass or does it cover non-biomass sites and sites with different characteristics? | 2010-10-11 | N/A - To be answered at Expert Panel meeting
ENWL040 | ENWT2002 | Expert Panel Question |  | We note that your roll out assumptions for GB outline the costs and benefits in 65 cities. Is this roll out based on a similar sized trial in each of the cities or upon a complete roll out in each of the cities? | 2010-10-11 | N/A - To be answered at Expert Panel meeting
ENWL041 | ENWT2002 | Expert Panel Question |  | Can you please provide more explanation on the roles of collaborators within the project, especially with regard to public engagement? | 2010-10-11 | N/A - To be answered at Expert Panel meeting
ENWL042 | ENWT2002 | Expert Panel Question |  | What is the role of the Joule Centre versus the other academic partners, and what are their strengths with regard to learning dissemination? | 2010-10-11 | N/A - To be answered at Expert Panel meeting
ENWL043 | ENWT2002 | Expert Panel Question |  | How will you learn from your customer engagement, given that it's quite arm's length? | 2010-10-11 | N/A - To be answered at Expert Panel meeting
ENWL044 | ENWT2001 & ENWT2002 | Expert Panel Question |  | How will you disseminate any "negative" learning that either you or your partners discover as part of the project? | 2010-10-11 | N/A - To be answered at Expert Panel meeting
ENWL045 | ENWT2001 | Expert Panel Question |  | Have the Co-operative decided on how they will connect (the decision was due September/October) - and if they haven't - how will this affect the project timing? | 2010-10-11 | N/A - To be answered at Expert Panel meeting
ENWL046 | ENWT2001 | Expert Panel Question |  | Can you please provide more explanation on the roles of the collaborators within the project, especially with regard to public engagement? | 2010-10-11 | N/A - To be answered at Expert Panel meeting
ENWL047 | ENWT2001 | Expert Panel Question |  | What is the role of the Joule Centre versus the other academic partners, and what are their strengths with regards to learning dissemination? | 2010-10-11 | N/A - To be answered at Expert Panel meeting
ENWL048 | ENWT2001 | Expert Panel Question |  | If ENW were awarded funding for both projects, would the Joule Centre have the capacity to undertake both? | 2010-10-11 | N/A - To be answered at Expert Panel meeting
ENWL049 | ENWT2002 | Expert Panel Question |  | What is the fundamental objective behind the deployment of the DEMS device and what learning will it create? | 2010-10-14 | N/A - To be answered at Expert Panel meeting