## Initial Risk Register
| Appendix 12 - Initial Risk Register | [7 empty] | SHEPD - Northern Isles New Energy Solutions | [16 empty] | Threat | 1 | Open
Assessment
Ref. | Date Raised | Threat / Opportunity | Current Assessment | External Risk (Y/N) | Status | Probability | Impact | Score | Owner | Description of Risk | Risk Response / Action | Target Date | Cost Impact | Programme Impact | Exposure | Date Closed | High Open | Medium Open | Low Open | High Opened in last week | medium opened in last week | Low opened in last week | High closed in last week | Medium closed in last week | Low closed in last week
Workpackage 1 - Project Management
R001 | 2010-08-01 | Threat | M | N | OPEN |  |  | 0 | Project Director | Resources: (Availability of Skills, Training, Locations) | Resource Plan and Gap analysis being prepared. | 2010-11-01 |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
R002 | 2010-08-02 | Threat | H | Y | OPEN |  |  | 0 | Project Director | Technical Solutions | Basis of design report to be completed and peer reviewed by all technical stakeholders prior to implementation. This will include external technical review by expert such as KEMA. | 2010-11-01 |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
R003 | 2010-08-03 | Threat | H | N | OPEN |  |  | 0 | Project Steering Board | Relationship breakdown with Collaborators | Engage with partners to formalise relationships at the earliest possible stage. All collaborators have clear and understaood roles in the project | 2011-01-01 |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
R004 | 2010-08-04 | Threat | M | N | OPEN |  |  | 0 | Project Director | Procurement | Engage with SSE Procurement and collaborators to ensure mutually agreeable procurement strategy is in place and agreed at early stage. | 2010-11-01 |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
R005 | 2010-08-05 | Threat | H | N | OPEN |  |  |  | Project Director | Overall Cost and Programme Management | Follow Large Capital Projects Governance Framework to ensure delivery - arrange addituional training for all involved. | 2010-11-01
R006 | 2010-08-06 | Threat | H | Y | OPEN |  |  | 0 | Project Steering Board | Failure of Bid | No LCNF Funds available . Consider future bid strategy | 2010-11-30 |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | H | Y | Open |  |  |  | Project Director | System not performing as anticipated | Install additional real time monitoring equipment, potentially from PSYMETRIX to assess the overall stability of the network.
Workpackage 2 - Integrated Operations and Communicationsns
R007 | 2010-08-24 | Threat | H | Y | OPEN |  |  |  | Project Manager | Availibility of suitable communication infrastructure provider on Shetland | Prepare Scoping and Tender Document - prepare to tender comms service. Where possible look to utilise existing comms provision on the island ie SSE network, mobile, broadcast etc. | 2010-09-30
R008 | 2010-08-24 | Threat | M | N | OPEN |  |  |  | Project Manager | Lack of Skilled Resource | Prepare Resource Requirement Plan | 2010-11-01 |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Workpackage 3 - Modelling and Planning
R009 | 2010-08-13 | Threat | M | Y | OPEN |  |  | 0 | Delivery Manager | Failure of Equipment to Perform as anticipated | Basis of design report to be completed and peer reviewed by all technical stakeholders prior to implementation. This will include external technical review by expert such as KEMA. | 2010-03-31 |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
R010 | 2010-08-25 | Threat | M | N | Open |  |  |  | Development Manager | Baseline engineering modesl not adequate | Engage with System Planning and University of Strathclyde to agree baseline model | 2011-01-01
R011 | 2010-08-20 | Threat | M | Y | Open |  |  | 0 | Development Manager | Delays to provision of IT systems by partners in project | Risk corresponding delay in program | 2010-09-03 |  |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
R012 | 2010-08-21 | Threat | M | Y | Open |  |  | 0 | Development Manager | Loss of critical staff at one of the partners in the project | Work carried out by a team rather than a single person. (risk delay of 6 months to recruit replacement employee.) | 2011-01-01 |  |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Workpackage 4 - Network Monitoring
R013 | 2010-08-01 | Threat | H | Y | OPEN |  |  | 0 | Development Manager | Adequacy of Monitoring Equipment | Negotiations ongoing with two suppliers to identify potential solutions. This will include additional real time monitoring of system stability. | 2010-11-30 |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
R014 | 2010-08-01 | Threat | H | Y | OPEN |  |  | 0 | Support team | Installation of the Monitoring equipment - safety | Procedures and Practices require to be reviewed | 2010-11-30 |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
R015 | 2010-08-12 | Threat | M | N | OPEN |  |  | 0 | Support Team | CI/ CML Impact for Installations | Procedures and Practices require to be reviewed | 2011-03-31 |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
R017 | 2010-08-01 | Threat | M | Y | Open |  |  | 0 | Development Manager | Suitable Monitoring Solutions not available | Two potential suppliers identified. | 2011-01-01 |  |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
R018 | 2010-08-01 | Threat | M | Y | Open |  |  | 0 | Stakeholder Manager | Manage Customer Expectations | Proactively work with all stakeholders at all times - invite to Consumer events, promotion of project etc.Develop Communications Plan to coordinate activities. | 2010-11-01 |  |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
R019 | 2010-08-01 | Threat | M | Y | Open |  |  | 0 | Support Team | Monitoring Equipment Failures | Prepare Contingency plans, impact on network operation | 2011-01-01 |  |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
R020 | 2010-08-01 | Threat | M | N | Open |  |  | 0 | Project Manager | Skilled Resource Availability | Scope requirements and Prepare Resource Plan | 2010-09-03 |  |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
R021 | 2010-08-01 | Threat | M | N | Open |  |  | 0 | Development Manager | Failure of ANM scheme | Peer review design and build on experience from Orkney RPZ | 2010-09-03 |  |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
R022 | 2010-08-01 | Threat | M | N | Open |  |  | 0 | Development Manager | Lack and Quality of SHEPD Network Information | Investiagte Quality and prepare correction plan | 2010-09-03 |  |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
R023 | 2010-08-01 | Threat | M | N | Open |  |  | 0 | Support Team | Lack of suitable planning tools | Develop new software and algorithms | 2010-09-03 |  |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
R024 | 2010-08-01 | Threat | M | N | Open |  |  | 0 | Support Team | Lack of skilled resource | Prepare scope and Resource Plan | 2010-09-03 |  |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Workpackage 5 - Integrated Renewables
R025 | 2010-08-01 | Threat | M | N | Open |  |  |  | Stakeholder Manager | Failure to attract new renewable generators to connect to the network | Develop and publise new rules for connection to scheme as per the Communications Plan Host public event in Shetland in October 2010 to inform developer community. | 2010-09-03
R026 | 2010-08-01 | Threat | M | N | Open |  |  |  | Delivery Manager | Project elements happen at differenent times ie wind turbines delayed has impact on SHEAP boilers | Programme management is key - ANM scheme to be flexible eneough to cope with this eventuality | 2010-09-03
R027 | 2010-08-01 | Threat | M | N | Open |  |  |  | Delivery manager | Battery efficiency or reliability does not meet required standards. | Utilise experience of previous battery projects during tender assesment. Manufacturer to warrant battery performance with contractual remedies for non compliance | 2010-09-03
R028 | 2010-08-01 | Threat | M | N | Open |  |  |  | Support Team | Issues with power quailty / protection systems on local network. | Advance modelling to identify possible issues, network monitoring and power quality meters to be installed as part of 4A. System operation to be tested and verified. Additional real time monitoring | 2010-09-03
Workpackage 6 - Large Scale Demand Response
R029 | 2010-08-01 | Threat | M | Y | OPEN |  |  | 0 | Delivery Manager | Inability to source an electric boiler to meet functional requirements. | Along with SHEAP identified potentially compliant equipment in Scandinavia. Initial discussions with potential supplier ongoing. | 2010-11-30 |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
R030 | 2010-08-02 | Threat | M | Y | OPEN |  |  |  | Development Manager | Supply Contract for SHEAP boiler is difficult to secure due to the perceived profile risk by suppliers. | Initial discussions with suppliers to try and shape contract - additional funds requested ifrom LCN fund to provide large enough incentive for customer to connect. | 2011-01-01
R031 | 2010-08-02 | Threat | M | Y | OPEN |  |  |  | Development Manager | Failure of SHEAP to secure ERDF funding for project. | SHEAP and SSE jointly developing bid for ERDF funding. Initial discussions with funding bodies have been positive. | 2015-11-30
R032 | 2010-08-03 | Threat | M | Y | OPEN |  |  |  | Development Manager | Identify other potentially "responsive" non domestic demands | Develop and publise new rules for connection to scheme as per the Communications Plan Host public event in Shetland in October 2010 to inform developer community. | 2011-01-01
Workpackage 7 - Domestic and SME DSR
R033 | 2010-08-11 | Threat | M | N | OPEN |  |  | 0 | Development Manager | Failure of SIC to secure ERDF funding for project. | SIC and SSE jointly developing bid for ERDF funding. Initial discussions with funding bodies have been positive. Alternative funding sources to be identifed if appropriate and also potential to amend scope if appropriate. | 2015-03-31 |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
R034 | 2010-08-01 | Threat | M | Y | OPEN |  |  | 0 | Development Manager | Delay in availibility of the Dimplex storage equipment | Initial six home trial starting October 2010 to test performance. Review progress regularly to gain confidence. Dimplex, SIC and HHA having pre start meeting in Sept. 2010 to identify any issues and agree programme. | 2015-11-30 |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
R035 | 2010-08-01 | Threat | M | Y | OPEN |  |  | 0 | Project Director | Failure of new storage heaters to perform as anticipated | Initial six home trial starting October 2010 to test performance. Review progress regularly to gain confidence. | 2010-09-03 |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
R036 | 2010-08-01 | Threat | L | Y | OPEN |  |  | 0 | Delivery Manager | Failure of SIC and Hjatland to maintain refurbishment programme | Monitor and evaluate continually to assess risk. Agree and document clear scope of works between all parties in advance of works proceeding. ERDF funding is time bound so refurbishment must be concluded within timescale. | 2011-01-01 |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
R037 | 2010-08-01 | Threat | M | N | OPEN |  |  | 0 | Delivery Manager | Customer ex gratia Payments | Will be proven as part of the trial. Feedback to be assessed and payments amended in line with feedback. | 2011-01-01 |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Workpackage 8 - Non Domestic Responsive
R038 | 2010-08-01 | Threat | M | Y | OPEN |  |  | 0 | Development Manager | Widen technology to include alternate heating systems such as heat pumps or refridgeration | Discuss with equipment suppliers and customers. | 2014-12-01 |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
R039 | 2010-08-01 | Threat | L | Y | OPEN |  |  | 0 | Support Team | New interface arrangements required for the SME sector | Develop mid market solution to have appropriate functionality | 2011-07-31 |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
R040 | 2010-08-15 | Threat | L | N | OPEN |  |  | 0 | Stakeholder Manager | Insufficient involvement with Consumers | Develop and publicise new rules for connection to scheme as per the Communications Plan Host public event in Shetland in October 2010 to inform potential customers. Develop potential ex gratia payments to encourage customer participation. | 2011-01-01 |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
R041 | 2010-09-01 | Threat | M | Y | OPEN |  |  |  | Development Manager | Supply Contract for SMEs' is difficult to secure due to the perceived profile risk by suppliers. | Initial discussions with suppliers to try and shape contract - additional funds requested in LCN bid to support this. | 2011-07-31
Workpackage 9 - Learning and Desimmination
R042 | 2010-08-01 | Threat | M | N | OPEN |  |  | 0 | Learning and Dissemination Manager | Learning outcomes not as anticipated | Ensure clear scope of works with Univ of Strathclyde and Reading University in advance of work commencing | 2010-09-03
R043 | 2010-08-02 | Threat | M | Y | OPEN |  |  | 0 | Learning and Dissemination Manager | Upscale to GB level - outputs from NINES | Engage with National Grid to agree study parameters in advacne | 2010-09-03
R044 | 2010-08-02 | Threat | M | Y | OPEN |  |  |  | Learning and Dissemination Manager | Resources | Resource Plan and Gap analysis being prepared. | 2015-08-31
R045 | 2010-08-02 | Threat | M | Y | OPEN |  |  |  | Stakeholder Manager | Failure to communicate project outcomes and objectives. | Communications Plan to be agreed prior to project initiation to address all customer groups. | 2015-08-31
R046 | 2010-08-02 | Threat | M | Y | OPEN |  |  | 0 | Stakeholder Manager | Manage Customer Expectations | Proactively work with all stakeholders at all times - invite to Consumer events, promotion of project etc. Develop Communications Plan to co-ordinate activities. | 2010-11-01 |  |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Workpackage 11 - Large Scale Storage
R01101 | 2010-08-03 | Threat | M | N | OPEN |  |  |  | Delivery manager | Battery efficiency or reliability does not meet required standards. | Utilise experience of previous battery projects during tender assesment. Manufacturer to warrant battery performance with contractual remedies if they fail to perform. | 2011-03-31
R01102 | 2010-08-03 | Threat | M | N | OPEN |  |  |  | Delivery manager | Leaking of the battery chemicals | The battery modules are hermatically sealed units with multiple layers of insulation ensure the chemicals cannot leak. The mudules have also undergone extensive destructive testing including water submersion, falling from height and exposure to fire without any chemical leaks. | 2010-09-03
R01103 | 2010-08-03 | Threat | M | N | OPEN |  |  |  | Delivery manager | Battery / power conversion system not procured in time for required project completion. | Ensure tender process is done quickly, but without compromising the validity of the assessment process. | 2010-09-03
[17 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[17 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Formulas:
High Opened in last week = AND(((#REF!)="HIGH"),(([Status])<>"Closed"),((TODAY()-(#REF!)<7)))
High Opened in last week = AND((([Current Assessment])="HIGH"),(([Status])<>"Closed"),((TODAY()-([Date Raised])<7)))
medium opened in last week = AND(((#REF!)="MEDIUM"),(([Status])<>"Closed"),((TODAY()-(#REF!)<7)))
medium opened in last week = AND((([Current Assessment])="MEDIUM"),(([Status])<>"Closed"),((TODAY()-([Date Raised])<7)))
Low opened in last week = AND(((#REF!)="LOW"),(([Status])<>"Closed"),((TODAY()-(#REF!)<7)))
Low opened in last week = AND((([Current Assessment])="LOW"),(([Status])<>"Closed"),((TODAY()-([Date Raised])<7)))
High closed in last week = AND(((#REF!)="HIGH"),(([Status])="Closed"),((TODAY()-([Date Closed])<7)))
High closed in last week = AND((([Current Assessment])="HIGH"),(([Status])="Closed"),((TODAY()-([Date Closed])<7)))
Medium closed in last week = AND(((#REF!)="MEDIUM"),(([Status])="Closed"),((TODAY()-([Date Closed])<7)))
Medium closed in last week = AND((([Current Assessment])="MEDIUM"),(([Status])="Closed"),((TODAY()-([Date Closed])<7)))
Low closed in last week = AND(((#REF!)="LOW"),(([Status])="Closed"),((TODAY()-([Date Closed])<7)))
Low closed in last week = AND((([Current Assessment])="LOW"),(([Status])="Closed"),((TODAY()-([Date Closed])<7)))
Date Raised = [Date Raised, row above]
Note on D6: Current Assessment: Score: High Risk 16-25 Medium Risk 9-15 Low Risk 1- 8
Note on F6: Status of Risk: Open: The risk is active and being managed Closed: Risk expired or has become an issue (transferred to the issue log).
Note on G6: Probability 5 - High 4 - Significant 3 - Moderate 2 - Minor 1 - Low
Note on H6: Impact 5 - High - major impact on project. Success of project in jeopardy. Almost impossible to resolve. Excessive delays and prohibitive additional costs incurred 4 - Significant - major impact on project objectives. Difficult but not impossible to resolve. Significant delays and additional costs incurred. 3 - Moderate - limited impact on project objectives. Resolution possible. Additional resources required, no delay, but additional costs incurred 2 - Minor - little impact on project objectives. Resolution will not result in changes to deliverables. Can be resolved with current resources 1 - Low - No impact on project objectives. Resolution does not impact on quality, cost or delivery
Note on I6: Score: Probability x Impact
Note on L6: Corrective Action: Appropriate actions will fall into one of the following categories: Prevention. Countermeasures are put in place that will prevent the risk happening, or reduce impact on the project if the risk was realised. Reduction. Plan some action to reduce the probability of the risk occurring, to reduce its potential impact on the business. Transfer the risk to someone else. Remove the risk from the project scope at the planning stage. This action may require some negotiation with the customer in order for it to be agreed and executed. Contingency. When actions are planned and organised to come into force when the risk arises. Accept the Risk. The Project Board decides to accept the risk as it stands and face the consequences if the risk should occur. This course of action is taken where the risk is unavoidable or the expense of avoiding it would far outweigh the costs of allowing the risk to happen.
Note on M6: Target Date: Target Date forCorrective Action/Mitigation Plan to be in place
Note on N6: Cost Impact = Direct Margin Impact Cost impact is the variation to the cost budget if the threat or opportunity is not managed
Note on P6: Exposure depends on Probability: prob of 1 = 10%; prob of 2 = 30%; prob of 3 = 50%; prob of 4 = 65%; prob of 5 = 85%
Note on Q6: Date Closed: This is either the date the risk has been realised (column M) or the date the risk has expired (conditions for the risk to be realised no longer exist).