## Project Registration
Tier1
| First Tier LCN Project Registration |  | Yes | No
DNO(s)
EDF Energy Networks
Registration date
Project description
| Project title | Demonstrating the benefits of short-term discharge energy storage on an 11kV distribution network
| Project background | Electrical storage offers one means to manage intermittent demand and intermittent generation on a distribution network within existing network constraints, principally thermal capacity. EDF Energy Networks has previously explored with Durham University and ABB the benefits that storage can offer in managing intermittent generation. As a result EDF Energy Networks is purchasing a Li-Ion storage device which will be commissioned in September 2010. This project will take the existing results from network simulations and validate them by running progressive experiments on the storage device itself, throughout a number of seasonal, load and generation output variations on the network.
| Scope and objectives | Martham primary substation is an example of a primary substation on EDF Energy Networks’ 11kV network which has distributed generation (DG) attached. This comprises a wind farm with 10 turbines, each of 200kW generating capacity. Whilst the network is robust to all current combinations of load and generation, future load growth or additional generation would eventually push thermal capacities to the point of requiring reinforcement. The objectives of this project are to: • Perform validation of the storage device’s capabilities with respect to data sheet performance, when installed on a real network. Specifically, the efficiency of the device will be measured; • Demonstrate load-shifting within the limits of the device capability (200kWh, 1 hour discharge duration); • Understand the extent to which these interventions could be scaled up to manage larger quantities of demand or generation; • Validate a number of existing use-cases which have been proposed and simulated, rank their usefulness and understand their relative value to the DNO and to an intermittent generator; • Understand the potential lifetime of the device; • Embed the learning into a design tool for network planners, and into dissemination material for the UK DNO community; and • Propose next steps. Durham University will suggest a number of modes of operation based on their previous simulations, which have shown potential benefits in relieving thermally stressed components, reducing technical losses, reducing reverse power flow, and preserving headroom for further DG to join the network. Each mode will be verified by ABB and EDF Energy Networks’ Control before being trialled. Equipment and commissioning costs have already been provisioned and are out-of-scope of this project.
| Success criteria | The project will have succeeded if the partners are able to: • Validate, and if necessary update and re-run existing network simulations of a number of use-cases; • Report practical, measured performance of storage with respect to data sheet performance; • Report on any practical difficulties encountered and new operating practices required to manage a storage device on the 11kV network; • Categorise use-cases for storage on the 11kV network into those of most value and those which only offer diminishing returns; and • Indicate the conditions under which storage may present a compelling option (such as network characteristics, and the level of fund-sharing with other actors).
| TRL(s) | 7
| Predicted end date | 2012-10-01
| External Collaborators and external funding | Durham University will carry out the monitoring and analysis of the storage device’s performance. ABB UK will contribute £89,000 to fund 50% of the work carried out by Durham University.
| Solutions | The solution consists of a Li-Ion battery manufactured by SAFT, and the associated MACH2 Energy Storage System (ESS) controller manufactured by ABB. The controller will be interfaced to EDF Energy Networks’ existing Network Management System (NMS) and SCADA systems.
| Potential for new learning | Electrical energy storage is currently very rare on UK distribution networks, especially on 11kV networks. There have been a number of reports stating that there are benefits of connecting storage. Six or seven competing battery technologies have been developed and trialled to differing degrees overseas, but few have been trialled by UK DNOs. The installation will take place at the normal open point between feeders supplied by two different primary substations. This has the potential to explore a wide range of use-cases (i.e. charge and discharge into feeder #1, charge from feeder #1 and discharge into feeder #2, and so on). The results will be shared at the annual DNO conference. In addition, Durham University are likely to publish at conferences and in journals.
| Risks | EDF Energy Networks and ABB take longer commissioning the storage device than planned. ABB and EDF Energy Networks will, in turn, need to approve suggested modes of operation prior to running them on the network. It is possible that some experiments may be deemed to be unsuitable, particularly if external factors mean that the network is running outside of its normal running arrangement.
| Scale of Project | The duration of the project has been chosen in order allow time to set up the necessary operating procedures and then to experience a number of seasonal variations on the 11V network. Towards the end of the trial, a number of options will be considered including forensic analysis to determine the lifetime remaining.
| Geographic area | At a normal open point (NOP) at Hemsby, North Norfolk between Martham and Ormesby primary substations. Bloodhills windfarm (10 by 200kW turbines) is connected to one of the Martham feeders.
| Does the Project involve customer engagement? | No
Funding
| Revenue allowed for within the DPCR5 settlement (£) | 0
| Indication of the total Allowable First Tier Project Expenditure (£) | 225000
Publication
| Does the DNO provide Ofgem with consent to publish its First Tier LCN Project Registration Pro-forma in full? | Yes
If not, please justify which parts the DNO considers to be confidential
Related Undertakings
| Payments to Related Undertakings (£) | £0 For purposes of clarity: The storage device is expected to have an efficiency of 80% and will therefore exhibit a small net consumption. Energy imports to charge up the battery and exports from the battery will be logged and the net difference paid to a supplier. For the purposes of transparency, EDF Energy Networks will not use EDF Energy as a supplier on this occasion.
| If a payment is to be made to any Related Undertaking that is a Distribution System User, have the same terms been offered to similar Distribution System Users of the part of the network that is within the project boundary? | Yes
| Has the DNO used reasonable endeavours to make the opportunity available to similar Distribution System Users of the part of the network that is within the project boundary? | Yes
IPR arrangements
| If IPRs are generated, will they be shared with all of the other DNOs? | Yes
| If no, then please provide a compelling justification for the project being approved | For purposes of clarity: The ABB MACH2 controller platform is a fully developed and commercial product and, as such, the trial is only expected to consist of minor configuring of the device. Any project specific issues highlighted with the MACH 2 itself to achieve the project functionality that may require further software adjustments in the MACH 2 will be funded by ABB and IPR in those parts retained by ABB. Furthermore, ABB are providing their effort in-kind, and are matching the funding requested from the LCNF to cover Durham University’s costs. Durham University has confirmed that it will share the desktop planning tool with other DNOs via non-exclusive, royalty-free licenses. The tool will be built with DNO network planners in mind and will consolidate the results of previous simulation work developed by Durham University previously within the Aura NMS project. It will be available to DNOs if requested, but is intended to be superseded by the planning tool. For clarity, no further intellectual property from the Aura NMS project will be used within this project or will be made available to DNOs as a result of this project. All parties confirm that they will share the trial results, lessons learned and operating practise of how energy storage could be applied in the network with UK DNOs free of charge for their internal use.

## Project Changes
Tier1
| First Tier LCN Project Changes |  | Yes | No
DNO(s)
EDF Energy Networks
Change date
| Project description | Registration details | Updated details | Reason for changes
| Project title | Demonstrating the benefits of short-term discharge energy storage on an 11kV distribution network |  | N/A
| Project background | Electrical storage offers one means to manage intermittent demand and intermittent generation on a distribution network within existing network constraints, principally thermal capacity. EDF Energy Networks has previously explored with Durham University and ABB the benefits that storage can offer in managing intermittent generation. As a result EDF Energy Networks is purchasing a Li-Ion storage device which will be commissioned in September 2010. This project will take the existing results from network simulations and validate them by running progressive experiments on the storage device itself, throughout a number of seasonal, load and generation output variations on the network. | Electrical storage offers one means to manage intermittent demand and intermittent generation on a distribution network within existing network constraints, principally thermal capacity. UK Power Networks has previously explored with Durham University and ABB the benefits that storage can offer in managing intermittent generation. As a result, UK Power Networks purchased a Li-Ion storage device which was commissioned in April 2011. This project will take the existing results from network simulations and validate them by running progressive experiments on the storage device itself, throughout a number of seasonal, load and generation output variations on the network. | The commissioning of the device took longer than expected and the device was only commissioned in April 2011 (date changed from September 2010). Additionally the development of the maintenance contract, energy contracts and the necessary IT integration has been protracted. As such, these contracts and the necessary IT systems were not in place at the time of commissioning.
| Scope and objectives | Martham primary substation is an example of a primary substation on EDF Energy Networks’ 11kV network which has distributed generation (DG) attached. This comprises a wind farm with 10 turbines, each of 200kW generating capacity. Whilst the network is robust to all current combinations of load and generation, future load growth or additional generation would eventually push thermal capacities to the point of requiring reinforcement. The objectives of this project are to: • Perform validation of the storage device’s capabilities with respect to data sheet performance, when installed on a real network. Specifically, the efficiency of the device will be measured; • Demonstrate load-shifting within the limits of the device capability (200kWh, 1 hour discharge duration); • Understand the extent to which these interventions could be scaled up to manage larger quantities of demand or generation; • Validate a number of existing use-cases which have been proposed and simulated, rank their usefulness and understand their relative value to the DNO and to an intermittent generator; • Understand the potential lifetime of the device; • Embed the learning into a design tool for network planners, and into dissemination material for the UK DNO community; and • Propose next steps. Durham University will suggest a number of modes of operation based on their previous simulations, which have shown potential benefits in relieving thermally stressed components, reducing technical losses, reducing reverse power flow, and preserving headroom for further DG to join the network. Each mode will be verified by ABB and EDF Energy Networks’ Control before being trialled. Equipment and commissioning costs have already been provisioned and are out-of-scope of this project. |  | N/A
| Success criteria | The project will have succeeded if the partners are able to: • Validate, and if necessary update and re-run existing network simulations of a number of use-cases; • Report practical, measured performance of storage with respect to data sheet performance; • Report on any practical difficulties encountered and new operating practices required to manage a storage device on the 11kV network; • Categorise use-cases for storage on the 11kV network into those of most value and those which only offer diminishing returns; and • Indicate the conditions under which storage may present a compelling option (such as network characteristics, and the level of fund-sharing with other actors). |  | N/A
| TRL(s) | 7
| Predicted end date | 2012-10-01 | 2014-01-31 | Following commissioning of the device in April 2011, we encountered and overcame a number of technical issues from the Energy Storage System, and also saw delays in the development of the maintenance and energy contracts. In light of this, we requested to extend the project end date to October 2013. We are now requesting that the project be further extended until January 2014 as a result of the CO2 fire suppression system activating due to a faulty smoke detector, and the consequent loss of operational use for approximately three months. We believe that by extending the project end date we will be able to complete the assessment on the benefits that energy storage can offer to distribution networks. This in turn will lead us to gain earlier confidence to adopt this technology as an alternative to traditional reinforcement, providing better value for money and increased security of supply for the end consumers. Furthermore, extending the end date of the project will increase the operational experience and learning that can be shared with other DNOs, helping to mitigate the risks of other storage demonstrations (including UK Power Networks' Smarter Network Storage project.)
| External Collaborators and external funding | Durham University will carry out the monitoring and analysis of the storage device’s performance. ABB UK will contribute £89,000 to fund 50% of the work carried out by Durham University. | N/A | N/A
| Solutions | The solution consists of a Li-Ion battery manufactured by SAFT, and the associated MACH2 Energy Storage System (ESS) controller manufactured by ABB. The controller will be interfaced to EDF Energy Networks’ existing Network Management System (NMS) and SCADA systems. | N/A | N/A
| Potential for new learning | Electrical energy storage is currently very rare on UK distribution networks, especially on 11kV networks. There have been a number of reports stating that there are benefits of connecting storage. Six or seven competing battery technologies have been developed and trialed to differing degrees overseas, but few have been trialed by UK DNOs. The installation will take place at the normal open point between feeders supplied by two different primary substations. This has the potential to explore a wide range of use-cases (i.e. charge and discharge into feeder #1, charge from feeder #1 and discharge into feeder #2, and so on). The results will be shared at the annual DNO conference. In addition, Durham University are likely to publish at conferences and in journals. | N/A | N/A
| Risks | EDF Energy Networks and ABB take longer commissioning the storage device than planned. ABB and EDF Energy Networks will, in turn, need to approve suggested modes of operation prior to running them on the network. It is possible that some experiments may be deemed to be unsuitable, particularly if external factors mean that the network is running outside of its normal running arrangement. | Whilst a revised timeline for the demonstration of benefits has been developed, there is still a small risk that there could be delays with the installation of additional network monitoring equipment and associated remote communications. Modifications to the MACH 2 control system are being undertaken to allow for greater control and data recording functionality, for example being able to control the ESS via a script command. As this is a modification to an existing system, there is a risk that development may take longer than expected. ABB and UK Power Networks will, in turn, need to approve suggested modes of operation prior to running them on the network. It is possible that some experiments may be deemed to be unsuitable, particularly if external factors mean that the network is running outside of its normal running arrangement. | Updated to reflect additional risks identified since the project was started.
| Scale of Project | The duration of the project has been chosen in order allow time to set up the necessary operating procedures and then to experience a number of seasonal variations on the 11V network. Towards the end of the trial, a number of options will be considered including forensic analysis to determine the lifetime remaining. | N/A | N/A
| Geographic area | At a normal open point (NOP) at Hemsby, North Norfolk between Martham and Ormesby primary substations. Bloodhills wind farm (10 by 200kW turbines) is connected to one of the Martham feeders. | N/A | N/A
| Does the Project involve customer engagement? | No
| Funding | Registration details | Updated details | Reason for changes
| Revenue allowed for within the DPCR5 settlement (£) | 0 | 0 | N/A
| Indication of the total Allowable First Tier Project Expenditure (£) | 225000 | 225000 | N/A
| Publication | Registration details | Updated details | Reason for changes
| Does the DNO provide Ofgem with consent to publish its First Tier LCN Project Changes Pro-forma in full? | Yes |  | N/A
| If not, please justify which parts the DNO considers to be confidential |  |  | N/A
| Related Undertakings | Registration details | Updated details | Reason for changes
| Payments to Related Undertakings (£) | £0 For purposes of clarity: The storage device is expected to have an efficiency of 80% and will therefore exhibit a small net consumption. Energy imports to charge up the battery and exports from the battery will be logged and the net difference paid to a supplier. For the purposes of transparency, EDF Energy Networks will not use EDF Energy as a supplier on this occasion. | £0 For purposes of clarity: The storage device is expected to have an efficiency of 90% (as quoted by ABB) and will therefore exhibit a small net consumption. Energy imports to charge up the battery and exports from the battery will be logged and the net difference paid to a supplier. EDF Energy are currently used as the energy supplier for this project. At the time the contract was negotiated and signed, UK Power Networks was no longer part of the EDF Group. | Clarifications made regarding the supplier and efficiency.
| If a payment is to be made to any Related Undertaking that is a Distribution System User, have the same terms been offered to similar Distribution System Users of the part of the network that is within the project boundary? | Yes | N/A | N/A
| Has the DNO used reasonable endeavors to make the opportunity available to similar Distribution System Users of the part of the network that is within the project boundary? | Yes | N/A | N/A
| IPR arrangements | Registration details | Updated details | Reason for changes
| If IPRs are generated, will they be shared with all of the other DNOs? | Yes |  | N/A
| If no, then please provide a compelling justification for the project being approved | For purposes of clarity: The ABB MACH2 controller platform is a fully developed and commercial product and, as such, the trial is only expected to consist of minor configuring of the device. Any project specific issues highlighted with the MACH 2 itself to achieve the project functionality that may require further software adjustments in the MACH 2 will be funded by ABB and IPR in those parts retained by ABB. Furthermore, ABB are providing their effort in-kind, and are matching the funding requested from the LCNF to cover Durham University’s costs. Durham University has confirmed that it will share the desktop planning tool with other DNOs via non-exclusive, royalty-free licenses. The tool will be built with DNO network planners in mind and will consolidate the results of previous simulation work developed by Durham University previously within the Aura NMS project. It will be available to DNOs if requested, but is intended to be superseded by the planning tool. For clarity, no further intellectual property from the Aura NMS project will be used within this project or will be made available to DNOs as a result of this project. All parties confirm that they will share the trial results, lessons learned and operating practise of how energy storage could be applied in the network with UK DNOs free of charge for their internal use. |  | N/A