## SPT-Lead
|  | Year 1 | Year 2 | Year 3 | Year 4- 4 months
SPT Project Leader |  | 2013/14 | 2014/15 | 2015/16 | 2016/17
Ensure that stakeholders are updated at regular intervals throughout the project
| Coordinating steering group meetings (once every two months) | 24 | 24 | 24 | 15
| Coordinating Project Delivery Team Monthly meetings | 36 | 36 | 36 | 20
| Report drafting, updating the Authority in the form of PPR | 20 | 20 | 20 | 10
| Project close down report |  |  |  | 40
Ensure that all relevant stakeholders are aware of the project and the associated implications, opportunities and responsibilities that apply to them
| Internal workshop planning/coordinating, five workshops identified in the WP5 | 25 | 0 | 0 | 0
| External workshop planning/coordinating, ownership and quality assurance of online portal | 20 | 20 | 20 | 10
Ensure that feedback is sought and gathered from all relevant parties at appropriate stages in the project, and that this is fed to the Project Delivery Team
| annual conference preparing, coordinating and follow up | 15 | 15 | 15 | 15
| international stakeholder engagement in the form of visit/teleconference | 15 | 15 | 15 | 15
| Assess the interactions of VISOR with existing IT and Power practices. This will include strategic and procedural aspects of grid monitoring, system planning & operation, and IT infrastructure. | 20 | 20 | 20 | 10
Plan, co-ordinate and supervise VISOR project activity within the TO/SO, including budgetary, scheduling and logistical aspects
| o TO/SO-level procurement activity associated with the project | 30 | 25 | 25 | 0
| o TO/SO field & IT installation associated with the project. | 20 | 20 | 0 | 0
| o TO/SO-level engineering analysis and reviewing work. | 5 | 15 | 15 | 15
| o Co-ordination with Suppliers on the specification, scheduling, delivery and acceptance of contracted products and services. | 20 | 20 | 20 | 10
Engineering Expertise – contribute to the knowledge and experience of the project
| o Primary point of contact for all matters relating to VISOR project within TO – both internal & external queries/actions | 20 | 20 | 20 | 15
| o Review and contribute to reports and papers on WAMS and Power System aspects, including: WAMS deployment & performance, Oscillations, Transient Stability, State Estimation and System Model validation. | 20 | 20 | 20 | 10
| o Work with the VISOR Project Knowledge Dissemination Co-ordinator to ensure and facilitate capture of learning from the project. | 15 | 15 | 15 | 10
| summary of man-days | 305 | 285 | 265 | 195 | Average FTE of the project duration
| Full time equivalent (FTE-per annum) | 1.525 | 1.425 | 1.325 | 1.7727 |  | 1.5119
| Project Management / Engineering split | 2.05 | 1.5909 | 1.9444 | 2.25
| Project Management % | 67.21% | 61.4% | 66.04% | 69.23%
| Engineering % | 32.79% | 38.6% | 33.96% | 30.77%

## NGET-Co Leader
|  | Year 1 | Year 2 | Year 3 | Year 4- 4 months
NGET Project Co-Leader |  | 2013/14 | 2014/15 | 2015/16 | 2016/17
Ensure that stakeholders are updated at regular intervals throughout the project
| Prepare and Participate Project Delivery Team Monthly meetings | 24 | 24 | 24 | 12
| Contributing to the Authority updates in the form of PPR | 10 | 10 | 10 | 5
| Project close down report assistances |  |  |  | 10
Ensure that all relevant stakeholders are aware of the project and the associated implications, opportunities and responsibilities that apply to them
| Internal workshop planning/coordinating, five workshops identified in the WP5 | 15 | 0 | 0 | 0
| External workshop planning/coordinating, quality assurance of online portal | 10 | 10 | 10 | 10
Ensure that feedback is sought and gathered from all relevant parties at appropriate stages in the project, and that this is fed to the Project Delivery Team
| annual conference preparing, coordinating and follow up | 10 | 10 | 10 | 10
| international stakeholder engagement in the form of visit/teleconference | 7.5 | 7.5 | 7.5 | 7.5
| Assess the interactions of VISOR with existing IT and Power practices. This will include strategic and procedural aspects of grid monitoring, system planning & operation, and IT infrastructure. The outcome should feed into the specifications, tender evaluation and the acceptance procedure to feed future GB rollout. | 20 | 15 | 15 | 10
Plan, co-ordinate and supervise VISOR project activity within the TO/SO, including budgetary, scheduling and logistical aspects
| o TO/SO-level procurement activity associated with the project: specifications contribution to ensure that it is future proofing, and serves the function for the potential roll out | 20 | 5 | 5 | 0
| o TO/SO field & IT installation associated with the project. | 20 | 10 | 0 | 0
| o TO/SO-level engineering analysis and reviewing work. | 5 | 10 | 5 | 15
| o Co-ordination with Suppliers on the specification, scheduling, delivery and acceptance of contracted products and services. | 20 | 10 | 10 | 5
Engineering Expertise – contribute to the knowledge and experience of the project
| o Primary point of contact for all matters relating to VISOR project within TO – both internal & external queries/actions | 20 | 20 | 15 | 7.5
| o Review and contribute to reports and papers on WAMS and Power System aspects, including: WAMS deployment & performance, Oscillations, Transient Stability, State Estimation and System Model validation. | 10 | 15 | 15 | 10
| o Work with the VISOR Project Knowledge Dissemination Co-ordinator to ensure and facilitate capture of learning from the project. | 10 | 10 | 10 | 10
| summary of man-days | 201.5 | 156.5 | 136.5 | 112 | Average FTE of the project duration
| Full time equivalent (FTE-per annum) | 1.0075 | 0.7825 | 0.6825 | 1.0182 |  | 87.27%

## SHE Transmission
|  | Year 1 | Year 2 | Year 3 | Year 4- 4 months
SHE Transmissioin Project Co-Leader |  | 2013/14 | 2014/15 | 2015/16 | 2016/17
Ensure that stakeholders are updated at regular intervals throughout the project
| Prepare and Participate Project Delivery Team Monthly meetings | 24 | 24 | 24 | 12
| Contributing to the Authority updates in the form of PPR | 10 | 10 | 10 | 5
| Project close down report assistances |  |  |  | 10
Ensure that all relevant stakeholders are aware of the project and the associated implications, opportunities and responsibilities that apply to them
| Internal workshop planning/coordinating, five workshops identified in the WP5 | 15 | 0 | 0 | 0
| External workshop planning/coordinating, quality assurance of online portal | 10 | 10 | 10 | 10
Ensure that feedback is sought and gathered from all relevant parties at appropriate stages in the project, and that this is fed to the Project Delivery Team
| annual conference preparing, coordinating and follow up | 10 | 10 | 10 | 10
| international stakeholder engagement in the form of visit/teleconference | 7.5 | 7.5 | 7.5 | 7.5
| Assess the interactions of VISOR with existing IT and Power practices. This will include strategic and procedural aspects of grid monitoring, system planning & operation, and IT infrastructure. | 10 | 10 | 10 | 5
Plan, co-ordinate and supervise VISOR project activity within the TO/SO, including budgetary, scheduling and logistical aspects
| o TO/SO-level procurement activity associated with the project; to ensure that the specifications reflect the existing communication infrastructure; ensure that each local business unit has the opportunity to review, comment and take the ownership of the specifications prior to the circulation | 20 | 5 | 5 | 0
| o TO/SO field & IT installation associated with the project: review the locations with planning team to identify the potential modifications and the impacts from the changes of reinforcements (taken into account the wide area reinforcements such as Caithness HVDC) | 20 | 10 | 0 | 0
| o TO/SO-level engineering analysis and reviewing work. | 5 | 10 | 5 | 15
| o Co-ordination with Suppliers on the specification, scheduling, delivery and acceptance of contracted products and services, (ensure that the planned outage window is fully utilised) | 20 | 10 | 10 | 10
Engineering Expertise – contribute to the knowledge and experience of the project
| o Primary point of contact for all matters relating to VISOR project within TO – both internal & external queries/actions | 20 | 20 | 15 | 7.5
| o Review and contribute to reports and papers on WAMS and Power System aspects, including: WAMS deployment & performance, Oscillations, Transient Stability, State Estimation and System Model validation. | 5 | 10 | 10 | 10
| o Work with the VISOR Project Knowledge Dissemination Co-ordinator to ensure and facilitate capture of learning from the project, and most of all, the learning can be taken in by the SSE internal units (based on the limited PMU experiences at SHE Transmission) | 15 | 15 | 15 | 10
| summary of man-days | 191.5 | 151.5 | 131.5 | 112 | Average FTE of the project duration
| Full time equivalent (FTE-per annum) | 0.9575 | 0.7575 | 0.6575 | 1.0182 |  | 84.77%

## Summary
Dedicated Project Leaders | Minimum Requirement (Average value for the duration of the project period) based on the detailed calcuation to fulfil the job description (FTE) | The figure used in the full proposal submission (FTE)
SPT | 1.5119 | 1.5
NGET | 87.27% | 1
SHE Transmission | 84.77% | 1