## Sheet1
Programme Key Milestones (approximately per quarter) |  |  |  |  | Synthotech Labour | [19 empty] | Synthotech Equipment | Synthotech Travel & Exp | Contractor | Synthotech IT | Premtech Labour | [11 empty] | Premtech Equipment | Premtech Travel & Exp | Contractor | Premtech IT | National Grid Labour | [13 empty] | National Grid Equipment | National Grid Travel & Exp | 3rd Contractors | National Grid IT
Task ID | Task | Start | Finish | Dur (NWDays) | Project Director |  | Project Lead / Mech Engineer |  | Project Planner |  | Engineer 1 |  | Engineer 2 |  | Junior Engineer |  | Controls & Systems Engineer |  | Technical Support |  | Administrator |  | Executive & Legal | [5 empty] | Director |  | Principal Engineer |  | Senior Engineer |  | Senior CAD Designer |  | CAD Designer / Assistant Engineer |  | Admin | [5 empty] | Project Manager |  | Project Lead |  | Project Support |  | GTAM Portfolio |  | GTAM Technical |  | RIIO Delivery |  | Comms
[5 empty] | Day rate = | 650 | Day rate = | 650 | Day rate = | 550 | Day rate = | 650 | Day rate = | 650 | Day rate = | 540 | Day rate = | 650 | Day rate = | 650 | Day rate = | 375 | Day rate = | 650 |  |  |  |  | Day rate = | 624 | Day rate = | 556 | Day rate = | 448 | Day rate = | 388 | Day rate = | 344 | Day rate = | 184 |  |  |  |  | Day rate = | 469.29 | Day rate = | 348.11 | Day rate = | 348.11 | Day rate = | 348.11 | Day rate = | 469.29 | Day rate = | 469.29 | Day rate = | 431.52
[5 empty] | No. days | Total | No. days | Total | No. days | Total | No. days | Total | No. days | Total | No. days | Total | No. days | Total | No. days | Total | No. days | Total | No. days | Total |  |  |  |  | No. days | Total | No. days | Total | No. days | Total | No. days | Total | No. days | Total | No. days | Total |  |  |  |  | No. days | Total | No. days | Total | No. days | Total | No. days | Total | No. days | Total | No. days | Total | No. days | Total
67 | Contract Award |  | 2014-12-02 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
98 | Completion of Concept & Methodology Documents rev 0 |  | 2015-02-27 | 64 | 6.4 | 4160 | 64 | 41600 | 12.8 | 7040 | 64 | 41600 | 64 | 41600 | 38.4 | 20736 | 32 | 20800 | 6.4 | 4160 | 19.2 | 7200 | 11 | 7150 | 68616.1 | 1960.46 | 0 | 5881.38 | 20 | 12480 | 20 | 11120 | 30 | 13440 | 10 | 3880 | 20 | 6880 | 10 | 1840 | 0 | 1000 | 0 | 0 | 32 | 15017.28 | 64 | 22279.04 | 32 | 11139.52 | 6.4 | 2227.904 | 22.4 | 10512.096 | 3.2 | 1501.728 | 3.2 | 1380.864
162 | Complete build of alpha prototype |  | 2015-06-11 | 75 | 7.5 | 4875 | 75 | 48750 | 15 | 8250 | 52.5 | 34125 | 60 | 39000 | 37.5 | 20250 | 37.5 | 24375 | 7.5 | 4875 | 30 | 11250 | 11 | 7150 | 60870 | 2029 | 0 | 6087 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 37.5 | 17598.375 | 75 | 26108.25 | 37.5 | 13054.125 | 7.5 | 2610.825 | 26.25 | 12318.8625 | 3.75 | 1759.8375 | 3.75 | 1618.2
117 | Complete 3D pipework models |  | 2015-08-20 | 51 | 5.1 | 3315 | 51 | 33150 | 10.2 | 5610 | 35.7 | 23205 | 51 | 33150 | 25.5 | 13770 | 25.5 | 16575 | 5.1 | 3315 | 20.4 | 7650 | 11 | 7150 | 44067 | 1468.9 | 0 | 4406.7 | 50 | 31200 | 22.5 | 12510 | 111.25 | 49840 | 171.25 | 66445 | 253.125 | 87075 | 10 | 1840 | 0 | 3000 | 0 | 0 | 25.5 | 11966.895 | 51 | 17753.61 | 25.5 | 8876.805 | 5.1 | 1775.361 | 17.85 | 8376.8265 | 2.55 | 1196.6895 | 2.55 | 1100.376
175 | Submit Stage 1 report |  | 2015-10-30 | 52 | 10.4 | 6760 | 52 | 33800 | 10.4 | 5720 | 52 | 33800 | 52 | 33800 | 26 | 14040 | 20.8 | 13520 | 5.2 | 3380 | 20.8 | 7800 | 11 | 7150 | 51126.4 | 1597.7 | 0 | 4793.1 | 25 | 15600 | 15 | 8340 | 40 | 17920 | 10 | 3880 | 20 | 6880 | 5 | 920 | 0 | 300 | 42197.5 | 0 | 26 | 12201.54 | 52 | 18101.72 | 26 | 9050.86 | 5.2 | 1810.172 | 18.2 | 8541.078 | 2.6 | 1220.154 | 2.6 | 1121.952 | 20000 | 10500 | 41400
221 | Complete manufacture of beta prototype |  | 2016-02-05 | 71 | 14.2 | 9230 | 56.8 | 36920 | 14.2 | 7810 | 71 | 46150 | 56.8 | 36920 | 42.6 | 23004 | 49.7 | 32305 | 7.1 | 4615 | 14.2 | 5325 | 11 | 7150 | 69111.57 | 2094.29 | 0 | 6282.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 35.5 | 16659.795 | 71 | 24715.81 | 35.5 | 12357.905 | 7.1 | 2471.581 | 24.85 | 11661.8565 | 3.55 | 1665.9795 | 3.55 | 1531.896 |  |  | 345000
224 | Complete beta prototype field trials |  | 2016-04-28 | 60 | 6 | 3900 | 48 | 31200 | 12 | 6600 | 42 | 27300 | 48 | 31200 | 30 | 16200 | 48 | 31200 | 6 | 3900 | 12 | 4500 | 11 | 7150 | 61997 | 1631.5 | 0 | 4078.75 | 63.75 | 39780 | 26.875 | 14942.5 | 148.75 | 66640 | 85 | 32980 | 170 | 58480 | 10 | 1840 | 0 | 1500 | 0 | 0 | 30 | 14078.7 | 60 | 20886.6 | 30 | 10443.3 | 6 | 2088.66 | 21 | 9855.09 | 3 | 1407.87 | 3 | 1294.56
238 | Beta prototype complete |  | 2016-07-14 | 56 | 11.2 | 7280 | 44.8 | 29120 | 11.2 | 6160 | 39.2 | 25480 | 44.8 | 29120 | 33.6 | 18144 | 44.8 | 29120 | 5.6 | 3640 | 11.2 | 4200 | 11 | 7150 | 55794.9 | 1594.14 | 0 | 3985.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 28 | 13140.12 | 56 | 19494.16 | 28 | 9747.08 | 5.6 | 1949.416 | 19.6 | 9198.084 | 2.8 | 1314.012 | 2.8 | 1208.256 |  |  | 345000
248 | Submit Stage 2 report |  | 2016-09-09 | 42 | 4.2 | 2730 | 33.6 | 21840 | 8.4 | 4620 | 25.2 | 16380 | 33.6 | 21840 | 16.8 | 9072 | 29.4 | 19110 | 4.2 | 2730 | 8.4 | 3150 | 11 | 7150 | 39103.92 | 1086.22 | 0 | 3258.66 | 20 | 12480 | 15 | 8340 | 20 | 8960 | 20 | 7760 | 20 | 6880 | 10 | 1840 | 0 | 500 | 0 | 0 | 21 | 9855.09 | 42 | 14620.62 | 21 | 7310.31 | 4.2 | 1462.062 | 14.7 | 6898.563 | 2.1 | 985.509 | 2.1 | 906.192 | 20000 | 10000 | 68400
282 | Write & Approve NRO |  | 2016-12-16 | 71 | 7.1 | 4615 | 56.8 | 36920 | 14.2 | 7810 | 49.7 | 32305 | 56.8 | 36920 | 42.6 | 23004 | 49.7 | 32305 | 7.1 | 4615 | 21.3 | 7987.5 | 11 | 7150 | 67771.025 | 1936.315 | 0 | 4840.7875 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 35.5 | 16659.795 | 71 | 24715.81 | 35.5 | 12357.905 | 7.1 | 2471.581 | 24.85 | 11661.8565 | 3.55 | 1665.9795 | 3.55 | 1531.896
273 | Complete manufacture of gamma development |  | 2017-03-27 | 72 | 14.4 | 9360 | 72 | 46800 | 14.4 | 7920 | 36 | 23400 | 28.8 | 18720 | 21.6 | 11664 | 28.8 | 18720 | 21.6 | 14040 | 21.6 | 8100 | 11 | 7150 | 66349.6 | 2488.11 | 0 | 4146.85 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 36 | 16894.44 | 72 | 25063.92 | 36 | 12531.96 | 7.2 | 2506.392 | 25.2 | 11826.108 | 3.6 | 1689.444 | 3.6 | 1553.472
290 | Gamma live field trial complete |  | 2017-06-15 | 59 | 11.8 | 7670 | 59 | 38350 | 11.8 | 6490 | 35.4 | 23010 | 23.6 | 15340 | 17.7 | 9558 | 17.7 | 11505 | 11.8 | 7670 | 17.7 | 6637.5 | 11 | 7150 | 53352.2 | 2000.7075 | 0 | 3334.5125 | 14.5 | 9048 | 7.25 | 4031 | 14.375 | 6440 | 24.375 | 9457.5 | 48.75 | 16770 | 5 | 920 | 0 | 1500 | 0 | 0 | 29.5 | 13844.055 | 59 | 20538.49 | 29.5 | 10269.245 | 5.9 | 2053.849 | 20.65 | 9690.8385 | 2.95 | 1384.4055 | 2.95 | 1272.984 | 41773
326 | Completion of delta development report |  | 2017-09-19 | 69 | 13.8 | 8970 | 69 | 44850 | 13.8 | 7590 | 34.5 | 22425 | 20.7 | 13455 | 20.7 | 11178 | 20.7 | 13455 | 20.7 | 13455 | 20.7 | 7762.5 | 11 | 7150 | 48092.96 | 2254.3575 | 0 | 3757.2625 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 34.5 | 16190.505 | 69 | 24019.59 | 34.5 | 12009.795 | 6.9 | 2401.959 | 24.15 | 11333.3535 | 3.45 | 1619.0505 | 3.45 | 1488.744
329 | Complete Data Assessment |  | 2017-12-12 | 61 | 12.2 | 7930 | 36.6 | 23790 | 12.2 | 6710 | 30.5 | 19825 | 18.3 | 11895 | 18.3 | 9882 | 18.3 | 11895 | 18.3 | 11895 | 24.4 | 9150 | 11 | 7150 | 38439.04 | 1801.83 | 0 | 3003.05 | 10 | 6240 | 5 | 2780 | 10 | 4480 | 5 | 1940 | 10 | 3440 | 2 | 368 | 0 |  | 0 | 0 | 30.5 | 14313.345 | 61 | 21234.71 | 30.5 | 10617.355 | 6.1 | 2123.471 | 21.35 | 10019.3415 | 3.05 | 1431.3345 | 3.05 | 1316.136
336 | Submit Stage 3 report |  | 2018-03-26 | 75 | 15 | 9750 | 45 | 29250 | 7.5 | 4125 | 22.5 | 14625 | 15 | 9750 | 15 | 8100 | 15 | 9750 | 22.5 | 14625 | 15 | 5625 | 11 | 7150 | 36080 | 1127.5 | 0 | 2818.75 | 10 | 6240 | 5 | 2780 | 10 | 4480 | 5 | 1940 | 10 | 3440 | 3 | 552 | 0 | 500 | 0 | 0 | 37.5 | 17598.375 | 75 | 26108.25 | 37.5 | 13054.125 | 7.5 | 2610.825 | 26.25 | 12318.8625 | 3.75 | 1759.8375 | 3.75 | 1618.2 | 20000 | 18000 | 23400
342 | Complete delta refinement |  | 2018-07-06 | 75 | 15 | 9750 | 45 | 29250 | 7.5 | 4125 | 22.5 | 14625 | 15 | 9750 | 15 | 8100 | 15 | 9750 | 15 | 9750 | 7.5 | 2812.5 | 11 | 7150 | 33620 | 1050.625 | 0 | 2626.5625 | 10 | 6240 | 10 | 5560 | 17.5 | 7840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 37.5 | 17598.375 | 75 | 26108.25 | 37.5 | 13054.125 | 7.5 | 2610.825 | 26.25 | 12318.8625 | 3.75 | 1759.8375 | 3.75 | 1618.2
352 | Submit Stage 4 report |  | 2018-09-03 | 42 | 4.2 | 2730 | 25.2 | 16380 | 4.2 | 2310 | 16.8 | 10920 | 8.4 | 5460 | 8.4 | 4536 | 4.2 | 2730 | 8.4 | 5460 | 8.4 | 3150 | 11 | 7150 | 17031.28 | 608.26 | 0 | 1520.65 | 8.75 | 5460 | 8.75 | 4865 | 20 | 8960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 21 | 9855.09 | 42 | 14620.62 | 21 | 7310.31 | 4.2 | 1462.062 | 14.7 | 6898.563 | 2.1 | 985.509 | 2.1 | 906.192 | 20000 | 5000 | 23400
363 | Issue specifications document |  | 2018-10-15 | 31 | 3.1 | 2015 | 18.6 | 12090 | 3.1 | 1705 | 12.4 | 8060 | 6.2 | 4030 | 6.2 | 3348 | 3.1 | 2015 | 6.2 | 4030 | 3.1 | 1162.5 | 11 | 7150 | 12769.54 | 456.055 | 0 | 1140.1375 | 1.5 | 936 | 1.5 | 834 | 3 | 1344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 15.5 | 7273.995 | 31 | 10791.41 | 15.5 | 5395.705 | 3.1 | 1079.141 | 10.85 | 5091.7965 | 1.55 | 727.3995 | 1.55 | 668.856 |  |  | 33120
367 | Submit Stage 5 report |  | 2018-11-12 | 21 | 2.1 | 1365 | 12.6 | 8190 | 2.1 | 1155 | 8.4 | 5460 | 4.2 | 2730 | 4.2 | 2268 | 4.2 | 2730 | 4.2 | 2730 | 2.1 | 787.5 | 11 | 7150 | 9678.34 | 345.655 | 0 | 691.31 | 1 | 624 | 1 | 556 | 2 | 896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 10.5 | 4927.545 | 21 | 7310.31 | 10.5 | 3655.155 | 2.1 | 731.031 | 7.35 | 3449.2815 | 1.05 | 492.7545 | 1.05 | 453.096 | 20000 | 2000
|  |  | TOTALS |  |  | 106405 |  | 562250 |  | 101750 |  | 422695 |  | 394680 |  | 226854 |  | 301860 |  | 118885 |  | 104250 |  | 128700 | 833870.875 | 27531.625 | 0 | 66653.6825 |  | 146328 |  | 76658.5 |  | 191240 |  | 128282.5 |  | 189845 |  | 10120 | 0 | 9000 | 42197.5 | 0 |  | 245673.315 |  | 364471.17 |  | 182235.585 |  | 36447.117 |  | 171971.3205 |  | 24567.3315 |  | 22590.072 | 141773 | 45500 | 879720 | 0
Cost Summary
Synthotech
| Labour | 2468329
| Equipment | 833870.875
| Travel & Expenses | 27531.625
| Contractors | 0
| IT | 66653.6825
| TOTAL | 3396385.1825
Premtech
| Labour | 742474
| Equipment | 0
| Travel & Expenses | 9000
| Contractors | 42197.5
| IT | 0
| TOTAL | 793671.5
National Grid
| Labour | 1047955.911
| Equipment | 141773
| Travel & Expenses | 45500
| Contractors | 879720
| IT | 0
| TOTAL | 2114948.911
Total
| Labour | 4258758.911
| Equipment | 975643.875
| Travel & Expenses | 82031.625
| Contrators | 921917.5
| IT | 66653.6825
| TOTAL | 6305005.5935
Additional cost from ISP
| Original | 4900000
| Current | 6305005.5935
| Over budget | 1405005.5935
| PIE | 189720
| Offline Test | 690000
| NGG | 335228.911
| Synthotech | 396385.1825
| Premtech | -206328.5
1405005.5935
Note on AU3: Wez Little: Tony Jackson
Note on BJ9: Wez Little: PIE
Note on BJ10: Wez Little: Offline Facilities
Note on BJ12: Wez Little: Offline Test Facilties
Note on BJ13: Wez Little: PIE
Note on BJ19: Wez Little: PIE
Note on BJ21: Wez Little: PIE Contractor
Note on BJ22: Wez Little: PIE
Note on BJ24: Wez Little: PIE £189,720.00
Note on C46: Wez Little: PIE & Climbing Frame