## Registration Log
Project Reference | Date Registered | DNO Group | Project Name | Project Value £m | Predicted End Date | Revised End Date | Current end date | Close down report due | Close down report received | Late? | Length (years)
EDFT1001 | 2010-06-07 | UKPN | Demonstrating the benefits of short-term discharge energy storage on an 11kV distribution network | 0.23 | 2012-10-01 | 2014-01-31 | 2014-01-31 | 2014-05-04 | Yes | OK | 3.7 | 2015-05-18
SPT1001 | 2010-07-09 | SP | Implementation of Real-Time Thermal Ratings | 0.45 | 2013-06-01 | 2013-07-31 | 2013-07-31 | 2013-11-01 | Yes | OK | 3.1
CET 1001 | 2010-09-10 | NPG | 33kv Superconducting Fault Limiter | 2.88 | 2013-06-01 | 2014-10-31 | 2014-10-31 | 2015-02-01 | Yes | OK | 4.1
SSET1001 | 2010-09-13 | SSE | 1MW Battery, Shetland | 1 | 2011-12-01 | 2013-12-01 | 2013-12-01 | 2014-03-04 | Yes | OK | 3.2
SSET1002 | 2010-09-13 | SSE | Demonstrating the benefits of monitoring LV network with embedded PV panels and EV charging point | 0.32 | 2012-09-01 |  | 2012-09-01 | 2012-12-03 | Yes | OK | 2
SSET1003 | 2010-09-13 | SSE | Trial Evaluation of Domestic Demand Management Solutions (DDMS) | 0.28 | 2011-12-01 | 2012-08-01 | 2012-08-01 | 2012-11-02 | Yes | OK | 1.9
EDFT1002 | 2010-09-21 | UKPN | Distribution Network Visibility | 0.25 | 2013-11-01 |  | 2013-11-01 | 2014-02-02 | Yes | OK | 3.1
WPDT1001 | 2010-11-22 | WPD | Interconnection of WPD and NGC SCADA systems | 0.078 | 2011-12-01 | 2012-12-31 | 2012-12-31 | 2013-04-03 | Yes | OK | 2.1
ENW 1001 |  | ENW | The 'Bidoyng' Smart Fuse | 0.44 | 2014-12-01 |  | 2014-12-01 | 2015-03-04 | Yes | OK | 115
WPDT1002 | 2011-01-04 | WPD | Network Management on the Isles of Scilly | 1.287 | 2012-09-01 | 2013-08-01 | 2013-08-01 | 2013-11-02 | Yes | OK | 2.6
SPT1002 | 2011-01-04 | SP | Ashton Hayes Smart Village | 0.2 | 2013-10-01 |  | 2013-10-01 | 2014-01-02 | Yes | OK | 2.7
CNT1001 | 2011-02-16 | WPD | PV Impact on surburban networks | 0.1 | 2012-11-01 | 2013-11-01 | 2013-11-01 | 2014-02-02 | Yes | OK | 2.7
CNT1002 | 2011-02-16 | WPD | Hook Norton Low Carbon Community Smart Grid | 0.34 | 2012-02-01 | 2013-10-01 | 2013-10-01 | 2014-01-02 | Yes | OK | 2.6
WPDT1003 | 2011-03-23 | WPD | Voltage Control System Demonstration Project | 0.525 | 2014-03-01 |  | 2014-03-01 | 2014-06-02 | Yes | OK | 2.9
SPT1003 | 2011-03-25 | SP | Clyde Gateway LR1 (London Road 1) | 0.33 | 2013-12-01 | 2013-03-31 | 2013-12-01 | 2014-03-04 | Yes | OK | 2.7
ENWT1002 | 2011-04-10 | ENW | Voltage Management on Low Voltage Busbars | 0.485 | 2012-10-01 | 2013-10-01 | 2013-10-01 | 2014-01-02 | Yes | OK | 2.5
ENWT1003 | 2011-04-10 | ENW | Low Voltage Network Solutions | 1.49 | 2014-03-01 |  | 2014-03-01 | 2014-06-02 | Yes | OK | 2.9
SSET1004 | 2011-06-10 | SSE | Honeywell I&C ADR - Demonstrating the Functionality of Automated Demand Response | 0.26 | 2012-03-01 | 2012-08-01 | 2012-08-01 | 2012-11-02 | Yes | OK | 1.1
SSET1005 | 2011-06-10 | SSE | LV Network Modelling and Analysis Environment | 0.32 | 2012-10-01 |  | 2012-10-01 | 2013-01-02 | Yes | OK | 1.3
WPDT1004 | 2011-07-06 | WPD | Early learning of LV network impacts from estate PV cluster | 0.03 | 2012-08-01 | 2013-02-01 | 2013-02-01 | 2013-05-05 | Yes | OK | 1.6
WPDT1005 | 2011-07-14 | WPD | Seasonal Generation Deployment | 0.3 | 2013-04-01 | 2014-08-01 | 2014-08-01 | 2014-11-02 | Yes | OK | 3.1
WPDT1006 | 2011-12-23 | WPD | LV Current Sensor Technology Evaluation | 0.25 | 2013-06-01 |  | 2013-06-01 | 2013-09-02 | Yes | OK | 1.4
UKPNT1003 | 2011-12-23 | UKPN | LV Current Sensor Technology Evaluation | 0.25 | 2013-06-01 |  | 2013-06-01 | 2013-09-02 | Yes | OK | 1.4
UKPNT1004 | 2012-01-18 | UKPN | Validation of Photovoltaic (PV) connection assessment tool | 0.38 | 2014-11-01 |  | 2014-11-01 | 2015-02-02 | Yes | OK | 2.8
SSET1008 | 2012-01-31 | SSE | LV Network Connected Energy Storage | 0.31 | 2014-03-01 |  | 2014-03-01 | 2014-06-02 | Yes | OK | 2.1
WPDT1007 | 2012-02-28 | WPD | Implementation of an active fault level management scheme | 0.646 | 2014-12-01 |  | 2014-12-01 | 2015-03-04 | Yes | OK | 2.8
SPT1004 | 2012-03-01 | SP | Hydro Active Network Management | 0.2 | 2014-02-01 | 2014-12-31 | 2014-12-31 | 2015-04-03 | Yes | OK | 2.8
SSET1007 | 2011-10-01 | SSE | Orkney Energy Storage Park | 0.3 | 2012-10-01 |  | 2012-10-01 | 2013-01-02 | Yes | OK | 1
SSET1009 | 2012-06-01 | SSE | Trial of Orkney Energy Storage Park | 1.51 | 2015-03-01 |  | 2015-03-01 | 2015-06-02 |  | OK | 2.7
UKPNT1004 | 2012-06-01 | UKPN | Smart Urban Low Voltage Network | 2.14 | 2015-03-01 | 2016-03-01 | 2016-03-01 | 2016-06-02 |  | OK | 3.8
SPT1005 | 2012-10-09 | SP | Temperature Monitoring Windfarm Cable Circuits | 0.72 | 2015-03-01 |  | 2015-03-01 | 2015-06-02 |  | OK | 2.4
WPDT1008 | 2012-10-16 | WPD | Community Energy Action | 0.2989 | 2014-05-01 | 2015-03-01 | 2015-03-01 | 2015-06-02 |  | OK | 2.4
WPDT1009 | 2013-01-18 | WPD | Electric Boulevards | 0.55 | 2015-03-01 | 2015-09-01 | 2015-09-01 | 2015-12-03 |  | OK | 2.6
ENWT1004 | 2013-03-01 | ENW | Low Voltage Integrated Automation | 0.6 | 2015-03-31 |  | 2015-03-31 | 2015-07-02 |  | OK | 2.1
WPDT1010 | 2013-08-07 | WPD | ECHO - Energy Control for Household Optimisation | 0.35 | 2015-02-01 | 2016-01-01 | 2016-01-01 | 2016-04-03 |  | OK | 2.4
ENWT1005 | 2013-08-20 | ENWL | LV Protection And Communications (LV PAC) | 0.745 | 2015-03-31 |  | 2015-03-31 | 2015-07-02 |  | OK | 1.6
SSET1010 | 2013-10-10 | SSE | Impact of electrolysers on the distribution network | 0.753 | 2015-03-31 |  | 2015-03-31 | 2015-07-02 |  | OK | 1.5
SPT1006 | 2014-04-24 | SP | Smart Building Potential Within Heavily Utilised Networks | 0.425 | 2015-03-01 |  | 2015-03-01 | 2015-06-02 |  | OK | 0.9
UKPNT1005 | 2014-06-13 | UKPN | Power Transformer Real Time Thermal Rating | 1.46 | 2016-12-01 |  | 2016-12-01 | 2017-03-04 |  | OK | 2.5
ENWT1006 | 2014-09-01 | ENWL | Combined On-Line Transformer Monitoring | 0.65 | 2016-09-01 |  | 2016-09-01 | 2016-12-03 |  | OK | 2
WPD1011 | 2014-12-01 | WPD | Voltage Control System Integration - D-SVC Phase 2 | 0.89 | 2017-06-01 |  | 2017-06-01 | 2017-09-02 |  | OK | 2.5
ENWT1007 | 2014-12-01 | ENWL | Fault Sense | 4 | 2018-03-01 |  | 2018-03-01 | 2018-06-02 |  | OK | 3.2
Formulas:
Current end date = MAX([Revised End Date],[Predicted End Date])
Close down report due = [Current end date]+93

## Closedown reports due
Project Reference | Date Registered | DNO Group | Project Name | Project Value £m | Predicted End Date | Revised End Date | Current end date | Close down report due | Close down report received | Late? | Length (years)
EDFT1001 | 2010-06-07 | UKPN | Demonstrating the benefits of short-term discharge energy storage on an 11kV distribution network | 0.23 | 2012-10-01 | 2014-01-31 | 2014-01-31 | 2014-05-04 | Yes | OK | 3.7 | 2015-05-18
SPT1001 | 2010-07-09 | SP | Implementation of Real-Time Thermal Ratings | 0.45 | 2013-06-01 | 2013-07-31 | 2013-07-31 | 2013-11-01 | Yes | OK | 3.1
CET 1001 | 2010-09-10 | NPG | 33kv Superconducting Fault Limiter | 2.88 | 2013-06-01 | 2014-10-31 | 2014-10-31 | 2015-02-01 | Yes | OK | 4.1
SSET1001 | 2010-09-13 | SSE | 1MW Battery, Shetland | 1 | 2011-12-01 | 2013-12-01 | 2013-12-01 | 2014-03-04 | Yes | OK | 3.2
SSET1002 | 2010-09-13 | SSE | Demonstrating the benefits of monitoring LV network with embedded PV panels and EV charging point | 0.32 | 2012-09-01 |  | 2012-09-01 | 2012-12-03 | Yes | OK | 2
SSET1003 | 2010-09-13 | SSE | Trial Evaluation of Domestic Demand Management Solutions (DDMS) | 0.28 | 2011-12-01 | 2012-08-01 | 2012-08-01 | 2012-11-02 | Yes | OK | 1.9
EDFT1002 | 2010-09-21 | UKPN | Distribution Network Visibility | 0.25 | 2013-11-01 |  | 2013-11-01 | 2014-02-02 | Yes | OK | 3.1
WPDT1001 | 2010-11-22 | WPD | Interconnection of WPD and NGC SCADA systems | 0.078 | 2011-12-01 | 2012-12-31 | 2012-12-31 | 2013-04-03 | Yes | OK | 2.1
ENW 1001 |  | ENW | The 'Bidoyng' Smart Fuse | 0.44 | 2014-12-01 |  | 2014-12-01 | 2015-03-04 | Yes | OK | 115
WPDT1002 | 2011-01-04 | WPD | Network Management on the Isles of Scilly | 1.287 | 2012-09-01 | 2013-08-01 | 2013-08-01 | 2013-11-02 | Yes | OK | 2.6
SPT1002 | 2011-01-04 | SP | Ashton Hayes Smart Village | 0.2 | 2013-10-01 |  | 2013-10-01 | 2014-01-02 | Yes | OK | 2.7
CNT1001 | 2011-02-16 | WPD | PV Impact on surburban networks | 0.1 | 2012-11-01 | 2013-11-01 | 2013-11-01 | 2014-02-02 | Yes | OK | 2.7
CNT1002 | 2011-02-16 | WPD | Hook Norton Low Carbon Community Smart Grid | 0.34 | 2012-02-01 | 2013-10-01 | 2013-10-01 | 2014-01-02 | Yes | OK | 2.6
WPDT1003 | 2011-03-23 | WPD | Voltage Control System Demonstration Project | 0.525 | 2014-03-01 |  | 2014-03-01 | 2014-06-02 | Yes | OK | 2.9
SPT1003 | 2011-03-25 | SP | Clyde Gateway LR1 (London Road 1) | 0.33 | 2013-12-01 | 2013-03-31 | 2013-12-01 | 2014-03-04 | Yes | OK | 2.7
ENWT1002 | 2011-04-10 | ENW | Voltage Management on Low Voltage Busbars | 0.485 | 2012-10-01 | 2013-10-01 | 2013-10-01 | 2014-01-02 | Yes | OK | 2.5
ENWT1003 | 2011-04-10 | ENW | Low Voltage Network Solutions | 1.49 | 2014-03-01 |  | 2014-03-01 | 2014-06-02 | Yes | OK | 2.9
SSET1004 | 2011-06-10 | SSE | Honeywell I&C ADR - Demonstrating the Functionality of Automated Demand Response | 0.26 | 2012-03-01 | 2012-08-01 | 2012-08-01 | 2012-11-02 | Yes | OK | 1.1
SSET1005 | 2011-06-10 | SSE | LV Network Modelling and Analysis Environment | 0.32 | 2012-10-01 |  | 2012-10-01 | 2013-01-02 | Yes | OK | 1.3
WPDT1004 | 2011-07-06 | WPD | Early learning of LV network impacts from estate PV cluster | 0.03 | 2012-08-01 | 2013-02-01 | 2013-02-01 | 2013-05-05 | Yes | OK | 1.6
WPDT1005 | 2011-07-14 | WPD | Seasonal Generation Deployment | 0.3 | 2013-04-01 | 2014-08-01 | 2014-08-01 | 2014-11-02 | Yes | OK | 3.1
WPDT1006 | 2011-12-23 | WPD | LV Current Sensor Technology Evaluation | 0.25 | 2013-06-01 |  | 2013-06-01 | 2013-09-02 | Yes | OK | 1.4
UKPNT1003 | 2011-12-23 | UKPN | LV Current Sensor Technology Evaluation | 0.25 | 2013-06-01 |  | 2013-06-01 | 2013-09-02 | Yes | OK | 1.4
UKPNT1004 | 2012-01-18 | UKPN | Validation of Photovoltaic (PV) connection assessment tool | 0.38 | 2014-11-01 |  | 2014-11-01 | 2015-02-02 | Yes | OK | 2.8
SSET1008 | 2012-01-31 | SSE | LV Network Connected Energy Storage | 0.31 | 2014-03-01 |  | 2014-03-01 | 2014-06-02 | Yes | OK | 2.1
WPDT1007 | 2012-02-28 | WPD | Implementation of an active fault level management scheme | 0.646 | 2014-12-01 |  | 2014-12-01 | 2015-03-04 | Yes | OK | 2.8
SPT1004 | 2012-03-01 | SP | Hydro Active Network Management | 0.2 | 2014-02-01 | 2014-12-31 | 2014-12-31 | 2015-04-03 | Yes | OK | 2.8
SSET1007 | 2011-10-01 | SSE | Orkney Energy Storage Park | 0.3 | 2012-10-01 |  | 2012-10-01 | 2013-01-02 | Yes | OK | 1
SSET1009 | 2012-06-01 | SSE | Trial of Orkney Energy Storage Park | 1.51 | 2015-03-01 |  | 2015-03-01 | 2015-06-02 |  | OK | 2.7
UKPNT1004 | 2012-06-01 | UKPN | Smart Urban Low Voltage Network | 2.14 | 2015-03-01 |  | 2015-03-01 | 2015-06-02 |  | OK | 2.7
SPT1005 | 2012-10-09 | SP | Temperature Monitoring Windfarm Cable Circuits | 0.72 | 2015-03-01 |  | 2015-03-01 | 2015-06-02 |  | OK | 2.4
WPDT1008 | 2012-10-16 | WPD | Community Energy Action | 0.2989 | 2014-05-01 |  | 2014-05-01 | 2014-08-02 | Yes | OK | 1.5
WPDT1009 | 2013-01-18 | WPD | Electric Boulevards | 0.55 | 2015-03-01 |  | 2015-03-01 | 2015-06-02 |  | OK | 2.1
ENWT1004 | 2013-03-01 | ENW | Low Voltage Integrated Automation | 0.6 | 2015-03-31 |  | 2015-03-31 | 2015-07-02 |  | OK | 2.1
WPDT1010 | 2013-08-07 | WPD | ECHO - Energy Control for Household Optimisation | 0.35 | 2015-03-01 |  | 2015-03-01 | 2015-06-02 |  | OK | 1.6
ENWT1005 | 2013-08-20 | ENWL | LV Protection And Communications (LV PAC) | 0.745 | 2015-03-31 |  | 2015-03-31 | 2015-07-02 |  | OK | 1.6
SSET1010 | 2013-10-10 | SSE | Impact of electrolysers on the distribution network | 0.753 | 2015-03-31 |  | 2015-03-31 | 2015-07-02 |  | OK | 1.5
SPT1006 | 2014-04-24 | SP | Smart Building Potential Within Heavily Utilised Networks | 0.425 | 2015-03-01 |  | 2015-03-01 | 2015-06-02 |  | OK | 0.9
UKPNT1005 | 2014-06-13 | UKPN | Power Transformer Real Time Thermal Rating | 1.46 | 2016-12-01 |  | 2016-12-01 | 2017-03-04 |  | OK | 2.5
ENWT1006 | 2014-09-01 | ENWL | Combined On-Line Transformer Monitoring | 0.65 | 2016-09-01 |  | 2016-09-01 | 2016-12-03 |  | OK | 2
Formulas:
Current end date = MAX([Revised End Date],[Predicted End Date])
Close down report due = [Current end date]+93

## Value of Projects
Licensee | CRC 13 DNO Annual Allowance (£m nominal amounts) | Value for DPCR5 | Value of Registered Projects £m
Electricity North West Ltd | 1.3 | 6.5
Northern Electric Distribution Ltd | 0.9 | 4.5
Yorkshire Electricity Distribution plc | 1.2 | 6
Western Power Distribution (South Wales) plc | 0.6 | 3
Western Power Distribution (South West) plc | 0.8 | 4
Central Networks West plc | 1.4 | 7
Central Networks East plc | 1.4 | 7
UKPN (LPN) plc | 1.2 | 6
UKPN (SPN) plc | 1.2 | 6
UKPN (EPN) plc | 1.9 | 9.5
SP Distribution Ltd | 1.1 | 5.5
SP Manweb plc | 0.8 | 4
Scottish Hydro Electric Power Distribution plc | 0.4 | 2
Southern Electric Power Distribution plc | 1.6 | 8
Total | 15.8 | 79
Amount Remaining
ENW | 1.3 | 6.5 | 3.015 | 3.485
NPG | 2.1 | 10.5 | 2.88 | 7.62
WPD | 4.2 | 21 | 5.6449 | 15.3551
UKPN | 4.3 | 21.5 | 4.71 | 16.79
SP | 1.9 | 9.5 | 2.325 | 7.175
SSE | 2 | 10 | 5.053 | 4.947

## Old
First Tier registered Projects Overview
DNO Group | DNO | CRC 13 DNO Annual Allowance (£m nominal amounts) | CRC 13 Allowance over 5 Years (£m nominal amounts) | No. Projects registered | Total value of Registered Projects (£m) | Allowance Remaining £m | Reference no. of registered projects | Reference no. of registered projects
Central Networks | Central Networks West plc | 1.4 | 7 | 1 | 0.16 | 6.84 | CNT1001 | CNT1003
| Central Networks East plc | 1.4 | 7 | 1 | 0.41 | 6.59 | CNT1002 | CNT1003
Electricity North West | Electricity North West Ltd | 1.3 | 6.5 | 3 | 2.42 | 4.08 | ENW 1001 | ENW1002 |  | ENW1003
Central Electric UK | Northern Electric Distribution Ltd | 0.9 | 4.5 |  |  | 4.5
Central Electric UK | Yorkshire Electricity Distribution plc | 1.2 | 6 | 1 | 2.88 | 3.12 | CET 1001
Western Power Distribution | Western Power Distribution (South Wales) plc | 0.6 | 3 |  | 0.251 | 2.749 | WPDT1001 | WPDT1003
| Western Power Distribution (South West) plc | 0.8 | 4 | 1 | 0.451 | 3.549 | WPDT1002 | WPDT1003
EDF | EDF Energy Networks (LPN) plc | 1.2 | 6 |  |  | 6
| EDF Energy Networks (SPN) plc | 1.2 | 6 |  |  | 6
| EDF Energy Networks (EPN) plc | 1.9 | 9.5 | 2 | 0.48 | 9.02 | EDFT1001 | EDFT1002
Scottish Power | SP Distribution Ltd | 1.1 | 5.5 |  | 0.33 | 5.17 | SPT1003
| SP Manweb plc | 0.8 | 4 | 2 | 0.65 | 3.35 | SPT1001 | SPT 1002
Scottish and Southern Energy | Scottish Hydro Electric Power Distribution plc | 0.4 | 2 | 2 | 1.28 | 0.72 | SSET1001 | SSET1003
| Southern Electric Power Distribution plc | 1.6 | 8 | 3 | 0.9 | 7.1 | SSET1002 | SSET1004 | SSET1005
Total Pot | 80000000
|  | Project Reference |  |  | Date Registered | DNO | Project Value £m | Predicted End Date | Regulatory Years
| 1 | EDFT1001 |  |  | 2010-06-07 | EDF Energy Networks (EPN) plc | 0.23 | 2012-10-01 | 3
| 2 | SPT1001 |  |  | 2010-07-09 | SP Manweb plc | 0.45 | 2013-06-01 | 4
| 3 | CET 1001 |  |  | 2010-09-10 | Central Electric UK | 2.88 | 2013-06-01 | 4
| 4 | SSET1001 |  |  | 2010-09-13 | Scottish and Southern Energy | 1 | 2012-03-01 | 2 | ?
| 5 | SSET1002 |  |  | 2010-09-13 | Scottish and Southern Energy | 0.32 | 2012-03-01 | 2
| 6 | SSET1003 |  |  | 2010-09-13 | Scottish and Southern Energy | 0.28 | 2012-03-01 | 2 | ?
| 7 | EDFT1002 |  |  | 2010-09-21 | EDF Energy Networks (EPN) plc | 0.25 | 2013-11-01 | 4 | ?
| 8 | WPDT1001 |  |  | 2010-11-22 | Western Power Distribution (South Wales) plc & Western Power Distribution (South West) plc | 0.078 | 2011-12-01 | 2
| 9 | ENW 1001 |  |  |  | Electricity North West Ltd | 0.44 | 2012-11-01 | 3
| 10 | WPDT1002 |  |  | 2011-01-04 | Network Management on the Isles of Scilly | 1.12 | 2014-01-01 | 4 | ?
| 11 | SPT1002 |  |  | 2011-01-04 | Ashton Hayes Smart Village | 0.2 | 2012-12-01 | 3
| 12 | CNT1001 |  |  | 2011-02-16 | PV Impact on surburban networks | 0.1 | 2013-10-01 | 4
| 13 | CNT1002 |  |  | 2011-02-16 | Hook Norton Low Carbon Community Smart Grid | 0.35 | 2012-11-01 | 3
|  | WPDT1003 |  |  | 2011-03-23 | Voltage Control System Demonstration Project | 0.525 | 2014-03-01 | 3
|  | SPT1003 |  |  | 2011-03-25 | Clyde Gateway LR1 (London Road 1) | 0.33 | 2013-03-01 | 2
|  | ENWT1002 |  |  | 2011-04-10 | Voltage Management on Low Voltage Busbars | 0.485 | 2012-10-01 | 2
|  | ENWT1003 |  |  | 2011-04-10 | Low Voltage Network Solutions | 1.49 | 2014-03-01 | 3
|  | SSET1004 |  |  | 2011-06-10 | Honeywell I&C ADR - Demonstrating the Functionality of Automated Demand Response | 0.26 | 2011-11-01 | 1
|  | SSET1005 |  |  | 2011-06-10 | LV Network Modelling and Analysis Environment | 0.32 | 2011-10-01 | 1
|  | WPDT1004 |  |  | 2011-07-06 | Early learning of LV network impacts from estate PV cluster | 0.03 | 2012-08-01 | 1
|  | WPDT1005 |  |  | 2011-07-14 | Seasonal Generation Deployment | 0.3 | 2013-04-01 | 2
|  | WPDT1006 |  |  | 2011-12-23 | LV Current Sensor Technology Evaluation | 0.25 | 2013-06-01 | 2
number of |  | UKPNT1003 |  |  | 2011-12-23 | LV Current Sensor Technology Evaluation | 0.25 | 2013-06-01 | 2
customers
2009/10 |  | 7.17
2597659 | 7172692.75
2441615 | 6741821.85
3507431 | 9684768.06
2241478 | 6189200.74
2242957 | 6193284.58
2357463 | 6509460.16
1572232 | 4341269.22
2254618 | 6225483.09
734947 | 2029346.05
2919504 | 8061375.72
1991924 | 5500128.71
1483801 | 4097092.3
1094220 | 3021375.73
1532913 | 4232701.05
28972762
2.76