## Report
DRAFT External Design Advisory Group - Monthly Programme Report | [5 empty] | Date report updated | 2016-02-04
Upcoming Key milestones (dates tbc pending Programme board sign off) | 1. Scenario 1 L1-L3 Design Authority sign off (date tbc) | 2 Dual Fuel Policy Design Authority sign off (date tbc) |  |  | 3. Scenario 2 Design Authority sign off (date tbc)
Commentary on critical path milestones - Design Baseline 1 (see accompanying plan on a page) The first milestone on the critical path is a decision on Objections policy - expected September 2016 with an indication of direction of travel in May 2016. The second milestone is the approval of the Switching Scenario package 4, followed by an approval of an updated objections operational requirement which will feed into solution architecture assessment of options and selection of preferred model. This will then develop switching scenarios for the RFI and deliver Baseline 1. The critical path will be discussed at Programme Board for approval in February.
Programme Progress update Overall *External Programme assurance in place, finalising detailed analysis of plans, timescales and critical path. We aim to share an approved version of the programme-level plan to Design Baseline 1 with EDAG in March. *DECC Published draft legislation on 21 January for pre-legislative scrutiny. Written responses are due 11 Feb. Design Authority *First meeting held 1/2/16 where ToR and ways of working were discussed. Business process design workstream *13 sessions have now been held with the Design Team. The Design Team meets twice weekly and is successfully using Huddle *The first User Group session was held on 25/01/2016 and attended by 26 external parties. The next user group meeting will be held on 22/2 *Good progress in mapping levels 1-3 of consumer switching scenario 1. Expect to sign this off at Design Authority in March 2016 *Dual fuel policy issues paper ready for EDAG review *Progressing through policy discussions on cooling off and lock out periods, including workshop at Independent Suppliers Forum on 2 Feb. Regulatory Design *Design Team and User Group membership now complete. 4 Design Team meetings held to date. Methodology, product descriptions and initial work packages agreed with Design Team. The first User Group meeting was held on 1/2. Delivery Strategy *4 sessions have been held with the Design team and the first User Group meeting was held on 3/2. *Long listed options on transitional new arrangements have been developed for EDAG review. Work is progressing in all other areas Commercial *Statutory Consultation on DCC's role in developing centralised registration service is now closed. We are reviewing responses and engaging with DCC on price control and procurment products *External procurement assurance and price control consultant in place to support commercial workstream work. *First User Group expected Mar/Apr External Dependencies *Objections review *Priority Services Register Review
Top strategic risks and issues
Risk/issue |  |  | R/A/G | Mitigating actions |  |  |  | Advice sought from EDAG
I01. There is a concern that the programme does not have the required capabilites and numbers for successful delivery. For example limited 'out of industry' expertise or challenge; limited experience in Ofgem of delivering large-scale IT-enabled change. Link to issue I02. |  |  |  | 1) Recruitment for an experienced Programme Director underway - appointment expected Q1 16/17 2) EUK to discuss with switching sub-group the possibility of providing 'out of industry' design assurance 3) Programme assurance reviewing capability and resources across programme - recommendations by March 2016 4) Ongoing discussions with the DCC and code adminstrators on expert resource provision 5) Industry workgroups and EDAG formed with expertise from across industry - complete. 6) Consultancy on procurement, price controls and business case development in place - complete.
I02. BPD team plan has not yet been developed in full. However it is likely that rate of progress is slower than required in plan. This is due to several reasons including a better appreciation of the volume of work to be completed and the decentralised team structure as well as capacity of resources available, although solution architect now available. |  |  |  | 1) Programme Assurance reviewing resources - recommendations by March 2016 2) Workstream lead and team members considering more collaborative ways of working - update by March 2016 3) DCC to procure more specialised resources, once requirement is confimed - from April 2016.
R01. Industry concern timing of RFI and information requests at end of year. |  |  |  | 1) Detailed plan to set out when RFI will be issued - sign off expected March 2016 by Programme Board 2) Programme team to work with other stakeholders, where possible, to coordinate timing of RFIs - ongoing 3) RFI format and questions to be shared with recipients in advance to enable resource planning - date to be confirmed when plan signed off (expected March 2016). |  |  |  | Information on expected RFIs in 2016 and 2017, including timing and originators

## Entered data
Project Information | Information
Project name | 0
Project category | #REF!
SRO | 0
Sponsor | 0
Primary contribution to strategic output | #REF!
Link to FWP | #REF!
Project manager | #REF!
Project type | #REF!
Delivery confidence
This month | #REF!
Last month | #REF!
Key action required to increase or maintain delivery confidence: | #REF!
Time and budget
Project stage | #REF!
Last gateway review | #REF!
Next gateway review | #REF!
Lifetime forecast costs | #REF!
Lifetime spend to date | #REF!
ABM code | #REF!
Approved for stage | #REF!
Spend for stage | #REF!
Baseline end date | #REF!
RAG rating for meeting baseline end date | #REF!
Project start date | #REF!
Forecast end date | #REF!
Key delivery indicators | Rating | Commentary (if rating not green)
Resourcing | 0 | 0
Scope | 0 | 0
Dependencies | 0 | 0
External influences | 0 | 0
Leadership & governance | 0 | 0
Critical path stage milestones (date & if FWP) | Rating | Description
1 | 0 | 1. Scenario 1 L1-L3 Design Authority sign off (date tbc)
2 | 0 | #REF!
3 | 0 | 2 Dual Fuel Policy Design Authority sign off (date tbc)
4 | 0 | 0
Project update: | Programme Progress update Overall *External Programme assurance in place, finalising detailed analysis of plans, timescales and critical path. We aim to share an approved version of the programme-level plan to Design Baseline 1 with EDAG in March. *DECC Published draft legislation on 21 January for pre-legislative scrutiny. Written responses are due 11 Feb. Design Authority *First meeting held 1/2/16 where ToR and ways of working were discussed. Business process design workstream *13 sessions have now been held with the Design Team. The Design Team meets twice weekly and is successfully using Huddle *The first User Group session was held on 25/01/2016 and attended by 26 external parties. The next user group meeting will be held on 22/2 *Good progress in mapping levels 1-3 of consumer switching scenario 1. Expect to sign this off at Design Authority in March 2016 *Dual fuel policy issues paper ready for EDAG review *Progressing through policy discussions on cooling off and lock out periods, including workshop at Independent Suppliers Forum on 2 Feb. Regulatory Design *Design Team and User Group membership now complete. 4 Design Team meetings held to date. Methodology, product descriptions and initial work packages agreed with Design Team. The first User Group meeting was held on 1/2. Delivery Strategy *4 sessions have been held with the Design team and the first User Group meeting was held on 3/2. *Long listed options on transitional new arrangements have been developed for EDAG review. Work is progressing in all other areas Commercial *Statutory Consultation on DCC's role in developing centralised registration service is now closed. We are reviewing responses and engaging with DCC on price control and procurment products *External procurement assurance and price control consultant in place to support commercial workstream work. *First User Group expected Mar/Apr External Dependencies *Objections review *Priority Services Register Review | [6 empty] | Project update: Programme Progress update Overall *External Programme assurance in place, finalising detailed analysis of plans, timescales and critical path. We aim to share an approved version of the programme-level plan to Design Baseline 1 with EDAG in March. *DECC Published draft legislation on 21 January for pre-legislative scrutiny. Written responses are due 11 Feb. Design Authority *First meeting held 1/2/16 where ToR and ways of working were discussed. Business process design workstream *13 sessions have now been held with the Design Team. The Design Team meets twice weekly and is successfully using Huddle *The first User Group session was held on 25/01/2016 and attended by 26 external parties. The next user group meeting will be held on 22/2 *Good progress in mapping levels 1-3 of consumer switching scenario 1. Expect to sign this off at Design Authority in March 2016 *Dual fuel policy issues paper ready for EDAG review *Progressing through policy discussions on cooling off and lock out periods, including workshop at Independent Suppliers Forum on 2 Feb. Regulatory Design *Design Team and User Group membership now complete. 4 Design Team meetings held to date. Methodology, product descriptions and initial work packages agreed with Design Team. The first User Group meeting was held on 1/2. Delivery Strategy *4 sessions have been held with the Design team and the first User Group meeting was held on 3/2. *Long listed options on transitional new arrangements have been developed for EDAG review. Work is progressing in all other areas Commercial *Statutory Consultation on DCC's role in developing centralised registration service is now closed. We are reviewing responses and engaging with DCC on price control and procurment products *External procurement assurance and price control consultant in place to support commercial workstream work. *First User Group expected Mar/Apr External Dependencies *Objections review *Priority Services Register Review
Issues | Reference | Description, cause and impact | Rating |  | Rating
1 | I01. There is a concern that the programme does not have the required capabilites and numbers for successful delivery. For example limited 'out of industry' expertise or challenge; limited experience in Ofgem of delivering large-scale IT-enabled change. Link to issue I02. | 0 |  |  | #REF!
2 | R01. Industry concern timing of RFI and information requests at end of year. | 0 |  |  | 1) Detailed plan to set out when RFI will be issued - sign off expected March 2016 by Programme Board 2) Programme team to work with other stakeholders, where possible, to coordinate timing of RFIs - ongoing 3) RFI format and questions to be shared with recipients in advance to enable resource planning - date to be confirmed when plan signed off (expected March 2016).
Risks | Reference | Risk category | Description | Description | Risk score (1-25) | Rating | Mitigation
1 | 1) Recruitment for an experienced Programme Director underway - appointment expected Q1 16/17 2) EUK to discuss with switching sub-group the possibility of providing 'out of industry' design assurance 3) Programme assurance reviewing capability and resources across programme - recommendations by March 2016 4) Ongoing discussions with the DCC and code adminstrators on expert resource provision 5) Industry workgroups and EDAG formed with expertise from across industry - complete. 6) Consultancy on procurement, price controls and business case development in place - complete. | 0 |  | 0 | 0 | 0 | 0
2 | #REF! | 0 |  | 0 | 0 | 0 | 0

## Lists
G | G
GA | A
A | R
AR
R
Regulation of monpolies and enabling markets
Effective competition
High standards of outputs and protection
Partnership with government and stakeholders
Trust and confidence
Efficiency and effectiveness
Pipeline
Concept
Definition
Implementation
Handover and closeout
Archived
Unknown
Legislative Commitment
Continuous Improvement
Ad Hoc Request from Senior Management
Publically Committed To
Tier 1
Tier 2
Tier 3
Business /Operational
Commercial/ Legal
Communications
Financial
Fraud
Governance
Political
Regulatory
Resource
Security
Technical
Third party - external

## Sheet1 (hidden)
[Workstream NAME] HIGHLIGHT REPORT
| Basic Information | [12 empty] | RAG Ratings
| Workstream Name: | [5 empty] | Report Author | [8 empty] | Previous Reporting Period | Current Status
| Programme Name: |  |  | Switching Programme |  |  | Report approved by:
| Name of Project Manager: |  |  | Rob Church |  |  | Date Report completed:
| Name of Workstream lead: |  |  | Angelita Bradney |  |  | Reporting Period: | [6 empty] | Overall progress RAG Rating
| Project Objective | [5 empty] | Current Project Stage: |  | Blueprint
Overview of Programme/Project
| Explanation of current status | [6 empty] | Action to maintain or improve RAG of delivery confidence.
Explanation of current RAG Key Achievements/Progress Key Issues
Key Risks
| ID | Risk Owner | Risk Event | Risk Impact | Current Risk Rating | Actions to reduce risk to target and Progress. |  |  |  | Implementation date |  | Action Owner | Rating after mitigation | Decision, Action or Escalation Required. Note: if you are including a risk for information only, e.g. a decision/escaltion is not required, please indicate this below.
[15 empty] | Prev | Curr | F'cast
| 7. Milestones for the Next 12 Months | [12 empty] | Time RAG Rating | A/G
| ID | Milestone Title |  |  |  | Baseline or Planned Date for Delivery | Forecast Finish | Actual Finish | Milestone Owner | RAG | Justification of RAG |  |  |  |  | Variance from Baseline
M1
M2
M3
M4
M5
↑
↔
↓
Note on B3: The information in the first box should be taken from your business case and should remain largely unchanged except for changes in personnel. The second box may change more frequently as needed.
Note on R5: Approval should be given by the SRO
Note on R7: Period since last programme board (usually 1 month)
Note on X7: The overall progress RAG is an assessment of the progress against your plan/ schedule and is an aggregation of the constituent RAG ratings in the Highlight Report, and a sense check by the SRO. These two points of view may not always be identical, but should not diverge wildly nor should they differ on an on-going basis.
Note on P12: What actions are being taken to improve RAG of the Delivery Confidence, or where unable to improve, maintain the current Delivery confidence RAG. Where possible an indication of when they expect the RAG to change or what circumstances would cause a change should be included.
Note on B15: You will ONLY need to update the ‘Decision, Action or Escalation Required’ column. As with Issues, your risk register should be included as a separate worksheet and should automatically pull over the top risks once they have been ranked. Risks need only be changed on the risk log and then they will change automatically on the Highlight report. To add more issues simply insert a row at the bottom of the table, highlight all the columns in the last row of the table, and from the bottom right hand corner, drag that row into the row you have just inserted. This will pick up the next ranked risk.
Note on B16: Each programme will be asked to use a three letter unique identifier which should be used in the ID columns. For risks, the unique ID will be followed by R, and I, M, and B for Issues, Milestones and Benefits respectively. For example, the Portfolio Office identifier would be PFO For identifying risk, it would then be PFOR01, PFOR02 etc
Note on B26: Every milestone needs to have a unique identifier For example, the Portfolio Office identifier would be PFO For identifying milestones, it would be PFOM01, PFOM02 etc. Milestone should be forward looking, reporting on any which are in jeopardy of being missed in the future as well as those which have passed. This is particularly important for SRP milestones to avoid a separate commission in the same month. You are required to indicate the level as specified by the milestones tab, as well as the type of milestone. At programme level, all 0 – 2 level milestones should be reported. Any level 3 milestones which, if missed, will cause a delay to the programme should also be reported. This should be reported on a rolling 12 month period, with the previous month’s milestone ‘falling off’ once they are completed. ALL SRP milestones should be included and labelled using the drop down menu in “Type” column.
Note on B27: Every milestone needs to have a unique identifier For example, the Portfolio Office identifier would be PFO For identifying milestones, it would be PFOM01, PFOM02 etc. Should be used on all documentation and reports that reference this milestone.
Note on C27: Prog/ Proj: Programme or Project milestone SRP: Structural Reform Priority action GMPP: GMPP milestone OBP: Operational Business Plan Milestone BAU: Business as usual milestons Ass’nce/Appr’l: Assurance or Approval point
Note on L27: When the plan is agreed and approved the milestones are given a baseline date If the agreed date is not specific, then the default of the last calendar day will be used.
Note on N27: This is the date the plan is currently forecasting the milestone will be delivered by This must always be a date in the future. If a specific date is not available, then the default end of the month date will be used.
Note on P27: This is left blank if the milestone has not yet been completed. It should always be a specific date and should always be a date in the past
Note on R27: Responsible manager for the delivery of the milestone.
Note on U27: Leave blank if Green or Complete. If not Green provide an explanation for slippage/ potential impact/ action being taken to correct.
Note on AA27: If there is a variance between the forecast finish (or actual finish) to the baseline date provide the reason and the impact and how the variance will/was mitigated(either in this reporting period, or forecast in future periods)