## Sheet1
Workflow
Type | Meeting date | Delivery Strategy | Business Process Design | Commercial | Reg design | DIAT
EDAG | 2016-02-11 | -Transition strategy options
DA | 2016-02-24 | -Transition strategy options | -Basecase 1
UG | 2016-03-08 | -Governance implementation options
-Assurance strategy options
-Data cleanse and migration
EDAG | 2016-03-15 |  | -Switching Scenario 1
'-Switching Scenario 2
UG | 2016-03-21 |  | -Scenario 2 and 3
-CRS user life cycle
-MPxN life cycle
-Advance registration
DA | 2016-03-30 |  | -Switching Scenario 1
-Dual fuel switch
UG | 2016-04-04 |  |  |  | -Existing Regulatory Requirements
-Current registration and switching roles and requirements
UG | 2016-04-12 | -Testing strategy
-Post-implementation strategy
EDAG | 2016-04-18 |  | -CRS user life cycle
-MPxN life cycle
-Advance registration
UG | 2016-04-25 |  | -Switching Scenario 4-5
-Lock out
-Service availability
-Enquiries and reporting
-Timing of final bills
-Mapping of legacy systems
-Investigation of available technologies
DA | 2016-04-27 |  | -Advance registration
UG | 2016-05-10 | -Data cleanse and migration
UG | 2016-05-23 |  | -Switching Scenarios 6-7
-Information risk assessment
-Management of PPM debt
-Management of PSR
-Long list solution architecture options
EDAG | 2016-05-24 |  | -Timing of final bills
-Lock out
-Service availability
-Mapping of legacy systems
-Enquiries and reporting
DA | 2016-06-06 |  | -Lock out
-Service availability
-Enquiries and reporting
UG | 2016-06-06 |  |  |  | -Registration and switching governance framework
-CRS/NDS business rules
UG | 2016-06-07 | -Governance implementation options
-Assurance strategy options
EDAG | 2016-06-16 |  | -Switching scenarios 2-5
-Switching scenarios 6-7
-Management of PPM debt
-Information risk assessment
-Solution architecture longlist
UG | 2016-06-20 |  | -Management of PSR
-Incident management policy
-Definition of next day
DA | 2016-06-29 |  | -Switching scenarios 3-5
-Switching scenarios 6-7
-Management of PPM debt
-Information risk assessment
-Long list solution architecture options