## Report
DRAFT External Design Advisory Group - Monthly Programme Report | [5 empty] | Date report updated | 2016-04-06
Upcoming Key deliverables | 1. Advance registration, Design Authority approval Apr 16' | 2. Existing regulatory requirements document, Workstream lead approval Apr 16' |  |  | 3. Publish decision on DCC funding and obligations licence mod. May 16' |  |  | 4. Lockout Policy Design Authority approval Jun 16'
Deliverables achieved since last reporting period | Scenario 1 & 2 L1-L3 DA approval Mar 16' | Dual Fuel Policy DA approval Mar 16'
Critical path milestones - Design Baseline 1 (see accompanying plan on a page)
Programme Progress update Overall *Programme is progressing to plan *Programme Director, Rachel Clarke, in place from 4/4 *First Programme delivery group (SPDG) to be held 11/4. Second Senior Stakeholder group meeting scheduled for 21/4. Design Authority *Design Authority approved all products put forward at the meeting on 30/3. These included Switching scenarios 1 and 2 and the Dual Fuel policy paper. Business process design workstream * Huddle being successfully utilised - SECAS has installed Casewise and models being migrated * DCC solution architect in place. Additional resource procurement via the DCC for solution architecture, CRS non-functional requirements and out of industry challenge has commenced with availability expected from end April. *Third User Group on 21 Mar reviewed inter-relationships between cooling off, lock-out, objections & adv registrations (with overview to be provided at EDAG 11/4) Regulatory Design workstream *Work with design team is ongoing and working well *The team are considering the impact of work being done by CMA remedies on code governance. In light of this, the uder group scheduled for 4/4 has been postponed and a revised meeting date will be scheduled. *Product 1, which maps existing regulatory requirements is awaiting sign off from workstream lead *Product 2, a document that captures the impact of the TOM proposals (and emerging BPD output) on all existing licence conditions and codes, is progressing according to plan. UG members will review this document offline and will be asked to provide comments via email instead of at the meeting originally scheduled for 4/4. Delivery Strategy workstream *Work with both the design team and user group is ongoing and progressing well. All products are progressing to plan. *The team are currently scoping out a piece of work for DCC to complete on data cleanse. The team have spilt data cleanse and data migration into separate workpackages. The Ofgem team will continue to lead on migration, while the DCC take forward data cleanse. *The next User Group meeting is scheduled for 12 April. Commercial workstream *Statutory Consultation on DCC's role and funding in transitional phase now closed. Decision to be published in May. Summary of proposals to be reviewed with EDAG at April mtg *The first user group is expected to be held in June. External Dependencies to programme *Objections review - depedency being actively managed. *Priority Services Register Review - dependency being actively managed. *CMA remedies - dependency being actively managed.
Top strategic risks and issues
Risk/issue |  | Current RAG | Previous RAG | Mitigating actions |  |  |  |  | For information, action or advice sought from EDAG
I03. There is a concern that the programme does not have the required capabilites to successfully deliver. For example limited 'out of industry' expertise or challenge; limited experience in Ofgem of delivering large-scale IT-enabled change. |  |  |  | 1) EUK to discuss with switching sub-group the possibility of providing 'out of industry' design assurance Update required from EUK 2) DCC published tender document for resource on 29/3 with a view for resource to be in place as soon as possible. |  |  |  |  | 1)Update required from EUK
R01. Industry are concerned about the timing of RFI due to the number of other information requests at end of year. There is a risk that Industry will not respond to the programme's RFI as required and that the information the programme receives to infrom the cost benefit analysis is of poor quality or incomplete. |  |  |  | 1) RFI to be issued Apr 17 as detailed in plan shared with industry 2) Programme team to work with other stakeholders, where possible, to coordinate timing of RFIs - ongoing 3) RFI approach to be shared with recipients in advance to enable resource planning - Late 2016 |  |  |  |  | Information on expected RFIs in 2016 and 2017, including timing and originators
R02. Risk that products require multiple reviews/approval cycles which will impact on timely delivery |  |  |  | 1) Stakeholder management through review cycles - Ongoing 2) Increased engagement from Design and Impact Assessment Team - Ongoing 3) 2 months contingency planned in programme plan for DB1 |  |  |  |  | For information
R03. There is a risk that the external dependencies are delayed which could delay the ability of the Programme to define switching processes in Baseline 1. This would have an impact on timely delivery. |  |  |  | 1)Engage with policy teams on Objections and PSR 2)Undertake work based on policy assumption and accept risk of wasted work |  |  |  |  | For information
R04. There is a risk that the CMA remedies could impact on the timely delivery of our programme, particuarly the regulatory design products |  |  |  | 1)The regulatory design team are engaged with Ofgem Remedies team and are working together to understand impact of remedies on switching programme of work. Ongoing |  |  |  |  | For information
Management of Objections Aug 16'
Cooling off Aug 16'
Switching scenarios -workpackage 2 Nov 16'
Assess options and select preferred model Nov 16'
Design Baseline 1 Feb 16'

## Sheet1 (hidden)
[Workstream NAME] HIGHLIGHT REPORT
| Basic Information | [12 empty] | RAG Ratings
| Workstream Name: | [5 empty] | Report Author | [8 empty] | Previous Reporting Period | Current Status
| Programme Name: |  |  | Switching Programme |  |  | Report approved by:
| Name of Project Manager: |  |  | Rob Church |  |  | Date Report completed:
| Name of Workstream lead: |  |  | Angelita Bradney |  |  | Reporting Period: | [6 empty] | Overall progress RAG Rating
| Project Objective | [5 empty] | Current Project Stage: |  | Blueprint
Overview of Programme/Project
| Explanation of current status | [6 empty] | Action to maintain or improve RAG of delivery confidence.
Explanation of current RAG Key Achievements/Progress Key Issues
Key Risks
| ID | Risk Owner | Risk Event | Risk Impact | Current Risk Rating | Actions to reduce risk to target and Progress. |  |  |  | Implementation date |  | Action Owner | Rating after mitigation | Decision, Action or Escalation Required. Note: if you are including a risk for information only, e.g. a decision/escaltion is not required, please indicate this below.
[15 empty] | Prev | Curr | F'cast
| 7. Milestones for the Next 12 Months | [12 empty] | Time RAG Rating | A/G
| ID | Milestone Title |  |  |  | Baseline or Planned Date for Delivery | Forecast Finish | Actual Finish | Milestone Owner | RAG | Justification of RAG |  |  |  |  | Variance from Baseline
M1
M2
M3
M4
M5
↑
↔
↓
Note on B3: The information in the first box should be taken from your business case and should remain largely unchanged except for changes in personnel. The second box may change more frequently as needed.
Note on R5: Approval should be given by the SRO
Note on R7: Period since last programme board (usually 1 month)
Note on X7: The overall progress RAG is an assessment of the progress against your plan/ schedule and is an aggregation of the constituent RAG ratings in the Highlight Report, and a sense check by the SRO. These two points of view may not always be identical, but should not diverge wildly nor should they differ on an on-going basis.
Note on P12: What actions are being taken to improve RAG of the Delivery Confidence, or where unable to improve, maintain the current Delivery confidence RAG. Where possible an indication of when they expect the RAG to change or what circumstances would cause a change should be included.
Note on B15: You will ONLY need to update the ‘Decision, Action or Escalation Required’ column. As with Issues, your risk register should be included as a separate worksheet and should automatically pull over the top risks once they have been ranked. Risks need only be changed on the risk log and then they will change automatically on the Highlight report. To add more issues simply insert a row at the bottom of the table, highlight all the columns in the last row of the table, and from the bottom right hand corner, drag that row into the row you have just inserted. This will pick up the next ranked risk.
Note on B16: Each programme will be asked to use a three letter unique identifier which should be used in the ID columns. For risks, the unique ID will be followed by R, and I, M, and B for Issues, Milestones and Benefits respectively. For example, the Portfolio Office identifier would be PFO For identifying risk, it would then be PFOR01, PFOR02 etc
Note on B26: Every milestone needs to have a unique identifier For example, the Portfolio Office identifier would be PFO For identifying milestones, it would be PFOM01, PFOM02 etc. Milestone should be forward looking, reporting on any which are in jeopardy of being missed in the future as well as those which have passed. This is particularly important for SRP milestones to avoid a separate commission in the same month. You are required to indicate the level as specified by the milestones tab, as well as the type of milestone. At programme level, all 0 – 2 level milestones should be reported. Any level 3 milestones which, if missed, will cause a delay to the programme should also be reported. This should be reported on a rolling 12 month period, with the previous month’s milestone ‘falling off’ once they are completed. ALL SRP milestones should be included and labelled using the drop down menu in “Type” column.
Note on B27: Every milestone needs to have a unique identifier For example, the Portfolio Office identifier would be PFO For identifying milestones, it would be PFOM01, PFOM02 etc. Should be used on all documentation and reports that reference this milestone.
Note on C27: Prog/ Proj: Programme or Project milestone SRP: Structural Reform Priority action GMPP: GMPP milestone OBP: Operational Business Plan Milestone BAU: Business as usual milestons Ass’nce/Appr’l: Assurance or Approval point
Note on L27: When the plan is agreed and approved the milestones are given a baseline date If the agreed date is not specific, then the default of the last calendar day will be used.
Note on N27: This is the date the plan is currently forecasting the milestone will be delivered by This must always be a date in the future. If a specific date is not available, then the default end of the month date will be used.
Note on P27: This is left blank if the milestone has not yet been completed. It should always be a specific date and should always be a date in the past
Note on R27: Responsible manager for the delivery of the milestone.
Note on U27: Leave blank if Green or Complete. If not Green provide an explanation for slippage/ potential impact/ action being taken to correct.
Note on AA27: If there is a variance between the forecast finish (or actual finish) to the baseline date provide the reason and the impact and how the variance will/was mitigated(either in this reporting period, or forecast in future periods)