## Overview
Overview
No. | Reference (Paragraph number, glossary term or table name) | Change | Reason for Change | Raised when | Raised by | WPD response | NPg response | ENWL resposne | UKPN response | SPEN response | SSEN response | Ofgem response | Status
1 | Overview guidance | Text updated for changes on Revenue and Financial Issues Reporting pack. | For consistency | Pre-consultation | N/A | Figure 1.1 needs to be updated so it refers to Annex C Revenue only (instead of Annex C Revenue and Financial Issues) Table 2.1 still refers to the requirement for a FI commentary in Annex C. WPD suggest that this requirement is moved to Annex B alongside the remaining FI tables. WPD's preference however would be for the FI commentary to be merged into the C&V commentary (see row 83 on the Annex B log) | The change to reduce the Financial Issues reporting pack and to amalgamate the remaining tables into the costs and volumes reporting pack means that there is no separate FI reporting pack submission. We suggest the same change should be made to the commentary template to align the commentary with the reporting packs i.e. removing the separate FI commentary and including the relevant commentary sections in the Cost and Volumes commentary. This would remove the need for this commentary pack to be referenced in table 2.1. Also, Figure 1 which is used in this document and every Annex needs amending to show Annex C as Revenue rather Revenue and Financial Issues. | Figure 1.1 still refers to the Revenue and Financial issues pack Table 2.1 (RIGs annexes, reporting packs, commentaries and timeframes) notes the removal of the Financial Issues pack from Appendix C. The table suggests that a commentary will be required for the pack. This would be better placed within the Cost and Volumes pack as the commentary reflects tables which have transferred into that pack. |  |  |  | Figure 1.1 updated to be - 'Annex C Revenue' to be consistent with changes to the RIGs. FI commentary has been merged with C&V commentary - table 2.1 in overview updated. | Closed - RIGs changed
2 | Footnote on page 8 - Pension RIGs | Link to Pensions RIGs in RIGS overview. |  | Consultation | ENWL |  |  | The footer on page 8 “Pension RIGs” links to the June 2013 version of the document. These are out of date and the hyperlink should either be removed or updated to link to the new pack. |  |  |  | Link provided in overview has been removed. | Closed - RIGs changed

## Annex A
Annex A - Glossary
No. | Reference (Paragraph number, glossary term or table name) | Change | Reason for Change | Raised when | Raised by | WPD response | NPg response | ENWL response | UKPN response | SPEN response | SSEN response | Ofgem response | Status
1 | Glossary: Streetworks - Suspensions and Closures | Streetworks - Suspensions and Closures definition added. | Undefined in glossary | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
2 | Glossary: Troublecall | Definition for Troublecall renamed to Faults and updated | For clarification | Pre-consultation | N/A | OK | Ok. | The new definition added for ‘Faults’ is not placed in the correct place alphabetically. | We agree with the proposed changes to clarify the boundaries between Faults and Asset Replacement including the clarification of definitions and the introduction of Appendix 1 in Annex B. |  |  | Definition for Faults moved to be in alphabetical order. | Closed - RIGs changed
3 | Glossary: Troublecall Occurrences | Definition updated. | For clarification | Pre-consultation | N/A | OK | Ok. |  | We agree with the proposed changes to clarify the boundaries between Faults and Asset Replacement including the clarification of definitions and the introduction of Appendix 1 in Annex B. |  |  | No action required | Closed - RIGs changed
4 | Glossary: Faults | Original Definition for Faults deleted | For clarification | Pre-consultation | N/A | OK | Ok. |  | We agree with the proposed changes to clarify the boundaries between Faults and Asset Replacement including the clarification of definitions and the introduction of Appendix 1 in Annex B. |  |  | No action required | Closed - RIGs changed
5 | Glossary term: Renewable Generation | Definition for Renewable generation added to glossary. | Undefined in glossary | Pre-consultation | N/A | The footnote number in the first sentence is not subscript and makes the year 20093 instead of 2009. The last paragraph makes reference to 'the working group' without specifying which working group this is. We suggest removing the reference to working group, so that the sentence states: "This will serve as a working list of technologies that will be reviewed periodically on a regular basis by the working group." | Typo in the glossary definition - the erroneous '3' needs deleting after 2009. | Typographical error in line 2 of the Renewable Generation (date) line. | We agree with the proposed definition for Renewable Generation but we will be restating our 2015/16 figures because with no definition in place we had not included Waste incineration (not CHP), Mini CHP (<1MW), Small CHP (>=1MW,<5MW), Medium CHP (>=5MW, <50MW), Large CHP (>=50MW), in our July 2016 E7 LCTs submission. | Technologies and definitions listed in Directive 2009/28/EC of the European Parliament and of the Council of 23 April 20093 on the promotion of the use of energy from renewable sources. Please delete the “3” following 2009. |  | "3" updated to be a footnote | Closed - RIGs changed
6 | Glossary term: Smart Meter Interventions - Meter Operator Hotline | Definition for Smart Meter Interventions - Meter Operator Hotline added to glossary | Undefined in glossary | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
7 | Glossary term: Shallow Cables | Definition added for Shallow cables. | Undefined in glossary | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
8 | Glossary term: Operational IT and telecoms | Definition update for Operational IT and telecoms | For clarification | Pre-consultation | N/A | First bullet is incorrect. This has duplication of 'Marshalling Kiosks'. This should be 'Substation RTUs, Marshalling Kiosks and Receivers.' This is a new issue not previously identified. | Ok. |  | We agree with the proposed classification but based on this change we will be restating our 2015/16 figures because this moves costs and volumes from the CV31 Repair & Maintenance Protection lines to CV11 Operational IT&T. Previously we have reported repairs for operational communication purposes in CV31. |  |  | Updated in line with WPD comment. | Closed - RIGs changed
9 | Glossary term: Pre-Fault Availability | Definition added for Pre-Fault Availability. | Undefined in glossary | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
10 | Glossary term: Repairs | Definition for Repairs deleted. | Not required | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
11 | Glossary term: Repairs and Maintenance | Definition updated | For clarification | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
12 | Glossary term: Asset Replacement | Definition updated | For clarification | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
13 | Glossary term: Separately Identifiable Asset Register Asset | Definition added. | Undefined in glossary | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
14 | Section 4 Task allocation: 6.6/11kV Switch (PM) | Change 'Replacement or repair of control box (and/or other communications devices' to 'Replacement or repair of control box' | For clarification | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
15 | Section 4 Task allocation: 6.6/11kV CB (PM) | Change 'Replacement or repair of control box (and/or other communications devices' to 'Replacement or repair of control box' | For clarification | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
16 | Section 4 Task allocation:20kV Switch (PM) | Change 'Replacement or repair of control box (and/or other communications devices' to 'Replacement or repair of control box' | For clarification | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
17 | Section 4 Task allocation: 20kV CB (PM) | Change 'Replacement or repair of control box (and/or other communications devices' to 'Replacement or repair of control box' | For clarification | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
18 | Glossary: Asset Register - Other Movements | Definition updated | For clarification | Pre-consultation | N/A | Assets adopted from ICPs have been incorrectly removed from the list of assets that are reported under Asset Register - Other Movements. DNOs do not incur costs associated with adoption of assets installed by ICPs, therefore including these assets under connections would skew any associated cost analysis. Assets adopted from ICPs should be reported as 'Asset Register - Other Movements'. This same comment applies to paragraph 6.11 in the Annex B guidance – which should also be consistently corrected. | Ok. |  | We agree with the proposed classification of moving additions and disposal related to DG activity or assets adopted from ICPs to the V3 – Connections table. This will mean a restatement of volumes from V4 into V3 for 2015/16. |  |  | Assets adopted from ICPs - text added back in. | Closed - RIGs changed
19 | Glossary: Specified Lines | Specified lines definition updated | Information included on Single Emergency Number | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
20 | Activity Volumes - Inspections | Definition updated | For clarification | Pre-consultation | N/A | The additional details added into this definition are already contained within Annex B guidance. This now leads to duplication of instructions, which need to be kept in line in the future. WPD's preference is to retain the guidance within Annex B and leave the definition unchanged. | Ok. |  |  |  |  | No action required | Closed - RIGs changed
21 | Smart Meter Information Technology Costs | Definition updated | For clarification | Pre-consultation | N/A | WPD is happy with this much expanded definition in principle. However, we suggest 2 changes should be made: (1) Compliance - costs associated with external audits by an Independent Competent Organisation - WPD report these in 'Smart Meter Communication Licensee Costs' as these are invoiced together with the other costs reported in this activity. Therefore we suggest these costs should remain in 'Smart Meter Communication Licensee Costs' rather than 'Smart Meter Information Technology Costs' (2) Care should be taken with the capitalisation of various phrases in this definition, as capitalisation suggests that these phrases are defined separately elsewhere in the RIGs which is not the case. We suggest that the following terms are 'decapitalised' to avoid confusion: 'Hardware and Infrastructure Costs'; 'Application Software Development Costs'; 'Customer Relationship Management systems'; 'Gateways'; and 'Client'. 'Independent Competent Organisation' is a specific term defined in the Smart Energy Code and so this should be made clear in the definition (eg "Independent Competent Organisation (as defined in the Smart Energy Code)". | Ok. |  |  |  |  | No action | Open - future review
22 | Network Innovation Competition | Definition added | Undefined in glossary | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
23 | DCC User | Definition added | Undefined in glossary | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
24 | Glossary: Bus Stop Suspensions | Definition added |  | Pre-consultation | N/A | OK | [5 empty] | No action required | Closed - RIGs changed
25 | Glossary: Temporary Traffic Regulation Order | Definition added |  | Pre-consultation | N/A | OK | [5 empty] | No action required | Closed - RIGs changed
26 | Glossary: Temporary Traffic Regulation Notice | Definition added |  | Pre-consultation | N/A | OK | [5 empty] | No action required | Closed - RIGs changed
27 | Glossary: NABC - Bad Debt Expense associated with supplier failures (Net of Recoveries) | Definition added |  | Pre-consultation | N/A | OK | [5 empty] | No action required | Closed - RIGs changed
28 | Glossary: Stores |  |  | Consultation | WPD | This still shows red text for a previous change | [5 empty] | Change text to black - not part of consultation. | Closed - RIGs changed
29 | Glossary: NABC - Bad Debt Expense (Net of Recoveries) | Change proposed by WPD |  | Consultation | WPD | An additional exclusion should be added to this definition: please add 'bad debt expense associated with supplier failure". To avoid confusion, WPD also suggests that this activity is renamed to "NABC - Bad Debt Expense Other (Net Of Recoveries)" | [5 empty] | Annex A and B updated | Closed - RIGs changed

## Annex B
Annex B - Costs and Volumes
No. | Reference (Paragraph number, glossary term or table name) | Change | Reason for Change | Raised When | Raised by | WPD response | NPg response | ENWL resposne | UKPN response | SPEN response | SSEN response | Ofgem response | Status
1 | Forecasts | Forecast table requirements | To align TOTEX to PCFM | Pre-consultation | N/A | OK | Using uppercase for 'totex' isn’t in keeping with the Ofgem convention, which is lowercase |  | We see little value in splitting non op capex, CAI and BS further than was in the original version of M16. |  |  | No action required | Closed - RIGs changed
2 | M16 - Forecasts | Cell A2 is hard coded to NPGN. Updated to link to ='Cover Sheet'!$D$12 | Should not be hard coded. | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
3 | S1 Summary of C1 | BL67 in S1 Summary of C1 incorrectly linking to cell BK80 and BL62. | Incorrect link | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
4 | S1 - Summary of C1s,S2 - Summary of C1s (Real), S3 - C1 Movements (Real). | Cells BK8 and BL8 updated to read Network Innovation Allowance (NIA) (BK8) and Network Innovation Competition (NIC) (BL8) to be consistent with Cost Matrix tabs. | Incorrect title | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
5 | S1 - Summary of C1s | Formula in cells BL16, BL33, BL50 and BL67 updated to link to column BL on 2016 C1 instead of column BK. | Incorrect links | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
6 | SI1 - Performance Summary | Cell O20 is meant to be ‘% of allowance’ but the formula wrong way round, i.e. instead of row 19/row 18, it should be row 18/row 19. | Incorrect formula | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
7 | SI1 - Performance Summary | Network length - Row 12 Overhead Lines, Row 13 Underground Cables , and Row 13 Other (Subsea Cables) only links to EHV categories and so doesn’t include LV, HV and 132kV categories. Updated to include these. | Incorrect formula | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
8 | SI1 - Performance Summary | Row 25 title updated to 'Customer Interrupted 'Excluding exceptional events)'. | Incorrect title | Pre-consultation | N/A | Version 2.0 already had row 25 title as 'Customers Interrupted (excluding exceptional events)'. It is not clear what has changed. | Ok. |  |  |  |  | Version 2, row 25 was noted as including exceptional events. | Closed - RIGs changed
9 | SI1 - Performance Summary | Cell O9: This was originally a blank cell and the formula has been added in to take this figure from Tab M14. | No link | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
10 | SI1 - Performance Summary | TOTEX reported in cell O18 is in 12/13 prices. Tab updated | For clarification | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
11 | SI1 - Performance Summary | Rows 22-26: it should be specified in the table that these are both unplanned and unweighted (currently only specifies unweighted) | For clarification | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
12 | SI1 - Performance Summary | Rows 32-33: it should be specified that these are the average time to quote and connect - annex updated | For clarification | Pre-consultation | N/A | The word 'average' could also be added to cells D32 and D33 in the Excel workbook. | Ok. |  |  |  |  | Cost and volumes pack - average added to cells D32 and D33 for consistency. | Closed - RIGs changed
13 | SI1 - Key Summary Information: Unrestricted Domestic Tariff | Unrestricted Domestic Tariff reported in 12/13 prices. Tab updated. | For clarification | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
14 | Annex B: SI1 - Key Summary | Annex B: SI1 - Key Summary title updated to Performance Summary | To align with C&V pack | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
15 | Annex B: SI1 - Key Summary | Definition updated | To align with C&V pack and for clarification. | Pre-consultation | N/A | It is not clear what definition has changed. Is this referring to the guidance for SI1 being updated? | Ok. |  |  |  |  | Title change | Closed - No changed
16 | Annex B: SI1 - Key Summary | SI1 - guidance updated, CIs and CMLs in tab will be reported a year in arrears. | For consistency with text in M14 drivers | Pre-consultation | N/A | NO CHANGE HAS BEEN MADE. The additional guidance for reporting a year in arrears is not included | Ok. |  |  |  |  | Text added to SI1 - Perfromance summary annex B. | Closed - RIGs changed
17 | Tab C1 Cost Matrix - all years | Formula copied into cell BZ80 (consistent with cell BY80) | Formula missing | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
18 | CV tables | Tables updated: [1] Cell AD2 reads: Asset Additions/Activity Volumes [2] Cell B25 reads: Activity/Asset Costs and Volumes | For clarification | Pre-consultation | N/A | Cell B25 reads 'Asset Volumes and Costs' This is in line with the WPD feedback in the informal consultation. The change described here is incorrect. | Tables CV29, CV30, CV31, CV33 and CV35 still require Changes to Cells ‘B25’ and ‘AD2’ to ensure consistency with other Tables | Cell B25 reads: Asset Costs and Volumes – this should be updated to 'Activity/Asset Costs and Volumes'. |  |  |  | Tables CV29, CV30, CV31 and CV33 updated | Closed - RIGs changed
19 | Annex B: CV26 Faults | Annex B updated | For clarification | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
20 | Annex B: Asset Replacement CV7 | Annex B updated | For clarification | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
21 | Appendix 1 added to Annex B | Appendix 1 added to annex B showing Cost Allocation Scenarios Fault and Asset Replacement | Added for clarification | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
22 | CV29 - Tree Cutting | Row 96 should be % in volumes (column AD onwards) | Incorrect format | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
23 | CV30 - Inspections | Row 55 should be in unit 'inspections' not 'substations' | Incorrect unit | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
24 | CV17 - RLM | Tab CV17 - units updated. | For clarification | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
25 | CV26 - Faults | Multiplier updated to be 1000 rather than 100. Cells CA145:CM145 Cells CA146:CM146 | Incorrect multiplier. The errors relate to the calculation of fault rates. The calculation of fault rates is either per 100km of linear network or per 1000 units (for non-linear assets). | Pre-consultation | N/A | OK | Ok. |  |  | The RIGS stated that the fault rate is per unit (refer to Glossary). This inconsistent with industry practice (and historic reporting to Ofgem) which was to report ‘per 1000 units’ or ‘per 100km’ depending on the asset type. The table on CV26 neither reflects the RIGs or industry practice. The modification appears to partially (but not fully) correct the tables in line with industry practice. |  | Review industry practice in 2017/18 | Closed - no change
26 | CV26 - Faults | The error affects the fault rate calculations in cells CA142 to CM142 As an example of the error the current formula in CA142 is =IF('CV26 - Faults'!AD$142=0,0,('CV26 - Faults'!AD$142/SUM('V1 - Total Asset Movements'!BL$46:BL$49,BL$52:BL$54))*100) It should be =IF('CV26 - Faults'!AD$142=0,0,('CV26 - Faults'!AD$142/SUM('V1 - Total Asset Movements'!BL$46:BL$49, 'V1 - Total Asset Movements'!BL$52:BL$54))*100) | Incorrect formula | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
27 | CV33 - Substation Electricity | BL28:Bx28 amended to multiply by 1000000 rather than 1000 as header show the values to be reported as £/# | Incorrect multiplier. | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
28 | CV 35- Op Training (CAI) | Row 31 - the formulae on this row are picking up rows 28-29; should be picking up rows 28-30. | Incorrect link | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
29 | CV 35- Op Training (CAI) | Cells Z30, AA30, AQ30 and AR30 - formula missing, cells updated. | Missing formula | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
30 | CV 35- Op Training (CAI) | BL30 to Bx30 formula missing, cells updated | Missing formula | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
31 | M2 - DPCR5 WSC Schemes | Equation in column AI is [=IF(D35=0,"-",IF($A$3-D35>3,((AG35-W35)/W35),"too early"))] but should be or than or equal to so should be [=IF(D35=0,"-",IF($A$3-D35>=3,((AG35-W35)/W35),"too early"))] | Incorrect formula | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
32 | M3 - ED1 WSC Schemes | Equation in AO is [=IF(D35=0,"-",IF($A$3-D35>3,((AM35-Z35)/Z35),"too early"))] but should be more than or equal to so updated to be =IF(D35=0,"-",IF($A$3-D35>=3,((AM35-Z35)/Z35),"too early")) rather than | Incorrect formula | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
33 | M2 - DPCR5 WSC Schemes and M3 - ED1 WSC Schemes | Both these sheets are missing project numbers 5, 9, 11 | Missing rows in tables | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
34 | M2 - DPCR5 WSC Schemes | Tab M2 - DPCR5 WSC Schemes, Cells B14:G24 greyed out. | Not required | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
35 | M14 - Drivers | Network length formula in M14 (line 26) is not calculating properly. It’s not picking up Unpressurised cable at EHV and 132kV (lines 85, 88, and 115 of MEAV table refer). Updated. | Incorrect formula | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
36 | Commentary | High level tables at the beginning, CV22 Environmental Reporting should be added as a bullet point to non-load capex. | Missing detail | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
37 | Commentary | Table added in commentary for CV22 Environmental Reporting | Table missing | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
38 | Guidance for CV22 Environmental Reporting | Should include the same paragraph as others, "this worksheet requires the reporting of asset additions and disposals as a result of Environmental Reporting activities" | For clarification | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
39 | C23 - Other NABC | Extra NABC category to remove costs from totex relating to Last Resort Supply Payments. Glossary term added | For clarification | Pre-consultation | N/A | NO CHANGE HAS BEEN MADE This change has not been made and no glossary term has been included. | Ok. | Please clarify where this adjustment has been processed? |  |  |  | Annex A amended Bad Debt Expense associated with supplier failures to include Last resort supply payments | Closed - RIGs changed
40 | C23 - Other NABC | Split bad debt row in C23 into bad debts associated with supplier failures and other. Glossary term added | For clarification | Pre-consultation | N/A | OK, but see comments on Glossary. WPD suggest that "Bad Debt Expense" is renamed to "Bad Debt Expense Other" to avoid confusion. | Ok. |  |  |  |  | Annex A definition amended to Bad Debt Expense other and changed in Annex B | Closed - RIGs changed
41 | Annex B - 4.62 CV 7 - Asset Replacement | Text updated | For clarification | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
42 | Check Sheet | The checks on rows 193 and 194 link through to blank cells in tables M2 and M3 Worst Served Customers. As there are no checks in these tables, these rows can be greyed out in the Check Sheet | Not required | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
43 | I2 PCFM Inputs Nominal | Rows 90-96 (Moorside) do not feed in anywhere - should link to the relevant activities in rows 11-25. Rows 118-122 do not feed in anywhere and could be deleted from this table (Atypicals are analysed further down in table I2, Atypicals Non TIM, NIA, NIC and LCNF are not part of TIM and are therefore not relevant on this table) | Incorrect links | Pre-consultation | N/A | These issues has not been addressed, despite being flagged as change made in the February 2017 issues log. Agree rows 90:96 should feed into relevant activities in rows 11,12,20 and 25. Agree rows 118 - 122 do not feed anywhere; if these are removed then rows 203:207 can also be removed. | Ok. |  |  |  |  | Review 2017/18 | Closed - no change
44 | I2 PCFM Inputs Nominal | Formula in cell AJ16 should include cell AJ228 | Incorrect formula | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
45 | I2 PCFM Inputs Nominal | Blank cell AJ89 being added into Actual Non-Load Related Capex - Asset Replacement in cell AJ12. | Incorrect formula | Pre-consultation | N/A | Corrected in column AJ but still incorrect for columns AK:AQ. | Ok. |  |  |  |  | Rolled out to other year. | Closed - RIGs changed
46 | I2 PCFM Inputs Nominal | Any indirects allocated to Atypicals – Non Severe Weather in cells BI72:BI77 of C1 - Cost Matrix 2016 do not get picked up in table I2 as the values in AJ223:AJ238 are being picked up from table C15 - Atypicals 2016 only which does not include indirect allocations (paragraph from RIGS: For the avoidance of doubt the costs entered in this worksheet are direct costs only. Any associated indirect costs will be captured in the relevant indirect worksheets. DNOs will then allocate the indirect associated with Atypicals in C1 (Rows 72 to 77)). | Incorrect formula | Pre-consultation | N/A | As stated in the February 2017 WPD issues log, the change that has been made is incorrect as all the indirects are being allocated to one PCFM cost category. The indirect allocation to Atypicals Non Severe Weather in C1 - Cost Matrix 20xx cell BI78 should be included across table I2 rows 223-228. For example, the formula in cell AJ223 of table I2 should be: =SUM('C15 - Atypicals 2016'!$Y$64:$Y$72)+('C1 - Cost Matrix 2016'!BI78-'C1 - Cost Matrix 2016'!BI73)*(SUM('C15 - Atypicals 2016'!Y64:Y72)/(SUM('C15 - Atypicals 2016'!$AF$64:$AF$72)-SUM('C15 - Atypicals 2016'!$AD$64:$AD$72))). Similar formulae should be included in rows 224,225,226,227 and 229. Row 228 should be greyed out. The formula in cell AJ237 of table I2 should then be: 'C15 - Atypicals 2016'!AD65+('C1 - Cost Matrix 2016'!BI73). Rows 231, 232, 233, 234, 235 and 238 should also be greyed out. This is a complex change and could be extended so cells in table C15 are also greyed out to reflect that only pensions costs should be allocated to the "100% Revenue Pool" PCFM cost category. If this change is deferred until next year, there are some formula errors which do need to be addressed this year: row 237 in table I2 is linking to Controllable Opex (column AE in C15) and should be linking to 100% revenue pool (column AD). SIGNIFICANT: Row 229 is incorrectly bringing in ALL indirect allocations for CAIs and Business Support costs net of pensions (cells BD78 and BH78 in table C1). | Ok. | the formula needs to be updated – The current update includes all indirects allocated to 'non-distribution activities (exc Connections)' whereas they should only be adding in indirects allocated to 'Atypicals included within Totex'. |  |  |  | Formula updated | Closed - RIGs changed
47 | I2 PCFM Inputs Nominal | Labelling in cells D120 and D121 is the wrong way round | Incorrect titles | Pre-consultation | N/A | Labelling in D120 and D121 corrected but corresponding labelling in rows 205 and 206 is still incorrect. | Ok. |  |  |  |  | Labelling updated | Closed - RIGs changed
48 | I4 - Revenue, Fin Issue Inputs | Row 37, Total Expenditures updated to be Total C1 expenditure reported | For clarification | Pre-consultation | N/A | No longer relevant, as this part of the table has been removed following the removal of the FI pack | Ok. |  |  |  |  | No action required. | Closed - RIGs changed
49 | M13 Uncertainty Mechanism Information | Row 14 Load Related Expenditure links through to Total Net Costs Before Allocations -'Total Net Costs Before Allocations ' added to heading. | For clarification | Pre-consultation | N/A | (Repeated from Feb 17 issues log) Agreed heading changed; however it still needs to be clarified whether this should be Net Costs Before or After Allocations | Ok. | We note that the title has been updated, but the key issue is that the calculation does not correctly adjust the allowance for comparison against allowances – the allowance for LRRC was set as Total Net Costs after Allocations. |  |  |  | Amended to Total net costs after allocations | Closed - RIGs changed
50 | M13 Uncertainty Mechanism Information | Row 15 Rail Electrification converted to 12/13 prices. | For clarification | Pre-consultation | N/A | (Repeated from Feb 17 issues log) Agreed now converted to 12/13 prices. However labelling and linkage of this row should be reviewed in 17/18 | Ok. |  |  |  |  | Reviewing 2017/18 | Closed - No Change
51 | M13 Uncertainty Mechanism Information | WPD excluded and identified link box expenditure as Gross in M13 | Not applicable | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
52 | M13 Uncertainty Mechanism Information | Row 21 - the UCRE term does not apply to WPD so cell AJ21 should have “If” functionality to reflect this and the heading should also be updated. | Not applicable | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
53 | Paragraph 5.11 (V4 - Other Movements) | DG activity removed from V4 | For clarification | Pre-consultation | N/A | Assets adopted from ICPs have been incorrectly removed from the list of assets that are reported under V4. DNOs do not incur costs associated with adoption of assets installed by ICPs, therefore including these assets under connections would skew any associated cost analysis. Assets adopted from ICPs should be reported as 'Asset Register - Other Movements'. | Ok. |  |  |  |  | ICPs returned to V4 asset register | Closed - RIGs changed
54 | CV14 Legal and Safety | Annex B updated to include shallow cables. | Definition missing from guidance | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
55 | CV14 Legal and Safety | Row added in CV14 under category for shallow cables. | Addition to table | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
56 | I1 - PCFM Inputs 12-13 | The actual controllable opex values have not been adjusted for theft in conveyance forecast amount as set out in Appendix 1 of CRC5F Treatment of income from recovery in respect of relevant theft of electricity (needs to link to values in I3 as per your instructions to us this summer). | Incorrect formula | Pre-consultation | N/A | Formula has been updated since v2.0 issued in Feb but this is unclear from this issues log. This adjustment should be made within row 26 on I2, rather than being included in row 17 of I1. Actual Totex expenditure in I1 should simply be a conversion of Actual Totex Expenditure in I2; if this adjustment remains only in I1, the Controllable Opex value and Actual Totex Expenditure in I2 would be incomplete. Further, the (slow track) licence definition of Income from Theft Recovery includes this adjustment and row 26 of I2 is called "Income from Theft Recovery". | Ok. |  |  |  |  | Review 2017/18 | Closed - No Change
57 | Commentary C&V - M17 Forecasts TOTEX | Table added to commentary | Missing from commentary | Pre-consultation | N/A | OK | The contents page for the C&V Commentary pack needs to be updated |  |  | Add - M17 Forecasts TOTEX |  | table added | Closed - RIGs changed
58 | F2 - Net Debt & Tax Clawback, F8 - Reconciliation to Reg Accs | Moved F2/F6/F8 from Financial Issues reporting pack to Cost and Volumes pack. F2 and F6 combined. | Tabs fit better in C&V pack | Pre-consultation | N/A | See detailed comments below | Ok. |  |  |  |  | No action required here. Comments provided by licensee below. | Closed - RIGs changed
59 | Annex B: Cost and Volumes guidance | Guidance updated to include information from tables moved from Financial Issues Reporting pack (F2/F6/F8) and remove any text not required due to changes in Financial Issues reporting pack. | Guidance updated to reflect change in packs. | Pre-consultation | N/A | See comment in row 82 below. | Ok. | Guidance should be merged and reworded to be all about F2 table as F6 table no longer exists. |  |  |  | No action required here. Comments provided by licensee below. | Closed - RIGs changed
60 | I1 - PCFM Inputs 12-13 | The actual controllable opex values adjusted to include theft in conveyance from I3 | For clarification | Pre-consultation | N/A | Is this Ofgem's response to issue 56? Unclear. See WPD comments in relation to issue 56. | Ok. |  |  |  |  | Review 2017/18 | Closed - No Change
61 | I2 - PCFM Inputs Nominal | Added extra row at bottom of tab to sum each category of actual expenditure for use in F8 check. | To enable check | Pre-consultation | N/A | SIGNIFICANT: F8 previously reconciled Total Expenditure reported in the Regulatory Accounts to Total Expenditure reported in the Costs and Volumes Reporting Pack, which was linked to cell CB80 of table C1; Total Net Costs after Non Price Control allocation. Totex (sum of rows 11:17) in table I2 - PCFM Inputs Nominal is not the same thing as Total Expenditure reported in the Cost and Volumes reporting pack. Cell C43 in table F8 should be re-linked to cell CB80 in the relevant C1 table. See also issue raised in row 81. | Ok. | Previous F8 reconciled Total C1 costs to the Regulatory Accounts totals. The new F8 compares Totex figure (new row on I2) to Regulatory Accounts totals. Is this an intentional change? |  |  |  | Total row added | Closed - RIGs changed
62 | I4 - Revenue Pack Inputs | Removed redundant links for Financial Issues Pack. | Financial issues pack removed | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required. | Closed - RIGs changed
63 | I2 - PCFM Inputs Nominal | Amended formulae in cell range AJ21:AQ23 changed from "=IF(ISBLANK(AJ$29),AJ$26,AJ$29)" to "=IF(AJ$29=0,AJ$26,AJ$29)" respectively. | Incorrect formula | Pre-consultation | N/A | Incorrect table reference. Should be PCFM Inputs 12-13. Change agreed. | Ok. |  |  |  |  | Label in changes log amended | Closed - RIGs changed
64 | I4 - Revenue Pack Inputs | Change made to "I4 - Revenue, Fin Inputs" worksheet. Reversed sign when linking to the supporting tabs, so revenue is shown as a positive. | Incorrect link | Pre-consultation | N/A | THIS CHANGE HAS NOT BEEN FULLY MADE This change has only been made to cell AJ21. The reversal of the signage should be made to all cells in the range AJ20-AQ24. | We agree with this change, however it has only been made for 2015/16 – all other years would still require us to reverse the sign, so Ofgem need to apply this change to all years. | The change has only made for cell AJ21. All cells in range AJ20:AQ24 should be updated as they are picking up revenue figures from C+V pack. |  |  |  | No action required. Signage updated across all years. | Closed - RIGs changed
65 | I4 - Revenue Pack Inputs | DRS1 revenue should be included in the revenue RRP under Directly Remunerated Services. Amended formula in Tab I4 - Revenue, Fin Issue Inputs for the Directly Remunerated Services row. Formula now includes DRS1 revenue from tab C20 Connections Outside PC. | Incorrect link | Pre-consultation | N/A | THIS CHANGE HAS NOT BEEN MADE This change has not been made: the DRS row in table I4 has not been amended and table C20 has not been updated to allow reporting of DRS1 revenue | The remedial action has not been carried out - Ofgem need to make the change, ensuring that this is applied to each year. | the formula hasn't been updated for this, however the figure for income in C20 is Customer Contributions and not Revenue and so shouldn't be linked to for reconciliation of Revenue in Regulatory Accounts. |  | The modification referred to on point 65 on Ofgem Issues Log in relation to the inclusion of DRS1 Revenue on Table I4 does not seem to be carried out in the latest pack. |  | No action required. Formula for row Directly remunerated Services includes DRS1 revenue from tab C20 Connections Outside PC. | Closed - RIGs changed
66 | I4 - Revenue Pack Inputs | DRS1 revenue should be included in the revenue RRP under Directly Remunerated Services. Amended formula in Tab I4 - Revenue, Fin Issue Inputs for the Directly Remunerated Services row. Formula now includes DRS1 revenue from tab C20 Connections Outside PC. | Incorrect link | Pre-consultation | N/A | Change not made (duplicate of issue 65) | Repetition of 65. |  |  |  |  | See above. | Closed - RIGs changed
67 | Cost and Volumes Commentary | Table added for CV 20 Visual Amenity | Missing from commentary | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
68 | Cost and Volumes Commentary | Table added for CV 22 Environmental Reporting | Missing from commentary | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
69 | Cost and Volumes Commentary | Appendix 1 updated. | Changes to CV20 and CV22. | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
70 | Cost and Volumes Commentary | Table added for M17 Forecasts TOTEX | To reflect changes to Cost and Volumes pack. | Pre-consultation | N/A | OK (duplicate of issue 57) | Ok. |  |  |  |  | No action required | Closed - RIGs changed
71 | Annex B - M9a Traditional Street Works (Ex Ante) | Additional category of suspensions and closures added |  | Pre-consultation | N/A | OK | [5 empty] | No action required | Closed - RIGs changed
73 | CV20 - Visual Amenity | Update to paragraph 5.167 |  | Pre-consultation | N/A | Given that visual amenity was already adequately defined in the glossary, the additional detail included is superfluous and, as currently drafted, confusing. If it is to remain, it needs updating as follows: The purpose of this worksheet is to record the gross costs and volumes associated with Visual Amenity Projects. relating to the undergrounding of overhead lines under the Visual Amenity Allowance funding mechanism. The Visual Amenity funding mechanism allows undergrounding of overhead lines for Visual Amenity Inside Designated Areas. The mechanism also and allows for up to 10% of the total allowances to be used for undergrounding of overhead lines for Visual Amenity Outside Designated Areas where overhead lines span the boundary of Designated Areas. The worksheet records the costs of Visual Amenity Projects to feed into C1 and associated asset additions and disposals to feed into V1 – Total Asset Movements. | [5 empty] | The change in annex B to CV20 - Visual Amenity has been removed. The description has been left as in version 2.0. Change was not required. | Closed - no change
72 | Figure 1.1 missing from Annex B |  |  | Consultation | WPD | [6 empty] | Figure 1.1 updated to reflect name change to annex C. | Closed - RIGs changed
74 | F2 - Net Debt & Tax Clawback, F8 - Reconciliation to Reg Accs |  |  | Consultation | WPD | F2 name varies between worksheet and other references, e.g. FI Commentary document is still referring to 2 tables, F2 and F6; Annex B guidance document refers to "F2 – Net Debt, & Interest & Tax Clawback" but still then has title "F6 – Tax Clawback Data"; table itself in C&V pack is called "F2 - Net Debt & Tax Clawback". Name should be consistent and references to data in this table should all be under this single consistent heading. | [5 empty] | Actioned | Closed - RIGs changed
75 | F2 - Net Debt & Tax Clawback, F8 - Reconciliation to Reg Accs |  |  | Consultation | WPD | Is there a reason why the financing information in F2 has to be split between <1 yr, >1yr <5 yrs, >5yrs? This is a new requirement but it is unclear what this information will be used for as it does not affect the tax clawback calculation. | [5 empty] | This has been done to standardise tab F2 (Net Debt & Tax Clawback) across all sectors | Closed - RIGs changed
76 | F2 - Net Debt & Tax Clawback, F8 - Reconciliation to Reg Accs |  |  | Consultation | WPD | Further guidance is required re: cost reporting convention. Currently, paragraph 1.12 in Annex B guidance states "All numbers must be entered as positive, except Customer Contributions and Cost Recoveries, which should be entered as a negative." However, items such as interest income, cash balances and loans to /other amounts due from other group companies should also be reported as positive amounts. Further, some of the adjustments to net debt to align it with the tax clawback definition should clarify whether these are adding or deducting, e.g. "Add back: Unamortised issue costs". "Amounts due to/(from) other group companies" could also be a fixed heading in row 25. | [5 empty] | - As para 1.12 stands, interest income, cash balances and loans to/other amounts due from other group companies would be reported as positive amounts. - We have deliberately not been specific on adding/deducting items in the table, to allow flexibility in the calculation where it is legitimately required. We would expect licensees to comment on this in their commentaries if this is the case. - Row 25 has been left open for the licensee to populate, as not all licensees require the heading proposed. | Closed - RIGs changed
77 | F2 - Net Debt & Tax Clawback, F8 - Reconciliation to Reg Accs |  |  | Consultation | WPD | F2 Row 68 should read: "Pensions: interest on scheme liabilities", and similarly in row 88 "Pensions: expected return on scheme assets". | [5 empty] | Actioned - F2 Row 69 & 89* | Closed - RIGs changed
78 | F2 - Net Debt & Tax Clawback, F8 - Reconciliation to Reg Accs |  |  | Consultation | WPD | SIGNIFICANT: F8 previously reconciled Total Expenditure reported in the Regulatory Accounts to Total Expenditure reported in the Costs and Volumes Reporting Pack, which was linked to cell CB80 of table C1; Total Net Costs after Non Price Control allocation. Table F8 in the latest pack now links to Totex (sum of rows 11:17) in table I2 - PCFM Inputs Nominal, which is not the same thing as Total Expenditure reported in the Cost and Volumes reporting pack. Cell C43 in table F8 should be linked to cell CB80 in the relevant C1 table. | [5 empty] | Actioned | Closed - RIGs changed
79 | Annex B: Cost and Volumes guidance |  |  | Consultation | WPD | Paragraph after 3.3 – should have a paragraph reference and should refer to table F6, not F8. | [5 empty] | Actioned | Closed - RIGs changed
80 | Financial Issues commentary document |  |  | Consultation | WPD | This is still a standalone document despite the tables being merged into the C&V pack. It would make more sense to also merge the FI commentary document into the C&V commentary document. | [5 empty] | Actioned - FI commentary document now merged into the C&V commentary document. | Closed - RIGs changed
81 | Annex B: Cost and Volumes guidance |  |  | Consultation | WPD | Heading on P35: "Allocation of Utilisation in year to tax pools for PCFM" should read "Allocation of Utilisation in year to PCFM cost categories". | [5 empty] | Actioned | Closed - RIGs changed
82 | Annex B: Cost and Volumes guidance |  |  | Consultation | WPD | Paragraph 4.91: "...(c) the tax category for the PCFM" should read "(c) the cost category for the PCFM". Similarly, in paragraph 4.85, "The Totex values are also required to be analysed into the tax category for the PCFM." should ready "The Totex values are also required to be analysed into the cost category for the PCFM." | [5 empty] | Actioned - paragraph 4.95* rather than 4.85 | Closed - RIGs changed
83 | Annex B: Cost and Volumes |  |  | Consultation | WPD | Table C15, heading in Y8, Y40, Y58 should read "Total allocation of Utilisation in year to cost categories for PCFM" | [5 empty] | Actioned | Closed - RIGs changed
84 | Financial Issues commentary document |  |  | Consultation | WPD | We note that there is still a requirement to submit tax returns and the SAO signoff. Is this still needed? It is unclear what Ofgem will do with this information. | [5 empty] | The tax returns and the SAO sign off are documents that licensees have to prepare on an annual basis, regardless of whether we request them or not. In light of this, we would like to retain and review a copy of them each year. | Closed - no change
85 | Annex C: Revenue guidance |  |  | Consultation | WPD | First bullet of paragraph 2.14 should refer to : "Costs and Volumes Reporting Pack – I4 – Revenue Pack and Financial Issues Inputs" | [5 empty] | Actioned | Closed - RIGs changed
86 | Check Sheet |  |  | Consultation | WPD | The table references on rows 213, 214 and 215 are incorrect and should be updated. The check in table M17 should be linked into row 215 | [5 empty] | Actioned | Closed - RIGs changed
87 | Annex B: Cost and Volumes commentary (section 2) |  |  | Consultation | WPD | The guidance in the commentary should be clear as to whether the analysis and explanations required for performance against allowance should be for the reporting year only or for the ED1 period to date | [5 empty] | Review 2017/18 | Closed - no change
88 | Worksheet I6 |  |  | Consultation | ENWL |  |  | Worksheet I6 - the 2016 RPI actual figure should also be in cell AJ9. |  |  |  | I6 table updated | Closed - RIGs changed
89 | Appendix 1 - Annex B |  |  | Consultation | ENWL |  |  | Typographical error in the ninth fault scenario in the new appendix …… pre-existence is incorrectly spelt. |  |  |  | Appendix 1 updated | Closed - RIGs changed
90 | Appendix 1 - Annex B |  |  | Consultation | ENWL |  |  | Pole termination fault on page 108 contains a duplicate word “It is decided to to replace the pole” |  |  |  | Appendix 1 updated | Closed - RIGs changed
91 |  |  |  | Consultation | SPEN |  |  |  |  | Steel poles are considered in the RIGS at 6.6/11kV but not at any other voltage. Consequently, this gap can lead to misinterpretation on whether these 132kV steel poles should be categorised as 132kV Poles or as 132kV Towers. |  | Review 2017/18 | Closed - no change
92 |  |  |  | Consultation | SPEN |  |  |  |  | Amend – ‘M16 Forecasts’ to ‘M16 Forecasts C1’ |  | Amended | Closed - RIGs changed
93 |  |  |  | Consultation | SPEN |  |  |  |  | F6 Table no longer exists. Should F6 commentary section now be included under F2, possibly as F2”b”? |  | Commentary updated | Closed - RIGs changed
94 | Appendix 1 - Annex B |  |  | Consultation | SPEN |  |  |  |  | Appendix 1 - C1 - building blocks - Load Related - change to Load Related Expenditure and put NO is ‘Cost variance..’ column |  | Review 2017/18 | Closed - no change
95 | Appendix 1 - Annex B |  |  | Consultation | SPEN |  |  |  |  | Appendix 1- C1 - Cost Matrix: change ‘performance against allowance..’ and ‘cost variance YonY..’ columns from Yes to NO |  | Review 2017/18 | Closed - no change
96 | Appendix 1 - Annex B |  |  | Consultation | SPEN |  |  |  |  | Appendix 1- For the following, change ‘table specific’ column from No to YES (CV5, CV8, CV36, CV37, CV38 and M14) |  | Review 2017/18 | Closed - no change
97 | Appendix 1 - Annex B |  |  | Consultation | SPEN |  |  |  |  | Appendix 1 - For the following, change ‘allocation / estimation..’ column from Yes to NO: (M16 and M17) |  | Review 2017/18 | Closed - no change
98 |  |  |  | Consultation | SPEN |  |  |  |  | 4.9 specify that E5 is TTC and E7 is TTQ (mentioning this as the leading sentences mentions Time to Quote before Time to Connect, so assumption may be made that E5 is TTQ and E7 is TTC |  | Review 2017/18 | Closed - no change

## Annex C
Annex C - Revenue and Financial Issues
No. | Reference (Paragraph number, glossary term or table name) | Change | Reason for change | Raised when | Raised by | WPD response | NPg response | ENWL response | UKPN response | SPEN response | SSEN response | Ofgem response | Status
1 | Financial issues reporting pack | Deleted tabs F1/F1a/F1b/F1c/F3/F4/F5/F7/F9. F2/F6/F8 moved to Cost and Volumes pack. (F2 and F6) combined. Financial Issues reporting pack has been removed. | Deleted tabs - data is picked up elsewhere. F2/F6/F8 fits better in cost and volumes pack. | Pre-consultation | N/A |  | Ok. |  | We agree with the proposed changes to remove the Financial Issues pack, and move F2 and F8 to the Cost & Volumes pack. |  |  | No action required | Closed - RIGs changed
2 | Annex C: Revenue and financial issues | Annex C updated to be called Revenue only | Financial issues removed from annex C | Pre-consultation | N/A |  | This change will need to reflected in Figure 1 of the Overview Document and every Annex document. |  | We agree with the proposed changes to remove the Financial Issues pack, and move F2 and F8 to the Cost & Volumes pack. |  |  | Figure 1 of overview document and every annex updated changes to the Revenue and Financial Issues pack. | Closed - RIGs changed
3 | Annex C: Revenue and financial issues | Text for financial issues removed from annex C and added to annex B (Cost and volumes guidance) | Financial issues removed from annex C | Pre-consultation | N/A |  | Ok. |  | We agree with the proposed changes to remove the Financial Issues pack, and move F2 and F8 to the Cost & Volumes pack. |  |  | No action required | Closed - RIGs changed
4 | Financial Issues Commentary | Financial Issues Commentary updated to reflect changes to Financial Issues Pack. | For consistency. | Pre-consultation | N/A |  | The change to reduce the Financial Issues reporting pack and to amalgamate the remaining tables into the costs and volumes reporting pack means that there is no separate FI reporting pack submission. We suggest the same change should be made to the commentary template to align the commentary with the reporting packs i.e. removing the separate FI commentary and including the relevant commentary sections in the Cost and Volumes commentary. This would remove the need for this commentary pack to be referenced in table 2.1. Also, Figure 1 which is used in this document and every Annex needs amending to show Annex C as Revenue rather Revenue and Financial Issues. |  | We agree with the proposed changes to remove the Financial Issues pack, and move F2 and F8 to the Cost & Volumes pack. |  |  | Figure 1.1 updated to be - Annex C Revenue to be consistent with changes to the RIGs. FI commentary has been merged with C&V commentary - table 2.1 in overview updated. | Closed - RIGs changed
5 | Revenue Reporting pack | RPI added for 2015-16 |  | Pre-consultation |  | Cell G8 in R5 checked to be 259.433 | Ok. |  |  |  |  | No action required | Closed - RIGs changed

## Annex D
Annex D - Secondary Deliverables
No. | Reference (Paragraph number, glossary term or table name) | Change | Reason for Change | Raised when | Raised by | WPD response | NPg response | ENWL response | UKPN response | SPEN response | SSEN response | Ofgem response | Status
1 |  |  |  | Consultation | UKPN |  |  |  | Secondary Deliverables – Microsoft Excel Ofgem template formulae errors: Summary_by_Asset tab Formulae error in columns D, E, F, G, H, I, J, K, L, M, N, O row cell 161, 493. Nature: the SUM formulae is duplicating the values picking up HI1-HI5 grand totals as well as 4x5 matrix values. Asset Categories affected: 20kV CB (GM) Primary, 132kV CB (Gas Insulated Busbars)(ID) (GM) HCT_HV tab Formulae error in columns CS, CZ, DG, DN, DU, EB, EI, EP, EW, FD, FK, GO, GV row cells 557, 563, 569, 575, 581, 587, 593, 599. Nature: the Multiply formulae is picking up an incorrect asset category values from Asset Risk Values tab subsequently incorrect PoF x CoF for this asset category. Asset Categories affected: 20kV CB (GM) Secondary HCT_EHV tab Formulae error in columns ET, EU, EV, EW, EX row cells 457, 463, 469, 475, 481, 487, 493, 499, 705-708, 711-714, 717-720, 723-726, 729-732, 735-738, 741-744, 747-750, 755-758, 761- 764, 767-770, 773-776, 779-782, 785-788, 791-794, 797-800, 805-808, 811-814, 817-820, 823- 826, 829-832, 835-838, 841-844, 847-850, 855-858, 861-864, 867-870, 873-876, 879-882, 885- 888, 891-894, 897-900, 905-908, 911-914, 917-920, 923-926, 929-932, 935-938, 941-944, 947- 950, 955-958, 961-964, 967-970, 973-976, 979-982, 985-988, 991-994, 997-1000, 1005-1008, 1011-1014, 1017-1020, 1023-1026, 1029-1032, 1035-1038, 1041-1044, 1047-1050, 1055-1058, 1061-1064, 1067-1070, 1073-1076, 1079-1082, 1085-1088, 1091-1094, 1097-1100, 1105-1108, 1111-1114, 1117-1120, 1123-1126, 1129-1132, 1135-1138, 1141-1144, 1147-1150, 1155-1158, 1161-1164, 1167-1170, 1173-1176, 1179-1182, 1185-1188, 1191-1194, 1197-1200, 1205-1208, 1211-1214, 1217-1220, 1223-1226, 1229-1232, 1235-1238, 1241-1244, 1247-1250, 1255-1258, 1261-1264, 1267-1270, 1273-1276, 1279-1282, 1285-1288, 1291-1294, 1297-1300, 1305-1308, 1311-1314, 1317-1320, 1323-1326, 1329-1332, 1335-1338, 1341-1344, 1347-1350. Nature: the Multiply formulae is picking up an incorrect asset category values from Asset Risk Values tab subsequently incorrect PoF x CoF for this asset category. Asset Categories affected: 33kV UG Cable (Oil), EHV Sub Cable, 33kV CB (Air Insulated Busbars)(ID) (GM), 33kV CB (Air Insulated Busbars)(OD) (GM), 33kV CB (Gas Insulated Busbars)(ID) (GM), 33kV CB (Gas Insulated Busbars)(OD) (GM), 33kV Switch (GM), 33kV RMU, 66kV CB (Air Insulated Busbars)(ID) (GM), 66kV CB (Air Insulated Busbars)(OD) (GM), 66kV CB (Gas Insulated Busbars)(ID) (GM), 66kV CB (Gas Insulated Busbars)(OD) (GM), 33kV Transformer (GM), 66kV Transformer. Note, in relation to 33kV UG Cable (Oil) asset category formulae error repeated in column EW only. HCT_132kV tab Formulae error in columns CS, CZ, DG, DN, DU, EB, EI, EP, EW, FD, FK, GO, GV row cell 457. Nature: the Multiply formulae is picking up an incorrect asset category values from Asset Risk Values tab subsequently incorrect PoF x CoF for this asset category. Asset Categories affected: 132kV CB (Gas Insulated Busbars)(OD) (GM) |  |  | Formulae updated | Closed - RIGs changed

## Annex E
Annex E - Reinforcement
No. | Reference (Paragraph number, glossary term or table name) | Change | Reason for change | Raised when | Raised by | WPD response | NPg response | ENWL response | UKPN response | SPEN response | SSEN response | Ofgem response | Status
1 | Column P of Summary table | The check using the summary data incorrectly inflates the risk points by multiplying the customer numbers by the number of substations in the LI4 and LI5 bands. This should only consider the number of customers. As an example of the change, the following correction has been applied to cell P9 =IF(F9+H9+J9+(K9*L9*'LI Logic and Risk'!$E$25)+(M9*N9*'LI Logic and Risk'!$E$26)=O9,"Ok","Err") changed to =IF(F9+H9+J9+(L9*'LI Logic and Risk'!$E$25)+(N9*'LI Logic and Risk'!$E$26)=O9,"Ok","Err") | Incorrect formula | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed

## Annex F
Annex F - Interruptions
No. | Reference (Paragraph number, glossary term or table name) | Change | Reason for change | Raised when | Raised by | WPD response | NPg response | ENWL response | UKPN response | SPEN response | SSEN response | Ofgem response | Status
1 | EE Impact Tab | Updated EE impact tab for proposed additional boxes to manage multiple one off events . | Required to calculate multiple one off events | Pre-consultation | N/A | FORMATTING Cells C4, C6:C8, F5:F8, L62:L74, L82:L94, L102:L114 should all be round figures, currently formatted to 2 decimal places. MISSING FORMULA Cell L40 should show the formula =L28 Cell M40 should show the formula =M28 Cell N40 should show the formula =N28 | Ok. |  |  | Support the proposals in full for Annex F |  | Formula updated - Cell L40 should show the formula =L28 Cell M40 should show the formula =M28 Cell N40 should show the formula =N28 | Closed - RIGs changed
2 | QoS Interruptions Stage Data template | One-off exceptional event thresholds on Interruptions tab updated to be in line with licence | Previously showing as 1 decimal place, rather than 2. | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
3 | Guaranteed Standards Reporting Pack - Revenue Link table | Table is bringing in values denoted as £m but values linked are in £. Need to bring in values and then /1000000 to ensure values linked in to the Revenue Return are of the correct order. | Incorrect calculation | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
4 | Tabs from 132kV non-damage onwards. | Formula in rows 10-10000 deleted | To reduce the size of pack. Formula can be copied down by DNO when adding to the list. | Pre-consultation | N/A | OK | Ok. |  | Although we support the underlying aim (file size reduction) we are not able to support this change as it introduces a risk of data errors as checking formulas have been removed. |  |  | No action required | Closed - RIGs changed

## Annex G
Annex G - Connections
No. | Reference (Paragraph number, glossary term or table name) | Change | Reason for change | Raised when | Raised by | WPD response | NPg response | ENWL response | UKPN response | SPEN response | SSEN response | Ofgem response | Status
1 | CR2 | CR2 Metered In-year, new tables added under columns AS:AV and AX:BA to report volumes under Exit points adopted from ICPs and Points of Connection provided to iDNOs. | To include ICPs and IDNOs | Pre-consultation | N/A | OK | Ok. |  | As previously communicated, we believe it is too late a change to implement at this stage. It will require going back retrospectively for data items that our systems have not split out, given there was not the requirement to do so previously. Implementing this change from 2017/18 onwards would make more sense. | We were surprised to see that DNOs are now required to report ICP and IDNO exit points, POC’s and UMS data. We would welcome confirmation of what has prompted this additional requirement. |  | Revert to original format - connections pack will be reviewed at a later date | Closed - no change
2 | CR3 | Columns added under table "Unmetered connection Work by…" | To include 3rd party and DNO | Pre-consultation | N/A | OK | Ok. |  | As previously communicated, we believe it is too late a change to implement at this stage. It will require going back retrospectively for data items that our systems have not split out, given there was not the requirement to do so previously. Implementing this change from 2017/18 onwards would make more sense. | We were surprised to see that DNOs are now required to report ICP and IDNO exit points, POC’s and UMS data. We would welcome confirmation of what has prompted this additional requirement. |  | Revert to original format - connections pack will be reviewed at a later date | Closed - no change
3 | CR3- Unmetered in year | CR3 Unmetered In-year formulae updated under Connection Sole Use Related column to account for changes above. | Consistency | Pre-consultation | N/A | OK | Ok. | We would not expect to have any direct costs or have visibility of any unmetered IDNO connections. The creation of these new columns is therefore superfluous | As previously communicated, we believe it is too late a change to implement at this stage. It will require going back retrospectively for data items that our systems have not split out, given there was not the requirement to do so previously. Implementing this change from 2017/18 onwards would make more sense. |  |  | Revert to original format - connections pack will be reviewed at a later date | Closed - no change
4 | CR1- In year summary | U8: W11 updated to keep sign convention throughout. In table CR3 margin should be income + costs | Consistency | Pre-consultation | N/A | OK | Ok. |  | As previously communicated, we believe it is too late a change to implement at this stage. It will require going back retrospectively for data items that our systems have not split out, given there was not the requirement to do so previously. Implementing this change from 2017/18 onwards would make more sense. | The entries on the CR2 Tables flow through to the auto-populated CR1, however, there is an error on M24 CR1 whereby it pulled from AI37 when is should be AI50. |  | Change made | Closed - RIGs changed
5 | CR2- Metered in year | The formulas in cells AC27 to AE27 and AC50 to AE50 appear incorrect as they are summing the percentages in the rows above rather than calculating percentages of the totals. | Incorrect formula | Pre-consultation | N/A | OK | Ok. |  |  | The entries on the CR2 Tables flow through to the auto-populated CR1, however, there is an error on M24 CR1 whereby it pulled from AI37 when is should be AI50. |  | Cell M24 in CR1 updated to pull data from AI50 cell in CR2 tab. | Closed - RIGs changed
6 | CR5- Metered Connections completed | Removed merged cells from header rows. |  | Pre-consultation | N/A | OK | Ok. | we note the minor formatting change on the table to remove a number of merged calls in the header rows to allow Ofgem to analyse the data. Unfortunately, this has not been done in a way which will to allow this to work. A number of the columns have merged cells for rows 7 & 8. Columns B-R, AG-AP, AW-BG all have this issue too. |  |  |  | Cells are not merged in these columns. | Closed - RIGs changed
7 | CR7- Annual Quotations issued | Removed merged cells from header rows. |  | Pre-consultation | N/A | OK | Ok. | This is a repeat of the issue described in CR5 |  |  |  | Cells are not merged in these columns. | Closed - RIGs changed
8 | CR11- Section 22 connections, update to annex H. | It would be helpful if the guidance made clearer if these are a subset of connections made and reported in table CR2 or additional. | Clarify whether Section 22 connections are to be included in table CR2 or not. | Pre-consultation | N/A | OK | Ok. |  |  |  |  | Change made | Closed - RIGs changed
9 | CR12- C&V cost summary | Row 24 gives an error in all the checks since there is no limit on the variance, even if the differences are very minor - tolerance updated to £1000. | To increase the tolerance | Pre-consultation | N/A |  | Ok. |  |  |  |  | Change made | Closed - RIGs changed
10 | CR13- TTQ & TTC | It would be more logical and also consistent with the Revenue Link Table at the start of the pack if Time to Quote was reported before Time to Connect. Amended table layout so that Time to Quote is reported before Time to Connect. | Consistency | Pre-consultation | N/A |  | Ok. |  |  | The whole table is in bright yellow. D5 to G8 should be a paler yellow as these are input fields and B5 to B8 should not be white. |  | Table shown as bright yellow to reflect change. Boxes changed to light yellow. | Closed - RIGs changed
11 | CR13- TTQ & TTC | Standardise reporting formats to two decimal places of days. | Consistency | Pre-consultation | N/A |  | Ok. |  |  | The whole table is in bright yellow. D5 to G8 should be a paler yellow as these are input fields and B5 to B8 should not be white. |  | Table shown as bright yellow to reflect change. Boxes changed to light yellow. | Closed - RIGs changed
12 | CR2 - Metered in year |  |  | Consultation | ENWL |  |  | CR2- Metered in year, update to annex H (noted in our earlier responses) - On reflection there may be benefit to identify any such reinforcement as a separate column. This would help the table reconcile to the C tables and so long as it is excluded from the calculation of indicative margin would still address our original issue. |  |  |  | Connections pack will be reviewed at a later date. | Open - future review
13 | CR5 and CR6 |  |  | Consultation | SPEN |  |  |  |  | The guidance document states that entries in CR5 and CR6 must be reported in £’s and pence and the CR4 table should be reported on £m’s to 2 decimal places. However, this does not translate to the CR4 as it pulls through in whole £’s. |  | Connections pack will be reviewed at a later date. | Open - future review

## Annex H
Annex H - Customer service
No. | Reference (Paragraph number, glossary term or table name) | Change | Reason for change | Raised when | Raised by | WPD response | NPg response | ENWL response | UKPN response | SPEN response | SSEN response | Ofgem response | Status
1 | Annex H - 3.7 and glossary | Changes to be made to customer service RIGs in respect of the SEN. | Update for Single Emergency Number | Pre-consultation | N/A | OK | The change fails to set out what happens if a customer calls one DNO (i.e. licensee) in a group, and that DNO handles the call on behalf of the other licensee. This could lead to genuine contacts being deleted. Also, given that 'wrong numbers' are covered in para 3.10, this change appears un-necessary. NPg suggests not making the change |  |  |  |  | No action required | Closed - RIGs changed
2 | Annex H - 3.8 | Text added - "Each DNO must submit the specified customer data to an independent third party on a weekly basis. For this purpose the ‘week’ begins on a Monday, and data should be submitted to the independent third party by 4pm on Tuesday following the week concerned. Where Bank Holidays take place in the week of submission, the submission deadline of Tuesday is extended by one day for each Bank Holiday" | To account for bank holidays | Pre-consultation | N/A | OK | We don't believe that this works as intended as it grants extra days when none are needed, and this may cause problems for the survey company. For example, if a bank holiday falls on a Friday 10th, we would gain an extra day for submission in that same week, i.e. the deadline of Tuesday 7th would be extended to Wednesday 8th. The intended effect can be achieved by a small edit to the original text. No additional sentence is necessary. ‘data should be submitted to the independent third party by 4pm on Tuesday the second working day following the week concerned’ |  | We note that the wording we previously provided does not appropriately cater for bank holidays which do not fall on a Monday. We propose the following wording which takes these circumstances into account: "For each Bank Holiday which takes place on the normal day of submission or during the six calendar days prior to the normal day of submission, the normal submission deadline of Tuesday is extended by one day for each Bank Holiday". |  |  | Text updated to be : 'data should be submitted to the independent third party by 4pm the second working day following the week concerned' | Closed - RIGs changed
3 | RIGS document: Table 3.1 - Interruption - planned | Footnote added to table 3.1. | For clarification on notification. | Pre-consultation | N/A | OK | This footnote includes some extraneous detail that we don't believe is 100% correct (e.g. the customer might not be entitled to a GSOP payment if an exemption applies). Also, use of ‘may’ leaves it open to a DNO to exercise discretion. Suggested changes below. If a customer has not received prior notification of a planned interruption then the customer should be entitled to a GSOP payment and should not be included in the "Interruptions - planned" category since they have not had an interaction with the DNO. However the customer may should be included within the "Interruptions -unplanned" category if they have called regarding the up to report an unplanned interruption. |  |  |  |  | Footnote removed - to be discussed further at QoS working group. | Open - future review
4 | RIGS document: Table 3.1 | Table 3.1 updated | For clarification | Pre-consultation | N/A | OK | Ok. |  | We are unclear as to why this is being introduced. We previously sought clarity in our response to the informal consultation but the justification for the change in this consultation was “for clarification”. This does not give enough detail to allow us to understand the reasons behind it and until we have this we are unable to support it. | In Table 3.1, we unfortunately do not agree with the addition of “or enquire about” within the ‘Interruption unplanned agent’ category. This additional wording changes the definition and has the potential to include jobs which are not currently included within the incentive. As the sample size is pertinent to this incentive, we need to ensure that it is consistent for all DNO’s. We suggest that this remains as it is currently in version 2 of the RIGS. |  | Change to table 3.1 removed - to be discussed further at QoS working group. | Open - future review

## Annex J
Annex J - Environment and Innovation
No. | Reference (Paragraph number, glossary term or table name) | Change | Reason for change | Raised when | Raised by | WPD response | NPg response | ENWL response | UKPN response | SPEN response | SSEN response | Ofgem response | Status
1 | Annex J : paragraph 4.42 and 4.43 | Paragraph 4.42 and 4.43 added for clarity for G83. | Clarification | Pre-consultation | N/A | The second bullet of 4.42 specifies one of the conditions for reporting renewable DG not connected under Engineering Recommendation G83 to be that the DG is ‘subject to use of system charges in the reporting year’. This means that it will only be counted if this condition is met. Paragraph 4.43 requires the volumes to be split between those where DG is ‘subject to use of system charges in the reporting year’ and those that are not. Because bullet 2 of 4.42 requires the DG to be ‘subject to use of system charges in the reporting year’ to be counted, then all the DG is ‘subject to use of system charges in the reporting year’. The requirement to split the data in 4.43 is unnecessary, because there is nothing other than DG ‘subject to use of system charges in the reporting year’ being reported. In addition to the above, there are other minor amendments required for clarity. We propose that the paragraphs should be amended as follows: 4.42. For the recording of renewable DG not connected under Engineering Recommendation G83, we would expect the DG must: • the DG to be “still energised in the reporting year”; • the DG was either “be subject to use of system charges in the reporting year”; and • the capacity is defined as follows: ,“the highest active electrical power that could be generated (or the relevant incremental change of this amount in cases of the expansion of existing DG plant) by a DG for the reporting year, according to the connection and use of system agreement(s) in force on 31 March of that relevant year or notification in cases of generation covered by Engineering Recommendation G83/1”. 4.42.4.43. For the recording of renewable DG not connected under Engineering Recommendation G83, where the DNO is able to split the number of those that are subject to ‘use of system charges in the reporting year’ against those that are not, it should do so within its RIGs commentary to Annex J. | The definition of capacity in para. 4.45 seems to contradict the definition in para 4.42. The drafting may need revisiting - the 3rd sub-bullet of 4.42 could be deleted, so there is only one definition of capacity. |  |  |  |  | Text changes to below: 4.42. For the recording of renewable DG not connected under Engineering Recommendation G83, we would expect: • the DG to be “still energised in the reporting year”; or • the DG was either “subject to use of system charges in the reporting year” 4.43. For the recording of renewable DG not connected under Engineering Recommendation G83, where the DNO is able to split the number of those that are subject to ‘use of system charges in the reporting year’ against those that are not, it should do so within its RIGs commentary to Annex J. | Closed - RIGs changed
2 | Annex J: paragraph 2.10. | Terms updated | Clarification | Pre-consultation | N/A | INCORRECT AMENDMENT MADE. Amendment 2 removes the term ‘Undergrounding for Visual Amenity’ and replaces it with ‘Non-Undergrounding Visual Amenity Schemes’. Non-Undergrounding Visual Amenity Schemes is already included in the list as bullet 8, so this change leads to a duplication. The deleted 'Undergrounding for Visual Amenity' has a clear definition within Annex A (Glossary) which describes it as undergrounding activity in non-designated areas and therefore this needs to be retained because it is different to the Visual Amenity reported in table E1. The proposed changes should be removed – the existing text is correct | Ok. |  |  |  |  | Bullet list restored to original | Closed - no change
3 | Annex J: paragraph 2.11. | Paragraph 2.11 updated for Non-Undergrounding Activity. | Clarification | Pre-consultation | N/A | INCORRECT AMENDMENT MADE. Amendment 3 attempts to provide a definition for Non-Undergrounding Visual Amenity Schemes. The new wording confuses Non-Undergrounding activity with Undergrounding activity where it states that “This activity is defined as schemes undertaken to reduce the visual impact on the landscape of overhead lines.” Non-undergrounding is not associated with overhead lines (a typical scheme could be making a substation look like a local redevelopment). There is no requirement for the new text because the definitions of Non-Undergrounding Visual Amenity Schemes and Undergrounding for Visual Amenity are adequate within Annex A. The changes should be removed. | Ok. |  |  |  |  | Changed back to original definition. | Closed - no change
4 | Annex J: paragraph 2.31. | Paragraph 2.31 updated. | Clarification | Pre-consultation | N/A | OK | Given the changes set out change the current approach, will Ofgem require DNOs to restate their reported data for 2014/15? |  |  |  |  | Instruction provided in Direction | Closed - RIGs changed
5 | Annex J: paragraph 2.43 | Paragraph updated for clarity. | Clarification | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed
6 | Annex J: paragraph 4.45 | Paragraph updated. | Clarification | Pre-consultation | N/A | Also need to delete the word 'size' following the words that have been deleted | See comment to item 1. |  | We source data on small scale generation from the Feed in Tariff database. We do this because we have found that we are not always informed of a generation connection under G83. However, the fields in this database are installed capacity and declared net capacity. We propose that for the “maximum export allowed” field in the RIGs, where the source is the Feed in Tariff database, DNOs should be allowed to use the total capacity field. To enable this, paragraph 4.45 of Annex J should be amended as the “not installed capacity” in brackets which has been added seems to prevent this. |  |  | Word 'size' and 'not installed capacity' removed from paragraph. | Closed - RIGs changed
7 | Annex J : paragraph 4.46 | Detail on reporting for Electric Vehicles added. | Missing from annex | Pre-consultation | N/A | OK | Ok. |  |  |  |  | No action required | Closed - RIGs changed