## Index
Chapter | Chapter name | Tab contents | Tables/ figures (from 2015-16 annual report)
2 | Expenditure, revenue, consumer bills and consumer bills and company returns | Totex | Table 2.1
|  | Forecast totex | Table 2.2, figure 2.1
|  | Non-controllable costs | Table 2.3
|  | Allowed Revenue | Table 2.4
|  | Customer bill impact | Figure 2.2, Table 2.5
|  | RoRE data | Figure 2.3
|  | RoRE chart | -
3 | Outputs | Safety | Table 3.3, 3.4, 3.5, 3.6, 3.7
|  | Reliability | Table 3.8, 3.9, 3.10, 3.11, 3.12, 3.13
|  | Customer Service | Table 3.14, 3.15, 3.16, 3.17
|  | Connections | Table 3.18
|  | Social obligations | Table 3.19
|  | Environment | Table 3.20, 3.21, 3.22
4 | Innovation | NIA | Table 4.1
5 | Analysis of expenditure | Analysis of expenditure | Figure 5.1, 5.2
Appendicies | Appendicies | Appendix 1 | Table A1.1, A1.2, figure A1.3
|  | Appendix 2 | Table A2.1, A2.2, A2.3, A2.4, A2.5
|  | Appendix 3 | Table A3.1, A3.2, A3.3, A3.4
|  | Appendix 5 | Table A5.1
|  | Appendix 6 | Table A6.1, A6.2

## Totex
Table 2.1
Pre-tax totex allowed vs actual in 2015-16
In Price Control (09/10) Price Base
NGGD
|  | East | London | North West | West Midlands
| Total allowed expenditure | 263 | 252 | 197 | 155
| Actual expenditure | 247 | 198 | 188 | 143
| Overspend (underspend) | -16 | -54 | -9 | -11
| Sharing Factor | 36.96% | 36.96% | 36.96% | 36.96%
| Allowed expenditure after sharing | 257 | 232 | 193 | 151
|  | NGN | SGN |  | WWU
|  | Northern | Scotland | Southern | Wales & West
| Total allowed expenditure | 217 | 163 | 338 | 212
| Actual expenditure | 189 | 137 | 279 | 174
| Overspend (underspend) | -28 | -26 | -58 | -38
| Sharing Factor | 36.02% | 36.27% | 36.27% | 36.83%
| Allowed expenditure after sharing | 207 | 154 | 316 | 198
In Report (15/16) Price Base
NGGD
|  | East | London | North West | West Midlands
| Total allowed expenditure | 316 | 303 | 237 | 186
| Actual expenditure | 297 | 238 | 226 | 172
| Overspend (underspend) | -19 | -65 | -11 | -14
| Sharing Factor | 36.96% | 36.96% | 36.96% | 36.96%
| Allowed expenditure after sharing | 309 | 279 | 233 | 181
|  | NGN | SGN |  | WWU
|  | Northern | Scotland | Southern | Wales & West
| Total allowed expenditure | 261 | 196 | 406 | 254
| Actual expenditure | 227 | 165 | 336 | 209
| Overspend (underspend) | -34 | -31 | -70 | -45
| Sharing Factor | 36.02% | 36.27% | 36.27% | 36.83%
| Allowed expenditure after sharing | 249 | 185 | 380 | 238

## Forecast totex
Table 2.2
GDNs' Totex - allowed vs actual three year cumulative and RIIO-GD1 forecast
GDN |  | 3 year cumulative |  |  |  | RIIO-GD1 Forecast
|  | Adj'd Allowance1 | Actual | Variance |  | Adj'd Allowance1 | Actual (forecast) | Variance
|  | £m | £m | £m | % | £m | £m | £m | %
NGGD | EoE | 970.6313 | 912.5142 | -58.1171 | -5.988% | 2557.112 | 2463.7415 | -93.3705 | -3.651%
| Lon | 871.6988 | 707.4624 | -164.2364 | -18.84% | 2364.9962 | 2071.3662 | -293.63 | -12.42%
| NW | 735.2996 | 712.7754 | -22.5242 | -3.063% | 1920.568 | 1769.3712 | -151.1969 | -7.873%
| WM | 567.6128 | 494.7007 | -72.9122 | -12.85% | 1491.9389 | 1308.9729 | -182.966 | -12.26%
NGN | NGN | 770.1568 | 672.5606 | -97.5962 | -12.67% | 2001.7211 | 1746.2683 | -255.4528 | -12.76%
SGN | Sc | 608.8866 | 483.4044 | -125.4821 | -20.61% | 1629.2602 | 1332.6673 | -296.5929 | -18.2%
| So | 1254.497 | 996.91 | -257.5869 | -20.53% | 3330.6438 | 2785.5816 | -545.0623 | -16.37%
WWU | WWU | 775.6575 | 644.6909 | -130.9667 | -16.88% | 2030.7986 | 1718.5892 | -312.2094 | -15.37%
Industry |  | 6554.4404 | 5625.0186 | -929.4218 | -14.18% | 17327.0389 | 15196.5581 | -2130.4807 | -12.3%
1 Adjusted allowance - includes adjustment for Tier 2A and additional allowances for Physical Site Security, Streetworks (incl. forecasted), fuel poor and Xoserve. These costs do not include PCFM policy adjustments.
Figure 2.1
Industry controllable totex forecasts, adjusted allowances and actuals trends

## Non controllable costs
Table 2.3
Non-controllable costs
| 2015-16 Year |  |  |  | Three-year cumulative |  |  |  | RIIO-GD1 Forecast
| Allowance | Actual | Variance |  | Allowance | Actual | Variance |  | Allowance | Actual | Variance
| £m | £m | £m | % | £m | £m | £m | % | £m | £m | £m | %
Total | 644.0849 | 671.5599 | 27.4751 | 4.266% | 1934.7233 | 2006.4709 | 71.7477 | 3.708% | 5130.5916 | 5504.2877 | 373.6961 | 7.284%
of which
Licence fee/network rates/other1 | 315.1055 | 388.1193 | 73.0138 | 23.17% | 944.9641 | 1139.9702 | 195.0061 | 20.64% | 2520.4914 | 3167.4477 | 646.9563 | 25.67%
NTS exit costs | 202.857 | 186.9709 | -15.8861 | -7.831% | 608.0371 | 565.7398 | -42.2973 | -6.956% | 1622.3219 | 1576.2305 | -46.0915 | -2.841%
Shrinkage | 83.5568 | 36.6275 | -46.9293 | -56.16% | 254.0253 | 155.6097 | -98.4156 | -38.74% | 647.2532 | 318.2474 | -329.0059 | -50.83%
Pensions | 42.5656 | 59.8423 | 17.2767 | 40.59% | 127.6969 | 145.1512 | 17.4544 | 13.67% | 340.525 | 442.3621 | 101.8371 | 29.91%
1 Costs split on average: Licence Fee 4%, Network business rates 92% and Other costs 4%

## Allowed Revenue
Table 2.4:
Allowed Revenue
| NGGD |  |  |  | NGN | SGN |  | WWU
| EoE | Lon | NW | WM | NGN | Sc | So | WWU
Allowed Revenue (exc. Revenue collection correction) | EoE: £m 2009/10 Prices
2013-14 | 527 | 354 | 382 | 282 | 343 | 269 | 615 | 346
2014-15 | 506 | 345 | 363 | 275 | 342 | 262 | 592 | 342
2015-16 | 510 | 371 | 365 | 275 | 346 | 247 | 588 | 325
2016-17 | 486 | 353 | 365 | 262 | 332 | 270 | 595 | 324
2017-18 | 487 | 333 | 346 | 256 | 317 | 257 | 575 | 323
2017-18 Allowed Revenue | EoE: £m nominal prices
Opening Base Revenue | 634 | 450 | 462 | 345 | 420 | 344 | 774 | 442
MOD | -16 | -26 | -20 | -17 | -14 | -12 | -30 | -22
Non Controllable Costs | 6 | 3 | 4 | 3 | 3 | 0 | -2 | 3
Capacity & Shrinkage Rollers | -2 | 1 | -3 | -3 | -7 | -3 | -7 | -10
Incentive Payments | 6 | 3 | 4 | 3 | 6 | 2 | 8 | 5
Network Innovation Allowance | 4 | 3 | 3 | 2 | 3 | 2 | 4 | 2
Correction Factors
Revenue collection | 0 | -3 | -8 | 1 | 7 | -9 | -9 | -6
Inflation forecast true-up | -14 | -10 | -10 | -8 | -9 | -6 | -16 | -9
Corrected Allowed Revenue | 620 | 420 | 433 | 327 | 410 | 317 | 722 | 404
Network Innovation Competition | 2.9 | 2.9 | 2.9 | 2.9 | - | - | - | -

## Customer Bill Impact
Table 2.5
Regional estimates of typical GB consumer cost to meet allowed revenue | [6 empty] | Figure 2.2: Estimate of typical 12-month fixed price contract billing to cover the allowed revenue payments
£ nominal prices per domestic customer
12 Months beginning: |  | 2013-04-01 | 2014-04-01 | 2015-04-01 | 2016-04-01 | 2017-04-01
GB customer count weighted average: |  | 115 | 115 | 119 | 121 | 118
Region | Licensee
East of England | EoE | 106.5977 | 105.6562 | 109.6903 | 106.3166 | 109.6122
London | Lon | 123.1097 | 123.3511 | 134.8575 | 132.7961 | 127.023 |  | Range of bills for a typical GB domestic consumer in all regions
North West | NW | 112.7501 | 109.5084 | 119.5882 | 121.2342 | 114.4056
West Midlands | WM | 111.6087 | 114.7558 | 113.57 | 114.1097 | 114.9974
North | NGN | 106.1907 | 111.0428 | 115.2652 | 117.332 | 114.6264
Scotland | Sc | 107.1598 | 111.1153 | 111.7321 | 123.5337 | 116.844 |  | Bill for a typical GB domestic cosumer; consumer count weighted average of regional tariffs
Southern | So | 127.4254 | 124.0699 | 125.4293 | 128.8332 | 125.8994
Wales and West | WWU | 118.7876 | 121.3879 | 120.5394 | 125.8771 | 123.1718
Annualised bill estimates as of each April for consumption volume and customer count views as per the relevant version of the Ofgem Supplier Cost Index

## RoRE chart
Current View of RoRE
Opening Position
IQI Ex-ante Reward/Penalty
Cost of Equity = 6.7%
[9 empty] | Performance | +ive | -ive
Tax Allowance Retained Within Deadband
Payments Under Guaranteed Standards
Discretionary Reward Scheme
Environmental Emissions Incentive
Exit Capacity Incentive
Shrinkage Roller Incentive
Broad Measure of Customer Satisfaction
Totex Incentive Mechanism
Fines & Redress Payments
RoRE | 8.941% | 10.37% | 9.756% | 10.65% | 11.23% | 11.98% | 11.45% | 11.31%
Reg. Equity | 854.0285 | 592.5072 | 595.047 | 449.8148 | 558.1881 | 449.8305 | 1000.9215 | 565.7427 | Measured in £m 2009/10 Prices
Group RoRE | 9.784% |  |  |  | 11.23% | 11.61% |  | 11.31% | Using a RAV Weighted Average

## RoRE
RoRE breakdown
| East | Lon | NW | WM | NGN | Sc | So | WWU
Cost of Equity | 6.7% | 6.7% | 6.7% | 6.7% | 6.7% | 6.7% | 6.7% | 6.7%
TIM Retained Proportion | 1.053% | 2.91% | 2.119% | 3.115% | 3.051% | 4.385% | 3.631% | 3.632%
IQI Additional Income | 0.1275% | 0.1703% | 0.138% | 0.1435% | 0.4422% | 0.3641% | 0.3338% | 0.1927%
Exit Capacity Incentive | 0.5054% | 0.3107% | 0.285% | 0.2266% | 0.1447% | 0.002387% | 0.1281% | 0.05174%
Broad Measure of Customer Satisfaction | 0.1957% | 0.06768% | 0.236% | 0.1533% | 0.3689% | 0.3159% | 0.3231% | 0.3681%
Shrinkage Roller Incentive | 0.05393% | 0.04867% | 0.03511% | 0.04365% | 0.07622% | 0.01787% | 0.04369% | 0.04916%
Environmental Emmissions Incentive | 0.2279% | 0.2012% | 0.1554% | 0.2014% | 0.3244% | 0.07852% | 0.1797% | 0.1876%
Discretionary Reward Scheme | 0.004011% | 0.003232% | 0.003848% | 0.003712% | 0.02401% | 0.008031% | 0.008155% | 0.02977%
Retained Tax Under Tax Trigger Deadband | 0.1201% | 0.1223% | 0.1258% | 0.1217% | 0.12% | 0.1183% | 0.1227% | 0.1213%
Fines & Redress Payments | -0.009233% | -0.0141% | -0.0134% | -0.01776% | 0% | 0% | 0% | 0%
Guaranteed Standards Payments | -0.03738% | -0.1538% | -0.02841% | -0.03634% | -0.01696% | -0.008369% | -0.02557% | -0.0182%
RoRE Total | 8.941% | 10.37% | 9.756% | 10.65% | 11.23% | 11.98% | 11.45% | 11.31%
Regulatory Equity | 854.0285 | 592.5072 | 595.047 | 449.8148 | 558.1881 | 449.8305 | 1000.9215 | 565.7427

## Outputs -Safety
Table 3.3
Iron mains risk reduction 2015-2016
Company | GDN | Risk reduction 8 year commitment | Proportionate annual risk reduction for one year | 3 Year target risk reduction | Actual risk reduction achieved |  | Risk removal outperformance |  | % of the 8 year commitment removed to date
[5 empty] | 2016 | 3-year total | 2016 | 3-year total
Incidents/year x 106
NGGD | EoE | 192567 | 24070.875 | 72212.625 | 34912.88 | 114268.88 | 45% | 58% | 59.34%
| Lon | 102281 | 12785.125 | 38355.375 | 13663.95 | 40025.95 | 7% | 4% | 39.13%
| NW | 154428 | 19303.5 | 57910.5 | 30640.0552 | 100978.0552 | 59% | 74% | 65.39%
| WM | 131394 | 16424.25 | 49272.75 | 24857.3311 | 63490.3311 | 51% | 29% | 48.32%
NGN | NGN | 111191 | 13898.875 | 41696.625 | 29893.2497 | 114225.4348 | 115% | 174% | 102.7%
SGN | Sc | 44277 | 5534.625 | 16603.875 | 12677.27 | 48001.3693 | 129% | 189% | 108.4%
| So | 137287 | 17160.875 | 51482.625 | 24211 | 104362.8055 | 41% | 103% | 76.02%
WWU | WWU | 98727 | 12340.875 | 37022.625 | 16723.5644 | 49032 | 36% | 78% | 49.66%
Table 3.4
Percentage of gas emergencies attended within standard
GDN |  | Percentage of uncontrolled gas emergencies attended within the one hour standard |  |  | Percentage of controlled gas emergencies attended within the two hour standard
|  | 2014 | 2015 | 2016 | 2014 | 2015 | 2016
NGGD | EoE | 97.91% | 97.6% | 97.94% | 98.99% | 98.47% | 98.77%
| Lon | 97.72% | 97.39% | 98.04% | 98.53% | 97.73% | 98.64%
| NW | 98.52% | 98.2% | 98.52% | 99.23% | 98.93% | 99.14%
| WM | 97.91% | 97.52% | 98.63% | 98.83% | 98.29% | 99.1%
NGN | NGN | 99.85% | 99.85% | 99.76% | 99.97% | 99.99% | 99.96%
SGN | Sc | 99.02% | 98.75% | 98.65% | 99.8% | 99.59% | 99.61%
| So | 98.52% | 98.5% | 98.27% | 99.51% | 99.37% | 99.2%
WWU | WWU | 98.33% | 98.48% | 98.59% | 99.49% | 99.6% | 99.6%
Table 3.5
Gas escapes prevented within 12 hours
Company | GDN | 2013-14 |  | 2014-15 |  | 2015-16
|  | Target | Actual | Target | Actual | Target | Actual
NGGD | EoE | 42% | 50% | 42% | 54% | 42.16% | 51.8%
| Lon | 43% | 44% | 43% | 48% | 42.9% | 52.2%
| NW | 34% | 45% | 34% | 48% | 34.4% | 51.36%
| WM | 36% | 43% | 36% | 50% | 36.4% | 51.15%
NGN | NGN | 60% | 62.3% | 60% | 62.9% | 57% | 64.44%
SGN | Sc | 60% | 72.5% | 60% | 69.18% | 60% | 71.58%
| So | 60% | 63.81% | 60% | 62.55% | 60% | 63.5%
WWU | WWU | 40% | 46.65% | 40% | 49.47% | 40% | 52.6%
Table 3.6
Repair risk performance
Company | GDN | Output requirement | 2014-15 |  | 2015-16
|  |  | Actual | Variance | Actual | Variance
NGGD | EoE | 5.1663 | 4.9941 | 3.333% | 4.677 | 9.471%
| Lon | 4.6214 | 8.9463 | -93.59% | 4.3225 | 6.468%
| NW | 4.9117 | 7.7688 | -58.17% | 4.7127 | 4.053%
| WM | 2.5023 | 3.3274 | -32.97% | 2.3101 | 7.679%
NGN | NGN | 34.4959 | 24.8 | 28.11% | 18.6014 | 46.08%
SGN | Sc | 2.46 | 2.0132 | 18.16% | 1.6205 | 34.13%
| So | 17.69 | 10.0256 | 43.33% | 11.0816 | 37.36%
WWU | WWU | 24.2 | 18.6322 | 23.01% | 11.57 | 52.19%
Table 3.7
Cumulative % off sub-deduct networks taken off risk (actual and forecast)
GDN | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
EoE | 50% | 78% | 83% | 105% | 105% | 105% | 105% | 105%
Lon | 52.3% | 74.9% | 80.9% | 86.9% | 100.9% | 100.9% | 100.9% | 100.9%
NW | 43.75% | 54.17% | 67.17% | 85.17% | 102.2% | 102.2% | 102.2% | 102.2%
WM | 41.59% | 53.86% | 62.86% | 81.86% | 99.86% | 99.86% | 99.86% | 99.86%
NGN | 6.716% | 64.93% | 90.11% | 95% | 97% | 98% | 99% | 100%
Sc | 34.78% | 52.17% | 60.87% | 89.87% | 99.87% | 99.87% | 99.87% | 99.87%
So | 41.5% | 70.75% | 82.31% | 92.31% | 100% | 100% | 100% | 100%
WWU | 8.28% | 9.554% | 48.41% | 75% | 90% | 100% | 100% | 100%

## Outputs- Interruptions
Table 3.8
Number of planned interruptions
Company | GDN | 2015-16 |  |  | RIIO-GD1
|  | Current target | Actual | Variance | Forecast
NGGD | EoE | 82187.9656 | 76135 | 7.365% | 588683.0103
| Lon | 51195.1815 | 58032 | -13.35% | 479558.8485
| NW | 68966.8193 | 67426 | 2.234% | 475571.5455
| WM | 50131.784 | 61702 | -23.08% | 377255.8677
NGN | NGN | 50961.2335 | 58925 | -15.63% | 474000.44
SGN | Sc | 35291.8928 | 31459 | 10.86% | 237074
| So | 85815.732 | 76738 | 10.58% | 688815
WWU | WWU | 56404.4169 | 45173 | 19.91% | 402690
Industry |  | 480955.0257 | 475590 | 1.115% | 3723648.7121
Table 3.9
Duration of planned interruptions (millions of minutes)
Company | GDN | 2015-16 |  |  | RIIO-GD1
|  | Current target | Actual | Variance | Forecast
NGGD | EoE | 38.4032 | 26.6024 | 30.73% | 215.7146
| Lon | 31.9594 | 21.5698 | 32.51% | 194.4076
| NW | 35.7748 | 22.5693 | 36.91% | 172.4545
| WM | 24.9774 | 22.228 | 11.01% | 154.6451
NGN | NGN | 27.3075 | 13.6582 | 49.98% | 139.2334
SGN | Sc | 12.2378 | 11.6741 | 4.606% | 89.9
| So | 30.6482 | 26.5754 | 13.29% | 254.4
WWU | WWU | 11.5065 | 10.3758 | 9.827% | 88.941
Industry |  | 212.8149 | 155.253 | 27.05% | 1309.6962
Table 3.10
Number of unplanned interruptions
Company | GDN | 2015-16 |  |  | RIIO-GD1
|  | Current target | Actual | Variance | Forecast
NGGD | EoE | 13365.2673 | 13451.38 | -0.6443% | 97766.94
| Lon | 11075.6286 | 12660.62 | -14.31% | 97281.5771
| NW | 12698.8754 | 12887 | -1.481% | 97734.115
| WM | 8821.8193 | 8338 | 5.484% | 62662
NGN | NGN | 8380.0622 | 14289 | -70.51% | 112354
SGN | Sc | 2152.1848 | 5028 | -133.6% | 17216
| So | 8677.0975 | 17652 | -103.4% | 66997
WWU | WWU | 11271.1528 | 10768 | 4.464% | 78656
Industry |  | 76442.088 | 95074 | -24.37% | 630667.6322
Table 3.11
Duration of unplanned interruptions (millions of minutes)
Company | GDN | 2015-16 |  |  | RIIO-GD1
|  | Current target | Actual | Variance | Forecast
NGGD | EoE | 6.2003 | 10.398 | -67.7% | 73.3465
| Lon | 13.82 | 68.5882 | -396.3% | 412.552
| NW | 9.7246 | 7.818 | 19.61% | 60.0391
| WM | 5.9828 | 5.2156 | 12.82% | 47.2604
NGN | NGN | 7.8375 | 11.8373 | -51.03% | 59.6465
SGN | Sc | 15.0707 | 3.61 | 76.05% | 31.7
| So | 22.644 | 20.4095 | 9.868% | 166.3
WWU | WWU | 5.6356 | 4.8344 | 14.22% | 43.6248
Industry |  | 86.9155 | 132.711 | -52.69% | 894.4693
Table 3.12
Position at start of RIIO-GD1 (number of Installations)
| EoE | Lon | NW | WM | NGGD | NGN | Sc | So | WWU
</= 50% | No individual GDN commitments for NGGD |  |  |  | 182 | 54 | 96 | 88 | 167
>50% to </=70% | NGGD: 142; NGN: 55; Sc: 29; So: 49; WWU: 97
>70% to </=80% | NGGD: 81; NGN: 29; Sc: 5; So: 15; WWU: 30
>80% to </=100% | NGGD: 164; NGN: 40; Sc: 14; So: 11; WWU: 52
>100% | NGGD: 41; NGN: 13; Sc: 3
Total no. of sites | NGGD: 610; NGN: 191; Sc: 147; So: 163; WWU: 346
Table 3.13
Position at end of 2015-2016 (number of installations)
| EoE | Lon | NW | WM | NGGD | NGN | Sc | So | WWU
</= 50% | 106 | 29 | 53 | 50 | 238 | 64 | 94 | 120 | 161
>50% to </=70% | 89 | 27 | 38 | 35 | 189 | 59 | 31 | 24 | 76
>70% to </=80% | 41 | 8 | 14 | 14 | 77 | 22 | 7 | 15 | 41
>80% to </=100% | 31 | 12 | 14 | 17 | 74 | 41 | 12 | 5 | 55
>100% | 10 | 7 | 9 | 8 | 34 | 8 | 4 | 0 | 1
Total no. of sites | 277 | 83 | 128 | 124 | 612 | 194 | 148 | 164 | 334

## Outputs- Customer Service
Table 3.14
GDN customer satisfaction survey data 2015-16
Company | GDN | Scores out of 10 |  |  |  |  | Ranking on average score | Financial Reward/(Penalty) (£m)
|  | Planned Interruption | Emergency Response and Repair | Connection | Average (2015-16) | Average (2014-15) |  | Planned Interruption | Emergency Response and Repair | Connection | Total Financial Reward/ (Penalty)
NGGD | EoE | 8.0709 | 9.3766 | 8.127 | 8.5248 | 8.35 | 6 | -0.03562 | 1.0508 | 0.2627 | 1.2779
| Lon | 7.9645 | 9.0346 | 6.8786 | 7.9592 | 7.78 | 8 | -0.16909 | 0.76741 | -0.76741 | -0.16909
| NW | 7.9699 | 9.3762 | 8.6743 | 8.6735 | 8.46 | 5 | -0.15282 | 0.75135 | 0.75135 | 1.3499
| WM | 7.7269 | 9.2635 | 7.825 | 8.2718 | 8.32 | 7 | -0.34617 | 0.56734 | -0.161 | 0.060164
NGN | NGN | 8.8588 | 9.5166 | 9.1207 | 9.1653 | 9.01 | 1 | 0.71852 | 0.71852 | 0.71852 | 2.1556
SGN | Sc | 8.8764 | 9.5179 | 9.0053 | 9.1332 | 8.79 | 2 | 0.48937 | 0.48937 | 0.48937 | 1.4681
| So | 8.6519 | 9.3593 | 8.4656 | 8.8256 | 8.64 | 4 | 1.2234 | 1.2234 | 1.2234 | 3.6703
WWU | WWU | 8.7201 | 9.5507 | 8.8841 | 9.0516 | 9.04 | 3 | 0.68147 | 0.25107 | 0.68147 | 1.614
Target |  | 8.09 | 8.81 | 8.04 | 8.3133 |  | Total | 2.4091 | 5.8193 | 3.1984 | 11.4268
Table 3.15
GDN customer satisfaction survey data - three-year average cumulative
Company | GDN | Scores out of 10 |  |  |  | Ranking on average score
|  | Planned Interruption | Emergency Response and Repair | Connection | Average
NGGD | EoE | 8.0912 | 9.2832 | 7.8178 | 8.3974 | 6
| Lon | 7.9249 | 8.917 | 6.6784 | 7.8401 | 8
| NW | 7.8456 | 9.2627 | 8.3362 | 8.4815 | 5
| WM | 7.8462 | 9.1576 | 7.7646 | 8.2561 | 7
NGN | NGN | 8.6309 | 9.3824 | 8.9127 | 8.9753 | 1
SGN | Sc | 8.7647 | 9.3253 | 8.5584 | 8.8828 | 3
| So | 8.5239 | 9.1908 | 8.3159 | 8.6769 | 4
WWU | WWU | 8.6637 | 9.3783 | 8.7434 | 8.9284 | 2
Target |  | 8.09 | 8.81 | 8.04
Table 3.16
GDN number of complaints for 2015-2016
Company | GDN | Unresolved at day +1 (%) | Unresolved at day +31 (%) | Repeat complaint (%) | Energy ombudsman decision against GDN (%) | Complaint metric score 2015-16 | Complaint metric score 2014-15 | 2015-16 Ranking | RIIO- GD1 ranking
NGGD | EoE | 71.1886 | 7.094 | 0.40448 | 0.12446 | 9.4617 | 9.8966 | 5 | 5
| Lon | 77.4394 | 8.8875 | 0.31075 | 0.21753 | 10.5873 | 11.4488 | 8 | 8
| NW | 76.0756 | 6.7551 | 0.24125 | 0.12063 | 9.7668 | 10.0784 | 7 | 7
| WM | 74.8581 | 6.2418 | 0.30554 | 0.087298 | 9.5199 | 9.8829 | 6 | 6
NGN | NGN | 17.1657 | 2.6613 | 1.1311 | 0 | 3.0805 | 2.656 | 2 | 1
SGN | Sc | 28.7671 | 0.45662 | 0 | 0 | 3.0137 | 8.8062 | 1 | 3
| So | 36.7716 | 1.1655 | 0.17483 | 0 | 4.1142 | 9.6341 | 3 | 4
WWU | WWU | 30.9685 | 3.6036 | 0.50676 | 0 | 4.4313 | 6.9276 | 4 | 2
Industry average |  | 51.6543 | 4.6082 | 0.38434 | 0.068738 | 6.7469 | 8.6663
Target | [5 empty] | 11.57
Table 3.17
GDN stakeholder engagement results
Company | GDN | Minimum criteria | Panel score (out of 10) 2015-16 | Panel score (out of 10) 2014-15 | Reward (£m) 2015-16 | Reward (£m) 2014-15
NGGD | EoE | √ | 6.9 | 5.9 | 1.7925 | 1.17
| Lon | √ |  |  | 1.3091 | 0.81
| NW | √ |  |  | 1.2817 | 0.84
| WM | √ |  |  | 0.96781 | 0.64
NGN | NGN | √ | 6.8 | 5.5 | 1.1834 | 0.62
SGN | Sc | √ | 5.75 | 6.4 | 0.50377 | 0.73
| So | √ |  |  | 1.2594 | 1.73
WWU | WWU | √ | 6.05 | 7.05 | 0.82177 | 1.26

## Outputs- connections
Table 3.18
Breakdown of new gas connections activity by GDN 2015-16
Company | GDN | New Housing | Existing Housing | Fuel Poor |  |  | Non-domestic | Total
|  |  |  | One-offs | Community Schemes | Other scheme types
NGGD | EoE | 2671 | 4734 | 1045 | 439 | 0 | 188 | 9077
| Lon | 1143 | 1984 | 243 | 0 | 0 | 141 | 3511
| NW | 700 | 1959 | 1274 | 283 | 0 | 107 | 4323
| WM | 810 | 1640 | 579 | 512 | 0 | 85 | 3626
NGN | NGN | 2062 | 2366 | 915 | 1543 | 0 | 593 | 7479
SGN | Sc | 1222 | 4219 | 1518 | 1098 | 70 | 390 | 8517
| So | 6090 | 5437 | 685 | 475 | 0 | 629 | 13316
WWU | WWU | 3878 | 5563 | 872 | 687 | 0 | 640 | 11640
Industry |  | 18576 | 27902 | 7131 | 5037 | 70 | 2773 | 61489

## Outputs- social obligations
Table 3.19
Fuel poor connections - actuals and RIIO-GD1 forecasts
Number of fuel poor connections | Three-year cumulative |  |  | RIIO-GD1 eight year
| Commitment | Actual | % variance | Revised commitment1 | Forecast | % variance
EoE | 3817.6667 | 4414 | 13.51% | 12046 | 12046 | 0%
Lon | 1020 | 742 | -37.47% | 2880 | 2880 | 0%
NW | 5020 | 5053 | 0.6531% | 13330 | 13330 | 0%
WM | 3130 | 3170 | 1.262% | 8360 | 8360 | 0%
NGN | 4916.6667 | 5329 | 7.738% | 14500 | 14577 | 0.5282%
Sc | 5521.6667 | 11418 | 51.64% | 17130 | 17143 | 0.07583%
So | 3322.875 | 3543 | 6.213% | 10367.25 | 10393 | 0.2478%
WWU | 4798.3333 | 5852 | 18.01% | 12590 | 12590 | 0%
Industry | 31547.2083 | 39521 | 20.18% | 91203.25 | 91319 | 0.1268%
1 The original price control volumes for fuel poor were increased as part of the Fuel Poor Network Extension Scheme published in September 2015, with the exception of Lon, NW and WM

## Outputs- Environment
Table 3.20
Number and capacity of biomethane studies and capacity connected in 2015-16
Biomethane Connections | GDN | Enquiries | Connection Studies | Connections | Capacity of studies (scmh) | Capacity connected(scmh) 2015-16 | Capacity connected(scmh) 2014-15
NGGD | EoE | 282 | 10 | 9 | 4875 | 4350 | 4160
| Lon | 6 | 1 | 0 | 1500 | 0 | 0
| NW | 18 | 2 | 1 | 350 | 100 | 1423
| WM | 66 | 10 | 2 | 6700 | 500 | 900
NGN | NGN | 45 | 7 | 8 | 3850 | 7500 | 1200
SGN | Sc | 92 | 16 | 7 | 5062 | 5062 | 3760
| So | 52 | 12 | 5 | 3875 | 3875 | 4650
WWU | WWU | 66 | 20 | 7 | 14172 | 7950 | 3250
All GDNs |  | 627 | 78 | 39 | 40384 | 29337 | 19343
Table 3.21
Shrinkage and leakage volumes in 2015-16
Company | GDN | Shrinkage |  |  | Leakage
|  | 2015/16 target | 2015/16 Actual | Shrinkage Incentive Revenue | 2015/16 target | 2015/16 Actual | Environmental Emissions Incentive Revenue
|  | GWh | GWh | £m | GWh | GWh | £m
NGGD | EoE | 503 | 449.3995 | 0.5603 | 470 | 419.5279 | 3.1432
| Lon | 274 | 244.0686 | 0.296 | 257 | 228.6018 | 1.6812
| NW | 367 | 340.8024 | 0.28266 | 346 | 320.3573 | 1.6497
| WM | 316 | 289.8191 | 0.28945 | 303 | 276.2764 | 1.7737
NGN | NGN | 432 | 381.6169 | 0.55523 | 407 | 360.1377 | 3.0799
SGN | Sc | 220 | 211.8201 | 0.079022 | 204 | 196.193 | 0.44757
| So | 606 | 554.2415 | 0.55029 | 573 | 526.376 | 2.951
WWU | WWU | 421.2 | 381.069 | 0.45325 | 396.2 | 362.9632 | 2.2741
Industry |  | 3139.2 | 2852.837 | 3.0662 | 2956.2 | 2690.4334 | 17.0005
Table 3.22
Total annual business carbon footprint (BCF)
Company | GDN | 2015-16 BCF (Excluding shrinkage) (tCO2e) | 2014-15 BCF (Excluding shrinkage) (tCO2e) | % Change 2015-2016 | Change 2015-2016 | Rank (based on % change)
NGGD | EoE | 25180 | 24731 | 1.783% | 449 | 3
| Lon | 15417 | 14896 | 3.379% | 521 | 4
| NW | 17007 | 16248 | 4.463% | 759 | 5
| WM | 12259 | 10843 | 11.55% | 1416 | 7
NGN | NGN | 23763.6364 | 25541.9566 | -7.483% | -1778.3202 | 2
SGN | Sc | 13787.43 | 11769.88 | 14.63% | 2017.55 | 8
| So | 26091.95 | 23138.47 | 11.32% | 2953.48 | 6
WWU | WWU | 16471.6288 | 18718.7807 | -13.64% | -2247.1519 | 1
Industry |  | 149977.6452 | 145887.0873 | 3.25% | 4090.5579

## NIA
Table 4.1
Network Innovation Allowance projects and expenditure in 2015-16
Company | GDN | 2013-14 |  |  | 2014-15 |  |  | 2015-16
|  | NIA expenditure (£m) | Number of projects (by company) | Percentage of allowance used (%) | NIA expenditure (£m) | Number of projects (by company) | Percentage of allowance used (%) | NIA expenditure (£m) | Number of projects (by company) | Percentage of allowance used (%)
NGGD | EoE | 1.4531 | 40 | 32.96% | 2.826 | 61 | 65.86% | 3.4531 | 61 | 79.81%
| Lon | 0.82447 |  | 27.83% | 1.6094 |  | 54.94% | 1.963 |  | 62.12%
| NW | 0.96875 |  | 30.25% | 1.8977 |  | 61.52% | 2.3168 |  | 74.89%
| WM | 0.68019 |  | 28.76% | 1.3846 |  | 59.25% | 1.6901 |  | 72.35%
NGN | NGN | 1.4162 | 27 | 49.57% | 2.3895 | 43 | 82.52% | 2.9486 | 44 | 99.66%
SGN | Sc | 1.2784 | 35 | 83.17% | 1.0295 | 46 | 67.86% | 1.4919 | 64 | 103.7%
| So | 2.8883 |  | 78.65% | 2.3367 |  | 65.1% | 3.3728 |  | 93.73%
WWU | WWU | 0.42736 | 14 | 20.71% | 1.6086 | 22 | 77.68% | 0.96873 | 33 | 48.33%
Total NIA Expenditure |  | 9.9368 |  |  | 15.082 |  |  | 18.2052

## Analysis of expenditure
Data for figure 5.1 and figure 5.2 | [6 empty] | Figure 5.1
| Cumulative actuals (figure 5.1) |  |  | Eight-year figure (figure 5.2) |  |  | Three-year cumulative underspend/ overspend against allowances
GDNs | Opex | Repex | Capex | Opex | Repex | Capex
EoE | 11.59% | -19.59% | -19.08% | 8.949% | -19.89% | -0.9386%
Lon | 13.1% | -38.88% | -17.07% | 6.04% | -27.11% | 7.251%
NW | 12.34% | -12.35% | -18.98% | 7.948% | -24.12% | -8.228%
WM | 0.6732% | -21.21% | -24.83% | 1.336% | -25.38% | -14.97%
NGN | -17.73% | -8.379% | -11.39% | -18.35% | -11.38% | -7.354%
Sc | -25.2% | -23.91% | -7.784% | -23.98% | -18.86% | -7.742%
So | -23.07% | -19.73% | -13.02% | -21.47% | -13.54% | -11.46%
WWU | -11.65% | -19.67% | -20.97% | -10.05% | -20.63% | -15.63%
Figure 5.2
Companies' projected eight year underspend/ overspend against allowances

## Appendix 1
Table A1.1: | [9 empty] | Figure A1.3:
MOD values | [9 empty] | Recalculated base revenue using actual performance data up to 2015-16
| £m 2015/16 Prices | 2013/14 | 2014/15 | 2015/16 | 2016/17 | 2017/18
| EoE | - | -3.8726 | -9.0836 | -16.3048 | -14.8423
| Lon | - | -3.3797 | -2.0105 | -5.4659 | -24.8337 |  |  |  |  | Base Revenue Components
| NW | - | -3.5021 | -10.3489 | 4.9324 | -18.4911
| WM | - | -2.6331 | -6.3061 | -6.4818 | -16.014 |  |  |  |  | Current view of Base Revenue for 2015/16 based on performance for first 3 years. Not reflective of companies forecasts of future reopeners.
| NGN | - | 1.1514 | -6.6306 | -7.4938 | -13.3211
| Sc | - | -0.33102 | -11.3904 | 7.2244 | -11.7153 |  |  |  |  | Fast Money
| So | - | -3.3068 | -22.0795 | -1.2999 | -28.1942
| WWU | - | -0.13954 | -11.3309 | -8.6695 | -20.7199 |  |  |  |  | Tax Allowance
| Total | - | -16.0135 | -79.1806 | -33.5589 | -148.1316
Table A1.2: | [10 empty] | Other Revenue Items*
RAV balance
| £m 2015/16 Prices | NGGD |  |  |  | NGN | SGN |  | WWU |  |  | Pre-RIIO Assets | RIIO Assets
|  | EoE | Lon | NW | WM | NGN | Sc | So | WWU
| RAV at 1st April 2013 | 3047.979 | 1976.2387 | 2095.5216 | 1588.8931 | 1896.5117 | 1536.0331 | 3442.6579 | 1935.9942 |  | Return on RAV for:
| Slow Money | 371.5537 | 330.234 | 284.0017 | 203.9678 | 304.0493 | 247.3351 | 505.0222 | 318.312
| Depreciation | -439.3086 | -291.0283 | -306.5137 | -231.6768 | -280.2194 | -231.7385 | -506.9141 | -294.9715 |  | Depreciation of RAV for:
| RAV at 31st March 2016 | 2980.2241 | 2015.4444 | 2073.0097 | 1561.1842 | 1920.3416 | 1551.6298 | 3440.766 | 1959.3347
Data for figure A1.3-recalculated base revenue | [10 empty] | Opening Position
|  | NGGD |  |  |  | NGN | SGN |  | WWU
| £m 2015/16 Prices | EoE | Lon | NW | WM | NGN | Sc | So | WWU |  | Base Revenue originally set at Final Determinations, before any RIIO performance was taken into account.
| Fast Money | 180.6848 | 154.567 | 133.1614 | 103.3154 | 133.9919 | 101.2195 | 200.7857 | 127.3632 |  | Opening Base Revenue
| RAV Depreciation for Pre-RIIO | 129.6365 | 84.3303 | 89.5635 | 67.7804 | 81.0941 | 66.0855 | 146.9907 | 91.8231
| RAV Depreciation for RIIO | 10.4905 | 9.003 | 7.8831 | 5.4491 | 8.1547 | 7.0516 | 14.0366 | 8.9885
| Return on RAV for Pre-RIIO | 105.6206 | 68.3694 | 72.4793 | 54.9481 | 65.528 | 52.9414 | 119.0049 | 66.7864
| Return on RAV for RIIO | 11.601 | 10.1678 | 8.8518 | 6.2473 | 9.3381 | 7.7546 | 15.6968 | 9.9455 |  | *Consisting of IQI Ex-ante Reward/Penalty, Legacy mechanisms, Pension Deficit Funding, Revenue Profiling, Uncontrollable Pass-through Items and Equity Issuance Costs.
| Tax Allowance | 41.61 | 35.5047 | 29.8957 | 25.357 | 32.6547 | 24.8625 | 59.1951 | 6.8775e-17
| Misc. | 119.2248 | 65.0909 | 90.9007 | 61.3613 | 82.0397 | 52.4845 | 165.1773 | 85.2417
| Base Revenue | 598.8683 | 427.0332 | 432.7355 | 324.4587 | 412.8012 | 312.3997 | 720.8871 | 390.1484
| Opening Base Revenue | 612.8419 | 443.0981 | 441.989 | 332.2337 | 419.4521 | 306.3011 | 725.042 | 402.9298

## Appendix 2
Table A2.1
Length of iron mains off-risk
Company | GDN | Secondary deliverable |  | 2015-16 actual delivery |  | 3 year cumulative
|  | Overall RIIO-GD1 (km) | Annual Average from interpolations of the 8 year deliverable | Length of Iron Mains Abandoned (km) | Variance of 2016 actual against annual average of the 8 year deliverable | length of iron mains abandoned (km) | Length abandoned in RIIO-GD1 compared with annualised secondary deliverable
NGGD | EoE | 4798.3834 | 599.7979 | 629.1557 | 4.895% | 1752.3956 | -2.612%
| Lon | 2887.7505 | 360.9688 | 326.9796 | -9.416% | 960.35 | -11.32%
| NW | 3491.4806 | 436.4351 | 481.596 | 10.35% | 1234.1866 | -5.737%
| WM | 2674.1633 | 334.2704 | 380.5609 | 13.85% | 885.781 | -11.67%
NGN | NGN | 3991.8984 | 498.9873 | 464.1813 | -6.975% | 1460.8397 | -2.413%
SGN | Sc | 1993.0921 | 249.1365 | 258.9311 | 3.931% | 767.1454 | 2.641%
| So | 5490.931 | 686.3664 | 649.4266 | -5.382% | 2127.1684 | 3.306%
WWU | WWU | 2875.9642 | 359.4955 | 348.3742 | -3.094% | 1091.9529 | 1.249%
Table A2.2
Tier 2 and 3 workloads
Company | GDN | Assumed workload in setting RIIO-GD1 final proposals |  | 2016 target after adjusting for Tier 2a workload | 2015-16 actual delivery |  | Delivery after the first 3 years of RIIO-GD1
|  | Total RIIO-GD1 8 year work load (km) | Annual average from interpolation of the 8 year workload (km) |  | Actual 2016 length of iron mains abandoned (km) | Variance of 2016 actual abandonment against 2016 assumed workload adjusted for Tier 2a | Actual length abandoned in RIIO-GD1 | Variance of actual RIIO-GD1 abandonment against assumed workload adjusted for Tier 2a
NGGD | EoE | 140.6834 | 17.5854 | 16.3132 | 13.5702 | -16.81% | 21.1729 | -30.6%
| Lon | 274.0594 | 34.2574 | 30.9268 | 12.9171 | -58.23% | 18.0956 | -67.68%
| NW | 195.1669 | 24.3959 | 20.3912 | 21.8504 | 7.156% | 49.4656 | 32.67%
| WM | 99.1109 | 12.3889 | 9.1356 | 7.8866 | -13.67% | 12.9652 | -18.51%
NGN | NGN | 285.0051 | 35.6256 | 30.7172 | 21.448 | -30.18% | 90.9551 | 46.6%
SGN | Sc | 155.6182 | 19.4523 | 19.1581 | 4.0615 | -78.8% | 5.8776 | -84.43%
| So | 268.9656 | 33.6207 | 30.3325 | 11.4908 | -62.12% | 23.6817 | -58.13%
WWU | WWU | 238.1586 | 29.7698 | 30.8975 | 15.8978 | -48.55% | 61.4058 | -8.502%
Table A2.3
Number of fractures and failures
Company | GDN | RIIO-GD1 target | Average Annualised target | 2013-14 actual | 2014-15 Actual | 2015-16 actual
NGGD | EoE | 13441.0057 | 1680.1257 | 999.45 | 1213.42 | 982.51
| Lon | 3993.4853 | 499.1857 | 277.55 | 307.58 | 308.49
| NW | 12362.041 | 1545.2551 | 755 | 909 | 819
| WM | 7421.172 | 927.6465 | 561 | 703 | 614
NGN | NGN | 21843.5613 | 2730.4452 | 815 | 883 | 685
SGN | Sc | 10386 | 1298.25 | 455 | 473 | 373
| So | 13001 | 1625.125 | 1077 | 1145 | 778
WWU | WWU | 8512.7231 | 1064.0904 | 581 | 616 | 519
Industry |  | 90960.9885 | 11370.1236 | 5521 | 6250 | 5079
Table A2.4
Secondary deliverable level and actual numbers of gas in building occurrences
Company | GDN | RIIO-GD1 target | Average Annualised target | 2013-14 actual | 2014-15 Actual | 2015-16 actual
NGGD | EoE | 910.5135 | 113.8142 | 74.34 | 123.06 | 89.24
| Lon | 329 | 41.125 | 23.66 | 30.94 | 32.76
| NW | 1069 | 133.625 | 54 | 89 | 66
| WM | 633 | 79.125 | 47 | 77 | 53
NGN | NGN | 1523.0848 | 190.3856 | 18 | 42 | 58
SGN | Sc | 525 | 65.625 | 33 | 29 | 21
| So | 605 | 75.625 | 64 | 94 | 73
WWU | WWU | 550 | 68.75 | 37 | 45 | 35
Table A2.5
Number of domestic service replacements 2015-16
GDN | Replacement with service alteration | Replacement after escape | Replacement associated with smart metering | Replacement with mains replacement | Other replacement | Total | Annualised RIIO-GD1 target | Variance %
EoE | 1444.54 | 3408.799 | 15.17 | 26134 | 3911.5631 | 34914.0721 | 30377 | 15%
Lon | 774.41 | 4164.251 | 11.83 | 26218 | 2424.7769 | 33593.2679 | 21481 | 56%
NW | 672 | 4251.26 | 15 | 30002 | 3130.12 | 38070.38 | 28383.25 | 34%
WM | 395 | 2377.52 | 13 | 26069 | 2881.92 | 31736.44 | 21125.125 | 50%
NGN | 1122 | 3838 | 0 | 21134 | 1485 | 27579 | 30932.25 | -11%
Sc | 140 | 1127 | 0 | 10604 | 2402 | 14273 | 13224.25 | 8%
So | 1356 | 4280 | 0 | 37888 | 4118 | 47642 | 49573.5 | -4%
WWU | 628 | 3797 | 0 | 16173 | 1224 | 21822 | 25209.375 | -13%

## Appendix 3
Table A3.1
Duration of telemetered faults
Company | GDN | Hours per AGI
|  | 2013-14 |  | 2014-15 |  | 2015-16
|  | Deliverable limit | Actual | Deliverable limit | Actual | Deliverable limit | Actual
NGGD | EoE | 127 | 70 | 123 | 80.37 | 119 | 34.09
| Lon | 127 | 132 | 123 | 171.14 | 119 | 48
| NW | 127 | 95 | 123 | 93.12 | 119 | 25.33
| WM | 127 | 173 | 123 | 175.2 | 119 | 30.04
NGN | NGN | 211 | 105 | 196 | 63 | 181 | 135
SGN | Sc | 238 | 139.775 | 238 | 100.202 | 238 | 121.157
| So | 134 | 297.142 | 134 | 173.935 | 134 | 52.1
WWU | WWU | 181 | 15.8 | 168 | 5.23 | 153 | 4.54
Table A3.2
Number of PSSR faults
Company | GDN | Fault Rate
|  | 2013-14 |  | 2014-15 |  | 2015-16
|  | Deliverable limit | Actual | Deliverable limit | Actual | Deliverable limit | Actual
NGGD | EoE | 8% | 5% | 8% | 5.44% | 7% | 6.681%
| Lon | 9% | 4% | 9% | 4.372% | 8% | 4.356%
| NW | 18% | 11% | 16% | 11.42% | 16% | 11.31%
| WM | 6% | 5% | 6% | 5.424% | 6% | 4.724%
NGN | NGN | 51% | 42.59% | 51% | 26.27% | 50% | 30.73%
SGN | Sc | 35.6% | 22.34% | 35.6% | 25.65% | 35.6% | 21.5%
| So | 20.9% | 19.42% | 20.9% | 20.9% | 20.9% | 18.7%
WWU | WWU | 7.3% | 48.1% | 7.2% | 5.7% | 7.1% | 4.988%
Table A3.3
Low pressure holder demolition
Company | GDN | 2015-16 | Cumulative | RIIO-GD1
|  | Actual | Actual | Target | Forecast
NGGD | EoE | 9 | 23 | 29 to 30 | 29
| Lon | 3 | 14 | 32 to 33 | 34
| NW | 9 | 14 | 35 | 35
| WM | 4 | 4 | 4 to 5 | 4
NGN | NGN | 3 | 6 | 23 to 24 | 23
SGN | Sc | 2 | 4 | 11 | 14
| So | 8 | 19 | 44 to 45 | 53
WWU | WWU | 1 | 10 | 7 to 8 | 10
Industry |  | 39 | 94 | 185 to 191 | 202
Table A3.4
Number of business days to digitise network records (% digitised by length)
Company | GDN | 2013-14 |  |  | 2014-15 |  |  | 2015-16
|  | < 30 days | < 60 days | > 60 days | < 30 days | < 60 days | > 60 days | < 30 days | < 60 days | > 60 days
NGGD | EoE | 45% | 21% | 34% | 65.99% | 29.15% | 4.861% | 43% | 48.97% | 8.03%
| Lon | 63% | 19% | 18% | 72.03% | 23.81% | 4.159% | 72.8% | 23.64% | 3.566%
| NW | 47% | 27% | 26% | 72.47% | 22.2% | 5.335% | 42.83% | 48.44% | 8.73%
| WM | 67% | 15% | 19% | 83.02% | 13.45% | 3.527% | 33.34% | 57.02% | 9.635%
NGN | NGN | 66.83% | 14% | 15% | 47.15% | 16.99% | 35.87% | 63.21% | 14.79% | 21.99%
SGN | Sc | 98% | 2% | 1% | 94.09% | 5.37% | 0.5394% | 97.15% | 2.171% | 0.6817%
| So | 97% | 1% | 2% | 97.74% | 0.9891% | 1.274% | 96.76% | 1.826% | 1.414%
WWU | WWU | 96% | 2% | 2% | 97.7% | 1.688% | 0.6106% | 97.82% | 1.147% | 1.035%

## Appendix 5
Table A5.1
Summary of environmental measures
Other emissions and natural resource use |  | Description | Units | EoE |  | Lon |  | NW |  | WM |  | NGN |  | Sc |  | So |  | WWU
|  |  |  | 2015/16 | 2014/15 | 2015/16 | 2014/15 | 2015/16 | 2014/15 | 2015/16 | 2014/15 | 2015/16 | 2014/15 | 2015/16 | 2014/15 | 2015/16 | 2014/15 | 2015/16 | 2014/15
Broad environmental measure | Biomethane | Biomethane enquiries | Number | 282 | 239 | 6 | 5 | 18 | 20 | 66 | 54 | 45 | 59 | 92 | 95 | 52 | 78 | 66 | 68
|  | Biomethane connection studies | Number | 10 | 44 | 1 | 1 | 2 | 2 | 10 | 3 | 7 | 6 | 16 | 9 | 12 | 13 | 20 | 17
|  | Capacity of Biomethane connection studies | m3/h | 4875 | 33287 | 1500 | 600 | 350 | 1350 | 6700 | 1650 | 3850 | 3960 | 5062 | 7450 | 3875 | 6767 | 14172 | 16200
|  | Biomethane connections | Number | 9 | 6 | 0 | 0 | 1 | 2 | 2 | 1 | 8 | 1 | 7 | 2 | 5 | 6 | 7 | 4
|  | Capacity of Biomethane connected | m3/h | 4350 | 4160 | 0 | 0 | 100 | 1423 | 500 | 900 | 7500 | 1200 | 5062 | 3760 | 3875 | 4650 | 7950 | 3250
| Unconventional sources of gas | Other unconventional sources of gas enquiries | Number | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 8 | 3 | 0
|  | Other unconventional sources of gas connection studies | Number | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 2 | 2 | 0
|  | Capacity of other unconventional sources of gas connection studies | m3/h | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 1200 | 0
|  | Other unconventional sources of gas connections | Number | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Capacity of other unconventional sources of gas connected | m3/h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Narrow environmental measures | Land remediation | Sites routinely monitored & maintained - statutory | Number | 50 | 43 | 8 | 7 | 18 | 36 | 16 | 11 | 54 | 40 | 22 | 13 | 20 | 12 | 13 | 25
|  | Non-gasholder demolition sites - statutory remediation | Number | 10 | 8 | 2 | 1 | 1 | 3 | 1 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 8 | 3
|  | Gasholder demolition sites - statutory remediation | Number | 2 | 4 | 3 | 6 | 1 | 18 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2
|  | Total sites (statutory remediation) | Number | 62 | 55 | 13 | 14 | 20 | 57 | 18 | 19 | 57 | 40 | 22 | 13 | 20 | 12 | 21 | 30
|  | Total cost | £m | 0.47383 | 1.6589 | 0.22547 | 2.1435 | 0.33774 | 11.2271 | 0.056882 | 0.078988 | 0.5425 | 0.54607 | 0.43 | 0.571 | 2.2 | 0.98 | 2.6007 | 2.3841
| Virgin aggregate | Virgin aggregate (as a percentage of total imported backfill) | % | 16.3202 | 29.163 | 0.17703 | 2.41 | 11.6479 | 18.8999 | 1.5601 | 12.5979 | 25.44 | 23.31 | 10.57 | 11.97 | 2.31 | 10.43 | 77 | 86.5112
|  | Virgin aggregate | Tonnes | 13725.03 | 27535.87 | 95.48 | 1076.9 | 13525.01 | 19257.59 | 1249.72 | 5060.94 | 33520.24 | 29426 | 9399.33 | 9593.2 | 5561.15 | 26629.18 | 86760 | 107524.675
| Spoil to landfill | Spoil to landfill (as a percentage of total excavated spoil) | % | 5.3114 | 7.2676 | 0.87859 | 0.74 | 1.5515 | 2.1892 | 0.0017818 | 0.33539 | 9.92 | 10.26 | 0.25 | 3.44 | 0.07 | 15 | 25 | 22.6178
|  | Spoil to landfill | Tonnes | 6437.94 | 10440.563 | 1018.38 | 592.19 | 3089.71 | 4072.21 | 2 | 623.88 | 17311 | 18565 | 220 | 2868 | 196 | 430.4 | 48142 | 45186.11
| ISO 1400 | ISO 14001 major non-conformities | Number | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Appendix 6
Table A6.1: | [10 empty] | Table A6.2:
Guaranteed standards of performance 2015-16 | [10 empty] | Additional Guaranteed standards of performance 2015-16
Guaranteed standard of performance | Target | EoE | Lon | NW | WM | NGN | Sc | So | WWU | Industry | Guaranteed standard of performance |  | EoE | Lon | NW | WM | NGN | Sc | So | WWU | Industry
Guaranteed Standard 4 - Regulation 10 - Provision of standard connection quotations =<275kWh per hour | 90% | 99.95% | 99.9% | 99.9% | 99.94% | 99.98% | 99.72% | 99.55% | 99.7% | - | Guaranteed Standard 1 - Regulation 7 - Supply Restoration | Number of Payments | 5962.9999 | 43293.6666 | 4133.9999 | 2093.6666 | 5806 | 1219 | 8568 | 847
| - | 320 | 520 | 50 | 140 | 10 | 160 | 870 | 2020 | 4090 |  | Total Value of Payments | 180329.997 | 1303689.998 | 128139.997 | 63609.998 | 174180 | 36650 | 257080 | 26050 | 2169729.99
Guaranteed Standard 5 - Regulation 10 - Provision of non-standard connection quotations =<275kWh per hour | 90% | 98.15% | 97.94% | 99.34% | 98.88% | 99.98% | 99.33% | 98.22% | 98.74% | - | Guaranteed Standard 2 - Regulation 8 - Reinstatement of customer's premises | Number of Payments | 4387 | 1913 | 715 | 1560 | 116 | 183 | 1031 | 355
| - | 1430 | 1850 | 30 | 90 | 40 | 1010 | 9420 | 6460 | 20330 |  | Total Value of Payments | 220050 | 96500 | 35900 | 78200 | 6050 | 9450 | 53000 | 17950 | 517100
Guaranteed Standard 6 - Regulation 10 - Provision of non-standard connection quotations > 275kWh per hour | 90% | 99.14% | 98.98% | 100% | 100% | 100% | 99.78% | 98.18% | 98.52% | - | Guaranteed Standard 3 - Regulation 9 - Priority domestic customers | Number of Payments | 4 | 10 | 14 | 16 | 0 | 0 | 3 | 18
| - | 600 | 1540 | 0 | 0 | 0 | 220 | 3020 | 860 | 6240 |  | Total Value of Payments | 96 | 240 | 336 | 384 | 0 | 0 | 72 | 432 | 1560
Guaranteed Standard 7 - Regulation 10 - Accuracy of quotations (percentage of quotations challenged but found to be accurate) | - | 40% | 25% | No accuracy challenges reported | [5 empty] | - | Guaranteed Standard 13 - Regulation 10A - Notification of planned supply interruptions | Number of Payments | 127 | 74 | 101 | 155 | 15 | 1 | 0 | 17
| - | 0 | 628.34 | 0 | 0 | 0 | 0 | 0 | 0 | 628.34 |  | Total Value of Payments | 2540 | 1480 | 2050 | 3130 | 300 | 20 | 0 | 370 | 9890
Guaranteed Standard 8 - Regulation 10 - Response to land enquiries | 90% | 98.37% | 98.73% | 98.52% | 98.83% | 100% | 100% | 100% | 98.72% | - | Guaranteed Standard 14 - Regulation 10B - Response to complaints | Number of Payments | 1773 | 2873 | 1609 | 1429 | 2 | 0 | 5 | 8
| - | 4970 | 3450 | 3440 | 2100 | 0 | 0 | 760 | 1440 | 16160 |  | Total Value of Payments | 35460 | 57460 | 32180 | 28580 | 40 | 0 | 100 | 160 | 153980
Guaranteed Standard 9 - Regulation 10 - Offering a date for commencement and substantial completion of connection works (=<275kWh per hour) | 90% | 97.73% | 93.3% | 98.07% | 97.86% | 99.97% | 99.85% | 99.9% | 99.95% | - | Guaranteed Standard 12 - Regulation 12 - Payments | Number of Payments | 4404 | 2916 | 687 | 960 | 60 | 63 | 391 | 26
| - | 35778.2 | 41600 | 14480.75 | 14145.4 | 430 | 1500 | 1300 | 1060 | 110294.35 |  | Total Value of Payments | 88080 | 58320 | 13740 | 19200 | 1200 | 1260 | 7820 | 520 | 190140
Guaranteed Standard 10 - Regulation 10 - Offering a date for commencement and substantial completion of connection works (>275kWh per hour) | 90% | 98.04% | 93.42% | 90.62% | 95.45% | 97.59% | 99.06% | 99.28% | 100% |  | Total | - | 526555.997 | 1517689.998 | 212345.997 | 193103.998 | 181770 | 47380 | 318072 | 45482 | 3042399.99
| - | 500 | 1180 | 620 | 700 | 4640 | 500 | 200 | 0 | 8340
Guaranteed Standard 11 - Regulation 10 - Substantial completion on agreed date | 90% | 94.41% | 93.89% | 97.06% | 92.99% | 98.42% | 98.22% | 98.58% | 94.24% | -
| - | 125340.85 | 107008.95 | 17602.15 | 41345.84 | 12898.99 | 6241.48 | 12203.6 | 57370.7137 | 380012.5737
Standard Special Condition D10(2)(f) Responding to telephone calls | 90% | 92.59% | 92.59% | 92.59% | 92.59% | 92.59% | 92.59% | 92.59% | 92.59% | -
| - | - | - | - | - | - | - | - | - | -
Total | - | 168939.05 | 157777.29 | 36222.9 | 58521.24 | 18018.99 | 9631.48 | 27773.6 | 69210.7137 | 546095.2637