## Gas
Switching Programme: Data Working Group Progress Report | [6 empty] | GAS | 2019-03-01
Data Cleansing
| Baseline Position | Current Position
Plot to Postal Addresses | (Feb-2019) | (Mar-2019) | Commentary
GT Registered Sites | 15095 | 14591 | Existing monthly BAU plot to postal process whereby Shippers provide a 'better PAF registered address'. Proactively working with Shipper organisations via the Consequential workgroup to prioritise this cleanse activity. This will be an ongoing cleanse activity, pre and post this Programme.
GT Unregistered Sites | 8465 | 8718 | Working alongside GT's to agree the cleanse activity for this pot. Figures will fluctuate due to new meter points being created and not confirmed into a Shippers portfolio
IGT Sites | TBC | TBC | All IGT organisations have a plot to postal process whereby developers and Utility Infrastructure Providers provide a 'better PAF registered address' where able. A change request is currently in flight where IGT's will have the ability to update 'plot addresses' held on UK Link in bulk in addition to the current process of individual updates. NB - Plot to Postal address cleanse data is also being provided to Ofgem via AIGT. This data is currently in review prior to submission to Ofgem.
| Baseline Position | Current Position
MTD Cleanse | (mm-2018) | (mm-2019) | Commentary
Large |  |  | Gas MTD Cleansing and tracking of progress will follow once the first reconciliation from CP17/411 is completed in April 2019
Medium
Small
|  |  |  | RAG | Completion Date
|  |  |  | Status | Baseline | Forecast | Commentary
Consequential Changes
MAP ID | Creation of MAP ID field within UK Link |  |  | G | 2019-07-01 | 2019-07-01 | The change is scheduled and on track for Xoserve's July 19 release
| Initial population of MAP ID detail within UK Link |  |  | G | 2019-11-01 | 2019-11-01 | Some MAP data has been provided to Xoserve, we are working with MAP organisations via CMAP to acquire as much MAP data as possible. Timeline of November 19 has been provided to CMAP as target date for data population.
| Ongoing population of MAP ID from MAPs |  |  | G | 2019-07-01 | 2019-07-01 | With the introduction of MAP ID to UK Link there will be the provision of ongoing updates via RGMA flows from a Shipper Organisation. MAP's will be provisioned with a flow to also provide MAP ID updates on an enduring basis to UK Link. Architectural design solutions are currently being analysed.
Shipper / Supplier Mapping | Cleansing activity for Shipper / Supplier mapping |  |  | G | 2019-12-01 | 2019-12-01 | This is an ongoing process with multiple Organisations to ensure the validity of Stakeholder associations. This activity will be ongoing until the migration of the process to Xoserve from SPAA
| Transfer ownership of stakeholder data from SPAA to Xoserve |  |  | G | 2020-02-01 | 2020-02-01 | The transfer of ownership of Stakeholder data from SPAA to Xoserve is on track for a February 2020 delivery
Registerable Meter Point Status | Recognition and mapping of existing meter point status and meter status to new RMP status values |  |  | A/G | 2020-11-01 | 2020-11-01 | Detailed design will confirm how the RMP status will be maintained within UK Link for provision to the new CSS Provider. Milestone of August 19 indicates the end of Xoserve's detailed design phase.
Data Item Creation
Licence Exempt Network (LEN) indicator | LEN indicator Data Item creation in UK Link |  |  | N/S | TBC | TBC | Detailed requirements to be defined for the enduring process and then to be scheduled into a change release
| LEN indicator data transformation/update/operational processes |  |  | N/S | TBC | TBC | Detailed requirements to be defined for the enduring process in order define datasets to be held
| LEN Site investigation |  |  | N/S | TBC | TBC | Need further information to understand this requirement
Other
Meter Point Address Data | Profiling of address data held within UK Link |  |  | C | 2019-03-01 | 2019-03-01 | Profiling has completed. Scope of profiling includes: - invalid/dummy postcodes - Addreses without a delivery point alias, building name or number - Missing street names and Post Towns of Unknown or Blank Output is currently being analysed.
| Creation of portfolio reporting for Industry cleansing activity |  |  | G | 2021-06-01 | 2021-06-01 | First portfolio reporting is due to be issued in May 19. These reports will provide individual Shipper Organisations the site detail to enable them to begin to cleanse the meter points within their individual Portfolios. From this point we can begin to track progress and trend reporting via this report.
| Shipper cleansing activity |  |  | G | 2021-06-01 | 2021-06-01 | Will be ongoing from May 19 as a monthly BAU process until Programme implementation
SPAA - Near Term Improvements
Gas Meter Technical Details | CP17/411 (Updates to Schedule 22 with specific reference to Section 7- Suppliers Reporting Obligations) |  |  | C | 2018-11-02 | 2018-11-02 | • Suppliers are required to ensure all appointed MAMs participate in the asset portfolio reconciliation activity • MAMs will be required to take a snapshot of the data items listed on 01 April each year and provide this extract to Xoserve (acting as the Central Data Service Provider) • Xoserve will then perform a comparison between the MAM-provided data set and the Supply Point registration data held in central systems • Xoserve will then report the volume and type of any discrepancies, in relation to each registered Supplier, to the SPAA Secretariat • Xoserve will also report this information to the relevant registered Supplier
| First reconciliation |  |  | G | 2019-04-01 | 2019-04-01 | • Xoserve has attended the SPAA Experts Group (SEG) and MAMCoP meetings to provide an overview of the required format of the reconciliation data and to advise on the data transfer medium • ElectraLink are supporting Supplier parties in navigating the obligations of Schedule 22 to assist in ensuring preparations are underway for the reconciliation
Xoserve (UK-Link) / MAP Reconciliation | Reconciliation of MAP and UK-Link held data SCP 467 – Market Participant MDD Migration to UNC Governance UNC Modification 0682 - Market Participant MDD Migration to UNC Governance from the SPAA UNC Modification 0684 - Amendment of the Data Permission Matrix to add Meter Asset Provider as a new User type DSC Change XRN 4851 |  |  | G | Feb 2020 | Feb 2020 | • ElectraLink has provided MAP information, as contained in the SPAA Market Participants MDD, to Xoserve for incorporation into central systems • Following the recommendations of the Joint MDD Migration Working Group, the Market Participants MDD will be migrating to UNC governance with the creation/administration of Market Participants data administered by Xoserve from February 2020 (provisional date) • Change Proposals/Modifications to SPAA, UNC, IGT UNC and the Data Service Contract (DSC) have been raised to implement this change and MAP data will be included in central systems as part of this change
Monitoring of Flow Rejections | CP17/406 implementation - introduction of an explicit requirement on Suppliers, Agents and Gas Transporters to monitor flow rejections and either resend the information or follow the exception process set out in the relevant sections of the RGMA baseline document |  |  | C | 2018-06-28 | 2018-06-28 | A common cause of rejections was the use of incorrect date formats flowing from historic records. On-going support now being provided by ElectraLink on an ad-hoc basis and by exception, where rejections occur.
Supplier / MAM validation of meter details | CP17/411 (Updates to Schedule 22 with specific reference to Section 7- Suppliers Reporting Obligations) implementation |  |  | C | 2018-11-02 | 2018-11-02 | CP17/411 introduced a new obligation for Suppliers to notify Xoserve (via their Shipper) of the appointed MAM on Change of Supplier
| Assurance reporting - detailing the volume of ONJOB, ONUPD and K08 transactions (those relating to MAM appointment) and shows the number of such flows, by Supplier, that have either been accepted or rejected and whether the flows have been submitted within required timescales |  |  | G | 2019-01-01 | 2019-01-01 | An anonymised version of the reporting is now being reviewed on a monthly basis by the SPAA Experts Group
Meter Model Table cleansing (exchange of meter details following change of MAM or new asset installation) | SPAA review of the Meter Product Table |  |  | G |  | 2019-03-01
| SPAA Change Proposal to remove inconsistent or blank values from the MDD Meter Product Table |  |  |  |  | 2019-04-01
Xoserve review of domains and logical formats of metering data held in UK Link with a view to ensuring this is aligned with other industry data

## Electricity
Switching Programme: Data Working Group Progress Report |  |  |  |  | Electricity | 2019-03-01
Data Cleansing
| Baseline Position | Current Position
Plot to Postal Addresses | 2018-04-01 | 2019-01-01 | Commentary
Suppliers: - Large | 136969 | 95010 | For 04/01/2019, Large Suppliers contribute to 84% of all instances of Plot to Postal MPANs with the remaining 16% made from Medium and Small Suppliers. The total instances of Plot to Postal count has decreased in the past 12 months from 161,507 to 113,075. The proportion of all MPANs worked is led by large Suppliers who account for a 30% reduction in total instances in the past 12 months, this is followed by Medium Suppliers with 28% and Small Suppliers with 25%
Suppliers: - Medium | 10666 | 7654
Suppliers: - Small | 13872 | 10411
| Baseline Position | Current Position
Related MPAN Cleanse 3B | 2019-10-01 | 2019-02-01 | Commentary
Suppliers: - Large | 6470 | 5806 | For 01/02/2019, Large Suppliers contribute to 61% of all instances of report 3b MPANs with Medium Suppliers at 18% and Small Suppliers at 21%. The total instances of report 3b Related MPANs has decreased in the past four months from 10,074 to 9,473. The proportion of all MPANs worked is led by large Suppliers who account for a 30% reduction in total instances in the past 12 months, this is followed by Medium Suppliers with 28% and Small Suppliers with 25%. The average count of Report 3b Related MPANs has decreased from 129 to 117 MPANs and single largest instance has also decreased from 1,734 to 1,475 MPANs
Suppliers: - Medium | 1463 | 1685
Suppliers: - Small | 2141 | 1982
Related MPAN Cleanse 4A | 2019-10-01 | 2019-02-01 | Commentary
Suppliers: - Large | 24761 | 21634 | For 01/02/2019, Large Suppliers contribute to 80% of all instances of report 4a MPANs with Medium Suppliers at 10% and Small Suppliers at 10%. The total instances of report 4a Related MPANs has decreased in the past four months from 30,805 to 27,110 MPANs. The proportion of MPANs worked was led by large Suppliers who account for a 13% reduction in total instances in the past four months, this is followed by Small Suppliers with 11% and Medium Suppliers with 7%. The average count of Report 4a Related MPANs has decreased from 371 to 334 MPANs and single largest instance has also decreased from 11,019 to 9,103 MPANs
Suppliers: - Medium | 2844 | 2633
Suppliers: - Small | 3200 | 2843
Related MPAN Cleanse 5B | 2019-10-01 | 2019-02-01 | Commentary
Suppliers: - Large | 70022 | 61425 | For 01/02/2019, Large Suppliers contribute to 82% of all instances of report 5b MPANs with Medium Suppliers at 5% and Small Suppliers at 12%. The total instances of report 5b Related MPANs has decreased in the past four months from 83,936 to 74,874 MPANs. The proportion of MPANs worked was led by Medium Suppliers who account for a 25% reduction in total instances in the past four months, this is followed by Large Suppliers with 12%. The average count of Report 5b Related MPANs has decreased from 953 to 850 MPANs and single largest instance has also decreased from 25,837 to 18,990 MPANs.
Suppliers: - Medium | 5655 | 4241
Suppliers: - Small | 8259 | 9208
Related MPAN Cleanse 6A | (10-2018) | (02-2019) | Commentary
Suppliers: - Large | 65643 | 65739 | For 01/02/2019, Large Suppliers contribute to 90% of all instances of report 6a MPANs with Medium Suppliers at 4% and Small Suppliers at 6%. The total instances of report 6a Related MPANs has decreased in the past four months by 29 from 83,936 to 74,874 MPANs. The proportion of MPANs worked was led by Small Suppliers who account for a 10% reduction in total instances in the past four months from October 2018 to February 2019. Both Large and Medium Suppliers has seen an increase of 0.15% and 12% respectively in the same time period. The average count of Report 6a Related MPANs has remained relatively static at 1,074 MPANs and single largest instance has decreased from 23,975 to 23,418 MPANs.
Suppliers: - Medium | 2756 | 3095
Suppliers: - Small | 4633 | 4169
Related MPAN Cleanse 6B | 2019-10-01 | 2019-02-01 | Commentary
Suppliers: - Large | 16587 | 15687 | For 01/02/2019, Large Suppliers contribute to 73% of all instances of report 6b MPANs with Medium Suppliers at 12% and Small Suppliers at 14%. The total instances of report 6b Related MPANs has decreased in the past four months by 1,023 from 22,341 to 21,318 MPANs. The proportion of MPANs worked was led by Small Suppliers who account for a 10% reduction in total instances in the past four months and is followed by Large Suppliers at 5% from October 2018 to February 2019. Medium Suppliers have seen an increase of 9% for the same period. The average count of Report 6b Related MPANs has decreased from 253 to 242 MPANs and single largest instance has also decreased from 3,722to 3,346 MPANs.
Suppliers: - Medium | 2366 | 2582
Suppliers: - Small | 3388 | 3049
Top Line MTD Cleanse | (mm-2018) | (mm-2019) | Commentary
Suppliers: - Large
Suppliers: - Medium
Suppliers: - Small
| Baseline Position | Current Position
MTR-Type -Mismatch | (mm-2018) | (mm-2019) | Commentary
Suppliers: - Large
Suppliers: - Medium
Suppliers: - Small
| Baseline Position | Current Position
NO-MTR-MTC | (mm-2018) | (mm-2019) | Commentary
Suppliers: - Large
Suppliers: - Medium
Suppliers: - Small
|  |  |  | RAG | Completion Date
|  |  |  | Status | Baseline | Forecast | Commentary
Consequential Changes
Update of Meter Details to MPAS (DTC CP 3554) | Implementation / testing of data flow changes |  |  | A/G | 2019-06-28 |  | Following the approval of DTC CP3554 (Update of Meter Details to MPAS), Industry will need to be prepared to issue Meter details via the D0312 and D0304 data flows to MPAS, instead of the current route of ECOES. The vast majority of these changes will occur with the existing service providers for ECOES and MPRS in order to integrate the current systems together with the obligation underpinning MOP activities being borne out through BSCP1515, currently out for consultation within industry. Changes to response codes on D0312/304 flows are to be defined in further consequential CPs with MPRS Validation Rules document due for release in April 2019.
| Implementation / testing of updated business processes for operations |  |  | A/G
| Execution of initial data migration |  |  | G | 2019-06-28 | 2019-06-28
Data Item Creation
Related MPANs | Related MPAN Data Item creation - MRA CP0256 |  |  | A/G | 2019-06-28 | 2019-06-28 | Following the approval of MRA CP0256, Industry will need to prepare their data for the new indicator for Related Metering Associations for the CSS. The new indicator will need to define the 'Primary' MPAN.
| Related MPAN Data Flow creation & amendments DTC CP 3550 |  |  | A/G
| Related MPAN transformation/update/operational processes |  |  | G | 2019-06-28 | 2019-06-28
Licence Exempt Network (LEN) indicator | LEN indicator creation - CP TBC |  |  | A/G |  |  | No CP to raise through FSEG. Has been passed to IREG for progression at their meeting on 10 April 2019
Import / Export indicator | Raising & consideration of programme Change Request |  |  | A/G |  |  | Is on agenda for the next Design Forum Group on 25 March 2019
Import / Export indicator | Import / Export indicator creation CP |  |  | A/G | 2020-02-01 | 2020-02-01 | CP still to be progressed for this change. Sponsor agreed at FSEG 12 Feb 2019. Next steps liaise with industry for a February 2020 implementation date. Update expected at FSEG 2 April 2019
Domestic/Non-Domestic indicator | Domestic/Non Domestic indicator creation - DTC CP 3556 |  |  | G | 2019-06-28 | 2019-06-28 | Accepted on 29/11/2018. Awaiting Implementation on 27/06/2019
Domestic/Non Domestic indicator data transformation
RMP Status indicator | RMP Status Data Item creation - DTC CP 3555 |  |  | G | 2019-06-28 | 2019-06-28 | Accepted on 29/11/2018. Awaiting Implementation on 27/06/2019
RMP Status transformation
Metered Status Indicator | Metered Indicator Item Creation - DTC CP3557 |  |  | G | 2019-06-28 | 2019-06-28 | Accepted on 29/11/2018. Awaiting Implementation on 27/06/2019
Metered Indicator transformation
Other
Meter Point Address Data | Review of Meter Point address data
Identification of incomplete addresses - non Plot
ECOES DBT Activity
Erroneous Switch indicator | Erroneous Switch indicator Data Item creation - CP TBC |  |  | A/G |  |  | CP still to be progressed for this change
REL Process | Creation, testing & implementation of new processes to hold a location address |  |  | A/G |  |  | CSSP / Address Service Provider to be procured and recommendations to be made.

## RAG
Switching Programme: Data Working Group Progress Report |  | Electricity | mmm-yy
C | Development completed and product/output approved
R | Significant risk to delivery – immediate mitigation required
A/R | Increased risk to delivery – urgent mitigation required
A | Delivery at risk/uncertain – manageable with mitigation
A/G | On track – successful delivery probable but being closely monitored
G | On track – successful delivery likely
N/S | Not Started