## Definitions
SWITCHING PROGRAMME RISK MANGEMENT WORKBOOK
This page shows the definitions of various fields and attributes in this workbook.
Risk Themes
1 | Average Weighted Risk Calculation:
| Severity | Severity Weighting | Likelihood | Likelihood Weighting | Proximity | Proximity Weighting | AVG Weighted Risk Rating | Risk Theme Average Weighted Risk (Ranges) | Risk Theme RAG rating
| 5 | 3 | 5 | 5 | Imminent (less than 1 month) | 1 | AVG (Severity X Severity Weighting X Likelihood X Likelihood Weighting X Proximity Weighting) | Over 30 | Very High
| 4 | 2 | 4 | 3 | Short Term (1-3 months) | 1 |  | Over 20 | High
| 3 | 1 | 3 | 1 | Medium Term (4-6 months) | 0.5 |  | Over 10 | Medium
| 2 | 1 | 2 | 1 | Long Term (7 months or more) | 0.3 |  | Over 5 | Low
| 1 | 1 | 1 | 1 |  |  |  | Under 5 | Very Low
[8 empty] | 0 or all risks closed | All Closed
Risk Register
1 | Risk Rating Categorisation:
LIKELIHOOD
| SEVERITY | 1- Rare Highly Improbable that it will occur during the lifetime of the project | 2 - Unlikely Not probable that it will occur during the lifetime of the project | 3 - Possible As likely as it is unlikely that the event will occur | 4- Likely Probable that it will occur during the lifetime of the project | 5 - Almost Certain High expectation that it will occur during the lifetime of the project
| 5 - Significant | Medium | High | High | Very High | Very High
| 4 - Major | Medium | Medium | High | High | Very High
| 3 - Moderate | Low | Low | Medium | High | High
| 2 - Minor | Very Low | Low | Low | Medium | Medium
| 1 - Insignificant | Very Low | Very Low | Low | Low | Low
2 | Risk Proximity: Imminent (less than 1 month), Short Term (1-3 months), Medium Term (4-6 months), Long Term (7 months or more)
3 | Stakeholder Governance Ownership: The governance forums that will hold ownership of the risk once the programme moves to other phases
Version Control
| Version | Date | Description of Change
| 0.1 | 2018-10-26 | Initial draft
| 0.2 | 2018-10-29 | Trends reporting included in 'Risk Themes'; workstream options added to 'Risk Register',Severity/Likelihood text fields,
| 0.3 | 2018-10-31 | Formatting of RAGs changed to gradients

## Risk themes
DATA RISK THEME REPORTING | Risk Theme | Theme Description | Theme Rating | Risk Trend | Summary Progress Update
TO DATA WORKING GROUP Click on Risk Theme name to show the detailed risk lines associated with theme rating | Industry Engagement & Planning | Risks in relation to industry engagement with data related activity including cleansing as well as clarity/achievability on planning | Medium | ó | * Data Working Group stood up early in advance of DBT phase with good representation from across industry. * Progress reporting in development for DWG which will be shared with Implementation Group. * Ofgem / Programme Coordinator to work with ESPs to identify and address industry parties where greater engagement / activity is required. * Industry and Ofgem planning is progressing, with further detail to come when DBT plan is baselined in May.
| Existing System Changes & Transitions | Risks in relation to implemention of changes to existing systems (MPAS/ECOES/UK LINK) ahead of transition stage 1. Includes creation of new data items/indicators and data migration. | Medium | ó | * Work ongoing across existing industry systems to progress Stage 0 changes. * Major MPRS release scheduled for June - system changes on track for delivery but some uncertainty on cutover process for related MPAN change. * Concerns over BSC SVG approval of BSC 1515 change proposal - currently engaging with Elexon to explore potential actions to support change process. * MAP ID field to be included in UK Link in July with transfer to Xoserve of mastery of Supplier/Shipper mapping on track for February 20.
ñ | CSS Transition & Migration | Risks in relation to data migration and transition activity to CSS. This includes management of in-flight switches, delta loads and any temporary interfaces. | Very Low | ó | * Data Assurance Framework in development which will seek to address many risks in this theme. * Risks to be reviewed further with completion of physical design. * SI mobilisation in progress ahead of further development of data migration/transition approach and plans.
ò | Data Quality & Cleansing | Risks in relation to cleansing of industry data ahead of transition stage 1 and all aspects of data quality. | Low | ó | * Data Working Group to commence monitoring of progress on data cleansing activity, with escalation to Implementation Group as necessary. * Electricity MAP ID data quality issues identified ahead of ECOES-MPAS migration, cleansing approach developed by C&C and awaiting approval by FSEG. * LDM Spreadsheet with existing industry data mapping developed and to be shared at March DWG with further cleanse prioritisation to follow.
ó | Address Matching & REL Creation | Risks in relation to the address matching and REL creation and update process. Includes rules, formats, standards and address testing. | Low | ó | * Plot to Postal address cleansing in progress across both electricity and gas systems. * Profiling of addresses in UK Link completed to identify address quality issues with shipper portfolio reporting to commence to assist cleanse. Similar activity to be required in electricity. * Early engagement with Address Service provider planned to support address match/REL creation approach.
| Design (Logical & Physical) | Risks is relation to data impacts of design both logical and physical. Includes management of change, adaptability, interface design as well as capability. | Medium | ó | * Change Requests to update Logical Data Model (ABACUS) are in progress which will address issues previously identified. * Data Management Principles developed and in review to provide clarity on design approach, roles & responsibilities, cleansing and quality.
| GDPR & Security | Risks in relation to industry data in the context of GDPR and broader information security. | Very Low | ó | * Programme Privacy Impact Assessment (PIA) & Information Risk Assessment (IRA) currently in review with recommendations to follow. * Programme Security Advisory Group being stood up. * Testing working group to be stood up during May - plan close working in relation to test data.

## >>INSTRUCTIONS (hidden)
>> Instructions for completing the Risk Register
1 | Column A - Risk ID. Sequentially give the new risk an ID. Please make sure it has an 'R' followed by 3 digits. For instance R001 or R099
2 | Column B - Risk Theme. Choose Risk theme from the drop down list of options
3 | Column C - Theme Description. PLEASE DON'T TOUCH or COPY & PASTE into this column. Field will populate automatically. Copy and Paste or typing will break the formula.
4 | Column D - Risk Description. Copy and Paste from previous Risk Register or type it in directly.
5 | Column E - Risk Category. Choose Risk Category from the drop down list of options.
6 | Column F - Risk Proximity. Choose Risk Proximity from the drop down list of options.
7 | Column G - Controls in Place. Copy and Paste from previous Risk Register or type it in directly.
8 | Column H - Severity. Type in agreed severity, following the definitions set out on the 'DEFINITIONS' tab. | Click here for DEFINITIONS tab
9 | Column J - Likelihood. Type in agreed likelihood, following the definitions set out on the 'DEFINITIONS' tab. | Click here for DEFINITIONS tab
10 | Column L - Risk Rating. PLEASE DON'T TOUCH or COPY & PASTE into this column. Field will populate automatically. Copy and Paste or typing will break the formula.
11 | Column N - Associated Actions. Type in Action Reference numbers of the actions on Action Log that are associated with the Risk in question. For instance A019, A021, A099
12 | Column O - Summary Progress Update. Type in the date of progress update first and then proceed to populate a summary. For the next update simply type Alt+Enter to create a new tab in the cell.
13 | Column P - GEMA Tier 1. Choose Y or N from drop down list of options
14 | Column Q - New Risk. Choose Y or N from drop down list of options
15 | Column R - Escalate to PM. Choose Y or N from drop down list of options
16 | Column S - Open/ Closed. Choose Open or Closed from drop down list of options
17 | Column T - Stakeholder Governance Ownership. A list of Options will be created. For the meantime please type in the governance group that will own this risk in the next phases of the programme.

## Master Risk Register
OFGEM Switching Programme Risk Register | [6 empty] | PROTECT SHEET WHEN DONE
Risk ID | Risk Theme | Theme Description (DON'T PASTE VALUES IN) (This field auto populates) | Risk Description (Including potential consequences) | Risk Category | Workstream | Risk Proximity | Controls in Place | Severity | Severity Score | Weighted Severity | Likelihood | Likelihood Score | Weighted Likelihood | Risk Score | Weighted RiskScore | Associated Actions | Summary Progress Update for Period | Risk Owner | Date Risk was raised | RESIDUAL RISK Severity | RESIDUAL Severity Score | RESIDUAL RISK Likelihood | RESIDUAL Likelihood Score | RESIDUAL Risk Score | DCC Risks | Stakeholder Governance Ownership | GEMA Tier 1 | Please Note Updates to Severity & Likelihood | Open /Closed | Extra Notes | Proximity Value
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
NR16 | Existing System Changes & Transitions |  | There is a risk that consequential change BSC CP1515 which supports the ECOES/MPRS migration is not approved. This could potentially delay the DTC change or mean that MOPs procedures may be out of step with system changes. |  | Data | Imminent (less than 1 month) | * MRA guidance note produced for MOPs detailing the new changes. | Major | 4 | 2 | Possible | 3 | 1 | 12 | 24 |  | 1) Ofgem engagement with Elexon to consider options to support approval by SVG on 2 April. | FSEG/Elexon | 2019-03-12 |  | 0 |  | 0 | 0 |  | Data WG |  |  | Open |  | 0
NR02 | Existing System Changes & Transitions |  | Related MPAN Migration - There is a risk that the related MPAN migration may be delayed due to system change delays or insufficient progress on cleansing activity |  | Data | Short Term (1-3 months) | * Gemserv & SCS PM of migration project | Major | 4 | 2 | Possible | 3 | 1 | 12 | 24 |  | 1) DWG to track progress on system changes and data cleansing with FSEG to progress further remedial actions as necessary - ongoing 2) Gemserv & SCS to agree and publish GONG approach/criteria at FSEG. _March 2019 | FSEG | 2019-02-21 |  | 0 |  | 0 | 0 |  | Data WG |  |  | Open |  | 1
NR11 | Design (Logical & Physical) |  | Logical Data Model - There is a risk that the LDM does not fully support the data requirements of all sites or ESP functions. This could result in the incorrect specification of the physical design and interfaces leading to change and delay. |  | Data | Short Term (1-3 months) | * DWG / FSEG and industry reviews of LDM | Major | 4 | 2 | Possible | 3 | 1 | 12 | 24 |  | 1) Final review of LDM mapping to complete in March 2) Change requests in progress to update LDM following industry feedback - April 2019 | Andrew Amato | 2019-02-21 |  | 0 |  | 0 | 0 |  | Data WG |  |  | Open |  | 1
NR04 | Address Matching & REL Creation |  | Address Matching - There is a risk that REL creation is delayed and quality compromised by uncertainty over address standards, format and rules. |  | Data | Medium Term (4-6 months) | * Planned Data Assurance activity to be undertaken | Major | 4 | 2 | Possible | 3 | 1 | 12 | 12 |  | 1) Ofgem to engage with Address Service Provider once appointed to provide clarity to DWG on addresing approach - April 2019 2) Specific Data Assurance Deep Dive planned (in Data Assurance Framework) over Address Matching (ahead of industry testing) | Andrew Amato | 2019-02-21 |  | 0 |  | 0 | 0 |  | Data WG |  |  | Open |  | 3
NR05 | Industry Engagement & Planning |  | Industry Engagment - There is a risk of a lack of engagement from some industry parties in data cleanse activity. This could result in insufficient progress causing delay to subsequent programme activity. |  | Data | Medium Term (4-6 months) | * Early formation of DWG to drive engagement * Programme Cooordinator Industry Coordination function | Major | 4 | 2 | Possible | 3 | 1 | 12 | 12 |  | 1) Gemserv & Xoserve to identify parties not engaging in cleanse activity and agree appropriate response with Ofgem - Ongoing 2) Licensed Party Assurance provider will review progress on data quality and data remediation activities | Andrew Amato | 2019-02-21 |  | 0 |  | 0 | 0 |  | Data WG |  |  | Open | Key at physical design stage, regarding design/build especially with smaller suppliers. | 3
NR08 | Design (Logical & Physical) |  | Data Understanding/Derivation/Sourcing - There is a risk that the LDM/PDM is misunderstood leading to confusion around cleansing and migration responsibilities and CSS data being derived or mapped incorrectly resulting in errors in migration, data quality issues and delay. |  | Data | Medium Term (4-6 months) | * Data ownership and data stewardship being defined for each data item. Data owner is responsible for specifying data standards to meet CSS requirements and Data steward is responsible for ensuring data meets those standard. * DWG / FSEG and industry reviews of LDM | Major | 4 | 2 | Possible | 3 | 1 | 12 | 12 |  | 1) Agreement of LDM data mapping to existing data - March 2019 2) Agreement of PDM data mapping to existing data - August 2019 3) Query management process (to be implemented with SI), with technology to help with common questions 4) Opportunity within Data Working Group to raise issues and concerns in relation to the data model if no answer obtained from the above | Andrew Amato | 2019-02-21 |  | 0 |  | 0 | 0 |  | Data WG |  |  | Open |  | 3
NR12 | Design (Logical & Physical) |  | Physical design of messaging to and from the CSS may require time stamping of data (in order to meet objection and other processing windows) that industry participants and existing system providers are not currently geared to provide or consume, leading to delays whilst they make changes to their systems. (note overlap with design risks) |  | Data | Medium Term (4-6 months) | * Review the requirement for time stamping during physical design of messages and extent to which this can be built into the interface. | Major | 4 | 2 | Possible | 3 | 1 | 12 | 12 |  | 1) Early engagement of CSS provider and SI in explaining needs of messaging in physical design to meet next day switching requirements and facilitation with industry to develop a practical working solution | Andrew Amato | 2019-02-21 |  | 0 |  | 0 | 0 |  | Data WG |  |  | Open |  | 3
R058 | Data Quality & Cleansing |  | There is a risk that the Programme will rely on Data Transformation Rules as a method for data cleansing placing the risk of meeting data reliability at Go Live rather than in advance of Go Live. |  | Data | Medium Term (4-6 months) | * Development of Data Principles | Moderate | 3 | 1 | Possible | 3 | 1 | 9 | 4.5 |  | 1) Core Systems Assurance Provider should plan to monitor progress on this risk - May 2019 | Andrew Amato | 2018-11-15 |  | 0 |  | 0 | 0 |  | Data WG |  |  | Open | Aware that new items are being created with derived data but may need further cleansing | 3
R083 | Data Quality & Cleansing |  | If the industry fails to progress data improvement activity to the required quality and timeline, it may introduce a delay to subsequent phases and ultimately may impact the ability of the Programme to go-live. This covers a series of root causes including lack of engagement, lack of industry resource, failure to (successfully) execute on data cleansing/improvement plans) |  | Data | Medium Term (4-6 months) | * DWG reporting to monitor cleanse progress and escalate as necessary. | Major | 4 | 2 | Possible | 3 | 1 | 12 | 12 |  | 1) Tracking of progress of data cleansing activity through DWG with escalations to Implementation Group (as required) - Ongoing 2) Assurance over data cleansing activities by Licensed Party Assurance Provider - Ongoing | Andrew Amato | 2018-12-19 |  | 0 |  | 0 | 0 |  | Data WG |  |  | Open |  | 3
NR10 | CSS Transition & Migration |  | Inflight Switches - There is a risk that all scenarios may not have been fully considered. This could lead to issues at go live leading to delay and/or poor customer experience. |  | Data | Long Term (7 months or more) | * Existing E2E Transition plans to be updated by SI | Major | 4 | 2 | Possible | 3 | 1 | 12 | 7.2 |  | 1) E2E Transition Plan - inflight switches policy paper shared with DWG - to be discussed at future meeting during physical design development - June 2019 2) In-flights data assurance deep dive (by CSS Provider/Programme Coordinator) - to be scheduled | Andrew Amato | 2019-02-21 |  | 0 |  | 0 | 0 |  | Data WG |  |  | Open |  | 4
NR13 | CSS Transition & Migration |  | Quality of data on de-energised sites results in erroneous or obsolete address records being brought forward |  | Data | Long Term (7 months or more) | * Proposed data principle that de-energised sites are not brought forward into CSS | Moderate | 3 | 1 | Possible | 3 | 1 | 9 | 2.7 |  | 1) Continue existing activity to monitor de-energised and potentially deenergised sites (Gemserv providing an aged list for market participants to review) - ongoing | Andrew Amato | 2019-02-21 |  | 0 |  | 0 | 0 |  | Data WG |  |  | Open |  | 4
R026 | Data Quality & Cleansing |  | There is a risk that data improvement work (in particular Data Remedy One) fails to deliver expected improvement in switching reliability. This could result in the new switching arrangements are not as reliable as expected, with loss of confidence from consumers and policymakers. |  | Data | Long Term (7 months or more) | * Creation and early mobilisation of Data Working Group (DWG) to monitor industry progress and ongoing risks with escalation as necessary | Major | 4 | 2 | Possible | 3 | 1 | 12 | 7.2 |  | 1) Tracking of progress of data cleansing activity through DWG with escalations to Implementation Group (as required) - Ongoing 2) Early engagement planned with Address Service provider to gain insight to plans/approach and share with DWG - April 2019 | Andrew Amato | 2018-11-15 |  | 0 |  | 0 | 0 |  | Data WG |  |  | Open |  | 4
R056 | CSS Transition & Migration |  | There is a risk that suppliers, shippers & ESPs do not have the ability (capacity) to make changes to their systems to accommodate changes to data to meet CSS timescales. |  | Data | Long Term (7 months or more) | * Impacted shippers, suppliers & ESPs should be engaged at an early stage so that they can plan and provide information about when they can make the changes. * Data changes should be designed, planned and monitored by the Data Working Group. | Major | 4 | 2 | Possible | 3 | 1 | 12 | 7.2 |  | 1) Tracking of activity & progress via Industry Coordination function & DWG - Ongoing 2) Core Systems Assurance Provider should plan to monitor progress on this risk - May 2019 | Andrew Amato | 2018-11-15 |  | 0 |  | 0 | 0 |  | Data WG |  |  | Open |  | 4
R066 | CSS Transition & Migration |  | There is a risk that the level of data validation and review will be compromised by the approach taken for managing Delta loads during transition. This could lead to go-live delays or future data quality issues. |  | Data | Long Term (7 months or more) | * Data Migration Approach, Data Principles - these will need to be applied by the SI and CSS Provider | Major | 4 | 2 | Possible | 3 | 1 | 12 | 7.2 |  | 1) Specific Data Assurance Deep Dive planned (in Data Assurance Framework) over approach and results of major data loads | Andrew Amato | 2018-11-15 |  | 0 |  | 0 | 0 |  | Data WG |  |  | Open | RMP data will be loaded into CSS at Stage 1. This will then have to be kept up to date by a series of delta loads up to and including the cutover process. There is tension between the desire to compress stages 1 to 3 and minimise the number/extent of delta loads (which the DCC would like) and the need to ensure that there is appropriate validation and review, especially of other data loads and builds in Stage 2 (including address data). | 4
R067 | CSS Transition & Migration |  | Performance of delta loads can be difficult to manage as they often require search for a small number of (changed) records in a large database, which, for many databases is performance intensive. Poorly designed or planned data loads could impact the performance of existing systems with the risk that they exceed the available overnight window. |  | Data | Long Term (7 months or more) | Data Migration Approach, Data Principles - these will need to be applied by the SI and CSS Provider | Major | 4 | 2 | Possible | 3 | 1 | 12 | 7.2 |  | 1) Specific Data Assurance Deep Dive planned (in Data Assurance Framework) over approach and results of major data loads | Andrew Amato | 2018-11-15 |  | 0 |  | 0 | 0 |  | Data WG |  |  | Open |  | 4
NR01 | Existing System Changes & Transitions |  | Related MPAN Migration - There is a risk that data quality within MPRS is compromised by due to uncertainty around go-live approach for the DTC CP 3550 implementation. |  | Data | Short Term (1-3 months) | * Gemserv & SCS PM of migration project | Moderate | 3 | 1 | Possible | 3 | 1 | 9 | 9 |  | 1) Agreed cutover approach via FSEG (Gemserv & SCS) - April 2019 2) Gemserv to consider need for further related MPAN cleansing guidance - April 2019 | FSEG | 2019-02-21 |  | 0 |  | 0 | 0 |  | Data WG |  |  | Open |  | 1
NR03 | Data Quality & Cleansing |  | ECOES - MPAS Migration - There is a risk that data quality within MPRS is compromised due to incorrect MAP ID currently in ECOES not being cleansed prior to DTC CP 3554. |  | Data | Short Term (1-3 months) | * Gemserv & SCS PM of migration project | Moderate | 3 | 1 | Possible | 3 | 1 | 9 | 9 |  | 1) FSEG to agree and implement data cleanse approach - March 2019 | FSEG | 2019-02-21 |  | 0 |  | 0 | 0 |  | Data WG |  |  | Open |  | 1
R068 | Industry Engagement & Planning |  | MOP Engagement - There is a risk that MOPs do not understand changes arising from DTC CP 3554 and therefore do not properly fulfil their obligations leading to data quality issues |  | Data | Short Term (1-3 months) | * MRA guidance * BSC CP 1515 requirements | Moderate | 3 | 1 | Possible | 3 | 1 | 9 | 9 |  | 1) FSEG to produce MOP guidance on use of amended DTC flows. - March 2) Suppliers to engage with their agents to ensure awareness of changes and that resposibilities are undertstood and carried out (DWG04-A03) - ongoing | FSEG/Suppliers | 2018-11-15 |  | 0 |  | 0 | 0 |  | Data WG |  |  | Open |  | 1
NR09 | Design (Logical & Physical) |  | Full Physical Design - There is a risk that the completion of the Full Physical Design identifies new data cleanse items or rework of existing activity. This could result in delay if cleansing activity is required ahead of Transition Stage 1. |  | Data | Medium Term (4-6 months) | * DWG engagement with CSS Provider | Moderate | 3 | 1 | Possible | 3 | 1 | 9 | 4.5 |  | 1) Ofgem to engage with CSS Provider once appointed to provide clarity to DWG on approach to physical design - April 2019 2) CSS Provider to publish fundamental changes in assumptions between the logical and physical data model & subsequent discussion in DWG - July 2019 | Andrew Amato | 2019-02-21 |  | 0 |  | 0 | 0 |  | Data WG |  |  | Open |  | 3
NR15 | Data Quality & Cleansing |  | Failure to understand and define accountabilities in regards to Data. (managed through Data Working Group) |  | Data | Long Term (7 months or more) | * Data ownership and data stewardship being defined for each data item. | Moderate | 3 | 1 | Possible | 3 | 1 | 9 | 2.7 |  | 1) Tracking of progress of data cleansing activity through DWG with escalations to Implementation Group (as required) - Ongoing 2) Assurance over data cleansing activities by Licensed Party Assurance Provider - Ongoing | Andrew Amato | 2019-02-21 |  | 0 |  | 0 | 0 |  | Data WG |  |  | Open | Data owner is responsible for specifying data standards to meet CSS requirements and Data steward is responsible for ensuring data meets those standard. | 4
R064 | CSS Transition & Migration |  | There is a risk that the level of validation and review for data loads in Stage 1 will be compromised. |  | Data | Long Term (7 months or more) | * System Integrator appointed to manage system Cutover Process | Moderate | 3 | 1 | Possible | 3 | 1 | 9 | 2.7 |  | 1) Specific Data Assurance Deep Dive planned (in Data Assurance Framework) over approach to in-flights transition | Andrew Amato | 2018-11-15 |  | 0 |  | 0 | 0 |  | Data WG |  |  | Open |  | 4
R065 | CSS Transition & Migration |  | There is a risk that as a result of the inflights approach that during the intial days of go live when there is an increased workload of switches to push through that trying to run backlog processes in the middle of on-line switch submissions could cause contention for system resources, and have an impact on performance out of proportion to the additional volume of transactions processed. |  | Data | Long Term (7 months or more) | * Testing of in-flights approach prior to go-live | Moderate | 3 | 1 | Possible | 3 | 1 | 9 | 2.7 |  | 1) Specific Data Assurance Deep Dive planned (in Data Assurance Framework) over approach and results of major data loads | Andrew Amato | 2018-11-15 |  | 0 |  | 0 | 0 |  | Data WG |  |  | Open |  | 4
R095 | CSS Transition & Migration |  | If the central master data migration log is not appropriately maintained, it may not hold an accurate and up to date view of the master data requirements. As a result, programme participants may be conducting activity which is based on inaccurate information or may not be required. This may lead to issues during key phases of the programme or post Go-live resulting in impacts to consumers or other industry participants |  | Data | Long Term (7 months or more) | * Data migration approach / tools to be developed by SI | Moderate | 3 | 1 | Possible | 3 | 1 | 9 | 2.7 |  | 1) Specific Data Assurance Deep Dive planned (in Data Assurance Framework) over approach and results of major data loads | Andrew Amato | 2018-12-19 |  | 0 |  | 0 | 0 |  | Data WG |  |  | Open |  | 4
R061 | Existing System Changes & Transitions |  | There is a risk that MPAS provider (St Clements) fails update their applications and successfully migrate Meter Asset Data or implement other required changes. |  | Data | Short Term (1-3 months) | * FSEG & DWG progress monitoring | Major | 4 | 2 | Unlikely | 2 | 1 | 8 | 16 |  | 1) Core Systems Assurance Provider should plan to monitor progress on this risk - May 2019 2) If there are issues in Existing Systems that would have a data impact then these should be detected by End to End Testing and User Entry Process Testing (UEPT) that are planned to use actual data (obfuscated if required) which will identify hidden data issues. (To be scheduled) | Andrew Amato | 2018-11-15 |  | 0 |  | 0 | 0 |  | Data WG |  |  | Open | This could create impact the critical path (the chances of at least 1 out of 26 DNO migrations failing, even if they are in theory, all based on the same data model, are high). | 1
NR14 | Design (Logical & Physical) |  | There is a risk that proposed changes to the messaging model (e.g. removal of RMP) will restrict future adaptability. |  | Data | Medium Term (4-6 months) | * Design Authority to review all changes to assess whether they impact adapability | Major | 4 | 2 | Unlikely | 2 | 1 | 8 | 8 |  | Not at DWG risk but included here for completeness - to be managed by Design workstream | Jenny Boothe | 2019-02-21 |  | 0 |  | 0 | 0 |  | Data WG |  |  | Open |  | 3
NR06 | Address Matching & REL Creation |  | REL Creation - There is a risk the RELs may be incorrectly derived due to uncertainty on address creation rules and a failure to design/build/test address matching alogrithms correctly. |  | Data | Long Term (7 months or more) | * Planned Data Assurance activity to be undertaken | Major | 4 | 2 | Unlikely | 2 | 1 | 8 | 4.8 |  | 1) Ofgem to engage with Address Service Provider once appointed to provide clarity to DWG on addresing approach - April 2019 2) Specific Data Assurance Deep Dive planned (in Data Assurance Framework) over Address Matching (ahead of industry testing) | Andrew Amato | 2019-02-21 |  | 0 |  | 0 | 0 |  | Data WG |  |  | Open |  | 4
NR07 | Design (Logical & Physical) |  | Data Accountability & Processes - There is a risk that accountabilities and associated processes are not clear for data validation. This could lead to incorrect processes causing quality issues, re-work and delay |  | Data | Long Term (7 months or more) | * Data ownership and data stewardship being defined for each data item. | Major | 4 | 2 | Unlikely | 2 | 1 | 8 | 4.8 |  | 1) LDM / PDM to provide clarity on data mastery - April & July 2019 2) DWG to provide forum to raise/address queries - Ongoing | Andrew Amato | 2019-02-21 |  | 0 |  | 0 | 0 |  | Data WG |  |  | Open | Data owner is responsible for specifying data standards to meet CSS requirements and Data steward is responsible for ensuring data meets those standard. | 4
NR17 | Address Matching & REL Creation |  | REL Creation - Risk that REL creation/update rules inhibit ability to switch where customer has different gas and electricity address where a service provider (e.g. price comparison or flipping site) uses the REL as a source. |  | Data | Long Term (7 months or more) | * Clear REL creation/update rules to be created, reviewed & validated. | Major | 4 | 2 | Unlikely | 2 | 1 | 8 | 4.8 |  | Review REL creation/update rules & CSS design with SI and CSS, Address Service Provider | Andrew Amato | 2019-02-21 |  | 0 |  | 0 | 0 |  | Data WG |  |  | Open |  | 4
R055 | Data Quality & Cleansing |  | There is a risk that a large number of data exceptions will occur post go-live and therefore causes a delay to the move from 5 days to next day switching |  | Data | Long Term (7 months or more) | * Specific Programme Coordinator Work Packages to provide assurance. * Validation/tests of data will be conducted post-cleansing of data and pre-migration of data. | Major | 4 | 2 | Unlikely | 2 | 1 | 8 | 4.8 |  | 1) Data assurance plan in development - May 2019. This will involve a structured set of activities to ensure progressive improvement in data quality 2) End to End Testing and User Entry Process Testing (UEPT) are planned to use actual data (obfuscated if required) which will identify hidden data issues. (To be scheduled) 3) DWG to help prioritise any (if any) issues that arise from testing (To be scheduled) | Andrew Amato | 2018-11-21 |  | 0 |  | 0 | 0 |  | Data WG |  |  | Open |  | 4
R060 | CSS Transition & Migration |  | Individual data loads could be large and take extended periods to run. If these loads fail and that failure is only detected at the end of the run, this could delay the programme, due to the lost time to discover the error, resolve it, and start the run. |  | Data | Long Term (7 months or more) | *DBT Plan contains bulk and delta data loads, as well as trial runs/rehearsals | Major | 4 | 2 | Unlikely | 2 | 1 | 8 | 4.8 |  | 1) Specific Data Assurance Deep Dive planned (in Data Assurance Framework) over approach and results of major data loads | Andrew Amato | 2018-11-15 |  | 0 |  | 0 | 0 |  | Data WG |  |  | Open |  | 4
R062 | CSS Transition & Migration |  | Control over temporary interfaces. There is a risk that the use of temporary point to point interfaces during mgration could lessen validation/reconciliation requirements. |  | Data | Long Term (7 months or more) | * Planned Data Assurance activity | Major | 4 | 2 | Unlikely | 2 | 1 | 8 | 4.8 |  | 1) Core Systems Assurance Provider should plan to monitor progress on this risk - May 2019 | Andrew Amato | 2018-11-15 |  | 0 |  | 0 | 0 |  | Data WG |  |  | Open | CSS Data Migration Plan, Section 3.5.1 considers that some temporary point to point interfaces may be used in migration - There is a risk that this could be misinterpreted and lead to insufficient reconciliation controls. The need for reconciliation is driven by the requirements to prove the migrated data is sufficiently complete, accurate and reliable (including integrity) not by the method in which the data is migrated (although the method may have an impact on the ease of performing the reconciliation, which could be a consideration). | 4
R063 | Design (Logical & Physical) |  | There is a risk that if the preferred approach for Transition is to have dual messaging of RMP data from suppliers to both the CSS and the DSP, then then there would need to be reconciliation controls to make sure that the data accepted by CSS was the same as the data accepted by DSP. |  | Data | Long Term (7 months or more) | * Planned Data Assurance activity | Major | 4 | 2 | Unlikely | 2 | 1 | 8 | 4.8 |  | 1) Review this risk as part of planning deep dives into bulk, delta, and in-flight data migrations | Andrew Amato | 2018-11-15 |  | 0 |  | 0 | 0 |  | Data WG |  |  | Open | It will not be good enough for the suppliers to check they have sent two files, additionally CSS and DSP will need to check that they have each processed all of the records or that they have a consistent set of rejections. | 4
R094 | GDPR & Security |  | GDPR may be used as an reason to delay or not provide data for testing or other key activity which requires an element of data sharing. This may result in delays to the entry of testing phases or compromise effective testing/rehersal for cutover. |  | Data | Long Term (7 months or more) | * Programme PIA/IRA in review & update with recommendations to follow * Programme Security Advisory Group | Major | 4 | 2 | Unlikely | 2 | 1 | 8 | 4.8 |  | 1) Work in conjunction with Testing Assurance to ensure that safeguards (if required) are met 2) Consider preparation of guidance (as necessary) for indsutry parties (SI/Ofgem) | Andrew Amato | 2018-12-19 |  | 0 |  | 0 | 0 |  | Data WG |  |  | Open |  | 4
R057 | Data Quality & Cleansing |  | Data quality rules relating to the physical data model are not published sufficient early, leading to insufficient time for industry participants (existing system providers and potentially wider market participants - suppliers, shippers, DNOs, GTs, iDNOs, iGTs, etc) to cleanse source data. Consequence is delays to programme to reach sufficient data quality for go-live, or higher than expected failed switches due to data issues, leading to concerns over the credibility of the switching service. |  | Data | Long Term (7 months or more) | Note - Faster Switching and CSS is focused on address and registration. As such it should not be impacted by problems with RGMA flows around meter asset data. Risk prioritisation exercise (already commenced) to focus efforts on data issues that are likely to impact switching. | Moderate | 3 | 1 | Unlikely | 2 | 1 | 6 | 1.8 |  | 1) Data prioritisation activity (already commenced) to identify data elements that will impact switching (started and present to DWG April) 2) Tracking of progress of data cleansing activity through DWG with escalations to Implementation Group (as required) - Ongoing 3) Assurance over data cleansing activities by Licensed Party Assurance Provider - Ongoing 4) Specific Data Assurance Deep Dive planned (in Data Assurance Framework) over Address Matching (ahead of industry testing) | Andrew Amato | 2018-11-15 |  | 0 |  | 0 | 0 |  | Data WG |  |  | Open |  | 4
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE
[9 empty] | 0 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | [6 empty] | FALSE

## Action Log (hidden)
Data Working Group Action Log |  |  |  | DRAFT for discussion
Action Ref | Source | Meeting Ref | Associated Risk and Issue | Action Description | Progress Update / Conclusion | Assigned to | Status | Due date | Date Raised | Date Closed | PMO Note | Extra Notes | Last Updated
A299
A300
A301
A302
A303
A304
A305
A306
A307
A308
A309
A310
A311
A312
A313
A314
A315
A316
A317
A318
A319
A320
A321
A322
A323
A324
A325
A326
A327
A328
A329
A330
A331
A332
A333
A334
A335
A336
A337
A338
A339
A340
A341
A342
A343
A344
A345
A346
A347
A348
A349
A350
A351
A352
A353
A354
A355
A356
A357
A358
A359
A360
A361
A362
A363
A364
A365
A366
A367
A368
A369
A370
A371
A372
A373
A374
A375
A376
A377
A378
A379
A380
A381
A382
A383
A384
A385
A386
A387
A388
A389
A390
A391
A392
A393
A394
A395
A396
A397
A398
A399
A400
A401
A402
A403
A404
A405
A406
A407
A408
A409
A410
A411
A412
A413
A414
A415
A416
A417
A418
A419
A420
A421
A422
A423
A424
A425
A426
A427
A428
A429
A430
A431
A432
A433
A434
A435
A436
A437
A438
A439
A440
A441
A442
A443
A444
A445
A446
A447
A448
A449
A450
A451
A452
A453
A454
A455
A456
A457
A458
A459
A460
A461
A462
A463
A464
A465
A466
A467
A468
A469
A470
A471
A472
A473
A474
A475
A476
A477
A478
A479
A480
A481
A482
A483
A484
A485
A486
A487
A488
A489
A490
A491
A492
A493
A494
A495
A496
A497
A498
A499
A500
A501
A502
A503
A504
A505
A506
A507
A508
A509

## Issue Log (hidden)
OFGEM Switching Programme Issue Log | [5 empty] | PROTECT SHEET WHEN DONE
Issue ID | Issue Description (including Impact) | Workstream | Impact/Severity Rating | Associated Actions | Planned Resolution Date | Agreed Resolution | Date Opened | Issue Owner | Progress Update | Date closed/ last updated | Key Issue? | SPDG? | GEMA Tier 1 | Programme Board? | Open /Closed | Old Issue ID

## >>> INSTRUCTIONS (hidden)
>>> Subsequent Pages for Project Manager and Risk Manager Only
Please do not make any direct changes to the subsequent pages as they will not reflect on the Master Risk Register.
ALL changes/ updates to Master Risk Register and Action Log will be semi-automatically reflected on the following pages.
INSTRUCTIONS TO PULL THROUGH UPDATES MADE ON MASTER RISK REGISTER
| 1 | On any of the subsequent pages, click on the FILTER icon in column B "Risk Themes".
| 2 | Find the Risk Theme in question i.e if you are on the 'Data & Security' page, find the 'Data & Security' option from the filter list.
| 3 | Deselect the required Risk Theme and select it again.
| 4 | Your updates to the Master Risk Register will now be reflected on the active page.
BUSINESS RULES FOR REPORTING ON RISK LINES
| 1 | Risk Themes that will be reported on a line by line detail to Programme Board are those themes with ratings 'High' or 'Very High'
| 2 | On the individual risk theme tabs, Copy (Ctrl +C) the filter view table including the header titles;
| 3 | Go to your Powerpoint template, Use the 'Paste SPECIAL' (Keep Source Formatting) to paste into a powerpoint template.
| 4 | On the Powerpoint template, you can select all to increase font; as well as amend rows
| 5 | To only report on the rows where line Risk Rating is contributing to a 'High', 'Very High' risk theme, leave only rows where Risk Rating is pink in colour, delete every other row.
| 6 | For further information in the appendix of Programme Board paper , repeat steps 2 and 3 for every Risk Theme and paste into Appendix

## Working Table(DON'T AMEND) (hidden)
|  |  |  | TODAY |  | LAST MONTH | THIS MONTH
|  |  |  | 2019-03-18 |  | 2019-02-01 | 2019-03-01
WORKING TABLE (Please do not touch blue columns. Only fill out the white columns for the corresponding week.)
Risk Theme | Weighted Average | Theme Risk Rating | Trend | Last Update Risk Theme Ratings | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01
Industry Engagement & Planning | 10.5 | Medium | ó | 10.5 | 2019-02-01: 10.5
Existing System Changes & Transitions | 18.25 | Medium | ó | 18.25 | 2019-02-01: 18.25
CSS Transition & Migration | 4.92 | Very Low | ó | 4.92 | 2019-02-01: 4.92
Data Quality & Cleansing | 6 | Low | ó | 6 | 2019-02-01: 6
Address Matching & REL Creation | 7.2 | Low | ó | 7.2 | 2019-02-01: 7.2
Design (Logical & Physical) | 10.0143 | Medium | ó | 10.0143 | 2019-02-01: 10.0143
GDPR & Security | 4.8 | Very Low | ó | 4.8 | 2019-02-01: 4.8
LOGIC
Severity | Weight | Likelihood | Weight |  | 2018-11-01: HOW TO COMPLETE THIS PAGE
5 | 3 | 5 | 5 |  | 2018-10-01: 1; 2018-11-01: This worksheet is the control Panel for the Risk theme Reporting for Programme Board so it is important to fill it in appropriately
4 | 2 | 4 | 3 |  | 2018-10-01: 2; 2018-11-01: BEFORE your monthly risk review meeting; copy and paste SPECIAL 123 'Values' from Weighted Average Column C into the column that corresponds to Last Month.
3 | 1 | 3 | 1 |  | 2018-10-01: 3; 2018-11-01: Always copy and paste values before the monthly meeting
2 | 1 | 2 | 1 |  | 2018-10-01: 4; 2018-11-01: The Spreadheet will do the rest of the work automatically;
1 | 1 | 1 | 1 |  | 2018-11-01: It will work out the difference between the scores noted BEFORE meeting and the 'now current' scores after the meeting and generate the trend report.
Weighted Average Range | RAG rating
Over 30 | Very High
Over 20 | High
Over 10 | Medium
Over 5 | Low
Under 5 | Very Low
Industry Engagement & Planning
Existing System Changes & Transitions
CSS Transition & Migration
Data Quality & Cleansing
Address Matching & REL Creation
Design (Logical & Physical)
GDPR & Security
Formulas:
LAST MONTH = DATE(YEAR([TODAY]), MONTH([TODAY])-1, 1)
THIS MONTH = DATE(YEAR([TODAY]), MONTH([TODAY]), 1)

## Reference (hidden)
Risk Theme | Theme Description
External Stakeholders | There is a risk that external stakeholders do not cooperate with the Programme, specifically that: * industry participants do not engage with, or support the Programme, or do not commit the required resource to focus on the Programme * other sectoral changes (e.g. HHS, price cap) are used by industry to delay their mobilisation activity or broader Programme implementation, or reduces industry senior management focus and resource on the Programme * industry use the involvement of DCC as an reason to challenge the Programme (e.g. value for money) There is also a risk that we do not see the anticipated increase in switching rates as a result of the new switching arrangements
Ofgem Skills and capabilities | There is a risk that the Ofgem Programme team does not contain, or have access to, the required knowledge or expertise (commercial, technical, delivery and programme management) as the Programme switches focus to the delivery phases. This includes the associated risk that key Programme knowledge is lost due to staff turnover
DCC Skills and capabilities | There is a risk that the DCC Programme team does not have access to the required knowledge or expertise. This includes the associated risk that key Programme knowledge is lost due to staff turnover
Ofgem-DCC relationship | There is a risk that the Ofgem-DCC relationship is ineffective, specifically that: * the inteligent client/inteligent supplier dynamic is not maintained/deteriorates due to quality issues * Ofgem's future price control decisions are compromised through decisions made on the Switching Programme
Blocker on innovation | There is a risk that the implementation of the chosen solution for the CSS and new switching arrangements are a blocker to innovation in the energy market There is also a risk in trying to resolve the above is to delay the Programme substantially to be able to define the requirements of specific changes
Programme Cost & Budget | There is a risk that the Programme is not fully funded to enable successful delivery. This includes funding from external funding sources (e.g. code bodies)
Timing & Delivery | There is a risk that key programme milestones are put at increased risk or achieved due to unforeseen events, incorrect planning assumption or missed dependencies.
Data & Security | There are a number of risks in the data and security theme, notably in that NCSC place a range of new security requirements on the Programme and that data related issues that may arise during cleansing / migration result in delays, additional costs or design changes.