## Sheet1
| Document Name | 20190620 CSSIA 11.5 Data Migration and Transition v0.3
# | Section Number | Review Comments | Organisation | DWG Action
1 | 11.5.1 | L2-TBC (New Milestone) - What is the entry criteria for this? | Xoserve | For Discussion
2 | 11.5.1 | L2-TBC (New Milestone) - L105 is not Data Migration elements at this point, given this, what is considered the entry for DM | Xoserve | For Discussion
3 | 11.5.1 | Xoserve are expecting an additional document from the SI articulkating the above requirements | Xoserve | Written
4 | 11.5.1 | Live Rehearsal - we would appreciate greater clarity on what consititues Live Rehearsal | Xoserve | Written
5 | 11.5.1 | This is a new L3 milestone that the SI has identified to ensure the following activities are prepared for and completed by the CSSPs and ESPs: - Can the date for this milestone be shared. Please can we get as early visibility of any supporting data for this milestone to allow us to plan in advance. | Xoserve | Written
6 | 11.5.1 | The above mentioned L3 milestone, we would like a clear definition of this milestone and what it entails from a Data perspective, as there was some uncertainty during the Test work Group | Xoserve | Written
7 | 11.5.1.1 | We suggest mentioning Delta migration in the plan summary section? | SSE | Written
8 | 11.5.1.2 Page 8 | The headers on this table do not reference LPs, only Supplier/Shipper is this correct | SPEN | Written
9 | 11.5.2 | We have noticed that there are not any responsibilities for suppliers. Is this correct? | SSE | For Discussion
10 | 11.5.2 | The Prog Coordinator only seems responsible up to Stage 1. | St Clements | Written
11 | 11.5.3 | RMP Data - Prod interface being used for Data migration purposes - Is the intention to connect to production environments? | Xoserve | For Discussion
12 | 11.5.3 | Active Registration Data - Clear definition of Data items and why they are required. | Xoserve | Written
13 | 11.5.3 | Active Registration Data - No mention of return of data post data migration (e.g. CSS Registration identifier for ESPs to update) | Xoserve | For Discussion
14 | 11.5.3 | 12 day queue for switches during transition - how should cool off be applied to switches sitting in the queue? Do we have to maintian the queue, and remove switches where customers change their mind during the 12 day period? | Centrica | Written
15 | 11.5.3 | What are the expectations for a customer who moves home during the period and want s to stay with current supplier after move is completed if this is within the transition period? | Centrica | Written
16 | 11.5.3 | What will be ther required switch date for the switches that are held in supplier queues during transition period? Should these be dated the day supplier submits the switch to CSS, or the date customer contacted supplier to request switch? | Centrica | Written
17 | 11.5.3 Data Migration Scope Table 4 ‘In-Flight’ Registration Data | Suppliers/Shippers will be prevented from submitting new switch requests. My interpretation of New Switch Requests in that (for electricity) it represents the sending of a D0055. Is that correct? And this includes scenarios where for example, the losing supplier has objected due to being in contract the day before T1 Date, any attempt to register the supply now with an Updated SSD would not be allowed until CSS Go Live. | EDW | Written
18 | 11.5.3 Data Migration Scope Table 4 ‘In-Flight’ Registration Data | From T1 Date (for example 12 calendar days prior to the CSS ‘go-live’ ). I am assuming that the process to object to a registration will continue within these [12] days. I am also assuming that registration can be withdrawn within these [12] days Is that correct? | EDW | Written
19 | 11.5.3 Data Migration Scope Table 4 ‘In-Flight’ Registration Data | Registrations that reach a ‘Confirmed’ or ‘Secured’ state in MPAS/UK Link before cutover commences at T2 Date (for example 4 calendar days before go-live) I am assuming that where the Supply is DCC Enabled, we will still be granted access to the Smart Meter on the Supply Start Date, even if it is in the standstill period. Is that correct? | EDW | Written
20 | 11.5.3 Data Migration Scope Table 4 ‘In-Flight’ Registration Data | Note that Switch Registrations which have been ‘held’ back from submission to MPAS/UK Link by Suppliers/Shippers due to being initiated from T1 Date I believe that intial registrations cannot be backdated, so if a new Connection occurs during the In-flight Registration Window, it will be registered with an incorrect date. I assume no process will be mandated to update the CSS for the correct date. Is that correct? | EDW | Written
21 | 11.5.3 Data Migration Scope Table 4 Active Registration Data | The term Registraton Type I don’t recognise. This needs to be defined | EDW | Written
22 | 11.5.3 Data Migration Scope Table 4 RMP Data | Regarding this: Each RMP has a unique number; otherwise known as the MPxN, and includes the meter point address as recorded in UK Link or MPAS. For electricity, can you please confirm that the RMP will be the MPAN exactly – and that there will not be a new RMP ID. | EDW | Written
23 | 11.5.3 Active Registration Data Page 12 | In the Transactional data section the field 'Fuel type' is included, how is this to be determined. I assume that CSS will identify this? | SPEN | Written
24 | 11.5.4 | The Technical Data Migration Group - Xoserve would appreciate an understanding of when this group is expected to be stood up. Given the timelines to develop the Data Migration Solution (L2-26 Milestone), we would assume that this working group will be stood up as soon as possible | Xoserve | For Discussion
25 | 11.5.4 | Do the large suppliers need to be at the Data Migration Group meetings as the bulk of the data migration will come from suppliers and DNOs? | SSE | For Discussion
26 | 11.5.4 | Are all suppliers requested to atttend the bi-weekly meeting for Data Migration Governance? What active role are suppliers asked to take as part of this? | Centrica | For Discussion
27
28 | 11.5.5.2 Page 19 | The new L3 milestones make prefect sense, it would be good however to have clarity around how far in advance these will be available (I appreciate that this is difficult to pin down at this point, but an aspirational timeline at least should be indicated | SPEN | Written
29 | 11.5.7 | Validation Catalogue, Cleansing Catalog - who is responsible for creating these catalog and what timelines are associated with these? | Xoserve | For Discussion
30 | 11.5.7 | There is no mention of reconciliation - what is the scope of reconciliation of data beween UKLINK and CSS | Xoserve | Written
31 | 11.5.7 | What is the frequency of the Data Quality Report? Bi weekly? | SSE | For Discussion
32 | 11.5.7.4 | Data Loading Strategy - Need to understand the Data loading strategy, especially on the back of fallouts for both testing and final migration | Xoserve | For Discussion
33 | 11.5.8 | Not consistent with the documents previously mentioned - Validation Catalog, as an example is missing. | Xoserve | Written
34 | 11.5.8 | Can you explain what is GitHub is please? | SSE | Written
35 | 11.5.9 | Table reference numbers are wrong in bulletpoints | Centrica | Written
36 | 11.5.9.1 | What is the 28utilization of MTC? | SSE | Written
37 | 11.5.9.2 | 11.5.9.2 Action during the transition stage, for Stage 2 states that interface RetailEnergyLocation will be enabled for this purpose but 11.5.9.3 Success/Exit criteria for Stage 2 refers to providing the REL to ECOES via the ElectricityRegistration interface. Which is the correct interface? | Gemserv | Written
38 | 11.5.9.2 | We believe that the use of the API to migrate REL addresses from CSS to ECOES would be a slow, high risk strategy. Considering there are IRO 35 million addresses in ECOES, if each API call were to take 0.1 seconds, then this process would take 40+ days to complete. We believe that this would be far better to be an extract from CSS into a file that can be loaded and parsed into the database directly. | Gemserv | For Discussion
39 | 11.5.9.3 | 11.5.9.3 defines, as success criteria for exiting Stage 2 that “Updates to Registration are provided to ECOES and DES via CSS interface ElectricityRegistration and GasRegistration”. But then goes on to state “This activity must be in place by no later than the end of Transition Stage 3” – so a successful exit from Stage 2 is dependent on an activity taking place in Stage 3? | Gemserv | Written
40 | 11.5.9.4 | Section 11.5.3 states that the SwitchingDomainData interface will be employed for the migration of switching domain data. Is there a reason that this is not also stated in section 11.5.9.4? | Gemserv | Written
41 | Document Control | It's not clear how the various documents referenced supplement this document, and what the document hierarchy is for these documents. It is difficult to review these documents in isolation, and it requires a lot of effort to go back to each of the referenced documents to find if questions to review queries are answered in the referenced documents | Centrica | For Discussion
42 | General | We have noticed that there are several references to "this will change after the physical design is completed". Is it worth waiting until then to review this document? | SSE | For Discussion
43 | General | Where there are references to the L phases of the plan could you also reference, where applicable, the HL milestone dates as this would make it easier to follow the document when major activities are due to drop without having to reference to the POAP to look up the L phase. | SSE | Written
44 | General | We believe it would be beneficial to include a glossary in this document | SSE | Written
45 | General | We believe it would be useful to include the Ofgem plan on a page so the L references can be referenced easily. I see that this document is referenced on page 2 but it would be useful to have a page in this document showing the plan with dates. | SSE | Written
46 | General | In a data migration activity it is usually key to have a physical mapping document that shoes how source data fields will be migrated to target data fields. It is not obvious that this sort of document is an output from the Programme. The Programme seems to be producing an “Approach” (ie a Strategy) and a Transition Plan, but not the key bit in the middle which is the detailed mapping. | St Clements | Written
47 | General | There is quite a lot of emphasis on the “what” of data migration but perhaps not enough emphasis on the “how” ie an industry migration plan and the coordination of activities in that plan once the migration is underway. The “what” is relatively straightforward (especially if the Programme generates a mapping doc); I think the “how” is the difficult bit (including the number of trial runs, whether the roll-back/fix-forward tipping point is the same for electricity and gas etc). However, the transition plan maybe covers some of this ground. I think the transition plan should very much be something that is developed at the start, rather than the end of the migration activities. | St Clements | For Discussion
48 | Generic for document | We would like to request Ofgem to send out Industry wide communications on the points above regarding dates of switches in queues, cool off and homemoves to ensure all suppliers handle these in the same manner at switch over | Centrica | For Discussion
49 | Page 11 | Switching Domain data - Ownership is called out as 'Industry Governance'. Currently there is no assigned owner for Switching Domain Data. This needs clarified by x] | Xoserve | Written
50 | Page 11 | Will switching domain data include market participant data, shipper supplier relationship and shipper network relationship | Xoserve | Written
51 | Page 12 / 'In-Flight' Object | The D-4.3.4 Transition Plan: In-Flight Switches Approach document defines T1 as ‘The last date on which suppliers can submit a switch request to MPRS or UK Link’. This is different from stating ‘…will be prevented from submitting new switch requests to MPAS/UK Link From T1 Date’. | Gemserv | Written
52 | Page 12 / 'In-Flight' Object | Clarify that 'This date' means the T1 Date | Gemserv | Written
53 | Page 12 / 'In-Flight' Object | Terminology differs from D-4.3.4 Transition Plan - "‘in-flight’ registration period" should be ‘Inflight switch management period’ | Gemserv | Written
54 | Page 12 / RMP Data Object | we do not feel that it is feasible to utilise a Web Service interface for the migration of 35 Million MPANs | Gemserv | For Discussion
55 | Page 12 / RMP Data Object | The terminology for Registration States will need to be verified to ensure the expected migration data content from MPAS can be verified | Gemserv | For Discussion
56 | Page 12 / RMP Data Object | In relation to the data elements who has the responsibility of defining how these map back to the equivalents on the source system (MPRS and UK-Link)? When does this need to be completed by? | Gemserv | Written
57 | Page 12 / RMP Data Object | Shipper MPID - note this is Gas only | Gemserv | Written
58 | Page 13 / 'In-Flight' Object | First paragraph contradicts the E2E Transition Plan – In Flight switches which states: “A smaller subset of registration data will not have fully progressed to being an active registration at cutover. These are known as ‘inflight switches’.” | Gemserv | Written
59 | Page 13 / 'In-Flight' Object | Second paragraph: '…inititated from T1 Date' should be '…inititated after T1 Date' Terminology differs from D-4.3.4 Transition Plan - "‘in-flight’ Registration Window" should be ‘Inflight switch management period’ | Gemserv | Written
60 | Page 13 / 'In-Flight' Object | Third paragraph - 'The period from T2 Date to..' should be 'The period from end of T2 Date to... | Gemserv | Written
61 | Page 13 / 'In-Flight' Object | Fourth paragraph: Terminology differs from D-4.3.4 Transition Plan - "‘in-flight’ Registration Window" should be ‘Inflight switch management period’ | Gemserv | Written
62 | Page 14 /Supplier Arranged Appointments Object | We do not feel that it is feasible to utilise a Web Service interface for the migration of ~50 Million Appointments | Gemserv | For Discussion
63 | Page 18 | To identify, agree and document data preparation and provision requirements for the ‘In-flight Switching Window’.' - Any file/interface definition needs to be completed to support this requirements | Xoserve | Written
64 | Page 19 | To identify, agree and document data archiving requirements for after go-live.' - Assume this is for CSS only not ESPs | Xoserve | Written
65 | Page 2 | We have noticed that some of the reference docs are dated back to Feb-18. Is the content still up to date with recent developments? | SSE | For Discussion
66 | Page 2 | Where can we find the Schedule 2.1 DCC Requirements document? | SSE | Written
67 | Page 28 | Terminology differs from D-4.3.4 Transition Plan - "‘in-flight’ Registration Window" should be ‘Inflight switch management period’ | Gemserv | Written
68 | Page 28 | In flight period should start from end of T1 date. | Gemserv | Written
69 | Page 28 | cutover' Windows should start from end of T2 | Gemserv | Written
70 | Page 28 | Terminology differs from D-4.3.4 Transition Plan - "‘in-flight’ Registration Window" should be ‘Inflight switch management period’ | Gemserv | Written
71 | Page 28 / Stage 3 column | Numbering issue with 5) and 4) ? | Gemserv | Written
72 | Page 29 / Stage 1 column | "(i.e. additional data items within the D0205 or a new specific 'D Flow" can be changed to "(new 'D0386' flow)" | Gemserv | Written
73 | Page 29 / Stage 1 column | Meter Asset Provider Ownership and Asset Deployment - This has been implemented through extended D0312 and D0304 flows from MOPs to MPAS | Gemserv | Written
74 | Page 30 / Stage 1 column | Please clarify the following: 'CSS holds Registration data, via a transitional interface,' | Gemserv | Written
75 | Page 31 | Can ETL be used as a feed during data migration stages 1-3 for production interfaces (post migration point-to-point from UKLINK) Page 2 - [5] D-4.2.6 CSS Data Migration Plan | Xoserve | For Discussion
76 | Page 31 / Table 16 | Poor quality images | Gemserv | Written
77 | Page 31 / Table 16 | What does 'CRS' refer to in the box labelled 'CSS (CRS)' | Gemserv | Written
78 | Page 31 / Table 16 | Different references to 'MPRS' and 'MPRS Instances' - standardisation or explanation required | Gemserv | Written
79 | Page 31 / Table 16 Stage 3 | Erroneous bullet in Interfaces Deployed | Gemserv | Written
80 | Page 4 | Data Quality Report - Is there a template that we need to use? If so, when is this expected to be released? | Xoserve | For Discussion
81 | Page 4 | Data Quality Report - We would like to have nmore information around the DQR | Xoserve | For Discussion
82 | Page 5 | Data migration test - It is stated that this will be in Production environment. Assume for ESPs, it will be the pre-Prod environment | Xoserve | For Discussion
83 | Page 8 | Is the SI designing the Data Migration Solution? | Xoserve | For Discussion