|  |  |
| --- | --- |
| **Draft Determination Publication** | |
| **Network Queries** | |
| **Network Reference number** | SGN\_DDQ\_Q33 |
| **Licence** | SGN |
| **Topic/Activity:** | Capex – E&I Minor works |
| **Question:** | Relating to draft\_determinations\_-\_sgn\_annex.pdf (table 49 and section 3.58)  *"We propose to disallow the costs for Battle PRS System 2, E&I Minor Works, and Westerham PRS System 2 because the engineering review identified that these projects duplicate or overlap with other SGN projects."*  Can we confirm the basis of the assessment as there are no overlapping costs and there is no duplication of work in the plans presented? |
| **DDQ raised by** | Danny Symes |
| **Date query raised** | 23/07/2020 |
| **Expected response date** | 30/07/2020 |
| **Ofgem Response:**  As stated in GD2 EJP Final Report 00 – Appendix 1 – SGN, there appears to be overlap with Battle 1 EJP (Pre-heating) and E&I upgrades. If you believe this is an error, please provide an explanation in your DD response, including clearly signposting all references to these individual projects in your BPDT. | |
| **Attachments:** | |