## SpC 5.6
Licence number and name: |  | SpC 5.6 - [3D; 8C; 8E; 8G; 8H; and 8K] - System Operator external incentives, costs and revenues [includes Demand Forecasting, Maintenance, Residual Balancing, GHG emissions]
Ofgem contact: |  | Max Lambert
No. | Date raised | Comment from | Reference (Part X, Para Y) | Comment | Suggested alternative drafting (if necessary) | Assigned to | Due Date | Response | Issue closed?
1 | Sep ConDoc | NGGT | SpC 5.6 - NTS System Operator external incentives, costs and revenues (Licence condition now moved to SpC 5.6) | [NGGT] don't agree with Ofgem's policy position on some incentives and this represents lost customer value. We also note that in our original business plan we proposed indexation of some incentive parameters. We do not support Ofgem's decision to remove this indexation which was not clear on all incentive in the draft determination document. Please see our response to DD question GT Core 1 and NGGT questions 1-7 for our detailed policy position. |  | Ofgem |  | Ofgem acknowledges NGGT's response to our draft determinations on the incentives in this licence condition, and would clarify ODIs are indexed to inflation (i.e. CPIH). However, this point is more related to policy; please see Final Determinations for our policy decisions. | Closed
2 | Sep ConDoc | NGGT | SpC 5.6.43 - Part F (Clause removed) | [NGGT] do not understand the purpose of this clause or the reference to implementation of updated financial incentives. The equivalent RIIO-1 clause related to the provision of information to Ofgem for a mid RIIO-1 incentive review, as there is no equivalent mid period review of incentives, we do not understand why this clause has been retained. All the data requested in this report would already be provided to Ofgem through annual reporting. Suggest this clause is removed completely. |  | Ofgem |  | Ofgem acknowledge this comment and agree that this clause should be removed, and it has been deleted from Part F of SpC 5.6. | Closed
3 | Sep ConDoc | NGGT | SpC 5.6.59 - Part K (SpC 5.6.59) | 5.6.59 requires reporting of actuals against perfect foresight of market prices. We do not understand what benefit this will deliver as we do not have perfect foresight when procuring shrinkage, so this represents a hindsight measure of performance. Reporting against average prices would be more meaningful and would show delivering value (or not) for consumers. |  | Ofgem |  | This is principally a policy comment, so please see our Final Determinations on NTS Shrinkage. We have engaged with NGGT on the specifics for reporting on NTS Shrinkage and the relevant draft licence text, and have developed a set of metrics for the Shrinkage Procurement Report, which will also include reporting against average prices (SpC 5.6 - Part K). Reporting on NTS Shrinkage costs will also be outlined in the RIGS. | Closed
4 | Sep ConDoc | NGGT | SpC 5.6.1 - Introduction (SpC 5.6.1) | Delete calculate in line 3 |  | Ofgem |  | This text has been amended. | Closed
5 | Sep ConDoc | NGGT | SpC 5.6.3 - Part A (SpC 5.6.3) | MIRtis detailed in Part F of licence, not E |  | Ofgem |  | This text has been amended. | Closed
6 | Sep ConDoc | NGGT | SpC 5.6.3 - Part A (SpC 5.6.3) | SCt is detailed in Part I, not G |  | Ofgem |  | This text has been amended. | Closed
7 | Sep ConDoc | NGGT | SpC 5.6.3 and 5.6.4 - Part B & Part C (SpC 5.6.3 & SpC 5.6.4) | Includes the term RBIRt, however in 5.6.4 this is referred to as 'RBIt'. The two need to be consistent. |  | Ofgem |  | This text has been amended with RBIRt the applicable term in SpC 5.6. | Closed
8 | Sep ConDoc | NGGT | SpC 5.6.3 - Part A (SpC 5.6.3) | RBCt definition has been simplified from RIIO-1 licence, but this needs to be defined as per RIIO-1 licence, otherwise it is unclear that the term refers to residual balancing. Previous definition was "means an amount (£m) equal to the revenue equivalent to the net residual balancing costs incurred by the licensee in respect of Formula Year t and shall be equal to the sum of the Basic Net Neutrality Amount and the Adjustment Neutrality Amount (having the meanings given to each of those terms in the network code) across all Days in Formula Year t". |  | Ofgem |  | The text for the RBCt definition in SpC 5.6.3 has been amended to reflect the definition in RIIO-1. | Closed
9 | Sep ConDoc | NGGT | SpC 5.6.9 - Part B (SpC 5.6.9) | Definition of CLP - this should refer to D+1 not D. |  | Ofgem |  | This text has been amended. | Closed
10 | Sep ConDoc | NGGT | SpC 5.6.22 - Part E (SpC 5.6.22) | Should the start date change to 31 July 2022, reporting on the first year of RIIO-2. |  | Ofgem |  | The text has been amended to read 31 July 2022 in SpC 5.6.22. | Closed
11 | Sep ConDoc | NGGT | SpC 5.6.26 - Part E (SpC 5.6.26) | As per previous comments, Ofgem need to state by when they will approve or reject. Our preference would be to remove "reject the proposed revisions" as we would always need to know why the revisions have been rejected. We also believe that Ofgem should provide recommendations (where applicable) in approval as well as rejection. |  | Ofgem |  | We have assessed time limits on a case by case basis, because of a potential impact on consumers where Ofgem's approval/rejection is tied to specific/strict timelines. We do recognise there should be a time limit here in SpC 5.6.26 to give certainty to NGGT's processes regarding GHG emissions, and have therefore inserted a 56 day requirement. We do not see the merit of proposing alternative recommendations in approval, but text has been drafted in SpC 5.6.27 to outline what will happen where the Authority takes no action within the aforementioned 56 day time limit. | Closed
12 | Sep ConDoc | NGGT | SpC 5.6.26 - Part E (SpC 5.6.26) | Remove "either" in line 2 |  | Ofgem |  | This text has been amended. | Closed
13 | Sep ConDoc | NGGT | SpC 5.6.27 - Part F (SpC 5.6.28) | Definitions for MCIRt and MDIt should ideally state "incentive revenue" (as per MDIRVt) |  | Ofgem |  | This text has been amended to add in 'revenue' for these respective terms under SpC 5.6.28. | Closed
14 | Sep ConDoc | NGGT | SpC 5.6.31 - Part F (SpC 5.6.32) | TVMt definition needs to be clear that it refers to maintenance affecting exit customers only |  | Ofgem |  | This text has been amended in SpC 5.6.32 to reflect this maintenance affecting customers offtaking from the NTS. | Closed
15 | Sep ConDoc | NGGT | SpC 5.6.31 - Part F (SpC 5.6.32) | Can Ofgem clarify whether term should only be whole days. |  | Ofgem |  | We have discussed this with NGGT, and have agreed this will operate in terms of whole days and therefore operate in the same manner as the Change of Days scheme. We feel the relevant text is sufficient. | Closed
16 | Sep ConDoc | NGGT | SpC 5.6.31 - Part F (SpC 5.6.32) | TVMt refers to "volume". This should refer to days. |  | Ofgem |  | The text for TVMt in SpC 5.6.32 has been amended to refer to days. | Closed
17 | Sep ConDoc | NGGT | SpC 5.6.34 - Part G (SpC 5.6.35) | 5.6.34 does not reflect the existing provision in Special Condition 8G. This is currently framed a reasonable endeavours obligation and should be retained here. There is no rationale to change this existing obligation to a best endeavours obligation. |  | Ofgem |  | We acknowledge that the use of reasonable endeavours is appropriate in SpC 5.6.35 where the licensee communicates its Maintenance Plan to Maintenance Relevant Parties. The text has been amended to reflect this. | Closed
18 | Sep ConDoc | NGGT | SpC 5.6.36 - Part G (SpC 5.6.37) | As previous comment, this should be a reasonable endeavours obligation. |  | Ofgem |  | We have amended "best endeavours to update" to "must update" in SpC 5.6.37, as it is of crucial importance and significance to Maintenance Relevant Parties - and in respect of the maintenance incentive itself - that the maintenance plan is updated each Regulatory Year. We believe the amended wording reflects the tightening of this obligation. | Closed
19 | Sep ConDoc | NGGT | SpC 5.6.50 - Part H (SpC 5.6.51) | 5.6.50 is superfluous and should be removed. It is not used elsewhere in the licence where the licensee is required to produce a document or report. The requirements of the report are set out in 5.6.49 and this is sufficient. |  | Ofgem |  | Where there are new reporting requirements or changes to reporting, we made the judgement to add in clauses to allow the Authority to consider the format, publication of or the data in reports during the next price control period. Amidst a potentially changing RIIO-2 environment, and with consideration of Net Zero, Ofgem wanted to reserve this right not for sudden, unprecedented changes but to accommodate new information in a changing environment against the rigidity of the licence. We have removed SpC 5.6.50 and amended SpC 5.6.51(e) to clarify these intentions following further engagement with NGGT. | Closed
20 | Sep ConDoc | NGGT | SpC 5.6.51 - Part H (Clause removed) | This paragraph should be removed if, as per previous comment, 5.6.50 is deleted. In any event the timescales in 5.6.50 do not appear to work. It suggests that the Authority will direct a different format of report 28 days before it has received it under 5.6.48. Also, if the paragraph is retained in a suitable form that addresses the timing issue, "agreed" in line 4 should be replaced with "required". |  | Ofgem |  | We have removed this paragraph from Part H. | Closed
21 | Sep ConDoc | NGGT | SpC 5.6 - Part K (SpC 5.6 - Part K) | Perfect Foresight definition - we believe there is missing clarity in the algebra as to over which days the calculation should be made (e.g. all days in a year, in a week etc.). This needs clarifying. |  | Ofgem |  | Following discussions with NGGT, we have amended SpC 5.6 - Part K to move the calculations and algebra into the Gas Volumes Methodology outlined in SpC 5.6.57, and the "best case scenario" costs derived from these calculations into the Shrinkage Procurement Reports under SpC 5.6.60 (in addition to data/costs that shall be set out in the RIGS). | Closed
22 | Sep ConDoc | NGGT | SpC 5.6.59 - Part K (SpCs 5.6.57 & 5.6.60) | Calculations required under 5.6.59, Part L and the definition of "Perfect Foresight" and "Prompt Costs" are not clear. The calculations required should be unambiguous and specified in the licence, not in definitions. We are happy to work with Ofgem on progressing these issues. |  | Ofgem |  | Following discussions with NGGT, we have amended the licence to move the calculations and algebra involved in calculating "Perfect Foresight" (now "best case scenario" under SpC 5.6.60), seasonal forecasts, quarter forecasts and the prompt daily volumes to be bought/sold into the Gas Volumes Methodology outlined in SpC 5.6.57. The original definitions of "Perfect Foresight" and "Prompt Costs" have been removed. | Closed
23 | Sep ConDoc | NGGT | SpC 5.6 - Definitions (SpC 5.6) | Definition of "Perfect Foresight" includes a mix of volume and cost elements, these should be split out as perfect foresight element only appears to link to the costs of purchasing the FGVT volume. |  | Ofgem |  | The "Perfect Foresight" definition that was structured as a mix of volume and cost has been removed. Following discussions with NGGT, we have amended the licence to move the calculations and algebra to the Gas Volumes Methodology under SpC 5.6.57, and the "Perfect Foresight" (now "best case scenario") costs derived from these calculations into the Shrinkage Procurement Reports in SpC 5.6.60 (in addition to data/costs that shall be set out in the RIGS). | Closed
24 | Sep ConDoc | NGGT | SpC 5.6 - Part L (SpC 5.6 - Part K) | Remove FGVT acronym from title of section and replace with "Forward Gas Volume Target (FGVT)" |  | Ofgem |  | The FGVT Statement has been removed, with the Gas Volumes Methodology now in place under SpC 5.6.57, so this is comment is no longer applicable. | Closed
25 | Sep ConDoc | NGGT | SpC 5.6.60 - Part L (SpC 5.6.57 - Part K) | Should this not be a cost target rather than a volume target? |  | Ofgem |  | The FGVT Statement has been removed, with the Gas Volumes Methodology now in place under SpC 5.6.57 to calculate volumes (and subsequent costs for the purposes of the Shrinkage Procurement Report in SpC 5.6.60) so this is comment is no longer applicable. | Closed
26 | Sep ConDoc | NGGT | SpC 5.6.60 - Part L (SpC 5.6.60 - Part K) | Replace Forecast with Foresight |  | Ofgem |  | The removal of "Perfect Foresight" from the definitions means this comment is no longer applicable. | Closed
27 | Sep ConDoc | NGGT | SpC 5.6.60 - Part L (SpC 5.6.57 - Part K) | FGVT is not defined anywhere. Whilst we understand the intent is for NG to produce a statement to show how FGVT is determined, we consider some regulatory guidance is required as to what the target should be based upon. |  | Ofgem |  | The FGVT Statement has been removed, with the Gas Volumes Methodology now in place, so this is comment is no longer applicable. The basis and definition of the Gas Volumes Methodology has been outlined in the licence in 5.6.57 and GT definitions. | Closed
28 | Sep ConDoc | NGGT | SpC 5.6.60 - Part L (SpC 5.6.57 - Part K) | 5.6.60 defines FGVT as forward gas volume target. Should this be defined in the definitions section with an explanation of what the term means. |  | Ofgem |  | The FGVT Statement has been removed, with the Gas Volumes Methodology now in place in SpC 5.6.57, so this is comment is no longer applicable. | Closed
29 | Sep ConDoc | NGGT | SpC 5.6 - Definitions (Definition removed) | In the definition of FGVT Independent Examiner in the GT annex, the word "for the purposes of this condition" should be deleted. |  | Ofgem |  | The FGVT Statement and corresponding need for Independent Examination has been removed so this comment is no longer applicable. | Closed
30 | Sep ConDoc | NGGT | SpC 5.6.61 - Part L (SpC 5.6.58 - Part K) | The licence will not come into effect until 1 April 2021. This paragraph imposes a new obligation on the licensee but this obligation cannot be imposed prior to 1 April 2021 to require a deliverable before that date. We therefore suggest this provision is amended so as to read "as soon as reasonably practicable following the commencement of the Regulatory Year commencing on 1 April 2021 and prior to the commencement of each subsequent Regulatory Year, the licensee must..." |  | Ofgem |  | We have amended the text in SpC 5.6.58 so that the licensee "must use reasonable endeavours to publish the Gas Volumes Methodology on its website on or before 1 July 2021, and by the commencement of each subsequent Regulatory Year on 1 April". | Closed
31 | Sep ConDoc | NGGT | SpC 5.6.65 - Part L (SpC 5.6.59) | Delete "either" |  | Ofgem |  | We have amended this text. | Closed
32 | Sep ConDoc | NGGT | SpC 5.6.65 - Part L (SpC 5.6.59) | Needs a date by which Ofgem will approve/reject by. As per previous comments, we believe if Ofgem do reject then they should provide recommendations/reasons for that rejection, hence our preference would be for b. to be removed. |  | Ofgem |  | We have amended this text, and outlined in SpC 5.6.59 that "the licensee may modify the Gas Volumes Methodology in agreement with the Authority". | Closed