## SpC_3.14
Licence number and name: |  | SpC 3.14: Fuel Poor Network Extension Scheme Volume Driver
Ofgem contact: |  | Rebecca Pickett
No. | Date raised | Comment from | Reference (Part X, Para Y) | Comment | Suggested alternative drafting (if necessary) | Assigned to | Due Date | Response | Issue closed?
1 | 2020-10-28 | Cadent | Part B 3.13.5 (d) | A GDN may have already committed to completing an FPNES connection or is in the middle of completion, therefore this closure period should apply to new connection applications only and any existing FPNES connections work should be completed within 12 months. | “(d) the date of the planned closure for new applicants, which will be not less than 30 days after the date of publication of the notice; (e) the date of work completion for existing applicants, which will be not less than 12 months after the date of publication of the notice; and” | Ofgem | December | The notice published in line with 3.13.5 would set out the details of which connections the closure would apply to and when it would come into force. This notice would be subject to consultation. We do not think it is appropriate to specify this level of detail about a potential notice in the licence to allow flexibility for an appropriate response to the situation in the event the scheme is closed. | Closed
2 | 2020-10-28 | Cadent | Part B 3.13.5 (e) | Government policy change may not be clear and an Ofgem notice should be treated a bit like a consultation on how the government policy change should be interpreted/implemented. A representation period should be no less than 2 months | “(f) a period during which representations may be made on the direction, which will be not less than 2 months” | Ofgem | December | We think setting a minimum two month representation period is disproportionate when we do not know what the circumstances would be if a direction was required. The licence sets the minimum period during which representations can be made, but in the event a direction was issued we would determine the appropriate length of consultation period depending on the situation. We think it is appropriate to keep the representation period as 15 days to allow for a quick decision to be made, in the event that there was a clear government policy which meant FPNES was no longer appropriate. | Closed
3 | 2020-10-28 | Cadent | 3.13.9 | Reporting requirements under the FPNES guidance document can be changed by direction. Ofgem need to be aware that it may take time to change systems and processes to capture new data or collate it in a new way. It may not be possible to immediately comply with new requirements upon the making of a direction if it does not have a reasonable and proportionate lead in time. |  | Ofgem | December | Paragraph 9 has been amended to no longer refer to reporting requirements, as these will be set out through the RIGs. | Closed
4 | 2020-10-28 | WWU | Para 3.13.3 | FPNES Connections is not a defined term, this either needs to be defined or C and DC need to be defined using existing definitions. | Ofgem to amend as appropriate. | Ofgem | December | Updated drafting to refer to refer to the definition of Delivered FPNES Connections. | Closed
5 | 2020-10-28 | WWU | Para 3.13.4 | A change in government policy should more properly be characterised as a condition precedent before the Authority can close the scheme. | Amend 3.13.4 to read "The Authority may will close the FPNES by direction where a change in government policy has made the FPNES redundant." | Ofgem | December | Wording has been amended to "The Authority will close the FPNES by direction where changes in government policy lead the Authority to the conclusion that the closure of the FPNES is appropriate in the circumstances" to reflect that the closure would be in relation to a change in government policy. | Closed
6 | 2020-10-28 | WWU | Para 3.13.5 | In consequence of the change to 3.13.4, 3.13.5 (a) is redundant and (b), (c), (d) and (e) need renumbering. for what will become (a) for a new accepted connection contract WWU currently has 180 days to agree a planned date and 270 days to complete the works. | Amend as follows: "Before issuing a direction, the Authority maywill publish a notice setting out: (a) the changes in government policy that it considers have made the FPNES redundant; (b)(a) the date by which the licensee must complete all planned connections under the FPNES which shall be at least 270 days after the date of the date of the planned closure of the FPNES; (cb) the resultant changes to the licensee's RIIO-GD2 FPNES Connection Target set out in Appendix 1; (dc) the date of the planned closure, which will be not less than 30 days after the date of publication of the noticedirection; and ..." Amend the rest of the numbering in the paragraph. | Ofgem | December | The notice published in line with 3.13.5 would set out the details of which connections the closure would apply to and when it would come into force. This notice would be subject to consultation. We do not think it is appropriate to specify this level of detail about a potential notice in the licence to allow flexibility for an appropriate response to the situation in the event the scheme is closed. | Closed
7 | 2020-10-28 | WWU | Para 3.13.6 | The definition of FPNES Governance Document should refer to Part C of SpC 3.13 instead of to "this condition". | Amend the definition of FPNES Governance Document as follows: "means the document of that name published on the Authority’s Website for the purposes of this condition Part C of SpC 3.13" | Ofgem | December | Updated definition to reflect comment. | Closed
8 | 2020-10-28 | WWU | Para 3.13.9 | In the current licence the guidance document makes no reference to reporting requirements this has previously been defined in the annual RRP guidance. There is no good reason for changing this. | Amend to delete "; and" at the end of (b) and insert "." and delete (c) entirety. | Ofgem | December | Paragraph 9 has been amended to no longer refer to reporting requirements, as these will be set out through the RIGs. | Closed
9 | 2020-10-28 | WWU | Para 3.13.10 | The document should have appropriate consultation before the Authority directs its implementation. Only allowing a period of 28 days at the end is not sufficient. This point applies to all other SpC that have Associated Documents. | Amend 3.13.10 by adding at the beginning "After appropriate consultation and" so that it reads "After appropriate consultation and bBefore issuing the FPNES Governance Document by direction, the Authority will publish on the Authority's Website:" | Ofgem | December | The current drafting set out in paragrpah 3.13.10 requires us to consult for 28 days before issuing the Governance Document, so this amendment is not required. | Closed
10 | 2020-10-28 | WWU | Para 3.13.11 | Notwithstanding our fundamental object to Ofgem having the right to make these changes to licence obligations by the use of Associated Documents, the Authority should give notice to the licensee that it has published what is in effect a change to the licence. This point applies to all other SpC that have Associated Documents. | Add at the end ", and at the same time give notice to the licensee of the publication of" so that it reads "Before amending the FPNES Governance Document by direction, the Authority will publish on the Authority's Website, and at the same time give notice to the licensee of the publication of:" | Ofgem | December | We don't think this addition is necessary. Licensees can sign up to the Ofgem Daily Update to receive notice of publications on our website. | Closed
11 | 2020-10-28 | WWU | Appendix 3 | Two lines for Wales & West Utilities Limited in this table, just one in Appendix 1 and 2. | Remove duplicate line. | Ofgem | December | Duplicate line removed. | Closed