## SpC 5.4
Licence number and name: |  | SpC 5.4 Vulnerability and Carbon Monoxide Allowance
Ofgem contact: |  | Rebecca Pickett
No. | Date raised | Comment from | Reference (Part X, Para Y) | Comment | Suggested alternative drafting (if necessary) | Assigned to | Due Date | Response | Issue closed?
1 | 2020-10-28 | Cadent | 3.8.2 and 3.8.3 | Formatting error - Join the paragraphs together and add the word ‘Vulnerability’ | "3.8.2 This condition also makes appropriate provision for the regulation, administration and governance of the Vulnerability and Carbon Monoxide Allowance” | Ofgem | December | Formatting error fixed | Closed
2 | 2020-10-28 | Cadent | Part A 3.8.4 | VCMAk not defined |  | Ofgem | December | Definition added | Closed
3 | 2020-10-28 | Cadent | 3.8.8 | When considering changing reporting requirements by direction Ofgem need to be aware that it may take time to introduce new systems and processes to capture new data/collate it in a new way. It may not be possible to start doing this immediately upon a direction being made. |  | Ofgem | December | We note this comment. If we decided to change any reporting requirements set out in the VCMA Governance Document, this would be subject to a consultation period, during which the GDNs can raise how long is required to introduce new systems and processes. We will take this into account when directing an amendment to the VCMA Governance Document. | Closed
4 | 2020-10-28 | Cadent | Part B 3.8.8 (c) | Additional ‘other’ in paragraph which should be removed. | “arrangements for ensuring that relevant learning from VCM Projects can be captured and disseminated to all other DN Operators; and” | Ofgem | December | Drafted amended to reflect comment. | Closed
5 | 2020-10-28 | Cadent | Appendix 1 | Licence (and any associated revenue adjustment formula) should clarify that funding won't be restricted by annual caps, but rather a period cap over 5 years |  | Ofgem | December | We think the formula achieves this intent. | Closed
6 | 2020-10-28 | WWU | Para 3.8.3 | Typo "lity and Carbon Monoxide Allowance." | Paragraph 3.8.2 should end reading "Vulnerability and Carbon Monoxide Allowance." and 3.8.3 should be deleted, this is a error. To avoid cross-referencing issues we have included "Not used" in 3.8.3. Ofgem to renumber. | Ofgem | December | Formatting error fixed | Closed
7 | 2020-10-28 | WWU | Part B | Mixed use of VCMA and VCM. | Suggest consistent reference to VCMA. | Ofgem | December | Updated drafting to use a consistent acronym. | Closed
8 | 2020-10-28 | WWU | Appendix 1 | This table should detail the split for each network on projects in their own network and that to be spent on joint GDN projects. We would prefer that the table only showed the total expenditure cap for the price control, this would allow each network to manage the spend rather than having to meet a value each year. Alternatively there could be a yearly average with a tolerance range around it to allow for setup costs and close down as envisaged in the guidance document. We don't think that the formula delivers the policy intent of allowing licensees to spend up to the aggregate cap with any unspent amount being returned to customers. | We have not submitted drafting to address the material issues in the comments on the left but we have the following drafting amendment: Amend the title to reflect the definition of the cap from "VCMA Expenditure Cap" to "VCMC" The final year should be "2025/26" not "2026/27" | Ofgem | December | The split between individual and collaborative projects has been set out in Appendix 1 and the formula has been updated to reflect this. The formula allows the network to manage the spend over the 5 years, and if the full expenditure cap is not reached, the unspent allowances will not be paid for by consumers. | Closed