## SpC 3.12
Licence number and name: |  | SpC 3.12 Capital Projects
Ofgem contact: |  | Jonathan Farrier
No. | Date raised | Comment from | Reference (Part X, Para Y) | Comment | Suggested alternative drafting (if necessary) | Assigned to | Due Date | Response | Issue closed?
1 | 30.10.2020 | SGN | 3.12.4 | The risk associated with the definition of outputs against the EJP creates a major issue. Clarity is required on how this will be assessed against the detail contained in EJP. The reduction stated is to Zero. It should be modified to allow for a more proportionate reduction to the deemed non delivery. |  | Ofgem | December | The description of outputs in Appendix 1 have been amended. | Closed
2 | 30.10.2020 | SGN | 3.12.2 | The Special Condition defines the output only as a reference to the EJP. The EJP contains detail from within the conceptual design. However, this detail will inevitably change as we progress towards the detailed and 'for construction' designs. SGN is therefore 'at risk' if the full content of a very detailed EJP is used as a reference. The customer benefit is realised if the intervention and the system clearly defined. For example, a REPLACEMENT of the GAS PRE-HEATING SYSTEM. However, the NARMs methodology goes even further by defining a monetary risk benefit for the intervention on the asset system, which represents the benefit to the customer. NARMs values are available for almost all projects with the exception of the following: Scotland T8: Pitcairngreen to Huntingtower - R04 and R05 (capacity), E&I upgrade programme (5 sites), ICMDL, Telemetry upgrades (8 offtakes), Dreghorn (capacity), E&I upgrade programme (4 sites), New PRS (Edinburgh South East Wedge) (capacity), Telemetry upgrade programme (73 PRS), Tranent (capacity) Metering uncertainty programme (6 sites), Southern E&I upgrade programme (2 sites), ICMDL, Telemetry upgrade programme (2 offtakes) E&I upgrade programme (23 sites), East Morden (Capacity), Telemetry upgrade (82 PRS), Wavendon (Capacity), Metering uncertainty programme (1 site), Note: the E&I projects detailed above are large programmes where the expenditure per site is small. These do not warant being included as an PCD. Note: 5 capacity projects included as PCD have only been generally defined within the EJP and these should be retained as specific intervention types on specific asset systems. | It is recommended that the references to the EJP in appendix 1 are replaced with the full NARMs risk benefit as at 31st March 2026 with the exception of projects listed (E&I to be excluded, capacity to be referred to by the intervention type and relevant system). | Ofgem | December | The description of outputs in Appendix 1 have been amended. | Closed
3 | 30.10.2020 | SGN | Definitions | The term 'delivery' is somewhat undefined in this context | should be defined as 'the commissioning or recommissioning into service of an asset after the stated intervention has been delivered'. | Ofgem | December | The description of outputs in Appendix 1 have been amended to make them clearer. | Closed
4 | 29.10.2020 | Cadent | 3.12.2a | Reference is made to 'date' the draft determination states in the Gas Distribution Annex p72 that 'expected timing of delivery is end of RIIO-GD2'. This renders the data surplus to requirement, or allows it to be defined as end of period. Other, in period, dates have not been suggested by ofgem for gas distribution. | remove 'delivery dates ' replace with '31st March 2026' | Ofgem | December | This is one of several possible drafting approaches, we have preferred the one in our proposed modifications. | Closed
5 | 29.10.2020 | Cadent | 3.12.5 | Reference is made to 'date' the draft determination states in the Gas Distribution Annex p72 that 'expected timing of delivery is end of RIIO-GD2'. This renders the data surplus to requirement, or allows it to be defiend as end of period. Other, in period, dates have not been suggested by ofgem for gas distribution. | remove 'delivery dates ' replace with '31st March 2026' | Ofgem | December | This is one of several possible drafting approaches, we have preferred the one in our proposed modifications. | Closed
6 | 29.10.2020 | Cadent | 3.12.6 | As written will recover 100% of funding for partial as well as full non delivery. This is not proportionate. See response to draft determination GDQ22/23. | remove 'in order to reduce the allowance for the output to zero.' and replace with 'in order to reduce the allowance for the output proportionally'. | Ofgem | December | Drafting has been amended so this is an evaluative PCD to reflect our Final Determinations position. Please see Final Determinations for our decision on this policy. | Closed
7 | 29.10.2020 | Cadent | 3.12.6 | As per our response to Kelvin Hui, on 10th September 2020, on the PCD Policy Document we do not believe that our Capital Projects should be Mechanistic PCDs. We believe they should be Evaluative PCDs, where they pass a materiality threshold of 0.5% of annual base revenue, as this will ensure that we can innovate and continue to engage stakeholders on the solutions used to deliver the outputs. Where they do not exceed a materiality threshold of 0.5% of annual base revenue a baseline allowance should be provided. |  | Ofgem | December | Drafting has been amended so this is an evaluative PCD to reflect our Final Determinations position. Please see Final Determinations for our decision on this policy. | Closed
8 | 29.10.2020 | Cadent | 3.12.8 | Offtakes & PRS Metering should not be included in the PCD for Cadent, they are part of the NARMs approach. This is therfore a 'double count'. See our response to DD GDQ22/23 | remove Offtakes and PRS Metering from Appendix 1 | Ofgem | December | This point relates to the policy in question, please see Final Determinations for our decision on this policy. | Closed
9 | 29.10.2020 | Cadent | 3.12.8 | We note SGN also has a large number of items in the PCD which should instead be part of NARMs | removes SGNs NARMs outputs from Appendix 1 | Ofgem | December | This point relates to the policy in question, please see Final Determinations for our decision on this policy. | Closed
10 | 29.10.2020 | Cadent | 3.12.8 | The allowances will need to be aligned to the values in FD. We have provided feedback to Ofgem that some of the values put forward in DD are not correct. |  | Ofgem | December | This point relates to the policy in question, please see Final Determinations for our decision on this policy. | Closed
11 | 29.10.2020 | Cadent | 3.12.8 | The items listed in Appendix 1 should be expanded for Cadent to include the Lowestoft Project (APP_CAD_09.63) and HP Valves APP_CAD_09.64. See our response to DD Cadent Q5 |  | Ofgem | December | This point relates to the policy in question, please see Final Determinations for our decision on this policy. | Closed
12 | 29.10.2020 | Cadent | 3.12.7 | Reference is made in this section to 3.12.5, is this a typo, should it infact be 3.12.6 | Replace '3.12.5' with '3.12.6' | Ofgem | December | Drafting amended to correct cross-reference. | Closed
13 | 29.10.2020 | Cadent | 3.12.8 | States 'the Regulatory Years to which those values relate' this text is not required, the delivery date for all items is 31st March 2026. As such phasing of allowance or spend is not relevent | remove 'the Regulatory Years to which those values relate' | Ofgem | December | This is one of several possible drafting approaches, we have preferred the one in our proposed modifications | Closed
14