## SpC 3.15 Asset Health PCD
Licence number and name: |  | SpC 3.15 Asset Health PCD
Ofgem contact: |  | Craig Molyneux
No. | Date raised | Comment from | Reference (Part X, Para Y) | Comment | Suggested alternative drafting (if necessary) | Assigned to | Due Date | Response | Issue closed?
1 | 2020-10-20 | NGGT | Part A | The formula logic of this condition is not clear and maybe unnecessary in Part A. NLAAt is defined as the sum of allowances in Appendix 1. NLARt is defined as the value that may be directed by the authority. Part D does not state that NLARt will be directed but that it will set out amendments to Appendix 1. |  | Craig |  | Clarified in consultation draft. | Closed
2 | 2020-10-20 | NGGT | General | Part C refers to the assessment of outputs being specified in the PCD Reporting Requirements and Methodology Document, however this document in its current draft form does not give specifics to the Asset Health non-lead PCDs. It is not clear how we will be measured or what the consequence of non-delivery. For post review, further discussion is required; recommend a bilateral to agree timelines, level of data required for a decision and if this is achievable. |  | Craig |  | Point accepted, these will be covered in FD as a starting point and discussed through bilaterals. | Closed
3 | 2020-10-20 | NGGT | General | We are working under the assumption of 4 areas for the non-lead PCD (Site Lighting, Cabs, Pipe Supports, and Pits) for Asset Health. |  | Craig |  | The categories are outlined in the relevant PCD annex - this now also includes fences in addition to the categories referenced. | Closed
4 | 2020-10-20 | NGGT | General | Given points outlined in the PCD Reporting Requirements and Methodology Document it would be beneficial for all PCD licence conditions to state whether they are Mechanistic or Evaluative? |  | Craig |  | Yes, we're doing this in FDs, this is evaluative. | Closed
5 | 2020-10-20 | NGGT | General | The approach to setting a potential value of NLARt if this PCD is considered mechanistic is not clear. The PCD Reporting Requirements and Methodology Document refers to licence formula. The formula in this condition then refers to the PCD Reporting Requirements and Methodology Document. This does not make it clear how we will be measured. |  | Craig |  | Not considered mechanistic, will be working on PCD reporting info going forwards. | Closed
6 | 2020-10-20 | NGGT | General | It is not clear how the necessary adjustment during the period on AH PCDs will be considered or applied. |  | Craig |  | Outputs table for PCD condition will be amended as required. | Closed
7 | 2020-10-20 | NGGT | Appendix 1 | How final determination will be translated into Appendix 1 is not clear. The current draft does not even represent the DD proposals which would provide understanding of how this appendix would work. |  | Craig |  | Table published alongside FDs. | Closed
8 | 2020-10-20 | NGGT | 3.15.2(b) | Should state “provide for an assessment of the Price Control Deliverable” for consistency with other PCD conditions. |  | Craig |  | Updated in consultation draft | Closed
9 | 2020-10-20 | NGGT | 3.15.3 | Replace “explains” with “sets out” |  | Craig |  | Amended. | Closed
10 | 2020-10-20 | NGGT | Headings | Headings should be framed as statements not questions. Part B heading should read “what the licensee id funded to deliver” and part D heading should read “Authority process in making a direction” |  | Craig |  | This is one of several possible drafting approaches, we have preferred the one in our proposed modifications. | Closed
11 | 2020-10-20 | NGGT | 3.15.7 | Should cross refer to 3.15.6 |  | Craig |  | Amended | Closed
12 | 2020-10-20 | NGGT | 3.15.8 | This provision should be 3.15.7(c) (and 3.15.9 renumbered accordingly) |  | Craig |  | Amended | Closed
13 | 2020-10-20 | NGGT | 3.15.9 (as written) | Should read “A direction under paragraph 3.15.7 will set out the value of the NLART term and the Regulatory Years to which those values relate” for consistency with other PCDs |  | Craig |  | Amended | Closed