## SpC 3.20
Licence number and name: |  | SpC 3.20: Diversions re-opener
Ofgem contact: |  | Graham Dickson/Callum Mayfield
No. | Date raised | Comment from | Reference (Part X, Para Y) | Comment | Suggested alternative drafting (if necessary) | Assigned to | Due Date | Response | Issue closed?
1 | 2020-10-28 | Cadent | Definitions | Clarify definition consistency with SLC and SSCs in SLC, a diversion may also include non pipe assets such as governors | means customer requested chargeable and non-chargeable works to move a distribution main or mains to allow for site development. |  |  | Drafting amended
2 | 2020-10-28 | Cadent | Definitions | Diversion costs definition - ensure that the RIGs definition is clear as this may not just be associated with pipes |  |  |  | Drafting amended
3 | 2020-10-28 | Cadent | Part B 3.18.5 | Drafting delivers position set out in DDs. However, policy needs revising in line with Cadent response to DDs. Our response to Core Document Q12 describes our position on re-opener windows. In summary, networks should be able to apply for a re-opener under any relevant UM in any given year of RIIO-2. However, networks should only have a maximum of two opportunities to make a submission for a given re-opener mechanisms over the length of the price control period. | An application to the Authority under paragraph [x] must be made Between [date] and [date] in any Regulatory Year, up to a maximum of two applications in the Price Control Period. |  |  | This point relates to the policy in question, please see Final Determinations for our decision on this policy
4 | 2020-10-28 | WWU | Definition of Diversion and Diversion Costs | Definitions are currently restricted to <7bar, we suggest that it should be equally applicable to >7bar. | Amend the definition of Diversion as follows: "means relocation of existing gas assets to accommodate third-party works for <7bar mains and associated services and >7bar mains and services." Amend the definition of Diversion Costs as follows: "means costs directly incurred, or expected to be so incurred by the licensee as a result of the relocation of existing gas assets to accommodate third-party works for <7bar mains and associated services and >7bar mains and services, other than costs which are recoverable directly from the customer or supplier, [as further clarified in the RIGs]" |  |  | This point relates to the policy in question, please see Final Determinations for our decision on this policy