## SpC 3.12 Kings Lynn
Licence number and name: |  | SpC 3.12 Kings Lynn Subsidence
Ofgem contact: |  | Craig Molyneux
No. | Date raised | Comment from | Reference (Part X, Para Y) | Comment | Suggested alternative drafting (if necessary) | Assigned to | Due Date | Response | Issue closed?
1 | 2020-10-20 | NGGT | General | Please see our response to consultation questions 20 and 21 relating to points applicable to PCDs and reopeners |  | Craig |  | Dates have been adjusted in line with NGGT timelines. | Closed
2 | 2020-10-20 | NGGT | Delivery Dates | There is no ability to request a change in delivery date under 3.12.6 unless clauses 3.12.6a) or b) are met. There may be occasions in which it would be in the interests of consumers to amend this date (where these triggers are not met). |  | Craig |  | Agree, amended | Closed
3 | 2020-10-20 | NGGT | 3.12.8 | 3.12.8 – as set out in our draft determination response (GT_Q3) it is important that Ofgem respond to reopener decisions by the proposed dates highlighted to Ofgem. Failure to do so may result in additional costs being incurred and project delays which should not be borne by the licensee if they have delivered to the agreed timescales. Propose that within this clause Ofgem sets out provisions for changes to subsequent reopener dates and increases of allowances for additional costs incurred if projects are delayed as a result of deferred decision making. |  | Craig |  | Don't agree on this principle - additional time is needed for reopener reviews if initial submission is of poor quality, and 28 day consultation windows are our standard approach. The licence puts obligations on licensees and not on Ofgem. | Closed
4 | 2020-10-20 | NGGT | Referencing | 3.12.10 reference to BTRRt should be KLSRt |  | Craig |  | Agree, amended | Closed
5 | 2020-10-20 | NGGT | Referencing | 3.12.13 reference to CEPRt should be KLSRt |  | Craig |  | Agree, amended | Closed
6 | 2020-10-20 | NGGT | Change is work has not progressed? | As 3.12.6 contemplates the amendment of outputs etc. In Appendix 1, it is not clear what would be requested if , under 3.12.6(b) the licensee did not intend to proceed. In such a case would the request be to amend the Appendix to reflect no output and zero allowances? Please could Ofgem clarify. |  | Craig |  | In this case we would use the reopener to assess the development spend against the allowance. | Closed
7 | 2020-10-20 | NGGT | Headings | Headings should be framed as statements not questions. Part B heading should read “What the licensee is funded to deliver” and art E heading should read“Authority process for making a direction” |  | Craig |  | This is the Ofgem drafting style - headings retained as questions. | Closed
8 | 2020-10-20 |  | 3.12.6 | As referred to above we believe this paragraph should make provision for a reopener to request delivery date changes where the additional funding request might not be triggered |  | Craig |  | Have amended to allow the Authority to specify different submission dates. | Closed
9 | 2020-10-20 |  | 3.19.8(c ) | Insert “in Appendix 1” after “allowances” at the end of the sentence. |  | Craig |  | Agree, amended | Closed
10 | 2020-10-20 |  | FEED Definition | Should refer to “tendered quote” rather than “fixed bid quote” |  | Craig |  | Agree, amended | Closed