## Re-Opener Guidance & Requiremen
Licence number and name: |  | N/A - applicable across all re-openers
Ofgem contact:
No. | Date raised | Comment from | Reference (Part X, Para Y) | Cross Sector/Finance Tracker Reference | Comment | Assigned to | Due Date | Response | Suggested alternative drafting (if necessary) | Issue closed?
1 | 2020-11-01 | SHET | 9.4 |  | We have no issues to raise in relation to SpC 9.4. We will raise any specific issues in response to Ofgem’s RIIO-2 Informal re-opener application guidance consultation for Transmission, Gas Distribution and Electricity System Operator licences. | Ofgem | 2020-11-11 | This point relates to the Re-opener Guidance & Application Requirements Document please see our draft document published for consultation.. |  | Closed
2 | 2020-11-01 | WWU | 9.4 |  | Change Re-opener Guidance and Application Requirements Document to 'Re-opener Application Requirements Document' | Ofgem | 2020-11-11 | This is one of several possible drafting approaches, we have preferred the one in our proposed modifications |  | Closed
3 | 2020-11-01 | SGN |  |  | Licence vs Network. We note that in section 2.13 we are asked to submit a single application covering both our license areas. This creates a risk that Ofgem will look at the net impact rather than treat them as individual and distinct applications. As it stands the threshold and the adjustment is defined by the licence and as such, while for practical reasons it may be convenient to submit a single document, it is important that each licensee's application for a reopener is considered in isolation for the majority of reopeners. The exception to this would be reopeners that are typically delivered centrally such as IT, data and cyber security where the projects are geographically independent. | Ofgem | 2020-11-11 | This point relates to the Re-opener Guidance & Application Requirements Document please see our draft document published for consultation.. |  | Closed
4 | 2020-11-01 | SGN |  |  | • Timing for responding to a reopener application. We fully acknowledge the time it will take to complete a full appraisal and to complete the necessary consultation processes. However, it is our view that nine months is too long to have certainty around the allowances that will be awarded and will jeopardise project delivery. If such timelines are necessary, then it is important that any preceding reopener takes this additional time into consideration when agreeing which projects to allow to progress. Without this, there will be a delivery gap between the first reopener projects awarded funding and the next set of projects agreed under the second reopener window. In cyber as an example, this could result in a 9 month period of uncertainty with security standards in the interim failing to keep pace with a changing threat level, followed by a catch up. | Ofgem | 2020-11-11 | This point relates to the Re-opener Guidance & Application Requirements Document please see our draft document published for consultation.. |  | Closed
5 | 2020-11-01 | SGN |  |  | SQ response. Whilst we acknowledge the importance of a tight turn around, it is important to recognise that particularly for more specialised re-openers the SQ response may be dependent on a key individual. This should be recognised in the response time and the current proposal appears very restrictive in that context. | Ofgem | 2020-11-11 | This point relates to the Re-opener Guidance & Application Requirements Document please see our draft document published for consultation.. |  | Closed
6 | 2020-11-01 | SGN |  |  | Our EJPs contain elements of a conceptual design and details on routing and sizing for example, which inevitably change as we progress through detailed design. In order to enable the flexibility to amend detailed elements where it is required by, or beneficial to, the project, we would suggest that delivery is linked to the realisation of the NARMs benefit for a given project. Alternatively, delivery could be defined as replacement of key systems only, although again we would wish to retain flexibility in approach. | Ofgem | 2020-11-11 | This point relates to the Re-opener Guidance & Application Requirements Document please see our draft document published for consultation.. |  | Closed

## Re-openersGeneral Design
Licence number and name: |  | N/A - applicable across all re-openers
Ofgem contact: |  | Cissie Liu
No. | Date raised | Comment from | Reference (Part X, Para Y) | Cross Sector/Finance Tracker Reference | Comment | Assigned to | Due Date | Response | Suggested alternative drafting (if necessary) | Issue closed?
1 | 2019-12-04 | Companies | 4 month deadline | N/A | Companies expressed interest in keeping a decision deadline, with the option for Ofgem to extend where needed. | Companies | 2020-02-17 | Ofgem are of the initial view that the licence is to mandate licensees, not the Authority. However, we may state our continued effort to make a timely decision in order to reflect decisions into the AIP. NG initial view: There should definitely be a time limit, not least because some of the decisions have a time limited window -e.g. if we have a supplier tender with a limited validity period we must have clarity of funding in time to give notice to proceed. A time limit is also necessary to ensure that any resulting adjustment is determined in time to feed into the AIP/PCFM process for recovery in the following regulatory year |  | Closed
2 | 2019-12-04 | Companies | clarity of submission requirements | N/A | Both Ofgem and companies agreed there could be merit for Ofgem to provide more clarity on expectations of submissions | Companies | 2020-02-17 | Ofgem have drafted a licence condition enabling creation and implementation of guidance relating to re-opener submissions. |  | Closed
3 | 2019-12-04 | Companies | Authority triggered re-opener | N/A | Companies questioned whether there would be a set window for the Authority to trigger re-opener. Companies suggested a set window for licensee and Authority re-openers, and also the opportunity for other mutually agreed re-openers. Companies raised concern that they would not be ready to submit if not given advanced warning of Authority triggering a re-opener | Companies | 2020-02-17 | Ofgem to consider. NG initial view: We don’t think Authority triggering would be appropriate for all reopener mechanisms. Some reopeners we have proposed are highly project specific and tied to specific milestone driven PCDs like Bacton site re-development or FEED stage compressor PCD. Hence we think the appropriateness of Authority triggering should be considered on a case by case basis so the definition of what are relevant licence conditions in this context needs to be clearly understood. Under RIIO 1 the Authority has the right to propose relevant adjustments (in defined windows) in relation to certain tightly defined uncertain cost categories.
4 | 2019-12-04 | Companies | Authority triggered re-opener | N/A | Companies expressed concern that Authority triggered re-opener could adjust allowance downwards | CL |  | It is within the Authority's power to adjust allowance upwards or downwards, for the interest of licensees and consumers. For example, where outputs are not needed. |  | Closed
5 | 2019-12-04 | Companies | Authority triggered re-opener | N/A | Companies queried how Ofgem will know the materiality threshold has been reached to trigger the Authority triggered re-opener. | CL |  | Ofgem will develop a proposed approach/process for Autohrity triggered re-openers at DD. |  | Closed
6 | 2019-12-04 | Companies | Authority triggered re-opener | N/A | Companies raised oconcern that they may be disadvantaged if the Authority triggered a re-opener, and they have not had sufficient time to collect data. | CL |  | Relates to issue 3 above. Ofgem will develop a proposed approach/process for Autohrity triggered re-openers at DD. |  | Closed
7 | 2020-02-05 | Companies | Authority triggered re-opener | N/A | Companies queried how Ofgem would determine whether to trigger re-opener, if licensee has requested it, and if a process for this will be laid out for this. | Companies | 2020-02-17 | Ofgem will develop a proposed approach/process for Autohrity triggered re-openers at DD. |  | Closed
8 | 2020-02-05 | Companies | Authority triggered re-opener | N/A | Company queried whether if licence needs to reflect the scenario where the authority triggered re-opener is requested by licensee. Licensee acknowledge policy needs to be developed | Companies | 2020-02-17 | Ofgem will develop a proposed approach/process for Autohrity triggered re-openers at DD. |  | Closed
9 | 2020-02-18 | NPg | Authority triggered re-opener |  | Giving the Authority the ability to trigger a re-opener will create uncertainty for investors. If Ofgem is to continue to introduce this mechanism, the Authority should be required to comply with a clear set of "ground rules" so that there is certainty over the integrity of the process. |  |  | An authority triggered re-opener is already present in some RIIO-1 licenses. This is not a new mechanism. Ofgem will develop a proposed approach/process for Autohrity triggered re-openers at DD. |  | Closed
10 | 2020-03-03 |  | "Re-opener Guidance" |  | Asked if the Guidance could be used to vary the scope of individual re-opener conditions | G.Craig | 2020-03-03 | The scope of each re-opener is set out in the licence this can not be altered by any form of guidance document | No Action Required | Closed
11 | 2020-03-03 | Companies | "Re-opener Guidance" |  | The licence refers to Board Assurance this might not always be appropriate. It might be better to refer simply to Assurance and use Guidance itself to say when board assurance will be required | G.Craig | 2020-04-01 | The reference to board assurance has been removed. This issue of the appropriate level of assurance will be consulted on in the guidance itself | Reference to Board assurance removed | Closed
12 | 2020-03-03 | Companies | "Re-opener Guidance" |  | Discussion with regard to licence holders obligations in situation where no guidance published or published just before application deadline. | G.Craig | 2020-03-03 | In the absence of Guidance licence holders could not be expected to comply with something that did not exist. Under public law Authority must publish Guidance reasonably in advance of an application window before compliance with that Guidance could be expected. NG comment: While the above explanation is accepted, it should be noted that the first cyber reopener is proposed to commence at the beginning of the RIIO-2 period. To the extent further guidelines need established to ensure the efficient conduct of this reopener, then such guidance needs established - ideally up to 4 months prior to the commencement of RIIO-2. | No Action Required. Our intention is that re-opener guidance will be in place for those re-opener mechanisms with an application window at the commencement of the RIIO-2 period | Closed
13 | 2020-03-11 | NG | XX.1 |  | "applications for re-openers". Is it clear what this means? Perhaps expand by reference generically (as it is assumed that this will be a standard rather than a special condition but it could refer to specific conditions that provide for a reopener if it is to be a special condition) to conditions that provide for a cost reopener OR define reopener in the definitions | G.Craig |  | We will define Re-Openers to make clear the application of this condition |  | Closed
14 | 2020-03-11 | NG | XX.3 |  | Suggest: The licensee must prepare any application for a reopener in accordance with…" | G.Craig |  | Agreed | licence drafting reflects this suggestion | Closed
15 | 2020-03-11 | NG | Definitions |  | XX.6 provides that the Re-opener Guidance will contain obligations. It is therefore inappropriate to refer to it as solely a guidance document in the definitions. | G.Craig |  | We have changed the name to Re-Opener Guidance and Application Requirements Document to clarify that it contains both gfuidance and actual requirements | Drafting now refects the new name | Closed
16