## SpC 3.27
Licence number and name: |  | SpC 3.27: Cadent London Medium Pressure re-opener issues log
Ofgem contact: |  | Graham Dickson/Callum Mayfield
No. | Date raised | Comment from | Reference (Part X, Para Y) | Comment | Suggested alternative drafting (if necessary) | Assigned to | Due Date | Response | Issue closed?
1 | 2020-10-28 | Cadent | General | Our comments on this condition relate to delivering against the position set out in the Draft Determinations. However, as set out in our response to DDs we do not agree with this policy and have proposed how it should be updated for FDs. In summary, the funding for London Medium Pressure Repex should not be via a re-opener as: 1. The needs case has been accepted previously and the costs are not sufficiently uncertain for it to be proportionate or reasonable for all funding to be in a re-opener; 2. This is a programme of work; and justification by section does not reflect the wider programme benefits and overall safety risks posed by these iron pipes; 3. The mechanism would lead to a stop/start work programme which would reduce our ability to maximise delivery efficiency; 4. The re-opener process will create confusion and uncertainty amongst our suppliers and stakeholders, reducing our ability to confirm and deliver to our plan; 5. We have provided the additional evidence required to give Ofgem the certainty to include this work as a Price Control Deliverable. |  |  |  | This point relates to the policy in question, please see Final Determinations for our decision on this policy. | Closed
2 | 2020-10-28 | Cadent | Definition | Definition of London Medium Pressure Project needs amending. It references the submission in the Business Plan, which has been developed further and resubmitted as part of our response to the Draft Determinations, and maybe refined further before Final Determintions. | London Medium Pressure Project means the programme of works within the scope of the RIIO-2 London Medium Pressure Project within Cadent's RIIO-2 Business Plan as amended in Cadent's response to the Draft Determination, or as otherwise amended from time to time with the approval of Ofgem. |  |  | Definition no longer used. | Closed
3 | 2020-10-28 | Cadent | Definition | Definition of Project Section needs to change as it refers to Project Section as submitted in the December Business Plan. The overall plan in relation to the London MP Project has been redevelopped and refined in Cadent's response to the Draft Determinations, and may be refined further before Final Determinations. | Project Section means each of the twelve specified sections within the scope of the RIIO-2 London Medium Pressure Project (having deleted - "within Cadent's RIIO-2 Business Plan submission") |  |  | Definition no longer used. | Closed
4 | 2020-10-28 | Cadent | 3.25.5 | Drafting delivers position set out in DDs. However, policy needs revising in line with Cadent response to DDs. Our response to Core Document Q12 describes our position on re-opener windows. In summary, networks should be able to apply for a re-opener under any relevant UM in any given year of RIIO-2. However, networks should only have a maximum of two opportunities to make a submission for a given re-opener mechanisms over the length of the price control period. | An application to the Authority under paragraph [x] must be made Between [date] and [date] in any Regulatory Year, up to a maximum of two applications in the Price Control Period. |  |  | This point relates to the policy in question, please see Final Determinations for our decision on this policy. | Closed
5 | 2020-10-28 | Cadent | 3.25.6.f | Whilst an application may include information from tendering processes this shouldn't be a requirement. This was not a requirement when submitting our business plans so should not be a requirement for re-openers. | set out a description of the proposed Project Sections and detailed cost assessment for each Project Section of the London Medium Pressure Project to be implemented under the application supported by market assessment. |  |  | We have changed the policy in our Final Determinations and this drafting has been changed to reflect our decision. Please see Final Determinations for our decision on this policy. | Closed
6 | 2020-10-28 | Cadent | 3.25.6.g | Whilst all of this information may be provided in an application it shouldn't be a requirement. This was not a requirement when submitting our business plan so should not be a requirement for re-openers. | provide evidence demonstrating that stakeholders operating within the area covered by each Project Section proposed in the application have been consulted and coordination regarding permissions and access to the construction area has been progressed with local authorities |  |  | We have changed the policy in our Final Determinations and this drafting has been changed to reflect our decision. Please see Final Determinations for our decision on this policy. | Closed
7 | 2020-10-28 | Cadent | 3.25.7.a / 3.25.8(a) | The relevant dates should be between 1 April 2021 and 31 March 2026 - not 31 March 2024. | Between 1 April 2021 and 31 March 2026 |  |  | We have changed the policy in our Final Determinations and this drafting has been changed to reflect our decision. Please see Final Determinations for our decision on this policy. | Closed
8 | 2020-10-28 | Cadent | 3.25.1 | In our response to DD we have put forward a additional detail to suport the LMP being added to base allowance as a PCD. The drafting of this section will need to reflect the latest information submitted. |  |  |  | This point relates to the policy in question, please see Final Determinations for our decision on this policy. | Closed