## SpC 3.13
Licence number and name: |  | SpC 3.13: Funded Incremental Obligated Capacity Re-opener Price Control Deliverable
Ofgem contact: |  | Dale Winch
No. | Date raised | Comment from | Reference (Part X, Para Y) | New Reference (Part X, Para Y) | Comment | Assigned to | Response | Suggested alternative drafting (if necessary) | Issue closed?
1 | 2020-10-28 | NGGT | 3.13.2 (b), Part C 3.13.7/8. |  | Condition only refers to network reinforcement. Allowances for Funded Incremental Obligated Entry/Exit Capacity may be used to fund the construction of additional assets and/or contractual arrangements to facilitate the release of that capacity, depending on the most economic and efficient outcome determined by the methodologies in place. | Ofgem/NGGT | Amended to allow for the inclusion of these applications. |  | Closed
2 | 2020-10-28 | NGGT | 3.13.4 |  | FIOCt refers to the values included in the table represented in Appendix 1, the sum of allowances by year. There is no guidance to how prior spend incurred is dealt with, specifically if this should fall within a previous regulatory period or cross into another. PARCA phase 2 and 3 timescales can span a 7 year period and will therefore always now encounter this issue. The current licence (5F Part C) details that 20% of the Totex allowance for the entire project is released in y-2, with 80% y-1, where y is the Formula Year during which the Contractual Delivery Date for the capacity falls. | Ofgem | We will consider this more widely for PCDs. |  | Open
3 | 2020-10-28 | NGGT |  |  | The definitions for Entry/Exit lead Time do not appear in the updated licence (Entry/Exit Lead Time means the day which is 24 months from the first day of the next month following the date on which the allocation occurred). This obligation has fed through to various processes and methodology statements and we believe this should continue to remain within the licence and can work with Ofgem to determine the most suitable place. | NGGT | This was previously in Condition 2D which we have removed. (Part E: Legacy Permit Arrangements). However if NGGT can suggest a suitable location, we can consider this further. |  | Open
4 | 2020-10-28 | NGGT | N/A |  | The main detail of the process is included in the FIOC guidance document. The elements included in this condition, such as the approvals linked to planning consents, are commented upon in the response to that associated document rather than here. FIOC Re-opener. We support the introduction of this re-opener. However, we note that it was not described as a PCD in Ofgem’s draft determination or in our previous discussions with the Ofgem team, and yet the licence drafting has been put forward as a PCD. We note the comment at paragraph 9.13 of the consultation on this point. It is unclear why Ofgem has now taken this approach or how it would seek to define the associated output (which in any event would be nil at the commencement of the RIIO-2 period prior to the re-opener being triggered). In our view the associated output, when triggered, will be the release of the FIOC in respect of which we will have commercial obligations in keeping with our methodology statements. We feel it would be inappropriate to overlay these obligations with PCD machinery | Ofgem | As per our FD position, we consider a PCD, combined with a reopener to be appropriate here, to ensure flexibility for re-adjustment of allowances, if required. |  | Closed
5 | 2020-10-28 | NGGT | Defined Terms |  | The GT definitions annex includes definitions of “FIOC Output” and “FIOC delivery date” but these terms are not used in 3.13. The definition of FIOC Project Direction and COAE also refers to such terms. Similar terms are used in the context of the ET LOTI condition because LOTI is not a PCD. We would therefore suggest that it is more appropriate for FIOC to follow the LOTI approach and be framed as a re-opener which, if triggered would establish funding to deliver a FIOC Output by a FIOC Delivery Date. This is the approach that has been discussed to date in relation to this condition. | Ofgem | As per our FD position, we consider a PCD, combined with a reopener to be appropriate here, to ensure flexibility for re-adjustment of allowances, if required. |  | Closed
6 | 2020-10-28 | NGGT | N/A |  | Clarification is required of the output and delivery date that will be included and assessed. The driver of the condition is to release the commercial capacity as required by the associated PARCA process, licence, code and methodologies. If some/all of this capacity is physically unavailable, constraint actions and subsequent costs/impacts to incentives may be incurred as defined in Special Condition 4.4. A reduction of allowances would be an additional penalty on top of the existing mechanisms designed to incentive timely delivery and could potentially drive sub-optimal decisions for delivery | Ofgem | We will include the approved output and allowance into Appendix 1 in line with the decision made via direction on the project, and considering all of the supplied evidence and information from NGGT. |  | Closed
7 | 2020-10-28 | NGGT | N/A |  | If the approach outlined above is adopted with this condition giving rise to a FIOC Output rather than a PCD then a FIOC Project Direction should be made by statutory licence modification in order to give appropriate rights of appeal to the licensee. Such an approach would be consistent with that which we are advocating in respect of LOTI. The approach to FIOC licence drafting has, thus far, been based on the LOTI drafting and we fail to understand the current proposal to move away from this and follow a PCD approach. | Ofgem | We consider self-modification to remain the most appropriate and proportional for the reopener design for FIOC. We also consider as PCD and Reopener to be appropriate. |  | Closed
8 | 2020-10-28 | NGGT | Part F |  | There are no details given regarding the time frames for the direction given. Equally, none are given in the guidance document supporting this licence condition. Current Licence provisions in Part B of Special Condition 5F (paragraphs 13 and14) provide that the Authority should notify the licensee within 7 days of the Capacity Notice if implementation should be suspended for additional consideration, or 28 days if notifying on implementation/non-implementation of the proposal. Equally, set dates are provided within Part D and E relating to the direction of allowances for funding of FIOC. The associated PARCA process is designed around such timescales and clarity in needed for impacts of decision timeframes to project programmes, both for the licensee and the customer requesting the capacity. This is further discussed in the response to the associated FIOCR guidance document, but links to other concerns raised regarding this lack of transparency of the decision-making process for other PCDs. We would need to include required dates for decision within our submission in order to maintain the relevant program to deliver our obligations for customers | Ofgem | We do not consider the licence as the appropriate place for introducing timings for Ofgem. However we will consider how to best take this into account in the associated guidance. |  | Closed
9 | 2020-10-28 | NGGT | 3.13.10(c) |  | We support the intention of the COAE provisions to ensure unforeseeable risks are not carried without limit by the licensee. We welcome the ability to vary the threshold, but question why 20% should be applied as the default. | Ofgem | No change. This is set at a level that we consider is of sufficient proportionality for the additional cost and resource. This is also consistent with the level for LOTI. |  | Closed
10 | 2020-10-28 | NGGT | 3.13.10 |  | We understand the COAE is also intended to allow adjustment of changes to outputs other than their costs (e.g. scope changes, amendment to delivery dates). As drafted, Part C only allows such changes if they result in increases/decreases in spend greater than the materiality threshold. It is possible that such requested changes to outputs or delivery date would be cost neutral or would cost less than the relevant threshold. Without such provision in the Special Condition. The COAE mechanism could not be used and, a full statutory licence change would be required to allow this, which would be disproportionate given such changes would only be made where Ofgem agrees there is consumer benefit. Our understanding is that SpC 3.13.10(c) and SpC 3.13.10(d) should apply only to requests for changes to allowances. | Ofgem | The COAE requirements are intended for substantial changes to expenditure only, in order for the additional time/resource for a re-assessment to be of value. We do not intend for this mechanism to be used to make minor changes to the output, delivery date or allowance, and not this risk should sit with the licensee. |  | Closed
11 | 2020-10-28 | NGGT | 3.13.23 |  | We do not find it appropriate to refer to Funded Incremental Obligated Capacity Re-opener Guidance (suggesting it is advisory), when there is an absolute obligation to comply with it in SpC 3.13.23. | Ofgem | We have amended the name of the guidance document to more accurately reflect its intention. |  | Closed
12 | 2020-10-28 | NGGT | 3.13.4 |  | The definition of FIOCAt should refer to the sum of values for the Regulatory Year, since the Appendix covers a number of Regulatory Years. | Ofgem | No change. The reference to the allowance is correct, rather than referring to a specific regulatory year. |  | Closed
13 | 2020-10-28 | NGGT | 3.13.7 |  | Change to “amending any of the outputs, delivery dates or associated allowances in Appendix 1”. | Ofgem | Amended |  | Closed
14 | 2020-10-28 | NGGT | 3.13.8 |  | Suggest “An application may only be made where…”. The provision is not a licence obligation to obtain approval, but a limitation on when an application may be submitted for consideration | Ofgem | Amended, with slightly different wording. |  | Closed
15 | 2020-10-28 | NGGT | 3.13.9 |  | Suggest replacing “must not” with “may only”. The provision is not a licence obligation prohibiting submission of an application but a limitation on when one may be submitted for consideration | Ofgem | Amended |  | Closed
16 | 2020-10-28 | NGGT | 3.13.9(a) |  | Insert “to the Authority” after “relevant notice” in line 2. Line 2 should also cross refer to Special Condition 9.13 | Ofgem | Amended |  | Closed
17 | 2020-10-28 | NGGT | 3.13.9(b) |  | Insert “relevant” in front of “material” | Ofgem | Amended, with slightly different wording. |  | Closed
18 | 2020-10-28 | NGGT | 3.13.10(a) |  | Insert “the event” after “foreseen” | Ofgem | Amended |  | Closed
19 | 2020-10-28 | NGGT | 3.13.15 |  | Formatting. Should be just one paragraph. 3.13.15 will then become 3.13.12 etc. | Ofgem | Amended |  | Closed
20 | 2020-10-28 | NGGT | 3.13.12 |  | Refer to “any evidence available” and move “has occurred" to the end of the sentence | Ofgem | Retained "supporting evidence", as evidence is required in order for this to be assessed. Have amended "has occurred". |  | Closed
21 | 2020-10-28 | NGGT | 3.13.15(e) |  | We suggest that 3.13.15(e) should be removed on the basis that it is very unclear what is required. If the licensee does not provide appropriate supporting evidence, it risks Ofgem not approving the application. | Ofgem | Amended |  | Closed
22 | 2020-10-28 | NGGT | Part F |  | Should not be framed as a question. Change to “Authority process in making a direction”. | Ofgem | No change. |  | Closed
23 | 2020-10-28 | NGGT | 3.13.20 |  | Suggest replacing “A direction” with “A FIOC Project Direction”. | Ofgem | No change. This should refer to amendment by direction, not the process stage (FIOC Project Direction) |  | Closed
24 | 2020-10-28 | NGGT | 3.13.17 |  | If a direction under 3.13.17 amends Appendix 1, this is inconsistent with the formula in 3.13.4 which sets such a direction as being separate to the appendix. | Ofgem | No change, we believe these work together as intended. |  | Closed
25 | 2020-10-28 | NGGT | 3.13.19 |  | Should these paragraphs refer to Part C and Part D? I.e. will the guidance cover a COAE application? | Ofgem | No change. Guidance will only provide more information on the application process under Part C. The licence already covers sufficient detail on the COAE process and requirements. |  | Closed
26 | 2020-10-28 | NGGT | 3.13.23-3.13.24 |  | There is a lot of duplication between these two paragraphs and we suggest that they are condensed into a single provision. | Ofgem | No change. This is standard wording for licence drafting for guidance. |  | Closed

## SpC 9.13
Licence number and name: |  | SpC 9.13: Capacity Requests, Baseline Capacity and Capacity Substitution
Ofgem contact: |  | Dale Winch
No. | Date raised | Comment from | Reference (Part X, Para Y) | New Reference (Part X, Para Y) | Comment | Assigned to | Response | Suggested alternative drafting (if necessary) | Issue closed?
1 | 2020-10-28 | NGGT | 9.13.11 |  | Summary table does not include Non-incremental obligated capacity in the table requirements.This means the impact of the substitutions published in Part D are not summarisedand would need to be calculated. Suggest inclusionof this category of capacity. | Ofgem | Amended |  | Closed
2 | 2020-10-28 | NGGT | 9.13.1/9.13.4 |  | Change to “Firm capacity request some or all of which constitutes Incremental Obligated Capacity” | Ofgem | Amended |  | Closed
3 | 2020-10-28 | NGGT | 9.13.5(c) |  | The cross reference should be to special condition 3.13 | Ofgem | Amended. Now 3.13. |  | Closed
4 | 2020-10-28 | NGGT | 9.13.7 |  | Clarification needed in paragraphs (e)and(f). Through the attempted simplification of these sentences, it now no longer refers back to the volumes of non-incremental that would be the result of capacity substitution in (b) and funded incremental in (c), which makes these unclear or have elements that are non-applicable in some circumstances. | Ofgem | Amended |  | Closed
5 | 2020-10-28 | NGGT | 9.13.7(b) |  | The cross reference to 6(c) of 9.18 is wrong as this does not exists. Is it perhaps intended that this is seeking to refer to 9.18.4/5 a) and b) in terms of the licensee determining how capacity should be dealt with? Please can Ofgem clarify? | Ofgem | Amended to point to the correct location. |  | Closed
6 | 2020-10-28 | NGGT | 9.13.9 |  | This should refer to Licence Baseline Exit Capacity | Ofgem | Amended |  | Closed
7 | 2020-10-28 | NGGT | Defined Terms |  | The GT definitions annex includes a definition of Zero Licence Baseline Entry CapacityTable but the term is not used. | Ofgem | Definition removed |  | Closed
8 | 2020-10-28 | NGGT | Defined Terms |  | Should the definitions of Zero Licence Baseline Entry and Exit Points refer to “any baseline funding allowance”? | Ofgem | Amended |  | Closed
9