## SpC_3.23
Licence number and name: |  | SpC 3.23 Smart Metering Roll-out Re-opener
Ofgem contact: |  | Nicole Weir
No. | Date raised | Comment from | Reference (Part X, Para Y) | Comment | Suggested alternative drafting (if necessary) | Assigned to | Due Date | Response | Issue closed?
24 | 29.10.2020 | Cadent | 3.21.5 | Erroneous extra full stop | 3.21.4 | Nicole Weir | December | Removed. | Closed
25 | 29.10.2020 | Cadent | 3.21.5 | Drafting delivers position set out in DDs. However, policy needs revising in line with Cadent response to DDs. Our response to Core Document Q12 describes our position on re-opener windows. In summary, networks should be able to apply for a re-opener under any relevant UM in any given year of RIIO-2. However, networks should only have a maximum of two opportunities to make a submission for a given re-opener mechanisms over the length of the price control period. | An application to the Authority under paragraph [x] must be made Between [date] and [date] in any Regulatory Year, up to a maximum of two applications in the Price Control Period. | Nicole Weir | December | This point relates to the policy in question, please see Final Determinations for our decision on this policy. | Closed
26 | 29.10.2020 | Cadent | 3.21.7(b) | Further clarification needed on 'take account of any allowed expenditure, which can be avoided as a result;' | take account of any allowed expenditure, which can be avoided as a result of these additional Smart Metering Roll-out Costs; and | Nicole Weir | December | Made suggested change. | Closed
27 | 30.10.2020 | SGN | Reference Para 10.45 – 10.46 | It is highly likely that the most challenging Smart Metering installations, and those therefore most likely to require intervention, will remain back-weighted towards the end of the period. As such, we have concerns regarding the timing of the re-opener window being less than a year after the start of the new price control. While we acknowledge that such a window may be appropriate to capture GD1 close-out issues, particularly those which arise as a consequence of COVID-19, an early window would not sufficiently capture any challenges associated with the roll-out which materialise later in the price control period. Given the acknowledgment in the draft determination that the timing of the smart metering roll-out is out of the GDNs’ control, it is not appropriate for GDNs to carry the risk associated with a single, early, application window and recommend the inclusion of a second window in year four of the price control.We also have concerns regarding the high materiality threshold associated with this reopener. We anticipate this may only be met in the latter stages of the price control, when the intervention rate has reached an equivalent annual total of 5%. Given the proposed position in the draftdetermination to include a flat 2.5% intervention profile, we recommend that the materiality threshold is adjusted in order to accommodate any interventions in excess of this 2.5% baseline rate. |  | Nicole Weir | December | This point relates to the policy in question, please see Final Determinations for our decision on this policy. | Closed
28 | 28.10.2020 | Northern Powergrid | Introduction, para 3.21.2 | Refer to materiality threshold in Appendix 1 for consistency | See tracked changes in the GD licence | Nicole Weir | December | Materiality Threshold is no longer in Appendix 1. This is now a defined term. | Closed
29 | 28.10.2020 | Northern Powergrid | Part A, para 3.21.4 | Part C is about how to make an application so change t refer to materiality threshold in Appendix 1 for consistency | See tracked changes in the GD licence | Nicole Weir | December | Part C includes reference to the defined term Materiality Threshold. | Closed