## SpC 3.10 Bacton
Licence number and name: |  | SpC 3.10 Bacton Terminal Redevelopment
Ofgem contact: |  | Craig Molyneux
No. | Date raised | Comment from | Reference (Part X, Para Y) | Comment | Suggested alternative drafting (if necessary) | Assigned to | Due Date | Response | Issue closed?
4 | 2020-10-20 | NGGT | FOSR and Reopener Dates | There is no ability to request a change the date of submission of the final option selection report. There may be occasions in which it would be in the interests of consumers to amend this date Suggest change 3.10.7(b) to - be submitted by the date specified in Appendix 1, unless otherwise approved in writing by the Authority. |  | Craig |  | Agree, drafting amended. | Closed
5 | 2020-10-20 | NGGT | FOSR and Reopener Dates | 3.10.8 – as set out in our draft determination response (GT_Q3) it is important that Ofgem respond to reopener decisions by the proposed dates highlighted to Ofgem. Failure to do so may result in additional costs being incurred and project delays which should not be borne by the licensee if they have delivered to the agreed timescales. Propose that within this clause Ofgem sets out provisions for changes to subsequent reopener dates and increases of allowances for additional costs incurred if projects are delayed as a result of deferred decision making. |  | Craig |  | Don't agree on this principle - additional time is needed for reopener reviews if initial submission is of poor quality, and 28 day consultation windows are our standard approach. | Closed
6 | 2020-10-20 | NGGT | FOSR and Reopener Dates | 3.10.16 - We are concerned that Ofgem undertaking a 28 day consultation at this point given the timelines we set out in our response to DD consultation question NGGT_Q27 will lead to Ofgem not meeting the requested response timeline to ensure we can deliver the project to planned timescales. Please see also our DD response to GT_Q3 which demonstrates the importance of Ofgem responding to reopener decisions in a timely manner. We would like to ask that a turnaround time for Ofgem’s review is set. If not, additional costs may be incurred relating to project delays. We propose that within this clause Ofgem sets out provisions for changes to subsequent reopener dates and increases of allowances for additional costs incurred if projects are delayed as a result of deferred decision making. |  | Craig |  | Don't agree on this principle - additional time is needed for reopener reviews if initial submission is of poor quality, and 28 day consultation windows are our standard approach. | Closed
7 | 2020-10-20 | NGGT | FOSR and Reopener Dates | Please see our response to consultation questions 20 and 21 relating to points applicable to PCDs and reopeners. |  | Craig |  | Dates have been adjusted in line with NGGT timelines. | Closed
8 | 2020-10-20 | NGGT | Appendix 1 | Further discussions are required with Ofgem to form up the correct dates for inclusion in the version of Appendix 1 contained in Final Determination |  | Craig |  | Dates adjusted following bilateral. | Closed
9 | 2020-10-20 | NGGT | Headings | Headings should be framed as statements not questions. Part B heading should read “What the licensee is funded to deliver”. Part F heading should read “Authority process for making a direction” |  | Craig |  | This is one of several possible drafting approaches, we have preferred the one in our proposed modifications. | Closed
10 | 2020-10-20 | NGGT | Definitions | The definitions of “Final Options Selection Report” and “Front End Engineering Design” refer to “PCD Guidance”. Presumably this should now refer to “PCD Reporting Requirements and Methodology Document”. These definitions also refer to “Gas Network Development Process” which is not a defined term. |  | Craig |  | Definitions updated. | Closed
11 | 2020-10-20 | NGGT | 3.10.2 | Remove “and Authority” in 3.10.2(b) as there is no Authority triggered re-opener in this condition. |  | Craig |  | Drafting amended. | Closed
12 | 2020-10-20 | NGGT | 3.10.7(b) | We suggest (b) is amended to read “ be submitted by the date specified in Appendix 1, unless otherwise approved in writing by the Authority” |  | Craig |  | Drafting amended to allow for flexibility around submission dates with Ofgem's consent. | Closed
13 | 2020-10-20 | NGGT | 3.10.8© | Insert “in the Final Option Selection Report” after “options” at the end of the sentence |  | Craig |  | Amended. | Closed
14 | 2020-10-20 | NGGT | 3.10.10 | As referred to above we believe this paragraph should make provision for a reopener to request delivery date changes where the additional funding request might not be triggered. |  | Craig |  | Text around changes to reopener dates now allows for more flexibility in terms of timing, regardless of circumstances. | Closed
15 | 2020-10-20 | NGGT | 3.10.12€ | We suggest there is no need to refer to FEED in the sub-paragraph (e) as it must be included in (a) by virtue of 3.18.13(b) |  | Craig |  | Removed. | Closed
16 | 2020-10-20 | NGGT | FEED Definition | Should refer to “tendered quote” rather than “fixed bid quote |  | Craig |  | Agree, amended. | Closed
17 | 2020-10-20 | NGGT | FEED Definition | should refer to “tendered costs (where applicable)” rather than just tendered costs (as NG costs will be included and aren’t tendered) |  | Craig |  | Amended. | Closed
18 | 2021-01-20 | NGGT | 3.10.3 | Should cross refer to “paragraph 3.10.10 or 3.10.14” |  | Craig |  | References updated. | Closed
19 | 2021-01-20 | NGGT | 3.10.4 | BTRAt term – the total allowance should read £10.5m (post adjustment allowance, consistent with Appendix 1) |  | Craig |  | Allowances no longer referenced in licence text, instead referring to appendix. | Closed
20 | 2021-01-20 | NGGT | 3.10.6 | The definition of “Final Option Selection Report” in Special Condition 1.1 should be amended by deleting “as set out further in Associated Documents” and replacing this text with “as set out in the PCD Reporting Requirements and Methodology Document” (as per the definition of “Front End Engineering Design” in Special Condition 1.1). |  | Craig |  | Have updated this to refer to updated AD title. | Closed
21 | 2021-01-20 | NGGT | 3.10.7 (b) | we suggest that this is amended so as to read “by the delivery date specified in Appendix 1” to make clear that this is the first of the two dates that are set out in Appendix 1. |  | Craig |  | Drafting amended to specify delivery date. | Closed
22 | 2021-01-20 | NGGT | 3.10.10 | The application window dates here are different to those in Appendix 1.They should be as the 3.10.10 dates. |  | Craig |  | Dates corrected. | Closed
23 | 2021-01-20 | NGGT | 3.10.10 | replace “or during such later period” with “or such other periods” (as per the approach taken in Kings Lynn PCD at 3.12.6. |  | Craig |  | Drafting amended in line with King's Lynn. | Closed
24 | 2021-01-20 | NGGT | 3.10.12(b) | the definition of “Front End Engineering Design” in Special Condition 1.1 still refers to “fixed bid quote” rather than “tendered quote”. The issue log reflects that reference to “tendered quote” is agreed so the drafting needs to be updated accordingly. |  | Craig |  | Definition updated | Closed
25 | 2021-01-20 | NGGT | Appendix 1 | It could be made clearer that the delivery date of 28/02/2022 represents the delivery of 4.2 final option selection report (see comment at 3.10.7 above) and the Application window of 01/09/2023 - 07/09/2023 represents the delivery of the final preferred option report at 4.3. We suggest “Reopener” Application Window is added to the table title to make this clearer. |  | Craig |  | Table amended to clarify this. | Closed