## SpC_3.15
Licence number and name: |  | Pre-Construction Funding re-opener
Ofgem contact: |  | Joe Slater
No. | Date raised | Comment from | Reference (Part X, Para Y) | Comment | Suggested alternative drafting (if necessary) | Response | Issue closed?
1 | 2020-10-28 | SHET | SpC 3.22 | The licence condition as it is currently drafted is no longer fit for purpose. We do not think the position set out by Ofgem on PCF is accurate and we await the formal licence drafting consultation, following publication of FDs. Notwithstanding our fundamental issues with this licence condition, we also submit that the current close out provision is not workable in practice, as noted in the introduction. In any case, the close out window cannot be in January 2026 (when the T2 period is still ongoing.) Instead, the close out window should be handled as part of the submission of the final year’s RRP (when all of the data necessary for making an appropriate determination will be available). |  | This relates to a difference in opinion about the policy, our policy decision is set out in FDs. | Closed
2 | 2020-10-28 | SHET | SpC 3.22.4(b) | This is incorrect. It does not require a NOA proceed. See the definition of LOTI in the guidance. This should be removed |  | This relates to a difference in opinion about the policy, our policy decision is set out in FDs. | Closed
3 | 2020-10-28 | SHET | SpC 3.22.5 | We recognise that this is Ofgem’s DD position. We disagree with this policy position and expect a change in the licence to reflect revised policy at FD. |  | This relates to a difference in opinion about the policy, our policy decision is set out in FDs. | Closed
4 | 2020-10-28 | SHET | SpC 3.22.6 | As per SpC 3.22.5, LOTI is not only for NOA projects, therefore PCF is not only for NOA projects |  | This relates to a difference in opinion about the policy, our policy decision is set out in FDs. | Closed
5 | 2020-10-28 | NGET | Parts A,and D headings | It is not consistent with the licence generally to use questions as headings.We suggest:oChanging Part A to “Costs within scope of this Re-opener”. oChanging Part D to “Process for making directions under this condition”. |  | Drafting amended | Closed
6 | 2020-10-28 | NGET | SpC 3.22.5 | Suggest replacing “an adjustment” with “a direction”. |  | Drafting amended | Closed
7 | 2020-10-28 | NGET | SpC 3.22.6 | It is implicit that the application will be in writing and need not be set out expressly |  | This is one of several possible drafting approaches, we have preferred the one in our proposed modifications. | Closed
8 | 2020-10-28 | NGET | SpC 3.22.6© | Suggest “...why the Pre-Construction Works were required and why any Pre-Construction Works were aborted” or similar to cater for efficiently incurred abortive costs. |  | This issue is no longer relevant following updates to policy position | Closed
9 | 2020-10-28 | NGET | SpC 3.22.4, SpC3.22.6(d) | Investments to facilitate customer connections (instigated by the ESO through an NGESO Connection Application; ref. SO-TO Code, Schedule 5 ) and asset health investments >£100m should also be eligible for PCF, where relevant, in accordance with para. 4.25 of the DD ET Annex). In SpC 3.22.4(b), we suggest. “the LOTI was, at the time the costs were incurred: (i) subject to a NOA Proceed Signal, for Boundary Reinforcement Projects; (ii) subject to a notification by the ESO of an application for connection for connections; and (iii) subject to a positive NARMS indication for asset health related investment”. A similar change should be made to SpC 3.22.6(d) (or a cross-reference included to SpC 3.22.4(b) above. |  | Drafting amended | Closed
10 | 2020-10-28 | SPT | 3.22.1 | In addition to the wider comments on how the PCFt term contributes to the calculation of the Totex Allowance, noted that a direction from the Authority adjusts the value of the PCFt term. However, whilst the direction refers to this adjustment, the adjustment does not link into this licence condition: no mechanism is specified in the condition for how the PCFt term is adjusted. |  | Drafting amended | Closed
11 | 2020-10-28 | SPT | 3.22.1 (contd) | Furthermore, there is nothing in the licence setting out how the value of PCFt is derived, or indeed how or when it is applied to the Totex Allowance. Clarity on this is needed in the licence drafting. |  | Drafting amended | Closed
12 | 2020-10-28 | SPT | 3.22.4(b) & 3.22.6(d) | There may be occasion where we need to develop a NOA scheme without a “proceed”. Our Windyhill-Lambhill-Longannet 275kV Circuit Turn in to Denny North WLTI) is an example of this. Justification for this may be due to outage windows or contracted generation | (b) the LOTI was subject to a NOA Proceed Signal at the time the costs were incurred or, expenditure can be suitably justified; and | Drafting amended | Closed
13 | 2020-10-28 | SPT | 3.22.4(b) & 3.22.6(d) | This part of the licence assumes PCF is only required when a LOTI project has been given a NOA proceed in that particular year. This is not always the case. There may be occasion where we need to develop a NOA scheme without a “proceed”. Our Windyhill-Lambhill-Longannet 275kV Circuit Turn in to Denny North WLTI) is an example of this. Justification for this may be due to outage windows or contracted generation. The wording needs to be changed to ensure costs to develop schemes if there isn't a NOA proceed but is suitably justified can still be remunerated | (b) the LOTI was subject to a NOA Proceed Signal at the time the costs were incurred or, if not, expenditure can be suitably justified; and | Drafting amended | Closed
14 | 2020-10-28 | SPT | 3.22.5 | The proposed application window is very short and begins on a Sunday rather than a working day. The window also occurs in the last 3 months on the RIIO-T2 price control which seems inappropriate. The drafting provides that Ofgem can direct a later period – given that the price control period ends two months after the end of the proposed window this seems unworkable in practice - at the very least the drafting should be clarified to confirm that this period will not be any later than the end of the price control period. How does Ofgem anticipate dealing with PCF that continues to run up to/ beyond the end of the price control period? A mid-period window required, otherwise TOs will carry too much risk developing projects. | Additional mid-period window dates included | This issue is no longer relevant following updates to policy position | Closed
15 | 2020-10-28 | SPT | 3.22.6(b) and (c) | This provides for an adjustment to the PCFt term but as detailed above the licence does not set out how PCFt is set in the first instance. This requires clarification so that a licensee can make adjustments and explain how those adjustments are calculated. |  | Drafting amended | Closed
16 | 2020-10-28 | SPT | 3.22.8 | Given the process set out here for consulting on a direction, it is unclear why Ofgem would not proceed with a licence modification instead. The process set out here appears to have the same characteristics of the licence modification process, however, a direction removes the right of licensees to appeal to the CMA which is a key statutory protection which Parliament has afforded to licensees and which Ofgem should not override in this way. See also our comments on modification of licence conditions in our response to consultation question 1 in Appendix 1. |  | This is a standard RIIO-2 approach | Closed
17 | 2020-10-28 | SPT | 3.22.8 | Reference to any relevant Opex uplift , however provides no detail on how this will/should be calculated. Is this meant to represent the Opex Escalator Indexation Re-opener term in the PCFM? |  | Opex reference now removed as not relevant to PCF | Closed
18 | 2020-10-28 | SPT | 3.22.8 | As stated above in issue 3, the PCFt (Row 44 of PCFM SPT Tab) will include any relevant Opex uplifts, however the Opex Escalator Indexation Re-opener term is a separate row within the PCFM (Row 47). This will lead to a double count. |  | Opex reference now removed as not relevant to PCF | Closed
19 | 2021-01-19 | SPT | 3.15.7 | Given the interaction of this paragraph with 3.15.6, the Reopener for additional/revised PCF is only available when submitting a LOTI Initial Needs Case, unless Ofgem directs that a licensee can apply at another time. For SPT, the Eastern HVDC already has its Initial Needs Case, so there would be no trigger for SPT to seek a reopener for PCF (even if the cost of Pre Construction Works looks likely to be more than double during the course of the price control period) under either 3.15.6(a) or 3.15.6(b). This in effect means SPT can only rely on 3.15.6(a) as a reopener for new LOTI projects to be granted at Initial Needs Cases and there is no mechanism to increase PCF thereafter, even if the allowances would be double. This is unsatisfactory. It is not acceptable for a TO not to have recourse to an amendment process in circumstances where, having been diligent in its development (of an expensive & complex scheme), it has incurred justified and efficient expenditure that exceeds a pre-defined threshold. The threshold of expenditure >2x allowance was to prevent multiple approaches to Ofgem for cost escalations and TO’s agreed this as reasonable. The intent, however, was that when this threshold was (or was forecast) to be exceeded a TO could trigger a review. It looks like there is a clause missing, which would address this issue. |  | This is one of several different valid drafting approaches and we have chosen the one set out in our licence modifications. Not required as we already include an ability for Ofgem to direct an alternative time. | Closed
20 | 2021-01-19 | SPT | Appendix 1 | Allowance of £5.40m for LOTI FNC E-HVDC link. In FD this figure is £5.72m. This figure should be amended to reflect FD. |  | Drafting amended to £5.65m | Closed
21 | 2021-01-19 | NGET | 3.15.4 | The definition of “PCFAt” is currently incorrect as the value is not the sum of the allowances, but only the sum of the allowances relating to year t. We propose changing to “means the sum of allowances for Regulatory Year t in Appendix 1”. We note that the numbering here is in a different size to the other numbering. |  | The PCFM needs to have five annual values representing the net PCD allowance, represented by the t notation. The total of the baseline allowance less any directed reductions. So although PCDs get evaluated at the end of the price control, we still need the subscript t and a number for each year. | Closed
22 | 2021-01-19 | NGET | 3.15.6 | We propose that, in addition to this provision, a further provision should allow for applications to change outputs and delivery dates in Appendix 1 in appropriate circumstances which do not relate to cost changes. To keep this targeted, we propose that such an application may be made “...where the change to an output or delivery date is caused by an outcome of the NOA process”. |  | This relates to a difference in opinion about the policy, our policy decision is set out in FDs. | Closed
23 | 2021-01-19 | NGET | 3.15.6(b) | To remove ambiguity, we propose changing the wording at the end of this sub-paragraph to “...more than double the allowance provided for those Pre-Construction Works”. |  | Drafting amended | Closed
24 | 2021-01-19 | NGET | 3.15.7 | Given the defined term Initial Needs Case refers to a LOTI, the first reference to “LOTI” here should be deleted. |  | Drafting amended | Closed
25 | 2021-01-19 | NGET | Part D, Heading | Can “outputs” be deleted? |  | This is one of several different valid drafting approaches and we have chosen the one set out in our licence modifications. | Closed
26 | 2021-01-19 | NGET | 3.15.10(a) | The following wording is ambiguous: “where the authority considers that the licensee has completed a sufficient proportion of Pre-Construction Work...”. We propose that further clarity is provided on what is a sufficient proportion or the paragraph is reworded to “where the authority considers that the licensee has incurred Pre-Construction Work expenditure in an economic and efficient manner...”. |  | This is one of several different valid drafting approaches and we have chosen the one set out in our licence modifications. | Closed
27 | 2021-01-19 | NGET | 3.15.10© | We propose that “the Pre-Construction Works PCD allowance...” should be changed to “the allowance for the relevant Pre-Construction Works...”, to be consistent with sub-paragraphs (a) and (b). |  | This is one of several different valid drafting approaches and we have chosen the one set out in our licence modifications. | Closed
28 | 2021-01-19 | NGET | Appendix 1 (allowances) | To align with the formula, our understanding is that allowances should be provided per Regulatory Year. Also, it is not clear how these allowances have been derived. Clarity on the approach used is requested. |  | This is one of several different valid drafting approaches and we have chosen the one set out in our licence modifications. | Closed