## SpC 9.14
Licence number and name: |  | SpC 9.14 Prohibited procurement activities
Ofgem contact: |  | Kelvin Hui
No. | Date raised | Comment from | Reference (Part X, Para Y) | Comment | Suggested alternative drafting (if necessary) | Assigned to | Due Date | Response | Issue closed?
1 | 28.10.20 | NGGT |  | Drafting issues It should be noted that the proposed changes to this condition are not related to the sale by NGGT of Cadent Gas as is suggested by paragraph 9.65 of the consultation. The sale of Cadent Gas has led to the deletion of the NTS/GDN business separation conditions set out in Special Conditions 10A,B andC of the NGGT licence (as noted in 9.116 -9.124 of the consultation)but is not related to the proposed changes to this condition as suggested by the consultation. •Line 1 should refer to 9.14.4 •Lines 1,2 and 5 should refer to 9.14.3 |  | Kelvin Hui |  | Acknowledge error in the consultation - amendments made. | Closed
2 | 28.10.20 | NGGT |  | Market driven IT change Our response to NGGTQ29 of the draft determinations requested that two IT investments to facilitate Market Driven change be treated as SO pass-through items. Assuming the policy position is accepted we would expect it to be addressed within this licence condition. |  | Kelvin Hui |  | This has been addressed and actioned by the IT team. | Closed
3 | 2021-01-20 | NGGT |  | 9.14.3 (b)-This provision refers to the defined term “Relevant Gas Transporter”. The proposed change to the definition of “Relevant Gas Transporter” with reference to 9.14.3 is not required and is also inconsistent with the existing licence condition 10D. It is not clear why (a) and (b) in the definition need to be excluded from the defined term as it applies to 9.14.3(b). Both the licensee and an affiliate could hold a separate relevant gas transporter licence as contemplated by 9.14.3(b).Accordingly in the definition of “Relevant Gas Transporter” in Special Condition 1.1, the words beginning with “except in Special Condition 9.14 should be omitted” |  | Kelvin Hui |  | Agree - the amendment to the defintions means that there is a double negative i.e This would prevent NGGT affiliated comapanies to not not acquire capacity Amend the licence defintion | Closed