## SpC_3.10
Licence number and name: |  | SpC3.10 Tier 1 Mains Price Control Deliverable
Ofgem contact: |  | Duncan Innes
No. | Date raised | Comment from |  | Reference (Part X, Para Y) | Comment | Suggested alternative drafting (if necessary) | Assigned to | Due Date | Response | Issue closed?
1 | 29.10.2020 | Cadent | SpC 3.9 | 3.9.3 | T1MRAt is not defined and the constant 0.02 should be explained. | 0.02 This factor is included to limit upward adjustment to 2% T1MRAt ? | Ofgem | 2020-12-15 | T1MRAt definition has been added in | Closed
2 | 29.10.2020 | Cadent |  | 3.9.3 | As discussed in previous and ongoing engagement with Ofgem the 0.02 (2%) tolerance is too restrictive and a greater band should be used. |  | Ofgem | 2020-12-15 | This point relates to the policy in question, please see Final Determinations for our decision on this policy. | Closed
3 | 29.10.2020 | NGN | SpC 3.9 | Para 3.9.1 | Not clear whether this is an annual process or completed at the end of the price control. Not clear whether the Totex allowance includes a forecast for Tier 1, and this replaces that, or whether added on top. |  | Ofgem | 2020-12-15 | We have added a clarification that the calculation will occur after the end of the price control period | Closed
4 | 29.10.2020 | NGN |  | Appendix 1 | Dependant on the answers to the above, do we need Allowed Unit Costs for each year, as there will be assumed efficiency gains annually? We will need to report against them annually and in RRP? What Price Basis are the unit costs? |  | Ofgem | 2020-12-15 | There is no need for annual unit costs, since the value of T1MRA is only calculated at the end of the period. The price basis is 2018/19 as is the case throughout the licence. | Closed
5 | 29.10.2020 | NGN |  | Appendix 2 | Are these values £ or Km? If £ what is the price basis? Couldn’t Appendix 1 and 2 be brought together to make it clear how they relate to each other |  | Ofgem | 2020-12-15 | Units have been clarified for all the appendices. We think it is clearer to have a separate appendix for each element of the calculations. | Closed
6 | 29.10.2020 | NGN |  | Part A, para 3.9.3 | Are the dots in the Algebra meant to be multiplication signs? Value 0.02 needs to be a defined term - presume it’s a cap? Not clear what the last part of the algebra outside of the brackets is doing - T1MRAt is not defined Is T1MRA a value for the whole of the price control, with T1MRAt being a value for the year in question? |  | Ofgem | 2020-12-15 | Yes - dots represent multiplication. T1MRAt has been defined. 0.02 has been updated to 0.03 reflecting the policy decision to increase the cap. We think this can remain a number rather than a defined term. The final part of the equation allocates the total adjustment between individual years. Yes - T1MRA is for the whole of the price control. | Closed
7 | 30.10.2020 | SGN |  | 3.9.3 | A formula is shown for calculating the Tier 1 Mains Decommissioned Price Control Deliverable term (TIMDt). This formula contains the term T1MRAt. Please can you confirm what the term T1MRAt refers to? |  | Ofgem | 2020-12-15 | T1MRAt definition has been added in | Closed
8 | 30.10.2020 | SGN |  | Part C | Please can you confirm whether the reporting requirements detailed in Part C will be applied at the end of GD2 or on an annual basis over GD2. |  | Ofgem | 2020-12-15 | We have added a clarification that the calculation will occur after the end of the price control period | Closed
9 | 30.10.2020 | SGN |  | Appendix 1 | Please can you confirm the units for the Baseline Target Workloads and the Allowed Unit Costs in the Appendix 1 tables. |  | Ofgem | 2020-12-15 | The units have been added in for all appendices | Closed
10 | 2021-01-04 | Cadent | SpC3.10 Tier 1 Mains Price Control Deliverable | Appendices 1 & 2 | Need to ensure the correct workload figures are captured within the licence. London - minor variation in workload between those shown in appendices 1 & 2 of SpC 3.10 (1,531.3km) to that shown in Table 14 of Cadent Annex (1531.4km) North West - minor variation in workload between those shown in appendices 1 & 2 of SpC 3.10 (1,918.4km) to that shown in Table 15 of Cadent Annex (1,918.3km) |  | Ofgem | February | We will ensure that all values in the final version of the licence are correct. | Closed
11 | 2021-01-16 | Cadent | SpC3.10 Tier 1 Mains Price Control Deliverable | Appendices 2 & 3 | There are errors in the allowances and unit costs shown in this licence condition. We have submitted queries and evidence on these errors through the Final Determination Question (FDQ) process. The assessment and correction of these errors form part of Ofgem’s errata process and the inclusion of incorrect allowances and unit costs within this licence condition impacts and limits our ability to undertake an informed assessment through this licence consultation. |  | Ofgem | February | We are satisfied that the formula works as intended. | Closed
12 | 2021-01-16 | Cadent | SpC3.10 Tier 1 Mains Price Control Deliverable | 3.10.3 | We cannot confirm that this formula will adjust revenues correctly, and as intended by Ofgem’s Final Determinations, due to the absence of guidance notes for the PCFM handbook. As such, our ability to undertake an informed assessment of this licence condition is limited. |  | Ofgem | February | The operation of this condition, including the adjustment formula, is not affected by the values of the allowances and unit costs, and we are satisfied that it works as intended. | Closed
13 | 19.01.2021 | SGN |  | Appendix | Several inconsistencies have been identified with the SGN numbers shown in the appendices of this licence. These issues have been picked up in a FDQ (SGN_FDQ_010), and also mentioned in a letter recently sent concerning issues with the FD. We’re therefore unable to conclude our comments on this licence until these matters have been resolved. |  | Ofgem | February | This is the same issue raised in line 15 - see above for our response. | Closed