## SpC_3.27
Licence number and name: |  | SpC 3.27 SF6 asset intervention Re-opener and Price Control Deliverable (SF6t)
Ofgem contact: |  | Dale Winch
No. | Date raised | Comment from | Reference (Part X, Para Y) | Comment | Suggested alternative drafting (if necessary) | Response | Issue closed?
1 | 2020-11-18 | NGET | XX.6 | Request for the trigger options to be expanded to account for 1) changes in the cost or scope of what is set out in Appendix 1, due to additional information and 2) to allow for submission of further intervention plans at additional sites which will contribute to the Science Based Target. |  | As per our decision in FDs, interventions on additional sites may be considered under the MSIP re-opener. Therefore, we would not expect the scope and delivery of the outputs in this condition to require a re-opener. However Ofgem may trigger the re-opener if the circumstances relating to these specific sites have changed significantly. | Closed
2 | 2020-11-18 | NGET | XX.7 | Request the window for submissions be expanded, to include a window in 2021 and reference to a 2023 reopener which will use the Net Zero reopener for the remaining funds. |  | We do not consider that a window in 2021 is necessary here where baseline funding has been provided. However, the windows have been expanded and now are in 2022, 2023 and 2024. | Closed
3 | 2020-11-18 | NGET | XX.11 | PCD Reporting requirements set out within the methodology document are currently high-level and would benefit from being more defined, so this is applicable to this condition (and others). |  | To be considered as part of the PCD Guidance drafting work. | Closed
4 | 2020-11-18 | NGET | Definitions | The Master Definitions list doesn’t currently include Materiality Threshold for the ET sector. |  | Definition added. | Closed
5 | 2020-11-25 | NGET | Defined terms | Definitions need correcting. For example, Insulation and Interruption Gas does not mean "a gas with a global warning potential of greater than zero". | Insulation and/or interrupting gas (IIG) = "Gas used within electrical apparatus to provide dielectric withstand capability and/or current interruption capability within switching devices." | We think this was a typo in the draft condition. The definition of Insulation and Interruption Gas addresses the issue raised. | Closed
6 | 2020-11-25 | NGET | XX.1 | "This contributes to the calculation of the Totex Allowance" is an incomplete explanation of the purpose. How? |  | This is in line with standard wording used elsewhere within the licence. | Closed
7 | 2020-11-25 | NGET | XX.2 | This Condition needs to distinguish between baseline allowances and PCDs and the ability to reopen and update these. Part (a) does not do this. |  | Part B establishes the re-opener mechanism to allow for adjustments to the outputs, delivery dates and associated allowances. Unclear why the current drafting needs amending. | Closed
9 | 2020-11-25 | NGET | XX.4 | Incorrect reference to SF6At, should this be to SF6t? |  | Amended | Closed
10 | 2020-11-25 | NGET | Defined terms | Definitions need correcting. | SF6-free IIG = "An IIG which includes no SF6." | The definition of an 'SF6 Alternative Gas' covers this. | Closed
11 | 2020-11-25 | NGET | Appendix 1 | We are concerned that the inclusion of costs per site in Appendix 1 will prejudice our ability to effectively tender, we would ask that only the total cost be included. Also please can Ofgem provide clarity on what level of information it intends to include in the output column, some examples would be helpful. |  | Amended, so that only the total cost per site is displayed, in line with similar conditions. | Closed
12 | 2020-11-25 | NGET | Part D | We do not consider that this PCD should be subject to a true up as baseline allowances are not normally treated on a cost pass through basis, and instead would suggest that any over or underspend should be subject to TIM. We therefore suggest that Part D is removed. |  | Unclear what this is referring to as Part E contains the standard PCD assessment wording. | Closed
13 | 2021-01-19 | NGET | Defined terms | There is no definition of “Front End Engineering Assessments”, such term is used in 3.27.8(d). | "means assessment works which define the initial design and cost estimates for a proposed intervention which are informed by licensee site based survey and development activities. " | Amended. | Closed
14 | 2021-01-19 | NGET | Defined terms | There is no definition of “Asset Intervention Plan”, such term is used in 3.27.9(a). | means a plan outlining interventions for assets containing sulphur hexafluoride | Amended. | Closed
15 | 2021-01-19 | NGET | Part C | The reopener specifications neglect to state the agreement made with Ben Pirie that a reopener can be requested by National Grid in 2021 to submit additional information needed to justify costs for West Ham, Barking, Sellinge, Seabank and Stocksbridge. |  | This relates to a difference in opinion about the policy. Our policy decision is set out in FDs. | Closed
16 | 2021-01-19 | NGET | 3.27.7 | typo in “...under paragraph 3.27.6 between 25 January...”. It would also be clearer to say “...each of the Regulatory Years starting on 1 April 2023, 1 April 2024 and 1 April 2025...” |  | Between is a defined term. | Closed
17 | 2021-01-19 | NGET | Part D | we do not agree the ability for Ofgem to trigger the reopener is in keeping with the principle of the baseline allowances and request that it is removed from the licence. |  | This relates to a difference in opinion about the policy. Our policy decision is set out in FDs. | Closed
19 | 2021-01-19 | NGET |  | There should be reference to the Net Zero reopener which is planned for use with respect to SF6 in 2023 |  | These are separate policy areas. No reference is required within this condition. | Closed